## Standard_Quality_Dashboard - QE
Observation ID | Study ID | Targeted | PR ID | Site(s) | principal Investigator | EX Comp? | QE Threshold | Status | Observation Description (as submitted) | Awareness Date | Submission Date | Assessment Date | Title/Short Description | Business CAPA Plan Endorsed On | CAPA Plan in Place | Last Action Due Date | Investigation Summary and Conclusion | Effectiveness Check Required | Effectiveness Check Rationale | Investigation Completion Date | Closed On | PDAL Decision | Level 1 | Level 2 | Quality CAPA Plan Endorsed On | Quality Reviewer Approved On | Business Process | Submitter | Confirmed Serious Breach | Remediation Actions Taken (when QE was submitted) | CAPA Action Details | CAPA Action Owner | Root Cause Description | Root Cause Level 1 | Root Cause Level 2 | Root Cause Level 3 | Rapid Model | Business Category
QE-183460 | B7981027 | (Empty) | QE-183460 |  | PFIZER | N | Minor | Closed | Fully Execution of a Site Contract at USA/ Fretzin/ 1005 ahead of the Full Work Order being in place | 2025-05-13 | 2025-06-05 | 2025-06-06 19:52 | GCP_Minor_Jun-2025_B7981027: Clinical Trial Agreement_Pfizer_USA |  | NO |  |  | No |  |  | 2025-06-06 |  | Quality Procedures | Requirement/process not met |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Renata Dittrichi |  | Initial Investigation Upon becoming aware of the issue we immediately launched an internal investigation to identify the root cause. This involved reviewing the QC process, checking the previous communications and instructions that had been sent to the local Contracts Team and speaking with the Portfolio Lead, Local team involved and the LMs of that team in order to understand how the error occurred and what actions were needed.Findings Our investigation confirmed that the issue stemmed from an internal human error on our side. Whilst the QC process had occurred, and indeed there is a step in the QC process that required the team to confirm the WO is in place, this check had been missed. Correct Action As soon as the error was identified we implemented the necessary corrective measures to prevent further such errors occurring. These included reinforcing the QC process and highlighting the need for the process to be carried out fully and diligently, sending out a communication to all our Local Contract Negotiators globally informing them of the status of the WO with a clear statement that no Site Contracts can be FE until the Full WO is in place. Also looping in the Portfolio Lead for awareness and to instruct regarding retraining needs across the team. Quality Issue (QI) Raised To formally document the issue and track our resolution efforts we have raised an official Quality Issue (QI) (REF: QI#122796). This ensures that the root cause, corrective actions, and any future preventative measures are reviewed in line with our quality management protocols. |  |  | NA | Human Performance | Learning Error |  | MODEL 2 - HYBRID | Inflammation & Immunology
QE-183659 | B7981027 | (Empty) | QE-183659 |  | PFIZER | N | Minor | Closed | Documented review of the B7891027 and B7981028 IQMPs was not completed within 120 days of the approval of protocol amendment 2, as required by the now retired QMS06-GSOP-RF03 6.0 Study-Specific Quality Risk Management Checklist 03 Apr 2023. This requirement is now captured in QMS06-GSOP v9 effective 28Apr2025 section 4.4.2: "Updates to address the changes introduced in protocol amendments must be made within 30 business days before or 120 calendar days after the earliest amendment date to be included in that update of the study risk profile (aggregate) (ie, if two or more amendments occur within one month) and may include any other relevant updates. If no updates are required, the decision is documented in the risk management system." B7981028 is the extension study to B7981027, both of which approved protocol amendment 2 on 6Jan2025. FSFV has not been achieved by these studies, so no risk to participants or data integrity occurred. The study teams, including the assigned AQL, were consumed with implementing the EMA requirement for including the WISC-V assessment, which is new for Pfizer. The complexity of this tool and associated requirements distracted the AQL from the need for review specific to protocol amendment 2. | 2025-06-04 | 2025-06-06 | 2025-06-06 18:22 | GCP_Minor_Jun-2025_B7981027; B7981028: CMCD: Integrated Quality Management Plan (IQMP) Updates/Approvals_Pfizer_Global |  | NO |  |  | No |  |  | 2025-06-06 |  | Quality Procedures | Requirement/process not met |  |  | QMS06-Risk Management for Clinical Development | Walter Sauer |  | Confirmed with the study team that no updates to the B7981027 or 1028 IQMPs were required due to protocol amendments 2. During review of AMD 3 for both studies this week, where again no updates were required, the system was annotated to indicate that this week's review included both AMD 2 and 3. |  |  | NA | Human Performance | Omission Error |  | MODEL 2 - HYBRID | Inflammation & Immunology
QE-200595 | B7981027 | (Empty) | QE-200595 |  | PPD, INC. | N | Major | In Investigation | PPD received notification from Greiner Bio-One that their VACUETTE Serum Non-gel tubes are not FDA-cleared for routine clinical chemistry analysis. This information is critical as it may impact the regulatory compliance of the studies conducted using these tubes. The tubes are only approved for viral marker testing and routine immunohematology testing including red cell grouping, RH typing and antibody screening. Greiner Bio-One has not submitted these tubes for FDA approval for use in routine clinical chemistry analysis.The VACUETTE Serum Non-GEl tubes are CE-marked for use in routine chemistry testing in the EU under the In Vitro Diagnostic Regulation (IVDR). Therefore, there is no impact on studies conducted within the EU and APAC using these tubes. Only studies conducted in North America are impacted. The actual date this occurred is unknown so the awareness date was used for the date occurred.Serious breach will need to be assessed. Below is a list of potentially impacted studies:B7451023B7841014B7981027B7981028B8011006C0371002C0371003C1131003C2321003C2321014C3391008C4221015C4221016C4671026C5001001C5541010 | 2025-09-09 | 2025-09-10 | 2025-09-10 16:27 | GCP_Major_Sep-2025_Multiple: Greiner Bio-One_PPD, INC_USA |  | NO | 2026-09-24 |  | Yes |  |  |  |  | Compliance Requirements - Applicable Approvals/Regulatory Required Essential Documents, Third Party Management | Applicable regulatory approvals not obtained or inadequate use of regulatory required essential documents, Inadequate third-party contract dev,execution,revision/update (eg. obsolete safety exhibit, missing signature,dates mis-aligned) |  |  | CT29-Management of Clinical Study BioSpecimens | Karen Barrett |  | Immediate actions by PPD:Conducted a thorough review of all studies utilizing the Greiner Bio-One VACUETTE® SerumNon-Gel tubes.• Initiated communication with Greiner Bio-One to obtain detailed information and clarification regarding the intended use and regulatory status of these tubes.• Halted the use of these tubes for chemistry testing in new studies and have begun using SST-2.5mL (cat # 454243) from Greiner-Bio.PPD initiated a quality event within their QA system and will conduct a full investigation (QE067388). A comprehensive review by study teams of the study protocol and data to determine necesssary actions. |  |  | placeholder | Method/Procedure | Procedure/Form/Plan | Inconsistent With or a Different Interpretation of Regulatory Requirements (Document Standard Lacking/Incorrect Standard... | MODEL 2 - HYBRID | Inflammation & Immunology
QE-206303 | B7981027 | (Empty) | QE-206303 |  | SYNEOS HEALTH LLC | N | Minor | Closed | The INV04-GSOP-SD-GL01 SOP was updated, effective 22Aug2025 without notice and distributed to internally on 04Sep2025 to be implemented. This form's expected implementation differed from the previous version. With the previous version, a transition form was implemented only with a change in site monitor after the site had been initiated. The new form appeared to require transitions to be captured after a site had been selected. I requested clarification on the implementation expectations as my study (B7981027) is in start-up and had SWAT CRAs perform PTAs, some occurring several months prior due to a pause that had taken plan on the study. Several of these CRAs were no longer available and did not remain on the study to be able to provide a handover. My question was confirmed to have been raised to the BPO on 11Sep2025, and a response was received on 09Oct2025 confirming if the person conducting the SIV is different than the person that did the PTA, then the form is required. In the time that the SOP became effective and receipt of this confirmation, we had 5 sites initiated that did not have the form completed. We will be conducting a review of these 5 sites to remediate and reconstruct the issues, if any, that would have been pending for site activation. List of Impacted Sites:CountrySite IDPI First NamePI Last NameUnited States1096EdwardLainUnited States1020MarcMittonUnited States1142BrentSchillingerUnited States1054JenniferSoungUnited States1018CoryRubin | 2025-10-10 | 2025-10-10 | 2025-10-13 14:49 | GCP_Minor_Oct-2025_B7981027: Monitoring Responsibilities: Site Level Transition Form_Syneos Health_USA |  | NO |  |  | No |  |  | 2025-10-13 |  | Site Management and Monitoring | Failure to follow study specific monitoring plan/ requirements |  |  | INV04-Investigational Site Management and Monitoring | Jessica Aponte |  | Identified the sites that would have required the form and notified the study monitoring team to ensure upcoming SIVs have the form completed in advance if the CRA conducting the SIV differs from the CRA that conducted the PTA. This is estimated to be required for 66 sites with upcoming SIVs. |  |  | NA | Human Performance | Learning Error |  | MODEL 2 - HYBRID | Inflammation & Immunology
QE-207414 | B7981027 | (Empty) | QE-207414 |  | SYNEOS HEALTH LLC | N | Minor | Closed | During Clinical Monitoring follow-up to the site 1009 Dr. Durkin on B7981027/1028 studies on subject screening it was noted by the site that they are not enrolling patients yet due to pending their local IRB activation. The Site used Central IRB and never communicated with anyone during startup that they would be doing an additional submission to local for an activation. The site was IIP approved without the site telling anyone on this step. Site did say they mentioned this to the CRA during the SIV visit regarding this step. | 2025-10-14 | 2025-10-16 | 2025-10-17 15:04 | GCP_Minor_Oct-2025_B7981027: Site Activation_Syneos Health_USA |  | NO |  |  | No |  |  | 2025-10-17 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Kayla Shankle |  | Site has already submitted the application to our local IRB. Usually, it takes around 2 weeks to be activated locally. |  |  | NA | Human Performance | Application Error |  | MODEL 2 - HYBRID | Inflammation & Immunology
QE-207646 | B7981027 | N | QE-207646 | 1049 | Mercedes Gonzalez (B7981027-1049) | N | Minor | Closed | US Site 1049/Gonzalez on B7981027 used the available US Spanish ePROs on the study tablet for participant 10491003 prior to receiving IRB approval. At the time of the Screening visit, only the English ICDs (Main and Assent) were available and IRB approved, which is what the site used to consent this participant. The site noted the participant and the caregiver are bilingual. The caregiver chose the Spanish language for the PROs on the tablet. The site monitor was informed following the 15Oct2025 monitoring visit that the parent chose Spanish as their preferred method to complete the questionnaires. The Spanish questionnaires were completed at the Screening visit on 11Sep2025, and Baseline/Randomization visit on 07Oct2025.IRB approval of the Spanish ICDs occurred on 01Oct2025.IRB approval of the Spanish screens for the ePRO, dosing diary, and WISC-V scale were received on 10Oct2025. | 2025-10-16 | 2025-10-17 | 2025-10-17 18:30 | GCP_Minor_Oct-2025_B7981027: Informed Consent Process_Gonzalez, Mercedes_USA |  | NO |  |  | No |  |  | 2025-10-17 |  | Informed Consent | Inadequate consent process at the investigator site |  |  | CT05-Informed Consent Document | Jessica Aponte |  | When the IRB approval of the Spanish ICDs started occurring, the monitoring team was instructed on 06Oct2025 to complete outreach to specific sites that had translations submitted to ensure they do not screen/consent Spanish speaking participants until all approvals are in place. This was confirmed as completed for this site on 07Oct2025. In addition, one of the rater-administered assessments (C-SSRS) is still pending availability in Spanish on the device and is expected at the end of October.The study Clinician and CSTL were consulted to confirm the participant can continue in the study using the Spanish ePROs as available on the device as IRB approval has now been received. The PI has been asked via email today (17Oct2025) to confirm the English proficiency of the caregiver and participant and if any part of the consenting process was verbally translated to Spanish, as well as the reason the Spanish language was selected on the tablet while consenting occurred in English. We are pending a response from the PI.A PD will be captured for the use of the Spanish ePROs prior to receiving IRB approval. The site monitor is returning to the site for another monitoring visit 10-11Nov2025 to assess the source documentation for this participant. |  |  | NA | Human Performance | Learning Error |  | MODEL 2 - HYBRID | Inflammation & Immunology
QE-210321 | B7981027 | (Empty) | QE-210321 |  | ADVARRA INC | N | Minor | Closed | The central IRB, Advarra, issued approved Assents (ages 7-11) that included upside down text in the speech bubbles accompanying the illustrations within the assent. The start-up team identified the error made by the IRB post approval and the IRB issued corrected assents, but the IRB did not revise the file names of the erroneous approved assents posted on their portal to indicate they should not be used for the affected sites. The file name of the assent with the error was identical to the file name of the corrected assent. One of the sites, 1049/Gonzalez, used the assents with the errors for 4 of their participants. This was identified by the site monitor during the RMV on 15Oct2025. The erroneous file that site 1049 had available on the IRB portal was named exactly the same as the corrected file. The site has been provided with the instruction to use the corrected assent to re-assent the participants at their next visits. The first occurrence of an assent with this upside down text was with site 1005/Fretzin, and it was addressed prior to the site's activation. The file names for site 1005 were differentiated with different dates and no issues were identified at a site level. The issues were discussed with the sponsor on 29Oct2025 meeting and it was agreed to submit a QE. | 2025-10-29 | 2025-10-31 | 2025-10-31 18:01 | GCP_Minor_Oct-2025_B7981027: Informed Consent Process: Assent_Advarra Inc_USA |  | NO |  |  | No |  |  | 2025-10-31 |  | Informed Consent | Inadequate consent document content |  |  | CT05-Informed Consent Document | Jessica Aponte |  | The IRB was contacted on 17Oct2025 to raise the issue with the Assent and file name for site 1049 as well as requesting a QC of approved documents to identify additional occurrences. The IRB completed this review and identified one other site, 1010/Desai, with this error on their Spanish Assent and requirement to update the file name to indicate "Do Not Use". The IRB indicated they do not expect this error to occur again as the master version is correct. |  |  | NA | Human Performance | Application Error |  | MODEL 2 - HYBRID | Inflammation & Immunology
QE-210614 | B7981027 | (Empty) | QE-210614 |  | PFIZER | N | Minor | Closed | The Program B798 PEOI (Potential Events of Interests) are captured differently in the Clario 'Communication &amp; Process Plan' vs. the Clario "Adjudication Charter". For DM and Clinical Reconciliation listings, the "Adjudication Charter" PEOI list is being utilized. However, the vendor Clario (at Pfizer's Clinical direction) is utilizing the PEOIs embedded in an excel file in Clario 'Communication &amp; Process Plan'. This incongruence is causing reconciliation fallout and documentation that is confusing and not in alignment. | 2025-10-30 | 2025-11-03 | 2025-11-05 22:31 | GCP_Minor_Nov-2025_B798 Protocols: Potential Events of Interest (PEoI)_Pfizer_Global |  | NO |  |  | No |  |  | 2025-11-05 |  | Quality Oversight/Documentation | Inadequate quality documentation |  |  | CT22-Independent Oversight Committees | Ammber Dunn |  | Ammber initially met with B798 Clinical Lead Amy Freyman and Illeana to discuss this nonconformance in May 2025. It was decided at that time to no update to PEOI list was needed and that Charter should be updated. Charter has not been updated as agreed upon. |  |  | NA | Personnel | Inadequate Information for Determination |  | MODEL 2 - HYBRID | Inflammation & Immunology
QE-211185 | B7981027 | N | QE-211185 | 1104 | Brenda Simpson (B7981027-1104) | N | Minor | Closed | During the first RMV for site 1104/Simpson on B7981027, the site monitor identified several issues with the source documents for the two participants randomized and for a screen failed participant. The source documents reflected undated PI signatures, dated Inclusion/Exclusion (I/E) worksheets prior to the availability of all eligibility data, blank participant diary and IP accountability documents, blank Physical Exam and lab reports (no indication of review), and pre-signed blank source pages for the SF participant. Leading up to the monitoring visit, it was noted that both of the study coordinators (SC) at the site had resigned, one occurring earlier the month of October and the second one about a week prior to the monitoring visit. The SCs that had completed the source documents were no longer at the site and the PI was out of the office the day of the monitoring visit. One active participant was out of window for their Week 2 visit as the PI did not have any SCs available and active on the study to conduct the visit. These issues were escalated to the Pfizer Clinician on 22Oct2025 by the Global CTM (reporter of this QE). A meeting was scheduled to speak with the PI on 27Oct2025 to address the concerns and issues identified during the RMV. The Clinician confirmed significant deviations were noted that would require PI and site re-training. A follow up with the Clinician by the GCTM on 04Nov2025 confirmed submission of a QE should be completed.During the 27Oct2025, the PI and the CEO of the site met with the Site Monitor, GCTM, and both regional CTMs to discuss the findings from the RMV and review the ALCOA principals and PI responsibilities. The PI acknowledged responsibility for not following ALCOA and lack of appropriate oversight for study assessments as she should have ensured she completed the proper review and completion of source documentation with acknowledgment via her dated signature. The PI indicated she had addressed the issues with the source documents, to be reviewed and assessed by the Site Monitor at the next RMV. The CEO present on the call attributed the issues with the source documents to the SCs that departed the site and also noted a CAPA would be implemented. The status of the 2 active participants were reviewed and expectations for follow-up and visit conduct were discussed. New SC staff were trained on the study protocol by the PI on 21Oct2025; however, additional study trainings were still pending due to the need to get the new staff trained and added to SIP to flow to Firecrest for training assignments. The delay has caused a delay in data entry and query resolution as there are no active data entry users at the site.The monitor is presently conducting the next RMV today, 05Nov2025. | 2025-11-04 | 2025-11-05 | 2025-11-05 21:28 | GCP_Minor_Nov-2025_B7981027: PI Oversight; Source Documentation_Simpson, Brenda__USA |  | NO |  |  | No |  |  | 2025-11-05 |  | Data Collection and Management, Quality Oversight | Inadequate Principal Investigator quality oversight, Inadequate source data/documentation |  |  | No Process Assigned | Jessica Aponte |  | The PI hired new SCs to onboard to replace the SCs that left. The issues were escalated to the Pfizer study team on 22Oct2025. An initial meeting was scheduled with the PI to address the issues identified, completed 27Oct2025. The site was placed on Screening hold on 04Nov2025 until further assessment of site CAPA that was noted by the CEO that would be completed, and review of the site's progress. Also to assess the readiness of the new SCs added to the site staff. The Site Monitor has also expanded review of participant source to 100%. To be discussed with the Pfizer study team before lifting the Screening hold. |  |  | NA | Personnel | Lack of or Inadequate Oversight |  | MODEL 2 - HYBRID | Inflammation & Immunology
QE-220015 | B7981027 | N | QE-220015 | 1054 | Jennifer Soung (B7981027-1054) | N | Minor | Closed | US Site 1054/Soung on B7981027 used the available US Spanish ePROs on the study tablet for participants 10541001 and 10541004 without having received Spanish IRB approval. Only the English ICDs (Main and Assents) were available, and IRB approved, which is what the site used to consent these participants. The site monitor was informed during the 18-19Dec2025 monitoring visit that the parent and child both chose Spanish as their preferred method to complete the questionnaires. Site noted that both participants and caregivers are bilingual and proficient in both languages. The Spanish questionnaires were completed at the following visits: 10541001 on 14Oct25, 18Nov25, 4Dec25, 17Dec25. Participant 10541004 was done on 10Nov25, 15Dec25. IRB approval of the Spanish ICDs has not occurred at the time of this writing. PI has been asked why they haven't proceeded with gaining Spanish IRB approval and we are awaiting a response. | 2025-12-18 | 2025-12-21 | 2025-12-22 17:12 | GCP_Minor_Dec-2025_B7981027: ePRO Questionnaires (Spanish)_Seoung, Jennifer_USA |  | NO |  |  | No |  |  | 2025-12-22 |  | Ethics Oversight | Lacks evidence of ethics oversight |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Jennifer Goehring |  | When the IRB approvals of the Spanish ICDs started occurring, the monitoring team was instructed on 06 Oct 2025 to complete outreach to specific sites that had translations submitted to ensure they do not screen/consent Spanish speaking participants until all approvals are in place. This was confirmed as completed for this site on 10 Nov 2025. In addition, notification to sites was included in Volume 3 of the Global Newsletter sent to sites on 17Nov2025. The PI has confirmed with monitor while on site today (19 Dec 2025) the English proficiency of the caregiver and participant and that no part of the consenting process was verbally translated to Spanish. Parent and participant use Spanish and English interchangeably and this is the reason the Spanish language was selected on the tablet while consenting occurred in English. We are pending a written a response from the PI but they verbally reported that all language proficiencies will be documented and that the Spanish version of ePRO questionnaires will not be utilized until IRB approval is gained. A PD will be captured for the use of the Spanish ePROs prior to receiving IRB approval. The site monitor is in the process of setting up the next monitoring visit with coordinator for in January of 2026. |  |  | NA | Human Performance | Decision Error |  | MODEL 2 - HYBRID | Inflammation & Immunology
QE-227214 | B7981027 | (Empty) | QE-227214 |  | ANCILLARE | N | Minor | Closed | For protocol B7981027, during site set up, ECG unit was expected to be delivered to Polish site 1021. When SIV was conducted on 03Feb2026, it was brought to CRA's attention that site received delivery of a fridge instead. | 2026-02-03 | 2026-02-09 | 2026-02-09 18:49 | GCP_Minor_Feb-2026_B7981027: Study Supplies: ECG Unit_Ancillare_POL |  | NO |  |  | No |  |  | 2026-02-09 |  | Equipment, Facility and Sample/Specimens | Inadequate equipment/lab supply mgmt. |  |  | No Process Assigned | Sie Yan Chin |  | (1) Site activation is put on hold until a new ECG unit is supplied to the site. (2) Vendor has been contacted to identify the root cause. (3) A new request for expedited delivery of ECG to site has been triggered. |  |  | NA | Human Performance | Application Error |  | MODEL 2 - HYBRID | Inflammation & Immunology
QE-227763 | B7981027 | (Empty) | QE-227763 |  | ERESEARCH TECHNOLOGY INC, A CLARIO COMPANY, PFIZER | N | Major | Closed | Clario had a cybersecurity incident which involved Pfizer studies.Late on September 28, 2025, Clario’s IT Security Department learned that an unauthorized user obtained access to one instance of an application called Jira (the “incident”). Jira is separate from Clario’s clinical trial systems. The impacted instance of Jira is used by Clario’s Imaging R&amp;D team for software development-related project management. | 2025-10-03 | 2026-02-11 | 2026-02-12 15:34 | GCP_Major_Feb-2026_Multiple Protocols: Cyber Security Incident_Clario_Global |  | YES |  | <p>On 11 Feb 2026, the Pfizer Outcomes Vendor Services representative in the Business Vendor Strategic Management (BVSM) group reported that one of the vendors contracted for medical imaging and central reader services, Clario, and used on 29 Pfizer studies, experienced a cybersecurity incident. The event posed a potential for adverse impact to participant rights and/or Pfizer data confidentiality as the vendor’s data security has been compromised.</p><p><br></p><p>On 28 Sep 2025, Clario’s Information Technology (IT) Security Department learned that an unauthorized user obtained access to one instance of an application called Jira. Jira is an application that Clario licenses from a third-party and is separate from Clario’s clinical trial systems. One of the functionalities within Jira is the ability to send and receive messaging tickets. Clario’s R&amp;D professionals use this ticketing function to communicate with one another in connection with various Imaging &amp; Specialty Solutions software development projects.</p><p><br></p><p>In this cyber security incident, the threat actor accessed tickets within Jira and was able to download the tickets as well as attachments to those tickets. The threat actor also edited or deleted data in Jira but we were able to restore from backup.</p><p><br></p><p>The unauthorized access occurred through valid credentials for a single Jira user account that was not protected by multi-factor authentication (MFA). At the time of the incident, the compromised instance of Jira was accessible from the Internet. MFA was not enabled for this individual user because Single Sign-On (SSO) integration had not yet been deployed to production for the impacted instance of Jira at the time of the intrusion.</p><p><br></p><p>Upon learning of the incident, Clario immediately restricted public access to the impacted Jira application, disabled the compromised Jira account, and out of an abundance of caution disabled Microsoft O365 credentials for the user account associated with the compromised Jira account.&nbsp;</p><p><br></p><p>Clario also engaged external forensic experts (Mandiant) to support the investigation and remediation process. It was confirmed by Mandiant that the unauthorized user’s access appeared to have been limited to the instance of Jira and associated tools used internally by Clario’s Imaging R&amp;D team. This included messaging tickets sent and received by members of the Clario Imaging R&amp;D team through Jira and any files that may have been attached to those tickets.&nbsp;</p><p><br></p><p>The cybersecurity incident was submitted to Pfizer Protect at the time Pfizer BVSM became aware of the incident in on 03 Oct 2025. The Pfizer Global Information Security Team and the Pfizer Global Privacy Office were contacted at the time of awareness to begin their investigations.&nbsp;</p><p><br></p><p>It was confirmed by Pfizer Global Security that the Jira data was key-coded data and Clario did not hold the key to the data. As a result, there would be no way to link the key coded data to a participant.&nbsp;</p><p><br></p><p>Pfizer Global Information Security reported their investigation was closed on 09 Feb 2026 after receiving the Statement of Confidence from Clario that there was no evidence that the unauthorized access impacted Clario’s clinical trial systems or the study data contained in those systems nor did it impact Jira instances for other Clario service lines such as electronic Clinical Outcomes Assessment (eCOA) data.&nbsp;</p><p><br></p><p>The Outcomes Vendor Services Lead was able to perform a review of all impacted Jira instances and was able to confirm that the information in the Jira tickets did not contain Personal Identifying Information or Personal Health Information.</p><p><br></p><p>A review of the Clario and Mandiant investigation documentation for this cybersecurity incident was completed. It was confirmed no additional actions were required by Clario to address the issue and prevent it from recurring.</p><p><br></p><p>A Gap Analysis Investigation was conducted therefore no root cause was identified and a repeat occurrence review to identify prior QEs with the same or similar cause was not conducted.</p><p><br></p> | No | Quality Event only required gap analysis investigation | 2026-03-20 | 2026-03-20 |  | IT Systems, Quality Procedures | Failure to escalate or resolve a detected issue (quality control), IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) |  | 2026-03-20 20:41 | CP411, QMS01-Reporting and Management of Quality Events | Tracy Talaber Adams | FALSE | Upon learning of the incident, Clario immediately restricted public access to the impacted Jira application, disabled the compromised Jira account, and – out of an abundance of caution –disabled Microsoft O365 credentials for the user account associated with the compromised Jira account. At the direction of counsel, they also engaged external forensic experts to support investigation and remediation process. The unauthorized user’s access appears to have been limited to the instance of Jira and associated tools used internally by Clario’s Imaging R&amp;D team. This includes messaging tickets sent and received by members of the Clario Imaging R&amp;D team through Jira and any files that may have been attached to those tickets. Clario have seen no evidence that the unauthorized user connected to Clario’s systems more broadly nor that the unauthorized user was able to access Clario’s clinical trial applications where study data is stored.Clario notified Pfizer of the incident 5 business days after they learned of the issue. Pfizer Security and Global Privacy were engaged. |  |  | Gap Analysis&nbsp; | Gap Analysis | N/A | N/A | MODEL 2 - HYBRID | Inflammation & Immunology
QE-229881 | B7981027 | N | QE-229881 | 1034 | Takehiro Takahashi (B7981027-1034) | N | Minor | Closed | Blood samples for genetic testing were collected without the patient's consent and sent to a vendor. | 2026-02-20 | 2026-02-24 | 2026-02-24 16:18 | GCP_Minor_Feb-2026_B7981027: Biospecimen Management_Takahashi, Takehiro_JPN |  | NO |  |  | No |  |  | 2026-02-24 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens | Jun Hashimoto |  | We informed the hospital staff of the blood collection error and asked them to investigate the cause in more detail. We reported the incident to the client and asked them not to analyze the blood samples. |  |  | NA | Human Performance | Learning Error |  | MODEL 2 - HYBRID | Inflammation & Immunology
QE-231463 | B7981027 | N | QE-231463 | 1104 | Brenda Simpson (B7981027-1104) | N | Minor | Closed | Site 1104 on B7981027 had been instructed to report a protocol deviation (PD) to the central IRB, Advarra, for participant 11041002 having shaved their head prior to the Baseline visit, as it interfered with the completion of the study efficacy assessments (SALT) which is a study primary endpoint. The site's Regulatory contact submitted the PD to Advarra on 02Mar2026 via the IRB portal and included the participant's first name in the PD event description and in an attachment included with the submission. The IRB posted the submission and disseminated the submission to all study contacts listed, which included the participant's first name in the email. This includes 23 emails under the managing CRO and 3 site emails. | 2026-03-02 | 2026-03-03 | 2026-03-04 20:03 | GCP_Minor_Mar-2026_B7981027: Participant Confidentiality / Data Privacy_Simpson, Brenda; Advarra_USA |  | NO |  |  | No |  |  | 2026-03-04 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Jessica Aponte |  | The Global CTM (gCTM) noted the PHI/PII in the Advarra notice regarding the submission via email within an hour of receipt on 02Mar2026, and notified all recipients to immediately delete the email as it contained PHI and respond with confirmation the email had been deleted. The gCTM also contacted the IRB contact regarding the improper posting of PHI and the site revised their submission to remove the attachment and participants name from the submission. This was confirmed to have been completed by the IRB Director approximately 3 hours after the incident occurred. The IRB Director noted the confidentiality language in the template ICF includes the investigator, study staff, or persons working on behalf of the sponsor (ie, CRO) covered access to this information. The site's regulatory coordinator provided a Note to File to document the event. |  |  | NA | Human Performance | Omission Error |  | MODEL 2 - HYBRID | Inflammation & Immunology
QE-231463 | B7981027 | (Empty) | QE-231463 |  | ADVARRA INC | N | Minor | Closed | Site 1104 on B7981027 had been instructed to report a protocol deviation (PD) to the central IRB, Advarra, for participant 11041002 having shaved their head prior to the Baseline visit, as it interfered with the completion of the study efficacy assessments (SALT) which is a study primary endpoint. The site's Regulatory contact submitted the PD to Advarra on 02Mar2026 via the IRB portal and included the participant's first name in the PD event description and in an attachment included with the submission. The IRB posted the submission and disseminated the submission to all study contacts listed, which included the participant's first name in the email. This includes 23 emails under the managing CRO and 3 site emails. | 2026-03-02 | 2026-03-03 | 2026-03-04 20:03 | GCP_Minor_Mar-2026_B7981027: Participant Confidentiality / Data Privacy_Simpson, Brenda; Advarra_USA |  | NO |  |  | No |  |  | 2026-03-04 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Jessica Aponte |  | The Global CTM (gCTM) noted the PHI/PII in the Advarra notice regarding the submission via email within an hour of receipt on 02Mar2026, and notified all recipients to immediately delete the email as it contained PHI and respond with confirmation the email had been deleted. The gCTM also contacted the IRB contact regarding the improper posting of PHI and the site revised their submission to remove the attachment and participants name from the submission. This was confirmed to have been completed by the IRB Director approximately 3 hours after the incident occurred. The IRB Director noted the confidentiality language in the template ICF includes the investigator, study staff, or persons working on behalf of the sponsor (ie, CRO) covered access to this information. The site's regulatory coordinator provided a Note to File to document the event. |  |  | NA | Human Performance | Omission Error |  | MODEL 2 - HYBRID | Inflammation & Immunology
QE-234134 | B7981027 | (Empty) | QE-234134 |  | SYNEOS HEALTH LLC | N | Major | In Investigation | Several gaps were identified for subcontractor approvals that were not obtained per QMS09. A total of 17 gaps were identified across 9 subcontractors that were engaged between Jul-2020 and Sep-2025, across 14 studies. The gaps fall under two main categories: “vendor approval is project specific and does not include the project” (7 instances), and “service contracted is not an approved service type for the vendor” (10 instances). Given that the root causes are portfolio-level rather than study-level, we are submitting a portfolio-level QE including all projects/vendors impacted, per the below list.C1071015 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C3651032 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C4991001 Part 2 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C4541011 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C5001004 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.B7451023 - Ametris (Digital Devices Bundled with Service): Vendor approval is project specific and does not include this project.C4951002 - Lionbridge Technologies LLC (Translations Services): Vendor approval is project specific and does not include this project.B7461039 - ClinPlus (Study Coordination Support Services): Service contracted is not an approved service type for this vendor.B7451031 - ICON Clinical Research Limited (Translations Services, Scales Only): Service contracted is not an approved service type for this vendor. C4541011 - HealthCarePoint.com Public Benefit Corporation (Rater Training): Service contracted is not an approved service type for this vendor.C4541011 - ICON Clinical Research Limited (Translations Services, Scales Only): Service contracted is not an approved service type for this vendor. C4951002 - Endpoint Clinical L.P. (Interactive Response Technology): Service contracted is not an approved service type for this vendor.B7471015 - ICON Clinical Research Limited (Medical Imaging - Central Reader): Service contracted is not an approved service type for this vendor.C4851001 - Marken Ltd. (Biospecimen Management): Service contracted is not an approved service type for this vendor.B7981027 - eResearch Technology (Rater Training): Service contracted is not an approved service type for this vendor.B7981028 - eResearch Technology (Rater Training): Service contracted is not an approved service type for this vendor.C4951063 - ICON Clinical Research Limited (Translations Services, Scales Only): Service contracted is not an approved service type for this vendor. | 2026-03-16 | 2026-03-17 | 2026-03-18 17:58 | GCP_Major_Mar-2026_Process/Enterprise Level: CMCD: Vendor Responsibilities: Sub-Contractor Approval_Syneos Health; Pfizer_Global |  | NO | [7 empty] | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | QMS09-Vendor Engagement | Lourdes Arnillas |  | Re-formatting of tools to ensure relevant information is included – completed 25Feb2026Rollout of a new process training across the portfolio – completed 03Mar2026Submission of subcontractor approval requests to close all 17 gaps – completed 13Mar2026Submission of this Quality Event (flagged for action on 16Mar2026) | [6 empty] | MODEL 2 - HYBRID | Inflammation & Immunology