## Standard_Quality_Dashboard - SQ
Case ID | Case Status | Observation ID | Obs Status | Submission Date | Issue Audit Report (Actual) | Center Number | principal investigator | Country | Description | Study ID | Protocol ID | Title Short Description | Drug Program Code | Rating | Event Type | Case CAPA Approved Due Date | Case CAPA Approved On | CAPA Plan In Place Timely | Obs CAPA Approved Due Date | Obs CAPA Approved On | Obs Target Completion Date | Obs Actual Completion Date | Case CAPA Closure Timely | Case Target Completion Date | Case Actual Completion Date | Obs CAPA Closure Timely | Selected Business Process | Taxonomy Level 1 | Taxonomy Level 2 | Study Status | Business Category | Study Phase | Study Priority | Asset | Dev China | Dev Japan | Rapid Model | Business Category
AIA-009545 | Pending Finding Closure | QE-227814 | Issued | (Empty) | 2026-02-24 | 1095 | (Empty) | CHINA | The source documentation at the investigator site did not comply with ALCOACCEA (Accurate, Legible, Contemporaneous, Original, Attributable, Complete, Consistent, Enduring, and Available) principles for 2 of 3 participants reviewed. [Pfizer Protocol B7981027 (Version 4.0: 07 Oct 2025); ICH E6 R3 2.12.2]. 1. The following data were not consistent. Participant 10951008: The Audiometry Worksheet was co-signed and dated by the sub-investigator on 18 Nov 2026, however, the Screening visit was conducted on 18 Nov 2025. 2. The following data were incomplete. Participant 10951002: Investigational Product compliance was not documented in the medical records at Study Visit Week 2 as required by the protocol. | B7981027 | B7981027 | An Investigator Site Audit of Study B7981027, Site 1095, Professor Zigang Xu, Beijing, China. | (Empty) | Minor | AUDIT | 2026-04-07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | NOT APPLICABLE; NOT APPLICABLE | Data Collection and Management | Inadequate source data/documentation | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
AIA-009545 | Pending Finding Closure | QE-227815 | In Response | (Empty) | 2026-02-24 | 1095 | (Empty) | CHINA | The Biospecimen Management Plan (BAP) did not include biospecimen handling information for pharmacokinetic samples collected from investigator sites in China. [Pfizer Protocol B7981027 (Version 4.0: 07 Oct 2025); Pfizer Biospecimen Management Plan B7981027 (Version 1.0: 13 Aug 2025) ]. Protocol Amendment 4, dated 07 Oct 2025, and Protocol Amendment 3, dated 10 Apr 2025, specified that pharmacokinetic samples were to be collected at Study Visit Week 4 or Week 8 (if not performed at Week 4). However, this was not included in the BAP dated 15 Aug 2025 . Note: the central lab manual was in place to guide the investigator sites how to manage PK samples and to deliver the samples to the central laboratory. The investigator site collected the PK samples as per the requirement of the central lab manual and the protocol for the 3 reviewed participants. | B7981027 | B7981027 | An Investigator Site Audit of Study B7981027, Site 1095, Professor Zigang Xu, Beijing, China. | (Empty) | Minor | AUDIT | 2026-04-07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
AIA-009545 | Pending Finding Closure | QE-227816 | Issued | (Empty) | 2026-02-24 | 1095 | (Empty) | CHINA | Adverse event (AE) documentation and reporting for 1 of 3 participants reviewed was inconsistent and incomplete. [Pfizer Protocol B7981027 (Amendment 4: 07 Oct 2025); ICH E6 R3 2.12.5] Participant 10951002: 1. The stop date of the adverse event "Eczema" was recorded as 12 Dec 2025 in the eCRF, while the medical records dated 23 Dec 2025 documented the stop date of the AE as 12 Dec 2025, but the medical records dated 26 Jan 2026 indicated the stop date of the AE was 26 Jan 2026. There was no clarification in the medical records which stop date was accurate. Note: During the audit interview, the sub-investigator clarified that the AE stopped on 26 Jan 2026. 2.&nbsp;The eCRF documented administration of "Cetirizine Hydrochloride Tablets" from 23 Dec 2025 to 25 Dec 2025 for the treatment of the AE “Urticaria”, whereas the medical records dated 26 Jan 2026 indicated loratadine 10 mg was taken orally once daily for three days, topical emollient was used for approximately four days, and cetirizine was taken from 23 Dec 2025 to 25 Dec 2025. Confirmation with the sub-investigator indicated that only loratadine was taken for the treatment of urticaria. | B7981027 | B7981027 | An Investigator Site Audit of Study B7981027, Site 1095, Professor Zigang Xu, Beijing, China. | (Empty) | Minor | AUDIT | 2026-04-07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | NOT APPLICABLE; NOT APPLICABLE | AE reporting to Sponsor | Incomplete AE reporting | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
QE-200595 | In Investigation | QE-200595 | In Investigation | 2025-09-10 | (Empty) | (Empty) | PPD, INC. | (Empty) | PPD received notification from Greiner Bio-One that their VACUETTE Serum Non-gel tubes are not FDA-cleared for routine clinical chemistry analysis. This information is critical as it may impact the regulatory compliance of the studies conducted using these tubes. The tubes are only approved for viral marker testing and routine immunohematology testing including red cell grouping, RH typing and antibody screening. Greiner Bio-One has not submitted these tubes for FDA approval for use in routine clinical chemistry analysis.The VACUETTE Serum Non-GEl tubes are CE-marked for use in routine chemistry testing in the EU under the In Vitro Diagnostic Regulation (IVDR). Therefore, there is no impact on studies conducted within the EU and APAC using these tubes. Only studies conducted in North America are impacted. The actual date this occurred is unknown so the awareness date was used for the date occurred.Serious breach will need to be assessed. Below is a list of potentially impacted studies:B7451023B7841014B7981027B7981028B8011006C0371002C0371003C1131003C2321003C2321014C3391008C4221015C4221016C4671026C5001001C5541010 | B7981027 | B7981027 | GCP_Major_Sep-2025_Multiple: Greiner Bio-One_PPD, INC_USA | B798 | Major | SQE | 2026-04-02 | (Empty) | (Empty) | 2026-04-02 | (Empty) | 2026-09-24 | (Empty) | (Empty) | 2026-09-24 | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Compliance Requirements - Applicable Approvals/Regulatory Required Essential Documents | Applicable regulatory approvals not obtained or inadequate use of regulatory required essential documents | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
QE-200595 | In Investigation | QE-200595 | In Investigation | 2025-09-10 | (Empty) | (Empty) | PPD, INC. | (Empty) | PPD received notification from Greiner Bio-One that their VACUETTE Serum Non-gel tubes are not FDA-cleared for routine clinical chemistry analysis. This information is critical as it may impact the regulatory compliance of the studies conducted using these tubes. The tubes are only approved for viral marker testing and routine immunohematology testing including red cell grouping, RH typing and antibody screening. Greiner Bio-One has not submitted these tubes for FDA approval for use in routine clinical chemistry analysis.The VACUETTE Serum Non-GEl tubes are CE-marked for use in routine chemistry testing in the EU under the In Vitro Diagnostic Regulation (IVDR). Therefore, there is no impact on studies conducted within the EU and APAC using these tubes. Only studies conducted in North America are impacted. The actual date this occurred is unknown so the awareness date was used for the date occurred.Serious breach will need to be assessed. Below is a list of potentially impacted studies:B7451023B7841014B7981027B7981028B8011006C0371002C0371003C1131003C2321003C2321014C3391008C4221015C4221016C4671026C5001001C5541010 | B7981027 | B7981027 | GCP_Major_Sep-2025_Multiple: Greiner Bio-One_PPD, INC_USA | B798 | Major | SQE | 2026-04-02 | (Empty) | (Empty) | 2026-04-02 | (Empty) | 2026-09-24 | (Empty) | (Empty) | 2026-09-24 | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Third Party Management | Inadequate third-party contract dev,execution,revision/update (eg. obsolete safety exhibit, missing signature,dates mis-aligned) | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
QE-227763 | Closed | QE-227763 | Closed | 2026-02-11 | (Empty) | (Empty) | ERESEARCH TECHNOLOGY INC, A CLARIO COMPANY | (Empty) | Clario had a cybersecurity incident which involved Pfizer studies.Late on September 28, 2025, Clario’s IT Security Department learned that an unauthorized user obtained access to one instance of an application called Jira (the “incident”). Jira is separate from Clario’s clinical trial systems. The impacted instance of Jira is used by Clario’s Imaging R&amp;D team for software development-related project management. | B7981027 | B7981027 | GCP_Major_Feb-2026_Multiple Protocols: Cyber Security Incident_Clario_Global | B798 | Major | SQE | 2026-03-29 | 2026-03-20 | Y | 2026-03-29 | 2026-03-20 20:41 | (Empty) | 2026-03-20 | (Empty) | (Empty) | 2026-03-20 | (Empty) | CP411 - Information Incident Response Policy | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
QE-227763 | Closed | QE-227763 | Closed | 2026-02-11 | (Empty) | (Empty) | ERESEARCH TECHNOLOGY INC, A CLARIO COMPANY | (Empty) | Clario had a cybersecurity incident which involved Pfizer studies.Late on September 28, 2025, Clario’s IT Security Department learned that an unauthorized user obtained access to one instance of an application called Jira (the “incident”). Jira is separate from Clario’s clinical trial systems. The impacted instance of Jira is used by Clario’s Imaging R&amp;D team for software development-related project management. | B7981027 | B7981027 | GCP_Major_Feb-2026_Multiple Protocols: Cyber Security Incident_Clario_Global | B798 | Major | SQE | 2026-03-29 | 2026-03-20 | Y | 2026-03-29 | 2026-03-20 20:41 | (Empty) | 2026-03-20 | (Empty) | (Empty) | 2026-03-20 | (Empty) | QMS01 - Quality Events | Quality Procedures | Failure to escalate or resolve a detected issue (quality control) | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
QE-227763 | Closed | QE-227763 | Closed | 2026-02-11 | (Empty) | (Empty) | PFIZER | (Empty) | Clario had a cybersecurity incident which involved Pfizer studies.Late on September 28, 2025, Clario’s IT Security Department learned that an unauthorized user obtained access to one instance of an application called Jira (the “incident”). Jira is separate from Clario’s clinical trial systems. The impacted instance of Jira is used by Clario’s Imaging R&amp;D team for software development-related project management. | B7981027 | B7981027 | GCP_Major_Feb-2026_Multiple Protocols: Cyber Security Incident_Clario_Global | B798 | Major | SQE | 2026-03-29 | 2026-03-20 | Y | 2026-03-29 | 2026-03-20 20:41 | (Empty) | 2026-03-20 | (Empty) | (Empty) | 2026-03-20 | (Empty) | CP411 - Information Incident Response Policy | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
QE-227763 | Closed | QE-227763 | Closed | 2026-02-11 | (Empty) | (Empty) | PFIZER | (Empty) | Clario had a cybersecurity incident which involved Pfizer studies.Late on September 28, 2025, Clario’s IT Security Department learned that an unauthorized user obtained access to one instance of an application called Jira (the “incident”). Jira is separate from Clario’s clinical trial systems. The impacted instance of Jira is used by Clario’s Imaging R&amp;D team for software development-related project management. | B7981027 | B7981027 | GCP_Major_Feb-2026_Multiple Protocols: Cyber Security Incident_Clario_Global | B798 | Major | SQE | 2026-03-29 | 2026-03-20 | Y | 2026-03-29 | 2026-03-20 20:41 | (Empty) | 2026-03-20 | (Empty) | (Empty) | 2026-03-20 | (Empty) | QMS01 - Quality Events | Quality Procedures | Failure to escalate or resolve a detected issue (quality control) | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
QE-234134 | In Investigation | QE-234134 | In Investigation | 2026-03-17 | (Empty) | (Empty) | SYNEOS HEALTH LLC | (Empty) | Several gaps were identified for subcontractor approvals that were not obtained per QMS09. A total of 17 gaps were identified across 9 subcontractors that were engaged between Jul-2020 and Sep-2025, across 14 studies. The gaps fall under two main categories: “vendor approval is project specific and does not include the project” (7 instances), and “service contracted is not an approved service type for the vendor” (10 instances). Given that the root causes are portfolio-level rather than study-level, we are submitting a portfolio-level QE including all projects/vendors impacted, per the below list.C1071015 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C3651032 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C4991001 Part 2 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C4541011 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C5001004 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.B7451023 - Ametris (Digital Devices Bundled with Service): Vendor approval is project specific and does not include this project.C4951002 - Lionbridge Technologies LLC (Translations Services): Vendor approval is project specific and does not include this project.B7461039 - ClinPlus (Study Coordination Support Services): Service contracted is not an approved service type for this vendor.B7451031 - ICON Clinical Research Limited (Translations Services, Scales Only): Service contracted is not an approved service type for this vendor. C4541011 - HealthCarePoint.com Public Benefit Corporation (Rater Training): Service contracted is not an approved service type for this vendor.C4541011 - ICON Clinical Research Limited (Translations Services, Scales Only): Service contracted is not an approved service type for this vendor. C4951002 - Endpoint Clinical L.P. (Interactive Response Technology): Service contracted is not an approved service type for this vendor.B7471015 - ICON Clinical Research Limited (Medical Imaging - Central Reader): Service contracted is not an approved service type for this vendor.C4851001 - Marken Ltd. (Biospecimen Management): Service contracted is not an approved service type for this vendor.B7981027 - eResearch Technology (Rater Training): Service contracted is not an approved service type for this vendor.B7981028 - eResearch Technology (Rater Training): Service contracted is not an approved service type for this vendor.C4951063 - ICON Clinical Research Limited (Translations Services, Scales Only): Service contracted is not an approved service type for this vendor. | B7981027 | B7981027 | GCP_Major_Mar-2026_Process/Enterprise Level: CMCD: Vendor Responsibilities: Sub-Contractor Approval_Syneos Health; Pfizer_Global | B798 | Major | SQE | 2026-05-02 | (Empty) | (Empty) | 2026-05-02 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology