## Standard_Quality_Dashboard - QE
Observation ID | Study ID | Targeted | PR ID | Site(s) | principal Investigator | EX Comp? | QE Threshold | Status | Observation Description (as submitted) | Awareness Date | Submission Date | Assessment Date | Title/Short Description | Business CAPA Plan Endorsed On | CAPA Plan in Place | Last Action Due Date | Investigation Summary and Conclusion | Effectiveness Check Required | Effectiveness Check Rationale | Investigation Completion Date | Closed On | PDAL Decision | Level 1 | Level 2 | Quality CAPA Plan Endorsed On | Quality Reviewer Approved On | Business Process | Submitter | Confirmed Serious Breach | Remediation Actions Taken (when QE was submitted) | CAPA Action Details | CAPA Action Owner | Root Cause Description | Root Cause Level 1 | Root Cause Level 2 | Root Cause Level 3 | Rapid Model | Business Category
2201270 | B7981028 | (Empty) | 2201236 |  |  | N | Major | Closed | Product Protocol Number: B7451015 (Alias: JADE EXTEND) B7451037 B7931028 B7981007 B7981028 B7981032 C1071001 (Alias: (MAGNETISMM-1) C1131001 Involved Party / Country: Vendor: Labcorp Central Laboratory Services / United States Quality Event Description: Labcorp Central Laboratory Services (formerly Covance Central Laboratory Services (CCLS)) is contracted to provide specimen management, laboratory collection kits and kit logistics and also the management of clinical trial laboratory data. As related to this event, Labcorp follows their own processes related to T- and B-Cell Quantitation by Flow Cytometry (Test ID: TBNK) assay, analyses and non-CRF data transfers. Pfizer study protocols further describe blinded and exploratory laboratory data for reporting purposes. On 12-Jan-2022, a Labcorp Global Study Manager (GSM) reported via routine email communication to 1 Pfizer study team representative that the processing and analysis completed by Labcorp Indianapolis (USA) - Flow Cytometry Laboratory resulted in a reported data error following their implementation of TruCount Tubes (for flow cytometry) on 10-Jun-2021 and 23-Jul-2021. On 10-Feb-2022, Labcorp provided a listing of 256 laboratory sample accession numbers associated with Pfizer trials that were impacted by this Labcorp Enterprise Level quality event. Eight (8) ongoing Pfizer studies were informed as follows B7451015, B7451037, B7931028, B7981007, B7981028, B7981032, C1071001 and C1131001. Although there was a delay to report the quality event to Pfizer, Labcorp has reported that they managed the data discrepancy before any study data set was prepared and before any reporting event, including publication. Therefore, the SQE Team prioritized studies for data revision according to upcoming submissions and agreed that there are no submission timelines at risk due to this event. Consequent to agreement that there is no (significant) impact to data integrity, there was no indication that study participant location and serious breach reporting requirements were required to be further investigated. B7451015 is a phase 3 multi-center, long-term extension study investigating the efficacy and safety of arocitinib, with or without topical medications, administered to subjects aged 12 years and older with moderate to severe atopic dermatitis. B7451037 is a phase 2a randomized, double-blind, placebo-controlled, parallel group, multi-center study to investigate the mechanism of action of abrocitinib monotherapy in adult participants with moderate-to-sever atopic dermatitis. B7931028 is a phase 2b, double-blind, randomized, placebo-controlled, multicenter, dose-ranging study to evaluate the efficacy and safety profile of pf-06700841 in participants with active systemic lupus erythematosus (sle). B7981007 is a phase 2a, double-blind, randomized, placebo-controlled, parallel group study to evaluate the efficacy and safety of oral PF-06651600 and PF-06700841 as induction and open label extension treatment in subjects with moderate to severe crohn’s disease. B7981028 is a phase 3 pediatric long term extension study with PF-06651600 for the treatment of alopecia areata (AA). B7981032 is a phase 3, open label, multi-center, long-term study investigating the safety and efficacy of PF-06651600 in adult and adolescent participants with AA. C1071001 (MAGNETISMM-1) is a phase 1, open label study to evaluate the safety, pharmacokinetic, pharmacodynamic and clinical activity of elranatamab (PF-06863135), a B-Cell maturation antigen (BCMA) – CD3 bispecific antibody, as a single agent and in combination with immunomodulatory agents in patients with relapsed/refractory advanced multiple myeloma (MM). C1131001: a phase 1, randomized, multi-center, double-blind, sponsor open, placebo-controlled, single and multiple dose-escalation study to evaluate the safety, tolerability, pharmacokinetics and pharmacodynamics of pf-06835375 in subjects with seropositive systemic lupus erythematosus or rheumatoid arthritis. | 2022-01-13 | 2022-01-13 | 2022-01-13 | GCP_T2_Jan-2022_Multiple Protocols: Vendor Responsibilities: Sample Analysis_Labcorp Central Laboratory Services_USA |  | YES | 2022-06-03 | Root Cause Analysis-A cumulative total of 256 laboratory sample accession numbers associated with 7 Pfizer Clinical Trials were impacted by this event. Labcorp was requested to provide the outcome of their investigation to describe failure to perform analytical testing correctly (according to instructions, calibration, validation). Subsequently, a Root Cause Analysis (RCA) was conducted and the outcome of the Labcorp Quality Management System (QMS) report was reviewed with SQE Team (QE-00263743; Title: TBNK Trucount issue [Enterprise Level Investigation]).-Following receipt of laboratory sample accession numbers impacted by this Labcorp Enterprise Level quality event, all 8 ongoing Pfizer studies were informed - B7451015, B7451037, B7931028, B7981007, B7981028, B7981032, C1071001, C1131001.-Not Required | Yes |  | 2022-02-10 | 2022-05-17 18:01 |  | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis |  | 2022-02-11 20:57 | No Process Assigned | Amanda Stetka | Not Applicable | Labcorp asked to provide more details regarding scope (participant #, visit dates, visit numbers, tests involved). Issue escalated up the SM line. Meeting being arranged to discuss scope and next steps. | The SQE Team, including members of the Study Team, will determine if there is any impact to data and if the data will be used for study reporting. | Tegtmeier, Jamie |  |  |  |  | MODEL 2 - HYBRID | Inflammation & Immunology
QE-183659 | B7981028 | (Empty) | QE-183659 |  | PFIZER | N | Minor | Closed | Documented review of the B7891027 and B7981028 IQMPs was not completed within 120 days of the approval of protocol amendment 2, as required by the now retired QMS06-GSOP-RF03 6.0 Study-Specific Quality Risk Management Checklist 03 Apr 2023. This requirement is now captured in QMS06-GSOP v9 effective 28Apr2025 section 4.4.2: "Updates to address the changes introduced in protocol amendments must be made within 30 business days before or 120 calendar days after the earliest amendment date to be included in that update of the study risk profile (aggregate) (ie, if two or more amendments occur within one month) and may include any other relevant updates. If no updates are required, the decision is documented in the risk management system." B7981028 is the extension study to B7981027, both of which approved protocol amendment 2 on 6Jan2025. FSFV has not been achieved by these studies, so no risk to participants or data integrity occurred. The study teams, including the assigned AQL, were consumed with implementing the EMA requirement for including the WISC-V assessment, which is new for Pfizer. The complexity of this tool and associated requirements distracted the AQL from the need for review specific to protocol amendment 2. | 2025-06-04 | 2025-06-06 | 2025-06-06 18:22 | GCP_Minor_Jun-2025_B7981027; B7981028: CMCD: Integrated Quality Management Plan (IQMP) Updates/Approvals_Pfizer_Global |  | NO |  |  | No |  |  | 2025-06-06 |  | Quality Procedures | Requirement/process not met |  |  | QMS06-Risk Management for Clinical Development | Walter Sauer |  | Confirmed with the study team that no updates to the B7981027 or 1028 IQMPs were required due to protocol amendments 2. During review of AMD 3 for both studies this week, where again no updates were required, the system was annotated to indicate that this week's review included both AMD 2 and 3. |  |  | NA | Human Performance | Omission Error |  | MODEL 2 - HYBRID | Inflammation & Immunology
QE-200595 | B7981028 | (Empty) | QE-200595 |  | PPD, INC. | N | Major | In Investigation | PPD received notification from Greiner Bio-One that their VACUETTE Serum Non-gel tubes are not FDA-cleared for routine clinical chemistry analysis. This information is critical as it may impact the regulatory compliance of the studies conducted using these tubes. The tubes are only approved for viral marker testing and routine immunohematology testing including red cell grouping, RH typing and antibody screening. Greiner Bio-One has not submitted these tubes for FDA approval for use in routine clinical chemistry analysis.The VACUETTE Serum Non-GEl tubes are CE-marked for use in routine chemistry testing in the EU under the In Vitro Diagnostic Regulation (IVDR). Therefore, there is no impact on studies conducted within the EU and APAC using these tubes. Only studies conducted in North America are impacted. The actual date this occurred is unknown so the awareness date was used for the date occurred.Serious breach will need to be assessed. Below is a list of potentially impacted studies:B7451023B7841014B7981027B7981028B8011006C0371002C0371003C1131003C2321003C2321014C3391008C4221015C4221016C4671026C5001001C5541010 | 2025-09-09 | 2025-09-10 | 2025-09-10 16:27 | GCP_Major_Sep-2025_Multiple: Greiner Bio-One_PPD, INC_USA |  | NO | 2026-09-24 |  | Yes |  |  |  |  | Compliance Requirements - Applicable Approvals/Regulatory Required Essential Documents, Third Party Management | Applicable regulatory approvals not obtained or inadequate use of regulatory required essential documents, Inadequate third-party contract dev,execution,revision/update (eg. obsolete safety exhibit, missing signature,dates mis-aligned) |  |  | CT29-Management of Clinical Study BioSpecimens | Karen Barrett |  | Immediate actions by PPD:Conducted a thorough review of all studies utilizing the Greiner Bio-One VACUETTE® SerumNon-Gel tubes.• Initiated communication with Greiner Bio-One to obtain detailed information and clarification regarding the intended use and regulatory status of these tubes.• Halted the use of these tubes for chemistry testing in new studies and have begun using SST-2.5mL (cat # 454243) from Greiner-Bio.PPD initiated a quality event within their QA system and will conduct a full investigation (QE067388). A comprehensive review by study teams of the study protocol and data to determine necesssary actions. |  |  | placeholder | Method/Procedure | Procedure/Form/Plan | Inconsistent With or a Different Interpretation of Regulatory Requirements (Document Standard Lacking/Incorrect Standard... | MODEL 2 - HYBRID | Inflammation & Immunology
QE-210614 | B7981028 | (Empty) | QE-210614 |  | PFIZER | N | Minor | Closed | The Program B798 PEOI (Potential Events of Interests) are captured differently in the Clario 'Communication &amp; Process Plan' vs. the Clario "Adjudication Charter". For DM and Clinical Reconciliation listings, the "Adjudication Charter" PEOI list is being utilized. However, the vendor Clario (at Pfizer's Clinical direction) is utilizing the PEOIs embedded in an excel file in Clario 'Communication &amp; Process Plan'. This incongruence is causing reconciliation fallout and documentation that is confusing and not in alignment. | 2025-10-30 | 2025-11-03 | 2025-11-05 22:31 | GCP_Minor_Nov-2025_B798 Protocols: Potential Events of Interest (PEoI)_Pfizer_Global |  | NO |  |  | No |  |  | 2025-11-05 |  | Quality Oversight/Documentation | Inadequate quality documentation |  |  | CT22-Independent Oversight Committees | Ammber Dunn |  | Ammber initially met with B798 Clinical Lead Amy Freyman and Illeana to discuss this nonconformance in May 2025. It was decided at that time to no update to PEOI list was needed and that Charter should be updated. Charter has not been updated as agreed upon. |  |  | NA | Personnel | Inadequate Information for Determination |  | MODEL 2 - HYBRID | Inflammation & Immunology
QE-214803 | B7981028 | (Empty) | QE-214803 |  | ADVARRA INC | N | Minor | Closed | During the 11Nov2025 monitoring visit, the site monitor noted that the Assent form used for 10202001 on B7981028 had text that was upside down in the speech bubble. The site had pulled the document directly from the Central IRB portal from their approved documents. The GCTM (QE reporter) escalated the issue to the IRB contact on 14Nov2025 with photographic evidence of the upside text from the hard copy used on site, along with a screenshot of the documents available on the IRB portal, which did not include the Assent form with the error. The site provided the electronic file they used, and it had the same file name and document information (approval and version) as the document that was posted on the IRB portal, but the IRB portal version did not contain the error. The GCTM included these documents to the IRB contact as well, noting that the erroneous document could not be found on the IRB portal for this site. The issue with formatting error had been previously raised to the IRB for the B7981027 study as per the previous QE submitted, QE-210321. During the investigation of the previous issue, the IRB noted they are not allowed to delete any documents from the IRB portal, so it was an issue the GCTM raised that not only had there also been a formatting error on the B7981028 study, but the erroneous document was no longer present on the portal. The IRB confirmed on 20Nov2025 that an IRB coordinator had removed the incorrect version from the portal, which was against standard process and correct process was reviewed. The IRB has been asked to QC the rest of the sites in B7981028, the outcome is pending. | 2025-11-21 | 2025-11-24 | 2025-11-25 18:10 | GCP_Minor_Nov-2025_B7981028: Informed Consent Document: Assent_Advarra_USA |  | NO |  |  | No |  |  | 2025-11-25 |  | Quality Oversight/Documentation | Inadequate quality documentation |  |  | CT05-Informed Consent Document | Jessica Aponte |  | The site monitor instructed the site pull the correct version of the Assent from the IRB portal and re-administer the Assent at the next participant visit. The IRB has re-uploaded the incorrect version of the Assent to the IRB portal with indication "DO NOT USE" in the file name. IRB requested to QC the rest of the documents for the rest of the sites. |  |  | NA | Human Performance | Application Error |  | MODEL 2 - HYBRID | Inflammation & Immunology
QE-222525 | B7981028 | N | QE-222525 | 1020 | Mercedes Gonzalez (B7981028-1020) | N | Major | Approved - In CAPA | B7981028 Site 1020 site study coordinator (SC) emailed the Unblinded CRA requesting the score of an assessment (SALT) at Month 3 for 10202001 that is supposed to remain blinded to the site and blinded study team. The SC requested the score as they believed it had not transmitted on the eCOA device. The Unblinded Monitor responded to the SC with the score requested via email with the PI, another site staff member, blinded CRA, two regional CTMs and the Global CTM in copy.The Unblinded CRA does not conduct any monitoring and was put into place to communicate the Screening and Baseline SALT scores to sites with B7981031 participants that roll over into B7981028 to determine eligibility as the vendor did not include an Eligibility Report at study start and is not able to keep only SALT scores for these specific rollover patients unblinded for these specific visits and blind the rest of the visit scores for these participants and for those that roll over from the B7981027 study. The scores decide the responder status for the rollover participants from B7981031 at Month 9 as compared to Baseline, and whether they have to switch to placebo as a non-responder in a blinded manner. As the Screening and Baseline SALT scores for the B7981031 rollover participants does need to remain blinded, it was standard for the study team members that were in copy to have been part of an email notification to the site. There is a process document for the Unblinded CRA to follow that was put into place at the beginning of this process. The vendor Eligibility report is not expected to be available until April 2026.The incident was communicated to the Pfizer Study Clinician, CSTL, and Syneos Global PM on 09Jan2026 by the GCTM. The Clinician responded on 12Jan2026 with agreement to submit a QE. | 2026-01-09 | 2026-01-12 | 2026-01-13 19:12 | GCP_Major_Jan-2026_B7981028: Unblinding: SALT Assessment_Gonzalez, Mercedes; Syneos Health_USA |  | YES |  | <p>For Study B7981028, the Severity of Alopecia Tool (SALT) score was required at the Screening and Baseline visits for rollover participants from study B7981031 to confirm eligibility. The SALT assessment was entered into a vendor device by the Principal Investigator, and the SALT score was calculated by the vendor and was not visible to study team members. Due to the unavailability of an eligibility report containing only Screening and Baseline SALT scores from the vendor, an unblinded monitor process was implemented. Under this process, an unblinded Clinical Research Associate (uCRA) accessed the vendor portal to retrieve SALT scores at Screening and Baseline and communicated applicable scores to the site via email. SALT scores were required to remain blinded after Screening and Baseline visits. At the Month 9 visit, blinded SALT score was used to determine treatment response; non responders were reassigned to placebo in a blinded manner.</p><p><br></p><p>On 09 Jan 2026, the site 1020 Clinical Research Coordinator emailed the uCRA requesting the Month 3 SALT score for participant 10202001 to confirm transmission of the assessment. The uCRA responded by emailing the Month 3 SALT score and copying blinded site staff and blinded study team members, resulting in dissemination of unblinded SALT score to multiple blinded recipients. The issue was identified on 09 Jan 2026 by the Global Clinical Trial Manager, who recognized that the email contained unblinding information and escalated the finding to the study team.&nbsp;</p><p><br></p><p>An impact assessment completed on 22 Jan 2026 confirmed that the participant, site staff, and blinded study team members remained blinded to treatment assignment. The Month 3 visit was not a responder visit, and the SALT score did not disclose treatment assignment. The event was therefore confirmed as an unblinding without impact.&nbsp;</p><p><br></p><p>An historical review was conducted of QEs in the electronic Quality Management System (eQMS) database to identify QEs that meet the following search criteria: Keywords: signal unavailable, blind; Timeframe: two years (01 Jan 2024 – 02 Feb 2026). Each historical QE was reviewed along with the QE details, root causes, and corrective and preventive actions. Through this review, it was concluded that the current QE (QE-222525) was not a repeat occurrence.</p> | Yes |  | 2026-02-16 |  |  | Data Collection and Management | Incorrect assignment/randomization and/or maintenance of the study blind |  | 2026-02-17 15:20 | DMB06-Randomization Schedule Data Blinding and Break Blind | Jessica Aponte | FALSE | The GCTM requested all recipients to not review the email and delete immediately. A separate email was sent to the same recipients by the GCTM with a reminder to not request SALT scores for B7981031 participants after the Baseline visit and included the protocol sections that discusses the Continuation of Study Treatment criteria and the blinded manner by which this is determined. The Unblinded CRA was also requested to reach back to the recipients to request deletion (without the unblinded information) and confirmation of permanent deletion of the email. The Pfizer study team was notified via email on 09Jan2026. |  |  | The disclosure of the blinded Severity of Alopecia Tool (SALT) score at the Month 3 visit occurred because participant 10202001 was the first to reach this timepoint in the study. Both the site Clinical Research Coordinator (CRC) and the Unblinded Clinical Research Associate (uCRA) did not recognize that SALT scores were required to remain blinded beyond the Baseline visit, as this requirement was not clearly indicated in the communication sent to the site or detailed in the uCRA's procedural instructions. | Human Performance | Application Error | Signals Unavailable or Ineffective | MODEL 2 - HYBRID | Inflammation & Immunology
QE-222525 | B7981028 | (Empty) | QE-222525 |  | SYNEOS HEALTH LLC | N | Major | Approved - In CAPA | B7981028 Site 1020 site study coordinator (SC) emailed the Unblinded CRA requesting the score of an assessment (SALT) at Month 3 for 10202001 that is supposed to remain blinded to the site and blinded study team. The SC requested the score as they believed it had not transmitted on the eCOA device. The Unblinded Monitor responded to the SC with the score requested via email with the PI, another site staff member, blinded CRA, two regional CTMs and the Global CTM in copy.The Unblinded CRA does not conduct any monitoring and was put into place to communicate the Screening and Baseline SALT scores to sites with B7981031 participants that roll over into B7981028 to determine eligibility as the vendor did not include an Eligibility Report at study start and is not able to keep only SALT scores for these specific rollover patients unblinded for these specific visits and blind the rest of the visit scores for these participants and for those that roll over from the B7981027 study. The scores decide the responder status for the rollover participants from B7981031 at Month 9 as compared to Baseline, and whether they have to switch to placebo as a non-responder in a blinded manner. As the Screening and Baseline SALT scores for the B7981031 rollover participants does need to remain blinded, it was standard for the study team members that were in copy to have been part of an email notification to the site. There is a process document for the Unblinded CRA to follow that was put into place at the beginning of this process. The vendor Eligibility report is not expected to be available until April 2026.The incident was communicated to the Pfizer Study Clinician, CSTL, and Syneos Global PM on 09Jan2026 by the GCTM. The Clinician responded on 12Jan2026 with agreement to submit a QE. | 2026-01-09 | 2026-01-12 | 2026-01-13 19:12 | GCP_Major_Jan-2026_B7981028: Unblinding: SALT Assessment_Gonzalez, Mercedes; Syneos Health_USA |  | YES |  | <p>For Study B7981028, the Severity of Alopecia Tool (SALT) score was required at the Screening and Baseline visits for rollover participants from study B7981031 to confirm eligibility. The SALT assessment was entered into a vendor device by the Principal Investigator, and the SALT score was calculated by the vendor and was not visible to study team members. Due to the unavailability of an eligibility report containing only Screening and Baseline SALT scores from the vendor, an unblinded monitor process was implemented. Under this process, an unblinded Clinical Research Associate (uCRA) accessed the vendor portal to retrieve SALT scores at Screening and Baseline and communicated applicable scores to the site via email. SALT scores were required to remain blinded after Screening and Baseline visits. At the Month 9 visit, blinded SALT score was used to determine treatment response; non responders were reassigned to placebo in a blinded manner.</p><p><br></p><p>On 09 Jan 2026, the site 1020 Clinical Research Coordinator emailed the uCRA requesting the Month 3 SALT score for participant 10202001 to confirm transmission of the assessment. The uCRA responded by emailing the Month 3 SALT score and copying blinded site staff and blinded study team members, resulting in dissemination of unblinded SALT score to multiple blinded recipients. The issue was identified on 09 Jan 2026 by the Global Clinical Trial Manager, who recognized that the email contained unblinding information and escalated the finding to the study team.&nbsp;</p><p><br></p><p>An impact assessment completed on 22 Jan 2026 confirmed that the participant, site staff, and blinded study team members remained blinded to treatment assignment. The Month 3 visit was not a responder visit, and the SALT score did not disclose treatment assignment. The event was therefore confirmed as an unblinding without impact.&nbsp;</p><p><br></p><p>An historical review was conducted of QEs in the electronic Quality Management System (eQMS) database to identify QEs that meet the following search criteria: Keywords: signal unavailable, blind; Timeframe: two years (01 Jan 2024 – 02 Feb 2026). Each historical QE was reviewed along with the QE details, root causes, and corrective and preventive actions. Through this review, it was concluded that the current QE (QE-222525) was not a repeat occurrence.</p> | Yes |  | 2026-02-16 |  |  | Data Collection and Management | Incorrect assignment/randomization and/or maintenance of the study blind |  | 2026-02-17 15:20 | DMB06-Randomization Schedule Data Blinding and Break Blind | Jessica Aponte | FALSE | The GCTM requested all recipients to not review the email and delete immediately. A separate email was sent to the same recipients by the GCTM with a reminder to not request SALT scores for B7981031 participants after the Baseline visit and included the protocol sections that discusses the Continuation of Study Treatment criteria and the blinded manner by which this is determined. The Unblinded CRA was also requested to reach back to the recipients to request deletion (without the unblinded information) and confirmation of permanent deletion of the email. The Pfizer study team was notified via email on 09Jan2026. |  |  | The disclosure of the blinded Severity of Alopecia Tool (SALT) score at the Month 3 visit occurred because participant 10202001 was the first to reach this timepoint in the study. Both the site Clinical Research Coordinator (CRC) and the Unblinded Clinical Research Associate (uCRA) did not recognize that SALT scores were required to remain blinded beyond the Baseline visit, as this requirement was not clearly indicated in the communication sent to the site or detailed in the uCRA's procedural instructions. | Human Performance | Application Error | Signals Unavailable or Ineffective | MODEL 2 - HYBRID | Inflammation & Immunology
QE-227763 | B7981028 | (Empty) | QE-227763 |  | ERESEARCH TECHNOLOGY INC, A CLARIO COMPANY, PFIZER | N | Major | Closed | Clario had a cybersecurity incident which involved Pfizer studies.Late on September 28, 2025, Clario’s IT Security Department learned that an unauthorized user obtained access to one instance of an application called Jira (the “incident”). Jira is separate from Clario’s clinical trial systems. The impacted instance of Jira is used by Clario’s Imaging R&amp;D team for software development-related project management. | 2025-10-03 | 2026-02-11 | 2026-02-12 15:34 | GCP_Major_Feb-2026_Multiple Protocols: Cyber Security Incident_Clario_Global |  | YES |  | <p>On 11 Feb 2026, the Pfizer Outcomes Vendor Services representative in the Business Vendor Strategic Management (BVSM) group reported that one of the vendors contracted for medical imaging and central reader services, Clario, and used on 29 Pfizer studies, experienced a cybersecurity incident. The event posed a potential for adverse impact to participant rights and/or Pfizer data confidentiality as the vendor’s data security has been compromised.</p><p><br></p><p>On 28 Sep 2025, Clario’s Information Technology (IT) Security Department learned that an unauthorized user obtained access to one instance of an application called Jira. Jira is an application that Clario licenses from a third-party and is separate from Clario’s clinical trial systems. One of the functionalities within Jira is the ability to send and receive messaging tickets. Clario’s R&amp;D professionals use this ticketing function to communicate with one another in connection with various Imaging &amp; Specialty Solutions software development projects.</p><p><br></p><p>In this cyber security incident, the threat actor accessed tickets within Jira and was able to download the tickets as well as attachments to those tickets. The threat actor also edited or deleted data in Jira but we were able to restore from backup.</p><p><br></p><p>The unauthorized access occurred through valid credentials for a single Jira user account that was not protected by multi-factor authentication (MFA). At the time of the incident, the compromised instance of Jira was accessible from the Internet. MFA was not enabled for this individual user because Single Sign-On (SSO) integration had not yet been deployed to production for the impacted instance of Jira at the time of the intrusion.</p><p><br></p><p>Upon learning of the incident, Clario immediately restricted public access to the impacted Jira application, disabled the compromised Jira account, and out of an abundance of caution disabled Microsoft O365 credentials for the user account associated with the compromised Jira account.&nbsp;</p><p><br></p><p>Clario also engaged external forensic experts (Mandiant) to support the investigation and remediation process. It was confirmed by Mandiant that the unauthorized user’s access appeared to have been limited to the instance of Jira and associated tools used internally by Clario’s Imaging R&amp;D team. This included messaging tickets sent and received by members of the Clario Imaging R&amp;D team through Jira and any files that may have been attached to those tickets.&nbsp;</p><p><br></p><p>The cybersecurity incident was submitted to Pfizer Protect at the time Pfizer BVSM became aware of the incident in on 03 Oct 2025. The Pfizer Global Information Security Team and the Pfizer Global Privacy Office were contacted at the time of awareness to begin their investigations.&nbsp;</p><p><br></p><p>It was confirmed by Pfizer Global Security that the Jira data was key-coded data and Clario did not hold the key to the data. As a result, there would be no way to link the key coded data to a participant.&nbsp;</p><p><br></p><p>Pfizer Global Information Security reported their investigation was closed on 09 Feb 2026 after receiving the Statement of Confidence from Clario that there was no evidence that the unauthorized access impacted Clario’s clinical trial systems or the study data contained in those systems nor did it impact Jira instances for other Clario service lines such as electronic Clinical Outcomes Assessment (eCOA) data.&nbsp;</p><p><br></p><p>The Outcomes Vendor Services Lead was able to perform a review of all impacted Jira instances and was able to confirm that the information in the Jira tickets did not contain Personal Identifying Information or Personal Health Information.</p><p><br></p><p>A review of the Clario and Mandiant investigation documentation for this cybersecurity incident was completed. It was confirmed no additional actions were required by Clario to address the issue and prevent it from recurring.</p><p><br></p><p>A Gap Analysis Investigation was conducted therefore no root cause was identified and a repeat occurrence review to identify prior QEs with the same or similar cause was not conducted.</p><p><br></p> | No | Quality Event only required gap analysis investigation | 2026-03-20 | 2026-03-20 |  | IT Systems, Quality Procedures | Failure to escalate or resolve a detected issue (quality control), IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) |  | 2026-03-20 20:41 | CP411, QMS01-Reporting and Management of Quality Events | Tracy Talaber Adams | FALSE | Upon learning of the incident, Clario immediately restricted public access to the impacted Jira application, disabled the compromised Jira account, and – out of an abundance of caution –disabled Microsoft O365 credentials for the user account associated with the compromised Jira account. At the direction of counsel, they also engaged external forensic experts to support investigation and remediation process. The unauthorized user’s access appears to have been limited to the instance of Jira and associated tools used internally by Clario’s Imaging R&amp;D team. This includes messaging tickets sent and received by members of the Clario Imaging R&amp;D team through Jira and any files that may have been attached to those tickets. Clario have seen no evidence that the unauthorized user connected to Clario’s systems more broadly nor that the unauthorized user was able to access Clario’s clinical trial applications where study data is stored.Clario notified Pfizer of the incident 5 business days after they learned of the issue. Pfizer Security and Global Privacy were engaged. |  |  | Gap Analysis&nbsp; | Gap Analysis | N/A | N/A | MODEL 2 - HYBRID | Inflammation & Immunology
QE-234134 | B7981028 | (Empty) | QE-234134 |  | SYNEOS HEALTH LLC | N | Major | In Investigation | Several gaps were identified for subcontractor approvals that were not obtained per QMS09. A total of 17 gaps were identified across 9 subcontractors that were engaged between Jul-2020 and Sep-2025, across 14 studies. The gaps fall under two main categories: “vendor approval is project specific and does not include the project” (7 instances), and “service contracted is not an approved service type for the vendor” (10 instances). Given that the root causes are portfolio-level rather than study-level, we are submitting a portfolio-level QE including all projects/vendors impacted, per the below list.C1071015 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C3651032 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C4991001 Part 2 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C4541011 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C5001004 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.B7451023 - Ametris (Digital Devices Bundled with Service): Vendor approval is project specific and does not include this project.C4951002 - Lionbridge Technologies LLC (Translations Services): Vendor approval is project specific and does not include this project.B7461039 - ClinPlus (Study Coordination Support Services): Service contracted is not an approved service type for this vendor.B7451031 - ICON Clinical Research Limited (Translations Services, Scales Only): Service contracted is not an approved service type for this vendor. C4541011 - HealthCarePoint.com Public Benefit Corporation (Rater Training): Service contracted is not an approved service type for this vendor.C4541011 - ICON Clinical Research Limited (Translations Services, Scales Only): Service contracted is not an approved service type for this vendor. C4951002 - Endpoint Clinical L.P. (Interactive Response Technology): Service contracted is not an approved service type for this vendor.B7471015 - ICON Clinical Research Limited (Medical Imaging - Central Reader): Service contracted is not an approved service type for this vendor.C4851001 - Marken Ltd. (Biospecimen Management): Service contracted is not an approved service type for this vendor.B7981027 - eResearch Technology (Rater Training): Service contracted is not an approved service type for this vendor.B7981028 - eResearch Technology (Rater Training): Service contracted is not an approved service type for this vendor.C4951063 - ICON Clinical Research Limited (Translations Services, Scales Only): Service contracted is not an approved service type for this vendor. | 2026-03-16 | 2026-03-17 | 2026-03-18 17:58 | GCP_Major_Mar-2026_Process/Enterprise Level: CMCD: Vendor Responsibilities: Sub-Contractor Approval_Syneos Health; Pfizer_Global |  | NO | [7 empty] | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | QMS09-Vendor Engagement | Lourdes Arnillas |  | Re-formatting of tools to ensure relevant information is included – completed 25Feb2026Rollout of a new process training across the portfolio – completed 03Mar2026Submission of subcontractor approval requests to close all 17 gaps – completed 13Mar2026Submission of this Quality Event (flagged for action on 16Mar2026) | [6 empty] | MODEL 2 - HYBRID | Inflammation & Immunology