## Standard_Quality_Dashboard - SQ
Case ID | Case Status | Observation ID | Obs Status | Submission Date | Issue Audit Report (Actual) | Center Number | principal investigator | Country | Description | Study ID | Protocol ID | Title Short Description | Drug Program Code | Rating | Event Type | Case CAPA Approved Due Date | Case CAPA Approved On | CAPA Plan In Place Timely | Obs CAPA Approved Due Date | Obs CAPA Approved On | Obs Target Completion Date | Obs Actual Completion Date | Case CAPA Closure Timely | Case Target Completion Date | Case Actual Completion Date | Obs CAPA Closure Timely | Selected Business Process | Taxonomy Level 1 | Taxonomy Level 2 | Study Status | Business Category | Study Phase | Study Priority | Asset | Dev China | Dev Japan | Rapid Model | Business Category
2201236 | Closed | 2201270 | Closed | 2022-01-13 | (Empty) | (Empty) | (Empty) | (Empty) | Product Protocol Number: B7451015 (Alias: JADE EXTEND) B7451037 B7931028 B7981007 B7981028 B7981032 C1071001 (Alias: (MAGNETISMM-1) C1131001 Involved Party / Country: Vendor: Labcorp Central Laboratory Services / United States Quality Event Description: Labcorp Central Laboratory Services (formerly Covance Central Laboratory Services (CCLS)) is contracted to provide specimen management, laboratory collection kits and kit logistics and also the management of clinical trial laboratory data. As related to this event, Labcorp follows their own processes related to T- and B-Cell Quantitation by Flow Cytometry (Test ID: TBNK) assay, analyses and non-CRF data transfers. Pfizer study protocols further describe blinded and exploratory laboratory data for reporting purposes. On 12-Jan-2022, a Labcorp Global Study Manager (GSM) reported via routine email communication to 1 Pfizer study team representative that the processing and analysis completed by Labcorp Indianapolis (USA) - Flow Cytometry Laboratory resulted in a reported data error following their implementation of TruCount Tubes (for flow cytometry) on 10-Jun-2021 and 23-Jul-2021. On 10-Feb-2022, Labcorp provided a listing of 256 laboratory sample accession numbers associated with Pfizer trials that were impacted by this Labcorp Enterprise Level quality event. Eight (8) ongoing Pfizer studies were informed as follows B7451015, B7451037, B7931028, B7981007, B7981028, B7981032, C1071001 and C1131001. Although there was a delay to report the quality event to Pfizer, Labcorp has reported that they managed the data discrepancy before any study data set was prepared and before any reporting event, including publication. Therefore, the SQE Team prioritized studies for data revision according to upcoming submissions and agreed that there are no submission timelines at risk due to this event. Consequent to agreement that there is no (significant) impact to data integrity, there was no indication that study participant location and serious breach reporting requirements were required to be further investigated. B7451015 is a phase 3 multi-center, long-term extension study investigating the efficacy and safety of arocitinib, with or without topical medications, administered to subjects aged 12 years and older with moderate to severe atopic dermatitis. B7451037 is a phase 2a randomized, double-blind, placebo-controlled, parallel group, multi-center study to investigate the mechanism of action of abrocitinib monotherapy in adult participants with moderate-to-sever atopic dermatitis. B7931028 is a phase 2b, double-blind, randomized, placebo-controlled, multicenter, dose-ranging study to evaluate the efficacy and safety profile of pf-06700841 in participants with active systemic lupus erythematosus (sle). B7981007 is a phase 2a, double-blind, randomized, placebo-controlled, parallel group study to evaluate the efficacy and safety of oral PF-06651600 and PF-06700841 as induction and open label extension treatment in subjects with moderate to severe crohn’s disease. B7981028 is a phase 3 pediatric long term extension study with PF-06651600 for the treatment of alopecia areata (AA). B7981032 is a phase 3, open label, multi-center, long-term study investigating the safety and efficacy of PF-06651600 in adult and adolescent participants with AA. C1071001 (MAGNETISMM-1) is a phase 1, open label study to evaluate the safety, pharmacokinetic, pharmacodynamic and clinical activity of elranatamab (PF-06863135), a B-Cell maturation antigen (BCMA) – CD3 bispecific antibody, as a single agent and in combination with immunomodulatory agents in patients with relapsed/refractory advanced multiple myeloma (MM). C1131001: a phase 1, randomized, multi-center, double-blind, sponsor open, placebo-controlled, single and multiple dose-escalation study to evaluate the safety, tolerability, pharmacokinetics and pharmacodynamics of pf-06835375 in subjects with seropositive systemic lupus erythematosus or rheumatoid arthritis. | B7981028 | B7981028 | GCP_T2_Jan-2022_Multiple Protocols: Vendor Responsibilities: Sample Analysis_Labcorp Central Laboratory Services_USA | B798 | Major | SQE | 2022-02-27 | 2022-02-11 | Y | 2022-02-27 | 2022-02-11 20:57 | 2022-06-03 | 2022-05-17 | Y | 2022-06-03 | 2022-05-17 | Y | NOT APPLICABLE | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
QE-200595 | In Investigation | QE-200595 | In Investigation | 2025-09-10 | (Empty) | (Empty) | PPD, INC. | (Empty) | PPD received notification from Greiner Bio-One that their VACUETTE Serum Non-gel tubes are not FDA-cleared for routine clinical chemistry analysis. This information is critical as it may impact the regulatory compliance of the studies conducted using these tubes. The tubes are only approved for viral marker testing and routine immunohematology testing including red cell grouping, RH typing and antibody screening. Greiner Bio-One has not submitted these tubes for FDA approval for use in routine clinical chemistry analysis.The VACUETTE Serum Non-GEl tubes are CE-marked for use in routine chemistry testing in the EU under the In Vitro Diagnostic Regulation (IVDR). Therefore, there is no impact on studies conducted within the EU and APAC using these tubes. Only studies conducted in North America are impacted. The actual date this occurred is unknown so the awareness date was used for the date occurred.Serious breach will need to be assessed. Below is a list of potentially impacted studies:B7451023B7841014B7981027B7981028B8011006C0371002C0371003C1131003C2321003C2321014C3391008C4221015C4221016C4671026C5001001C5541010 | B7981028 | B7981028 | GCP_Major_Sep-2025_Multiple: Greiner Bio-One_PPD, INC_USA | B798 | Major | SQE | 2026-04-02 | (Empty) | (Empty) | 2026-04-02 | (Empty) | 2026-09-24 | (Empty) | (Empty) | 2026-09-24 | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Compliance Requirements - Applicable Approvals/Regulatory Required Essential Documents | Applicable regulatory approvals not obtained or inadequate use of regulatory required essential documents | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
QE-200595 | In Investigation | QE-200595 | In Investigation | 2025-09-10 | (Empty) | (Empty) | PPD, INC. | (Empty) | PPD received notification from Greiner Bio-One that their VACUETTE Serum Non-gel tubes are not FDA-cleared for routine clinical chemistry analysis. This information is critical as it may impact the regulatory compliance of the studies conducted using these tubes. The tubes are only approved for viral marker testing and routine immunohematology testing including red cell grouping, RH typing and antibody screening. Greiner Bio-One has not submitted these tubes for FDA approval for use in routine clinical chemistry analysis.The VACUETTE Serum Non-GEl tubes are CE-marked for use in routine chemistry testing in the EU under the In Vitro Diagnostic Regulation (IVDR). Therefore, there is no impact on studies conducted within the EU and APAC using these tubes. Only studies conducted in North America are impacted. The actual date this occurred is unknown so the awareness date was used for the date occurred.Serious breach will need to be assessed. Below is a list of potentially impacted studies:B7451023B7841014B7981027B7981028B8011006C0371002C0371003C1131003C2321003C2321014C3391008C4221015C4221016C4671026C5001001C5541010 | B7981028 | B7981028 | GCP_Major_Sep-2025_Multiple: Greiner Bio-One_PPD, INC_USA | B798 | Major | SQE | 2026-04-02 | (Empty) | (Empty) | 2026-04-02 | (Empty) | 2026-09-24 | (Empty) | (Empty) | 2026-09-24 | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Third Party Management | Inadequate third-party contract dev,execution,revision/update (eg. obsolete safety exhibit, missing signature,dates mis-aligned) | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
QE-222525 | Approved - In CAPA | QE-222525 | Approved - In CAPA | 2026-01-12 | (Empty) | 1020 | Mercedes Gonzalez (B7981028-1020) | UNITED STATES | B7981028 Site 1020 site study coordinator (SC) emailed the Unblinded CRA requesting the score of an assessment (SALT) at Month 3 for 10202001 that is supposed to remain blinded to the site and blinded study team. The SC requested the score as they believed it had not transmitted on the eCOA device. The Unblinded Monitor responded to the SC with the score requested via email with the PI, another site staff member, blinded CRA, two regional CTMs and the Global CTM in copy.The Unblinded CRA does not conduct any monitoring and was put into place to communicate the Screening and Baseline SALT scores to sites with B7981031 participants that roll over into B7981028 to determine eligibility as the vendor did not include an Eligibility Report at study start and is not able to keep only SALT scores for these specific rollover patients unblinded for these specific visits and blind the rest of the visit scores for these participants and for those that roll over from the B7981027 study. The scores decide the responder status for the rollover participants from B7981031 at Month 9 as compared to Baseline, and whether they have to switch to placebo as a non-responder in a blinded manner. As the Screening and Baseline SALT scores for the B7981031 rollover participants does need to remain blinded, it was standard for the study team members that were in copy to have been part of an email notification to the site. There is a process document for the Unblinded CRA to follow that was put into place at the beginning of this process. The vendor Eligibility report is not expected to be available until April 2026.The incident was communicated to the Pfizer Study Clinician, CSTL, and Syneos Global PM on 09Jan2026 by the GCTM. The Clinician responded on 12Jan2026 with agreement to submit a QE. | B7981028 | B7981028 | GCP_Major_Jan-2026_B7981028: Unblinding: SALT Assessment_Gonzalez, Mercedes; Syneos Health_USA | B798 | Major | SQE | 2026-02-27 | 2026-02-17 | Y | 2026-02-27 | 2026-02-17 15:20 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | DMB06 - Study Subject Randomization Schedule | Data Collection and Management | Incorrect assignment/randomization and/or maintenance of the study blind | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
QE-222525 | Approved - In CAPA | QE-222525 | Approved - In CAPA | 2026-01-12 | (Empty) | (Empty) | SYNEOS HEALTH LLC | (Empty) | B7981028 Site 1020 site study coordinator (SC) emailed the Unblinded CRA requesting the score of an assessment (SALT) at Month 3 for 10202001 that is supposed to remain blinded to the site and blinded study team. The SC requested the score as they believed it had not transmitted on the eCOA device. The Unblinded Monitor responded to the SC with the score requested via email with the PI, another site staff member, blinded CRA, two regional CTMs and the Global CTM in copy.The Unblinded CRA does not conduct any monitoring and was put into place to communicate the Screening and Baseline SALT scores to sites with B7981031 participants that roll over into B7981028 to determine eligibility as the vendor did not include an Eligibility Report at study start and is not able to keep only SALT scores for these specific rollover patients unblinded for these specific visits and blind the rest of the visit scores for these participants and for those that roll over from the B7981027 study. The scores decide the responder status for the rollover participants from B7981031 at Month 9 as compared to Baseline, and whether they have to switch to placebo as a non-responder in a blinded manner. As the Screening and Baseline SALT scores for the B7981031 rollover participants does need to remain blinded, it was standard for the study team members that were in copy to have been part of an email notification to the site. There is a process document for the Unblinded CRA to follow that was put into place at the beginning of this process. The vendor Eligibility report is not expected to be available until April 2026.The incident was communicated to the Pfizer Study Clinician, CSTL, and Syneos Global PM on 09Jan2026 by the GCTM. The Clinician responded on 12Jan2026 with agreement to submit a QE. | B7981028 | B7981028 | GCP_Major_Jan-2026_B7981028: Unblinding: SALT Assessment_Gonzalez, Mercedes; Syneos Health_USA | B798 | Major | SQE | 2026-02-27 | 2026-02-17 | Y | 2026-02-27 | 2026-02-17 15:20 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | DMB06 - Study Subject Randomization Schedule | Data Collection and Management | Incorrect assignment/randomization and/or maintenance of the study blind | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
QE-227763 | Closed | QE-227763 | Closed | 2026-02-11 | (Empty) | (Empty) | ERESEARCH TECHNOLOGY INC, A CLARIO COMPANY | (Empty) | Clario had a cybersecurity incident which involved Pfizer studies.Late on September 28, 2025, Clario’s IT Security Department learned that an unauthorized user obtained access to one instance of an application called Jira (the “incident”). Jira is separate from Clario’s clinical trial systems. The impacted instance of Jira is used by Clario’s Imaging R&amp;D team for software development-related project management. | B7981028 | B7981028 | GCP_Major_Feb-2026_Multiple Protocols: Cyber Security Incident_Clario_Global | B798 | Major | SQE | 2026-03-29 | 2026-03-20 | Y | 2026-03-29 | 2026-03-20 20:41 | (Empty) | 2026-03-20 | (Empty) | (Empty) | 2026-03-20 | (Empty) | CP411 - Information Incident Response Policy | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
QE-227763 | Closed | QE-227763 | Closed | 2026-02-11 | (Empty) | (Empty) | ERESEARCH TECHNOLOGY INC, A CLARIO COMPANY | (Empty) | Clario had a cybersecurity incident which involved Pfizer studies.Late on September 28, 2025, Clario’s IT Security Department learned that an unauthorized user obtained access to one instance of an application called Jira (the “incident”). Jira is separate from Clario’s clinical trial systems. The impacted instance of Jira is used by Clario’s Imaging R&amp;D team for software development-related project management. | B7981028 | B7981028 | GCP_Major_Feb-2026_Multiple Protocols: Cyber Security Incident_Clario_Global | B798 | Major | SQE | 2026-03-29 | 2026-03-20 | Y | 2026-03-29 | 2026-03-20 20:41 | (Empty) | 2026-03-20 | (Empty) | (Empty) | 2026-03-20 | (Empty) | QMS01 - Quality Events | Quality Procedures | Failure to escalate or resolve a detected issue (quality control) | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
QE-227763 | Closed | QE-227763 | Closed | 2026-02-11 | (Empty) | (Empty) | PFIZER | (Empty) | Clario had a cybersecurity incident which involved Pfizer studies.Late on September 28, 2025, Clario’s IT Security Department learned that an unauthorized user obtained access to one instance of an application called Jira (the “incident”). Jira is separate from Clario’s clinical trial systems. The impacted instance of Jira is used by Clario’s Imaging R&amp;D team for software development-related project management. | B7981028 | B7981028 | GCP_Major_Feb-2026_Multiple Protocols: Cyber Security Incident_Clario_Global | B798 | Major | SQE | 2026-03-29 | 2026-03-20 | Y | 2026-03-29 | 2026-03-20 20:41 | (Empty) | 2026-03-20 | (Empty) | (Empty) | 2026-03-20 | (Empty) | CP411 - Information Incident Response Policy | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
QE-227763 | Closed | QE-227763 | Closed | 2026-02-11 | (Empty) | (Empty) | PFIZER | (Empty) | Clario had a cybersecurity incident which involved Pfizer studies.Late on September 28, 2025, Clario’s IT Security Department learned that an unauthorized user obtained access to one instance of an application called Jira (the “incident”). Jira is separate from Clario’s clinical trial systems. The impacted instance of Jira is used by Clario’s Imaging R&amp;D team for software development-related project management. | B7981028 | B7981028 | GCP_Major_Feb-2026_Multiple Protocols: Cyber Security Incident_Clario_Global | B798 | Major | SQE | 2026-03-29 | 2026-03-20 | Y | 2026-03-29 | 2026-03-20 20:41 | (Empty) | 2026-03-20 | (Empty) | (Empty) | 2026-03-20 | (Empty) | QMS01 - Quality Events | Quality Procedures | Failure to escalate or resolve a detected issue (quality control) | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology
QE-234134 | In Investigation | QE-234134 | In Investigation | 2026-03-17 | (Empty) | (Empty) | SYNEOS HEALTH LLC | (Empty) | Several gaps were identified for subcontractor approvals that were not obtained per QMS09. A total of 17 gaps were identified across 9 subcontractors that were engaged between Jul-2020 and Sep-2025, across 14 studies. The gaps fall under two main categories: “vendor approval is project specific and does not include the project” (7 instances), and “service contracted is not an approved service type for the vendor” (10 instances). Given that the root causes are portfolio-level rather than study-level, we are submitting a portfolio-level QE including all projects/vendors impacted, per the below list.C1071015 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C3651032 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C4991001 Part 2 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C4541011 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C5001004 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.B7451023 - Ametris (Digital Devices Bundled with Service): Vendor approval is project specific and does not include this project.C4951002 - Lionbridge Technologies LLC (Translations Services): Vendor approval is project specific and does not include this project.B7461039 - ClinPlus (Study Coordination Support Services): Service contracted is not an approved service type for this vendor.B7451031 - ICON Clinical Research Limited (Translations Services, Scales Only): Service contracted is not an approved service type for this vendor. C4541011 - HealthCarePoint.com Public Benefit Corporation (Rater Training): Service contracted is not an approved service type for this vendor.C4541011 - ICON Clinical Research Limited (Translations Services, Scales Only): Service contracted is not an approved service type for this vendor. C4951002 - Endpoint Clinical L.P. (Interactive Response Technology): Service contracted is not an approved service type for this vendor.B7471015 - ICON Clinical Research Limited (Medical Imaging - Central Reader): Service contracted is not an approved service type for this vendor.C4851001 - Marken Ltd. (Biospecimen Management): Service contracted is not an approved service type for this vendor.B7981027 - eResearch Technology (Rater Training): Service contracted is not an approved service type for this vendor.B7981028 - eResearch Technology (Rater Training): Service contracted is not an approved service type for this vendor.C4951063 - ICON Clinical Research Limited (Translations Services, Scales Only): Service contracted is not an approved service type for this vendor. | B7981028 | B7981028 | GCP_Major_Mar-2026_Process/Enterprise Level: CMCD: Vendor Responsibilities: Sub-Contractor Approval_Syneos Health; Pfizer_Global | B798 | Major | SQE | 2026-05-02 | (Empty) | (Empty) | 2026-05-02 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) | ONGOING | Inflammation & Immunology | PHASE III | MAINTAIN | AA Pediatric Program | China Global | JP_Global | MODEL 2 - HYBRID | Inflammation & Immunology