## Standard_Quality_Dashboard - Au
AMS Audit PR ID | AMS Observation PR ID | Target Completion Date | Actual Completion Date | TCD Due/Overdue Days | TCD Status | Observation Closed On | Observation Rating | Observation Phase | Investigator Full Name | Country | Unique Site Number | Type Of Entity | Issue Of Audit Report Actual | Issue Audit Closure Rpt Act | Observation Description | Response (Trackwise Only) | Actions Taken | CAPA Action Description | CAPA Action Created by | Responsibility | Responsible Contact | Audit Coordinator | Observation Status | Audit Status | Level 1 | Level 2 | Selected Business Process | Responsible Party Value | Rapid Model | Business Category | Site Care Partner | Cluster | Area ID | Area Name
AIA-009684 | QE-232669 | [5 empty] | Minor |  | Tadeusz Debniak, Tadeusz Debniak | POLAND | B7981094_1056 | GCP Site Audit | 2026-03-12 |  | Two newsletters were missing from the Pfizer Trial Master File (PTMF) and an English version of a Country Level Assent Form contained a typographical error [Pfizer CT01-GSOP Trial Master Files Version 8.0 (effective 03 Oct 2022)]. The following were noted: 1.) The English version of the Country Level Older Assent Form (Version 14 Jan 2025) had a typographical error on page 7, as it stated "Printed Name of Participant (chiled)" instead of "child". &nbsp;This error did not affect the Polish version which was used to generate the site level assent documentation. 2.) The Newsletter Issue 3 (Nov 2025) was missing from the PTMF. 3.) The Newsletter Issue 4 (Feb 2026) missing from the PTMF. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Lena Zajko | In Response | Pending Finding Closure | Document Management | Missing document | CT01 - Trial Master Files | PFIZER | MODEL 1 - INSOURCED | Inflammation & Immunology | Zajko, Lena | GSSO | 310 | EMEA
AIA-009684 | QE-232846 | [5 empty] | Minor |  | Tadeusz Debniak, Tadeusz Debniak | POLAND | B7981094_1056 | GCP Site Audit | 2026-03-12 |  | Two essential documents were missing from the electronic Investigator Site File (eISF) [ICH E6 (R3) 2.12.11]. The following were noted: 1.) The Investigator Brochure Version 12 (Jul 2025) was missing from the eISF. 2.) The Audit Confirmation Letter (15 Jan 2026) was missing from the eISF. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Lena Zajko | Issued | Pending Finding Closure | Document Management | Missing document | CT01 - Trial Master Files | SITE PERSONNEL | MODEL 1 - INSOURCED | Inflammation & Immunology | Zajko, Lena | GSSO | 310 | EMEA
AIA-009684 | QE-232667 | [5 empty] | Minor |  | Tadeusz Debniak, Tadeusz Debniak | POLAND | B7981094_1056 | GCP Site Audit | 2026-03-12 |  | For 4 of 4 participants reviewed, discrepancies between the source data and the corresponding electronic Case Report Form (eCRF) were identified [Pfizer B7981094 eCRF Completion Guidelines Version 5.0 (effective: 29 Oct 2025)]. The following were noted: Participant 10561005 1.) During the Screening Visit (27 Aug 2025), the participant did not agree to the optional photography but consent obtained was entered into the Informed Consent - Photography eCRF. &nbsp;The study team confirmed that no photographs from this study had yet been used for anything outside of the study. 2.) During the Screening Visit, the QT corrected for heart rate by Fridericia's cube root formula (QTcF) value was recorded as 421 milliseconds in the medical notes but was entered as 417 milliseconds in the Locally Read ECGs - SCR eCRF 3.) During the Week 12 Visit (03 Dec 2025), the participant global impression of alopecia areata was recorded in the questionnaire as greatly improved, but was entered as moderately improved in the Patient Global Impression - Alopecia Areta eCRF Patient 10561011 4.) During the Week 12 Visit (08 Jan 2026), the participant global impression of alopecia areata was recorded in the questionnaire as greatly improved, but was entered as moderately improved in the Participant Global Impression - Alopecia Areata eCRF Patient 10561013 5.) During the Week 4 Visit (08 Dec 2025), the time of the in-clinic doses of 100mg and 50mg were recorded in the medical notes as 14:40 and 14:41 respectively, but were entered into the PK Dosing Onsite 100mg and 50mg eCRFs as 14:31 and 14:40. Patient 10561016 6.) The start date of concomitant medication Kyleena was recorded in the medical notes as Nov 2022, but was entered as Nov 2021 in the Concomitant/Prior Medication eCRF Note: during the audit, the Clinical Research Associate generated queries for the above discrepancies. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Lena Zajko | Issued | Pending Finding Closure | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | DMB07 - CRF and Database Design | SITE PERSONNEL | MODEL 1 - INSOURCED | Inflammation & Immunology | Zajko, Lena | GSSO | 310 | EMEA
AIA-009684 | QE-232670 | [5 empty] | Minor |  | Tadeusz Debniak, Tadeusz Debniak | POLAND | B7981094_1056 | GCP Site Audit | 2026-03-12 |  | For 1 of 4 patents reviewed, the reporting of adverse events (AEs) via the electronic Case Report Form (eCRF) from the investigator site to Pfizer were inaccurate [Pfizer Protocol B7981094 (Final: 07 Jan 2025)]. The following was noted: For Participant 10561011, the severity of the AE elevated creatine kinase level was recorded in the medical motes as moderate, but was entered as mild in the AE eCRF. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Lena Zajko | Issued | Pending Finding Closure | AE reporting to Sponsor | Incomplete AE reporting | AEM01 - Adverse Event Monitoring | SITE PERSONNEL | MODEL 1 - INSOURCED | Inflammation & Immunology | Zajko, Lena | GSSO | 310 | EMEA
AIA-009701 | QE-231930 | [5 empty] | Major |  | KWON, OHSANG | KOREA, REPUBLIC OF | B7981094_1035 | GCP Site Audit | 2026-03-10 |  | For 7 of 7 participants reviewed, the source documentation process was inadequate and source data documentation/collection did not comply with the ALCOAC (Accurate, Legible, Contemporaneous, Original, Attributable, Complete) principles. [Pfizer Protocol B7981094 Final: 7 Jan 2025; ICH E6 R3 2.12.2] 1. The following source data were not complete. 1.1 For 7 of 7 participants reviewed, the blood pressure (BP) and pulse measurements were generated by test machines as thermal printouts, and the Study Coordinator transcribed these values into the Vital Signs Form; however, no certified hard copies were retained to preserve the thermal paper source data from degradation. 1.2 For Participant 10351015, the menstrual history was not documented in the electronic medical record (EMR) at the Screening visit; only the contraception requirements and method were recorded. 2. The following source data were not accurate. 2.1 For Participants 10351002, 10351015 and 10311022, the urine pregnancy tests were performed onsite using test kits; however, both the test lists and test results were documented in the electronic medical record (EMR) as being part of central laboratory procedures.&nbsp; 3. &nbsp;The following source data were not consistent. 3.1 For 7 of 7 participants reviewed, discrepancies were observed for the sample collection time between the laboratory confirmation recorded in the EMR and the Lab Requisition Form. For example, 3.1.1 For Participant 10351015, at the Day 1 visit (29 Sep 2025), in the Lab Requisition Form the collection time 10:28 AM on 29 Sep 2025 was documented, while in the EMR the collection time was recorded as 8:25 AM on 30 Sep 2025; At the Week 4 visit (27 Oct 2025), the PK sample collection times in the Lab Requisition Form 10:27 AM, 11:37 AM, and 1:06 PM were documented, while the corresponding times documented in the EMR were 10:39 AM, 12:33 PM, and 2:06 PM, respectively. 3.1.2 For Participant 10351002, at the Screening visit (21 Jul 2025), the collection time documented in the Lab Requisition Form was 11:40 AM, while in the EMR the collection time was recorded as 1:51 PM; At the Week 24 visit (2 Feb 2026), the collection time 12:27 PM was documented in the Lab Requisition Form, while the collection time was recorded as 12:32 PM in the EMR. 3.1.3 For Participant 10351036, at the Screening visit, in the Lab Requisition Form the collection time 2:44 PM was documented, while in the EMR the collection time was recorded as 1:08 PM. 3.1.4 For Participant 10351003, at the Day 1 visit (19 Aug 2025), in the Lab Requisition Form the collection time 1:53 PM was documented, while in the EMR the collection time was recorded as 3:41 PM; At the Week 4 visit (22 Sep 2025), the PK sample collection times in the Lab Requisition Form 11:58 AM, 1:07 PM, and 2:37 PM were documented, while the corresponding times documented in the EMR were 12:23 PM, 1:13 PM, and 2:49 PM, respectively. 4. The following source data were not available. 4.1 &nbsp;For 7 of 7 participants reviewed, it was observed that documentation to demonstrate the incubation period, and shipment date of tuberculosis samples at the Screening visit, was not available. 4.2 For Participant 10351036, the partial completion status of the Tanner Stage for Male Patients assessment and the associated rationale were not documented in the EMR by the Principal Investigator at the Day 1 visit. 4.3 For Participant 10351036, a weight of 48.5 kg was documented on the Lab Requisition Form at the Week 4 visit, although the weight was not measured at that visit; the most recent documented weight was 48.2 kg at the Day 1 visit. 4.4 For Participant 10351022, no documentation of returned IP quantities was available for the Week 12 visit (12 Jan 2026). 5. Source data were not always documented in a timely manner, as evidenced by EMR audit trails. For example, 5.1 For Participant 10351015, returned investigational product (IP) quantities (50 mg × 12 capsules; 100 mg × 12 capsules) were entered on 06 Jan 2026 in the EMR, while the corresponding Week 12 visit occurred on 29 Dec 2025. Urine pregnancy test result was entered on 27 Oct 2025, while the corresponding Day 1 visit occurred on 29 Sep 2025. 5.2 For Participant 10351022, the returned IP quantities were entered on 04 Dec 2025, and the adverse event comment cold (31 Oct 2025 ~ 01 Nov 2025) was entered on 27 Jan 2026, while the corresponding Week 4 visit occurred on 17 Nov 2025. 5.3 For Participant 10351024, the participant eligibility confirmation dated 13 Oct 2025 was entered on 04 Dec 2025. 5.4 For Participant 10351024, the returned IP quantities were entered on 04 Dec 2025, and IP compliance was entered on 21 Jan 2026, while the Week 4 visit occurred on 13 Nov 2025. 5.5 For Participant 10351031, the returned IP quantities were entered on 04 Dec 2025, while the Week 4 visit occurred on 20 Nov 2025; The returned IP quantities were entered on 26 Jan 2026, while the Week 12 visit occurred on 22 Jan 2026. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Yoo-Soon Kim | Issued | Pending Finding Closure | Data Collection and Management | Inadequate source data/documentation | INV04 - Investigational Site Management and Monitoring | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Inflammation & Immunology | Kim, Yoo-Soon | GSSO | 311 | APAC
AIA-009701 | QE-231938 | [5 empty] | Minor |  | KWON, OHSANG | KOREA, REPUBLIC OF | B7981094_1035 | GCP Site Audit | 2026-03-10 |  | Essential documents were missing from the Pfizer Trial Master File (PTMF) [Pfizer CT01-GSOP Trial Master Files Version 8.0 (effective 03 Oct 2022)]. This included: 1. Financial Disclosure Summary Reports for the Principal Investigator &nbsp;and 3 Sub-Investigators. 2. Pfizer B7981094 Newsletter Issue 3 dated Nov 2025. 3. Central laboratory manual Version 5 dated 26 Sep 2025 4. Photographer Approval Result Report for the study coordinator. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Yoo-Soon Kim | In Response | Pending Finding Closure | Document Management | Inadequate record retention and archival | CT01 - Trial Master Files | PFIZER | MODEL 1 - INSOURCED | Inflammation & Immunology | Kim, Yoo-Soon | GSSO | 311 | APAC
AIA-009701 | QE-231937 | [5 empty] | Minor |  | KWON, OHSANG | KOREA, REPUBLIC OF | B7981094_1035 | GCP Site Audit | 2026-03-10 |  | The monitoring and monitoring oversight activities did not consistently follow the Pfizer standard operating procedure (SOP) and monitoring plan. [Pfizer Study Monitoring Plan for Protocol B7981094 Version 29 Sep 2025; Pfizer SOP INV04-GSOP Investigational Site Management and Monitoring (effective 02 Dec 2024)]. 1. The Site Signature Sheet and Delegation of Duties Log (INV02‑INV04‑GSOP‑RF09, Version 12.0) provided to the site did not include the following required sections, as they were removed by the Site Care Partner due to a misunderstanding of the completion instructions: Section 2: Types of Personal Data Collected and Processed; Uses and Disclosures of Personal Data; Transfer of Personal Data; Personal Data Rights; Retention; Data Protection; and Complaints and Data Protection Officer Contact Information. Section 3: Delegation Information. 2. In the Monitoring Visit Report, it was documented that the monitor visited the site on 22 Jan 2026 and 27 Jan 2026; however, in the Site Visit Log the monitoring visits were recorded as having occurred on 23 Jan 2026 and 29 Jan 2026. 3. Monitoring activities were insufficient to identify and/or address issues reported in other findings of this audit report. This included: 3.1 For 7 of 7 participants reviewed, the source documentation process was inadequate and source data documentation/collection did not comply with the ALCOAC (Accurate, Legible, Contemporaneous, Original, Attributable, Complete) principles. (QE-231930). 3.2 The Principal Investigator did not maintain a complete and accurate Signature Sheet and Delegations of Duties Log. (QE-231932). 3.3 Essential documents were not missing from the Pfizer Trial Master File (QE-231938). 3.4 Training records were not accurately maintained in the Training System Firecrest. (QE-231928). | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Yoo-Soon Kim | In Response | Pending Finding Closure | Site Management and Monitoring | Failure to follow study specific monitoring plan/ requirements | INV04 - Investigational Site Management and Monitoring | PFIZER | MODEL 1 - INSOURCED | Inflammation & Immunology | Kim, Yoo-Soon | GSSO | 311 | APAC
AIA-009701 | QE-231932 | [5 empty] | Minor |  | KWON, OHSANG | KOREA, REPUBLIC OF | B7981094_1035 | GCP Site Audit | 2026-03-10 |  | The Principal Investigator (PI) did not maintain a complete and accurate Signature Sheet and Delegations of Duties Log (SSDDL). [Pfizer Rater Qualification Plan B7981094 Version 12 Feb 2025; ;&nbsp; ICH E6 (R3 2.3.3) ]. The following were noted: 1. The Rater identification was not recorded for one Sub-Investigator as required by the Pfizer Rater Qualification Plan. 2. The PI and the audiologist provided their English signature on the SSDDL, whereas the electronic medical record and other study documents were signed using their Korean signature | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Yoo-Soon Kim | Issued | Pending Finding Closure | Document Management | Inadequate record retention and archival | INV04 - Investigational Site Management and Monitoring | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Inflammation & Immunology | Kim, Yoo-Soon | GSSO | 311 | APAC
AIA-009701 | QE-231928 | [5 empty] | Minor |  | KWON, OHSANG | KOREA, REPUBLIC OF | B7981094_1035 | GCP Site Audit | 2026-03-10 |  | Training records were not accurately maintained in the Training System Firecrest. [Pfizer Study Training Plan B7981094 Version 3 dated 19 Sep 2025]. The eight lab technicians and one audiologist were not registered in Firecrest to manage and record the training courses per study requirements. Note:Per site initiation visit report they were trained offline in the lab manual and audiometry at the site. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Yoo-Soon Kim | Issued | Pending Finding Closure | Training & Qualifications | Training not completed or documented in a timely manner | CT33 - Study-Specific Training | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Inflammation & Immunology | Kim, Yoo-Soon | GSSO | 311 | APAC
AIA-008469 | QE-218803 | 2026-03-16 | 2026-02-20 |  | Completed On Time |  | Minor |  | Jonathan Wolfe, Jonathan Wolfe | UNITED STATES | B7981094_1015 | GCP Site Audit | 2025-12-16 |  | For 4 of 4 participant records reviewed, the informed consent process notes and corrections to the informed consent document (ICD) were inadequate (ICH GCP E6 (R3) 2.8). 1. For 4 of 4 participant records reviewed, the documentation of the informed consent process was not accurate since the note in the participant chart was initialed by the study coordinator (without date), although the Principal Investigator (PI) had conducted the process.&nbsp; 2. Participant 10151002 consented on 30 Apr 2025 for the optional procedure; however, the informed consent process was not documented in the source records.&nbsp; 3. For Participant 10151006, a correction was made to the ICD by the study coordinator and not by the PI who had signed the ICD incorrectly. Note: the PI had signed both the “Person Obtaining Consent” and the “Impartial Witness” sections of the ICD in error. The “Impartial Witness” section was corrected by the coordinator.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Refer to Issue ID #1-AFQF48U, 1-AFQF48Y, 1-AFQF492 on the attached Clinical Trial Management System Issue Action log confirming all corrections/updates were completed for this finding. | 1. The Principal Investigator (PI) will create a note to file to clarify he was responsible for obtaining informed consent for all participants. He confirmed the informed consent process was followed but the study coordinator inadvertently signed off on the process document as she was a witness to the process. 2. The PI will add a late entry to confirm the consent process for the optional procedure.3. The PI will add a late entry to explain the initial errors and confirm the correction is made by him. 1-3 The Clinical Research Associate (CRA) will confirm NTF is created and filed. The CRA will confirm late entry is entered per ALCOAC (attributable, legible, contemporaneous, original, accurate, complete) principles.Responsible Roles: Principal Investigator/ Clinical Research Associate | Jennifer Wysocki |  | - | Jennifer Wysocki | Closed | Closed | Informed Consent | Inadequate consent process at the investigator site | CT05 - Informed Consent Documents | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Inflammation & Immunology | Wysocki, Jennifer Marie | GSSO | 84 | AMERICAS
AIA-008469 | QE-215072 | 2026-03-16 | 2026-03-13 |  | Completed On Time |  | Major |  | Jonathan Wolfe, Jonathan Wolfe | UNITED STATES | B7981094_1015 | GCP Site Audit | 2025-12-16 |  | Monitoring activities were inadequate with regards to detecting and/or effectively addressing issues identified in this audit (Study Monitoring Plan (Version 2: 29 Sep 2025), Pfizer Standard Operating Procedure INV04 GSOP Investigational Site Management and Monitoring (effective 01 Jun 2022)).&nbsp; Examples of deficiencies in monitoring activities noted in other observations were as follows:&nbsp; 1. QE-215066: For 4 of 4 participant records reviewed, source documentation practices were inadequate not in accordance with ALCOAC (attributable, legible, contemporaneous, original, accurate, complete) principles. 2. QE-215071: Documentation related to Investigational Product (IP) preparation was inadequate.&nbsp; 3. QE-215067: Electronic Case Report Forms (eCRFs) entries contained discrepancies with the source documentation 4. QE-215068: Essential documents were incomplete or missing from the electronic Investigator Site File.&nbsp; 5. QE-218208: The documented delegation of duties was inadequate.&nbsp; 6. QE-218224: One study coordinator conducted study related activities prior to completing training.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | All findings in this report have been corrected and applicable corrective and preventative actions have been completed for each applicable finding. Refer to the attached Clinical Trial Management System Issue Action log. | All findings in this report will be corrected and applicable corrective and preventative actions and effectiveness checks will be completed for each applicable finding. Responsible Roles: Clinical Research Associate | Jennifer Wysocki |  | - | Jennifer Wysocki | Approved - In CAPA | Closed | Site Management and Monitoring | Failure to detect/document | INV04 - Investigational Site Management and Monitoring | PFIZER | MODEL 1 - INSOURCED | Inflammation & Immunology | Wysocki, Jennifer Marie | GSSO | 84 | AMERICAS
AIA-008469 | QE-215072 | 2026-03-16 | 2026-03-13 |  | Completed On Time |  | Major |  | Jonathan Wolfe, Jonathan Wolfe | UNITED STATES | B7981094_1015 | GCP Site Audit | 2025-12-16 |  | Monitoring activities were inadequate with regards to detecting and/or effectively addressing issues identified in this audit (Study Monitoring Plan (Version 2: 29 Sep 2025), Pfizer Standard Operating Procedure INV04 GSOP Investigational Site Management and Monitoring (effective 01 Jun 2022)).&nbsp; Examples of deficiencies in monitoring activities noted in other observations were as follows:&nbsp; 1. QE-215066: For 4 of 4 participant records reviewed, source documentation practices were inadequate not in accordance with ALCOAC (attributable, legible, contemporaneous, original, accurate, complete) principles. 2. QE-215071: Documentation related to Investigational Product (IP) preparation was inadequate.&nbsp; 3. QE-215067: Electronic Case Report Forms (eCRFs) entries contained discrepancies with the source documentation 4. QE-215068: Essential documents were incomplete or missing from the electronic Investigator Site File.&nbsp; 5. QE-218208: The documented delegation of duties was inadequate.&nbsp; 6. QE-218224: One study coordinator conducted study related activities prior to completing training.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Refer to the attached Country Meeting minutes (page 9) for documentation of the escalated issue related to multiple folders (approximately 18 subfolders) under the IRB main folder which could cause confusion when sites are filing documents and Clinical Research Associates are monitoring the documents. The Clinical Research Associate (CRA) conducted Site Management and Monitoring Activities per INV04-GSOPRF13 and Clinical Research Associate confirmed all corrections have been made and marked the resolution within Clinical Trial Management System (CTMS). The Site Care Partner (SCP), reviewed the reports and associated logs and documented review per INV02-INV04- GSOP-RF14_Review of Site Activities. Refer to attached Visit Reports dated 09JAN2026 and 20FEB2026 and the Contact report dated 02MAR2026 for items that could not be addressed during the onsite visits. Also refer to the Issues Action log. | The Site Care Partner will escalate the issue to the study team related to multiple folders (approximately 18 subfolders) under the IRB main folder which could cause confusion when sites are filing documents and Clinical Research Associates are monitoring the documents. The Clinical Research Associate (CRA) will conduct Site Management and Monitoring Activities per INV04-GSOPRF13. CRA to confirm all corrections have been made and mark the resolution within Clinical Trial Management System (CTMS). The report reviewer, Site Care Partner (SCP), will review reports and associated logs. The SCP will document their review per INV02-INV04- GSOP-RF14_Review of Site Activities. Responsible Roles: Site Care Partner/Clinical Research Associate | Jennifer Wysocki |  | - | Jennifer Wysocki | Approved - In CAPA | Closed | Site Management and Monitoring | Failure to detect/document | INV04 - Investigational Site Management and Monitoring | PFIZER | MODEL 1 - INSOURCED | Inflammation & Immunology | Wysocki, Jennifer Marie | GSSO | 84 | AMERICAS
AIA-008469 | QE-215072 | 2026-03-16 | 2026-03-13 |  | Completed On Time |  | Major |  | Jonathan Wolfe, Jonathan Wolfe | UNITED STATES | B7981094_1015 | GCP Site Audit | 2025-12-16 |  | Monitoring activities were inadequate with regards to detecting and/or effectively addressing issues identified in this audit (Study Monitoring Plan (Version 2: 29 Sep 2025), Pfizer Standard Operating Procedure INV04 GSOP Investigational Site Management and Monitoring (effective 01 Jun 2022)).&nbsp; Examples of deficiencies in monitoring activities noted in other observations were as follows:&nbsp; 1. QE-215066: For 4 of 4 participant records reviewed, source documentation practices were inadequate not in accordance with ALCOAC (attributable, legible, contemporaneous, original, accurate, complete) principles. 2. QE-215071: Documentation related to Investigational Product (IP) preparation was inadequate.&nbsp; 3. QE-215067: Electronic Case Report Forms (eCRFs) entries contained discrepancies with the source documentation 4. QE-215068: Essential documents were incomplete or missing from the electronic Investigator Site File.&nbsp; 5. QE-218208: The documented delegation of duties was inadequate.&nbsp; 6. QE-218224: One study coordinator conducted study related activities prior to completing training.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Refer to attached Country Operations Meeting Minutes dated 21JAN2026 (Slide 9) and 04FEB2026; the February 2026 Newsletter (page 5) and associated email to sites, dated 10FEB2026. All actions were completed. Also, the Study Monitoring Plan was updated to include guidance around the requirements for the Pfizer provided worksheets (refer to Version 3.0 dated 13MAR2026 (section 1) attached). | The study team will share some lessons learned from this audit during a country call with the B7981094 Clinical Research Associates. For their awareness during future site monitoring and management activities, there will be a reminder on the following: -Compliance documentation required to be documented in the source per Protocol dated 07JAN2025, section 6.5. Specifically, documenting compliance percentage and confirming any compliance &lt;80% or &gt;120% between visits with study intervention and that there is documentation of appropriate actions per protocol. As the Pfizer-provided worksheets (e.g. SALT, EBA/ELA, C-SSRS, PGI-C, P-SAT) do not contain fields for Rater ID/initials, the site should ensure that the rater’s ID and the rater’s dated initials are documented directly in the source document at the time the assessment is completed. The Global Study Manager will also include these reminders in the upcoming Newsletter to the sites and study team.Responsible Roles: Global Study Manager/country Study Operations Manager | Jennifer Wysocki |  | - | Jennifer Wysocki | Approved - In CAPA | Closed | Site Management and Monitoring | Failure to detect/document | INV04 - Investigational Site Management and Monitoring | PFIZER | MODEL 1 - INSOURCED | Inflammation & Immunology | Wysocki, Jennifer Marie | GSSO | 84 | AMERICAS
AIA-008469 | QE-218224 | 2026-03-16 | 2026-02-24 |  | Completed On Time |  | Minor |  | Jonathan Wolfe, Jonathan Wolfe | UNITED STATES | B7981094_1015 | GCP Site Audit | 2025-12-16 |  | One study coordinator completed the Columbia-Suicide Severity Rating Scale (C-SSRS) prior to completing the respective training (ICH GCP E6(R3) 2.3.2, 5.1).&nbsp; The C-SSRS training was completed by the coordinator in September 2025; however, they had been completing the C-SSRS at study visits as required by the protocol for the following participants: 10151001 (randomized 23 Apr 2025), 10151002 (randomized 30 Apr 2025), 10151003 (randomized 13 Jun 2025), 10151005 (randomized 18 Jul 2025), 10151006 (randomized 01 Aug 2025).&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Refer to Issue ID #1-AFQF48Q on the attached Clinical Trial Management System Issue Action log confirming all corrections/updates were completed. Also, refer to attached Note to File dated 24FEB2026, explaining the SC will review all trainings on a quarterly basis as well as keep a spreadsheet with all trainings with start and end dates. | The Study Coordinator had a Columbia-Suicide Severity Rating Scale (C-SSRS) certificate dated 19JUL2023 which is valid for 2 years. The SC completed re-training and new certificate on 03SEP2025. There was a gap in certification between 20JUL2025 and 02SEP2025, which she performed the C-SSRS at baseline visit for 10151006. The study coordinator will create a note to file to explain the gap in certification and whether there are any additional actions needed to mitigate this risk in the future.Responsible Roles: Study Coordinator | Jennifer Wysocki |  | - | Jennifer Wysocki | Closed | Closed | Training & Qualifications | Training not completed or documented in a timely manner | CT33 - Study-Specific Training | SITE PERSONNEL | MODEL 1 - INSOURCED | Inflammation & Immunology | Wysocki, Jennifer Marie | GSSO | 84 | AMERICAS
AIA-008469 | QE-215067 | 2026-03-16 | 2026-02-20 |  | Completed On Time |  | Minor |  | Jonathan Wolfe, Jonathan Wolfe | UNITED STATES | B7981094_1015 | GCP Site Audit | 2025-12-16 |  | For 2 of 4 participants records reviewed, electronic Case Report Forms (eCRFs) entries contained discrepancies with the source documentation (Protocol B7981094 CRF Completion Requirements Template for Inform (Version 5: 29 October 2025)).&nbsp; 1. Participant 10151002:&nbsp; a. For Screening (09 Apr 2025):&nbsp; a1. The "Total Number of all prior episodes of alopecia areata (any type):" was reported as 0 in the eCRFs; however, "1" was recorded in the source documentation.&nbsp; a2. The Screening Electrocardiogram (ECG) values that were reported in the eCRFs contained discrepancies with the ECG in the participant chart as follows:&nbsp; a2a. "PR interval not otherwise specified" was reported as 161; however, as per the ECG, the value was 168 a2b. "QT interval not otherwise specified" was reported as 387; however, as per the ECG the value was 406 a2c. "QTCF interval not otherwise specified" was reported as 387; however, as per the ECG the value was 437 a2d. "QRS interval not otherwise specified" was reported as 88; however, as per the ECG the value was 81 a2e. "RR interval not otherwise specified" was reported as 995; however, as per the ECG the value was 801 a2f. "ECG Mean Heart Rate" was reported as 60; however, as per the ECG the value was 76 a3. The "Eyebrow Assessment" was reported as "moderate" in the eCRFs; however, it was rated as "minimal" in the source documentation.&nbsp; b. Day 1(30 Apr 2025): b1. The "Eyebrow Assessment" was reported as "moderate" in the eCRFs; however, it was rated as "minimal" in the source documentation.&nbsp; b2. The "Eyelash Assessment" was reported as "none" in the eCRFs; however, it was rated as "minimal" in the source documentation.&nbsp; c. Week 24 (16 Oct 2025): c1. The "Patient Satisfaction with Hair Growth" was reported as "very dissatisfied" in the eCRFs; however, the participant reported "very satisfied" in the source documentation.&nbsp; c2. The "Quadrant Score - Percent of Back" was reported as "44" in the "Severity of Alopecia Tool" in the eCRFs; however, it was recorded as "42" in the source documentation.&nbsp; c3. It was reported that 0 doses of the Investigational Product (IP) were missed on the "Oral Treatment - 50MG/PBO" and "Oral Treatment - 100MG/PBO" pages in the eCRFs; however, the participant had missed 6 doses of IP as documented in the participant dosing diary.&nbsp; 2. Participant 10151003:&nbsp; a. For Week 12 (05 Sep 2025), it was reported that 0 doses of the IP were missed on the "Oral Treatment - 50MG/PBO" and "Oral Treatment - 100MG/PBO" pages in the eCRFs; however, the participant had missed 4 doses of IP as documented in the participant dosing diary,&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Refer to Issue ID # 1-AFQF47W, 1-AFQF480 on the attached Clinical Trial Management System Issue Action log confirming all corrections/updates were completed for this finding. | 1 &amp; 2. Site to review the source documents to ensure the data is consistent between the Source and to address discrepancies between the Source and the electronic Case Report Form (eCRF). For all findings, the Clinical Research Associate (CRA) will confirm all updates were made in the source document and eCRFs per ALCOAC (attributable, legible, contemporaneous, original, accurate, complete) principles.Responsible Roles: Site Personnel/ Clinical Research Associate | Jennifer Wysocki |  | - | Jennifer Wysocki | Closed | Closed | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | DMB07 - CRF and Database Design | SITE PERSONNEL | MODEL 1 - INSOURCED | Inflammation & Immunology | Wysocki, Jennifer Marie | GSSO | 84 | AMERICAS
AIA-008469 | QE-215068 | 2026-03-16 | 2026-02-20 |  | Completed On Time |  | Minor |  | Jonathan Wolfe, Jonathan Wolfe | UNITED STATES | B7981094_1015 | GCP Site Audit | 2025-12-16 |  | Twelve essential documents were incomplete or missing from the electronic Investigator Site File (eISF) (ICH GCP E6 (R3) C.2.3). This included:&nbsp; 1. Nine Institutional Review Board (IRB) Approval Letters dated: 11 Apr 2025, 05 May 2025, 22 May 2025, 11 Jun 2025, 27 Jun 2025, 16 Jul 2025, 24 Jul 2025, 08 Aug 2025, and 01 Oct 2025.&nbsp; Note: WCG IRB Canada IRB approval letters and translated materials were erroneously filed in the eISF.&nbsp; 2. The Subject Identification Code List was not filed in the eISF.&nbsp; 3. The Deviation Log was not maintained in the eISF.&nbsp; 4. The Screening and Enrollment log did not have the updated status of Participant 10151007.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Refer to Issue ID #1-AFQF484, 1-AFQF488 on the attached Clinical Trial Management System Issue Action log confirming all corrections/updates were completed for this finding. | 1. The Clinical Research Associate (CRA) confirmed some of these documents were filed under a different folder. On 09JAN2026, the CRA and Study Coordinator (SC) reviewed all missing documents noted in this finding and CRA confirmed all documents are now filed in the appropriate folder in Florence electronic Investigator Site File (eISF). The CRA will review the Florence eISF Binder set up with the study coordinator to confirm filing of the documents in appropriate folders. The WCG IRB Canada IRB approval letters and translated materials were removed from the eISF, since they were erroneously filed.2 &amp; 4. The Subject Identification Code List and Screening and Enrollment Log will be current/up to date and filed in the ISF. The CRA will confirm documents are current and filed in the ISF.3. The Protocol Deviations (PDs) are documented in the source and discussions around the PDs are located in the follow-up letter (For example: action taken, follow-up actions, resolution, and closure of issues) and documentation is sent to the site for filing in the eISF, per INV04- GSOP-RF15 Site Management and Monitoring Follow-up Letter Template. Responsible Roles: Site Personnel/ Clinical Research Associate | Jennifer Wysocki |  | - | Jennifer Wysocki | Closed | Closed | Document Management | Missing document | CT01 - Trial Master Files | SITE PERSONNEL | MODEL 1 - INSOURCED | Inflammation & Immunology | Wysocki, Jennifer Marie | GSSO | 84 | AMERICAS
AIA-008469 | QE-215071 | 2026-03-16 | 2026-02-20 |  | Completed On Time |  | Major |  | Jonathan Wolfe, Jonathan Wolfe | UNITED STATES | B7981094_1015 | GCP Site Audit | 2025-12-16 |  | Documentation related to Investigational Product (IP) preparation was inadequate (Investigational Product Manual Protocol B7981094 (version 2: 13 Feb 2025)).&nbsp; 1. For 4 of 4 participant records reviewed, the reconciliation of the study intervention and compliance of the study intervention capsules dispensed and taken was not documented for the participants for the following visits:&nbsp; a. Participant 10151001: Day 1 (23 Apr 2025), Day 29 (21 May 2025), Day 85 (14 Jul 2025), Day 169 (09 Oct 2025), and Day 197 (05 Nov 2025).&nbsp; b. Participant 10151002: Day 1 (09 Apr 2025), Day 29 (30 May 2025), Day 85 (23 Jul 2025), Day 169 (16 Oct 2025), and Day 197 (12 Nov 2025).&nbsp; c. Participant 10151003: Day 1 (22 May 2025), Day 29 (11 Jul 2025), and Day 85 (05 Sep 2025).&nbsp; d. Participant 10151006: Day 1 (01 Aug 2025), Day 29 (29 Aug 2025), and Day 85 (24 Oct 2025).&nbsp; 2. On the Investigational Product Accountability Log (IPAL), the "disposition" columns were not completed. &nbsp; 3. Twenty-two bottles of ritlecitinib 50mg were documented on the IPAL as available for dispensation; however, twenty-four bottles of ritlecitinib 50mg were expected to be available at the site for dispensation as per the IMPALA inventory reports.&nbsp; Note: when the auditor reviewed the inventory on site, twenty four bottles of ritlectinib 50mg were present.&nbsp; 4. The following "Receipt Acknowledgement" questions were not answered for Shipment IDs 1888796 and 1869877: a. Were the contents of the shipment damaged or received in an unacceptable manner? b. Did any of the temperature monitoring devices alarm during shipment? | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Refer to Issue ID #1-AFQF47A, 1-AFQF47E, 1-AFQF47I on the attached Clinical Trial Management System Issue Action log confirming all corrections/updates were completed for this finding. | 1.The source document template has a section that confirms review of study intervention and compliance but does not specifically capture the details required per protocol. During onsite visit on 09JAN2026, Site Care Partner confirmed that a compliance calculator (includes # of days/ total dispensed/returned/pills taken/ compliance percentage) has been added to the source for future visits. The Principal Investigator will create a Note to File confirming that, for all participants and prior visits, there were no instances of compliance &lt; 80% or &gt;120%.2. The Investigational Product (IP) has not been returned or destroyed yet for this site. This issue was identified by the Clinical Research Associate on 10NOV2025 and entered into Siebel CTMS Issue ID 1-9OP23E9. The disposition section will be completed once IP is destroyed on site or returned to the Vendor. 3. The site personnel updated the Investigational Product Accountability Log (IPAL) to reflect all IP shipments and dispensation. The Clinical Research Associate will confirm the bottles available for dispensation per the IPAL is consistent with the IMPALA inventory reports and Inventory at the site. 4.The study coordinator added a late entry to answer the "Receipt Acknowledgement" questions for Shipment IDs 1888796 and 1869877. The Site Care Partner confirmed late entry was added per ALCOAC (attributable, legible, contemporaneous, original, accurate, complete) principles. Responsible Roles: Site Personnel/Principal Investigator/ Clinical Research Associate/ Site Care Partner | Jennifer Wysocki |  | - | Jennifer Wysocki | Approved - In CAPA | Closed | Medicinal Product | Inadequate accountability/record keeping | IP13 - Study Investigational Product Supplies | SITE PERSONNEL | MODEL 1 - INSOURCED | Inflammation & Immunology | Wysocki, Jennifer Marie | GSSO | 84 | AMERICAS
AIA-008469 | QE-215071 | 2026-03-16 | 2026-02-20 |  | Completed On Time |  | Major |  | Jonathan Wolfe, Jonathan Wolfe | UNITED STATES | B7981094_1015 | GCP Site Audit | 2025-12-16 |  | Documentation related to Investigational Product (IP) preparation was inadequate (Investigational Product Manual Protocol B7981094 (version 2: 13 Feb 2025)).&nbsp; 1. For 4 of 4 participant records reviewed, the reconciliation of the study intervention and compliance of the study intervention capsules dispensed and taken was not documented for the participants for the following visits:&nbsp; a. Participant 10151001: Day 1 (23 Apr 2025), Day 29 (21 May 2025), Day 85 (14 Jul 2025), Day 169 (09 Oct 2025), and Day 197 (05 Nov 2025).&nbsp; b. Participant 10151002: Day 1 (09 Apr 2025), Day 29 (30 May 2025), Day 85 (23 Jul 2025), Day 169 (16 Oct 2025), and Day 197 (12 Nov 2025).&nbsp; c. Participant 10151003: Day 1 (22 May 2025), Day 29 (11 Jul 2025), and Day 85 (05 Sep 2025).&nbsp; d. Participant 10151006: Day 1 (01 Aug 2025), Day 29 (29 Aug 2025), and Day 85 (24 Oct 2025).&nbsp; 2. On the Investigational Product Accountability Log (IPAL), the "disposition" columns were not completed. &nbsp; 3. Twenty-two bottles of ritlecitinib 50mg were documented on the IPAL as available for dispensation; however, twenty-four bottles of ritlecitinib 50mg were expected to be available at the site for dispensation as per the IMPALA inventory reports.&nbsp; Note: when the auditor reviewed the inventory on site, twenty four bottles of ritlectinib 50mg were present.&nbsp; 4. The following "Receipt Acknowledgement" questions were not answered for Shipment IDs 1888796 and 1869877: a. Were the contents of the shipment damaged or received in an unacceptable manner? b. Did any of the temperature monitoring devices alarm during shipment? | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Refer to Issue ID # 1-AFQF47A, 1-AFQF47E on the attached clinical Trial Management System Issue Action log confirming all corrections/updates were completed for this finding. | During the onsite visit on 09JAN2026, the Site Care Partner retrained the Study Coordinator on completing the Investigational Product Accountability Log (IPAL) contemporaneously and per completion Instructions associated with INV02-INV04-GSOP-RF11 11.0. The Clinical Research Associate will conduct Site Monitoring Activities to ensure the IPAL, and shipping documents are complete and updated per ALCOAC (attributable, legible, contemporaneous, original, accurate, complete) principles. Responsible Roles: Site Care Partner/ Clinical Research Associate | Jennifer Wysocki |  | - | Jennifer Wysocki | Approved - In CAPA | Closed | Medicinal Product | Inadequate accountability/record keeping | IP13 - Study Investigational Product Supplies | SITE PERSONNEL | MODEL 1 - INSOURCED | Inflammation & Immunology | Wysocki, Jennifer Marie | GSSO | 84 | AMERICAS
AIA-008469 | QE-215071 | 2026-03-16 | 2026-02-20 |  | Completed On Time |  | Major |  | Jonathan Wolfe, Jonathan Wolfe | UNITED STATES | B7981094_1015 | GCP Site Audit | 2025-12-16 |  | Documentation related to Investigational Product (IP) preparation was inadequate (Investigational Product Manual Protocol B7981094 (version 2: 13 Feb 2025)).&nbsp; 1. For 4 of 4 participant records reviewed, the reconciliation of the study intervention and compliance of the study intervention capsules dispensed and taken was not documented for the participants for the following visits:&nbsp; a. Participant 10151001: Day 1 (23 Apr 2025), Day 29 (21 May 2025), Day 85 (14 Jul 2025), Day 169 (09 Oct 2025), and Day 197 (05 Nov 2025).&nbsp; b. Participant 10151002: Day 1 (09 Apr 2025), Day 29 (30 May 2025), Day 85 (23 Jul 2025), Day 169 (16 Oct 2025), and Day 197 (12 Nov 2025).&nbsp; c. Participant 10151003: Day 1 (22 May 2025), Day 29 (11 Jul 2025), and Day 85 (05 Sep 2025).&nbsp; d. Participant 10151006: Day 1 (01 Aug 2025), Day 29 (29 Aug 2025), and Day 85 (24 Oct 2025).&nbsp; 2. On the Investigational Product Accountability Log (IPAL), the "disposition" columns were not completed. &nbsp; 3. Twenty-two bottles of ritlecitinib 50mg were documented on the IPAL as available for dispensation; however, twenty-four bottles of ritlecitinib 50mg were expected to be available at the site for dispensation as per the IMPALA inventory reports.&nbsp; Note: when the auditor reviewed the inventory on site, twenty four bottles of ritlectinib 50mg were present.&nbsp; 4. The following "Receipt Acknowledgement" questions were not answered for Shipment IDs 1888796 and 1869877: a. Were the contents of the shipment damaged or received in an unacceptable manner? b. Did any of the temperature monitoring devices alarm during shipment? | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Refer to Issue ID #1-AFQF47A on the attached Clinical Trial Management System Issue Action log confirming corrections/updates were completed for this finding. | The Source Document Template will be updated to clearly include a section for documenting reconciliation/compliance and dosing instructions reviewed during each visit, per protocol. The Clinical Research Associate will conduct Source Document Review per the Study Monitoring Plan. Responsible Roles: Site Personnel/ Clinical Research Associate | Jennifer Wysocki |  | - | Jennifer Wysocki | Approved - In CAPA | Closed | Medicinal Product | Inadequate accountability/record keeping | IP13 - Study Investigational Product Supplies | SITE PERSONNEL | MODEL 1 - INSOURCED | Inflammation & Immunology | Wysocki, Jennifer Marie | GSSO | 84 | AMERICAS
AIA-008469 | QE-215066 | 2026-03-16 | 2026-03-13 |  | Completed On Time |  | Major |  | Jonathan Wolfe, Jonathan Wolfe | UNITED STATES | B7981094_1015 | GCP Site Audit | 2025-12-16 |  | For 4 of 4 participant records reviewed, source documentation practices did not consistently adhere to ALCOAC (attributable, legible, contemporaneous, original, accurate, complete) principles. [Pfizer Protocol B7981094 (07 Jan 2025), ICH E6 (R3) 2.12.2].&nbsp; Examples include, but are not limited to:&nbsp; 1. For 4 of 4 participant records reviewed, the time questionnaires were administered and/or completed was not documented on the source records for the following visits:&nbsp; a. Participant 10151001: Week 4 (21 May 2025), Week 12 (14 Jul 2025) b. Participant 10151002: Week 4 (30 May 2025) c. Participant 10151003: Week 12 (05 Sep 2025) d. Participant 10151006: Screening (16 Jul 2025), Day 1 (01 Aug 2025), Week 4 (29 Aug 2025), Week 12 (24 Oct 2025) Note: the auditor was unable to verify if questionnaires were completed prior to other evaluations as the site generated source documents did not include a designated field to capture the time of administration.&nbsp; 2. For 4 of 4 participant records reviewed, the targeted Physical Exam (PE) was not initialed or signed by the person conducting the PE in the source documents for the following visits:&nbsp; a. Participant 10151001: Week 4 (21 May 2025),&nbsp; b. Participant 10151002: Week 4 (30 May 2025), Week 12 (23 Jul 2025), Week 28 (12 Nov 2024).&nbsp; c. Participant 10151003: Screening (22 May 2025),&nbsp; d. Participant 10151006: Screening (16 Jul 2025), Day 1 (01 Aug 2025), Week 4 (29 Aug 2025), Week 12 (24 Oct 2025) Note: the site generated source document lacked a section for the investigator to attest, via signature or initials, that they performed the PE.&nbsp; 3. For 4 of 4 participant records reviewed, the Clinical Assessment forms (Severity of Alopecia Tool (SALT), Eyelash Assessment (ELA), Eyebrow Assessment (EBA), or Columbia-Suicide Severity Rating Scale (C-SSRS)) had the rater ID and rater's initials; however, the date of the assessment was not documented by the rater for the following visits:&nbsp; a. &nbsp; &nbsp;Participant 10151001:&nbsp; a1. Week 4 (21 May 2025): SALT, ELA, EBA, C-SSRS a2. Week 12 (14 Jul 2025): EBA, ELA, C-SSRS a3. Week 24 (09 Oct 2025): EBA, ELA, C-SSRS a4. Week 28 (05 Nov 2025): EBA, ELA, C-SSRS b. &nbsp; &nbsp;Participant 10151002:&nbsp; b1. Week 4 (30 May 2025): EBA, ELA, SALT, C-SSRS.&nbsp; c. &nbsp; &nbsp;Participant 10151003:&nbsp; c1. Screening (22 May 2025): EBA, ELA, SALT, C-SSRS c2. Day 1 (13 Jun 2025): EBA, ELA, SALT, C-SSRS c3. Week 4 (11 Jul 2025): ELA, SALT, C-SSRS c4. Week 12 (05 Sep 2025): EBA, SALT, C-SSRS d. &nbsp; &nbsp;Participant 10151006:&nbsp; d1. Screening (16 Jul 2025): SALT, EBA, ELA d2. Day 1 (01 Aug 2025):SALT, EBA, ELA, C-SSRS d3. Week 4 (29 Aug 2025): SALT, C-SSRS d4. Week 12 (24 Oct 2025): SALT, EBA, ELA, C-SSRS 4. For 3 of 4 participant records reviewed (10151001, 10151002, 10151003), the Screening eligibility review worksheets were signed confirming participant eligibility prior to required safety laboratory result availability and review.&nbsp; Note: The safety laboratory results were available after the screening visit and were part of the eligibility review on Day 1 by the investigator. There were no laboratory results that were exclusionary.&nbsp; 5. For 1 of 4 participants reviewed (10151003), the Clinical Assessment forms (ELA, EBA, and/or CSSRS) did not have the rater ID, initials, or date documented on the forms for the following visits: Day 1 Study Visit (13 Jun 2025), Week 4 (11 Jul 2025).&nbsp; 6. For Participant 10151001: a. Corrections were not performed by the individual who made the documentation error; the study coordinator corrected errors on worksheets originally made by the Principal Investigator (PI), and the PI co-signed these corrections.&nbsp; b. At the Week 4 study visit (21 May 2025), the time of administration of the Investigational Product (IP) was not recorded in the participant dosing diary.&nbsp; c. At the Week 24 study visit (09 Oct 2025), on page 3 of 4 of the study visit worksheets, the header had an incomplete date recorded.&nbsp; d. For Week 28 (05 Nov 2025), the rater of the CSSR questionnaire did not initial the document; however, it was initialed by the coordinator.&nbsp; e. The Dosing Diary for 23 Apr - 22 May 2025 was missing the following information (page 1): Study Clinic (Contact, Name, Telephone Number) and Next Scheduled Visit (Date, Time).&nbsp; f . The Dosing Diary for 23 May - 14 July 2025 was missing the following information (page 1): Participant Information (Subject ID, Date Dispensed), Study Clinic (Contact, Name, Telephone Number).&nbsp; g. The Dosing Diary for 09 Oct - 04 Nov 2025 was missing the following information (page 1): Participant Information (Subject ID, Date Dispensed), Study Clinic (Contact, Name, Telephone Number) and Next Scheduled Visit (Date, Time).&nbsp; 7. Participant 10151002:&nbsp; a. Screening Visit (09 Apr 2025): a1. The review of the screening Electrocardiogram (ECG) was initialed, but was not dated by the investigator.&nbsp; a2. The Certified copy of the screening ECG was initialed and dated with a delay on 07 May 2025 by the investigator.&nbsp; a3. The Canfield Eligibility Report was not filed in the participant chart.&nbsp; b. Week 12 (23 Jul 2025):&nbsp; b1. The 30 May 2025 dose was documented as being missed in the source documents under "accountability 50mg" and "accountability 100mg" sections of the study visit worksheets; however, the IP dose was taken in clinic on 30 May 2025 as documented in the dosing diary.&nbsp; b2. "Any changes in health since the last visit" was documented as "no" in the source documents; however, the participant had an Adverse Event (AE) on 12 Jul 2025 as documented in the source records.&nbsp; 8. Participant 10151003:&nbsp; a. Screening (22 May 2025):&nbsp; a1. The "Screening" eligibility review worksheet did not have the last item (item 13) in the exclusion criteria reviewed by the investigator.&nbsp; Note: the participant did not meet the exclusion criteria.&nbsp; a2. The Type of current episode of AA - "Other AA" was not documented in the Alopecia Areata History in the study visit worksheet.&nbsp; b. Week 4 (11 Jul 2025):&nbsp; b1. The participant was asked to return to the site to repeat chemistry safety laboratory tests due to elevated values; however, the repeated chemistry lab results and the investigator’s review were not filed in the participant’s chart. Additionally, while the investigator instructed the participant to hold IP from July 15 to July 18, 2025, the communication to restart IP on July 19, 2025 was not documented in the participant’s source records. Note: there was no Adverse Event associated with the elevated laboratory results as per PI assessment.&nbsp; c. Week 12 (05 Sep 2025):&nbsp; c1. The "were any doses missed" was not completed for the "Accountability 50mg" and "Accountability 100mg" sections of the source documents.&nbsp; c2. The Dosing Diary was missing the following information (page 1): Participant Information (Subject ID, Date Dispensed) and Study Clinic (Contact, Name, Telephone Number).&nbsp; 9. Participant 10151006:&nbsp; a. Screening (16 Jul 2025):&nbsp; a1. The review of the screening Electrocardiogram (ECG) was initialed, but was not dated by the investigator.&nbsp; a2. The Canfield Eligibility Report was not filed in the participant chart.&nbsp; a3. The added note of "subject declined photo consent" on the informed consent process documentation was not initialed or dated.&nbsp; b. Week 12 (24 Oct 2024):&nbsp; b1. The participant was asked to return to the site for repeat chemistry safety laboratory tests; however, the documentation in the participant chart did not clearly indicate whether the participant was instructed to hold IP due to elevated laboratory test values.&nbsp; Note: As per interview with the study coordinator, IP was not held. &nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Refer to Issue ID #1-A59W2MB, 1-A59W2MG, 1-A59W2MK, 1-A59W2NI, 1-A59W2NM, 1-A59W2O0, 1-A59W2O4, 1-A59W2QU, 1-A59W2QY, 1-A59W31S, 1-AFQF46C on the attached Clinical Trial Management System Issue Action log confirming all corrections/updates were completed for this finding. | 1a-d. The Source document template lists the administration of the questionnaires prior to other assessments. A note to file will be created to explain site's process and confirm the site staff administers the questionnaires prior to other assessments.2a-d. Action is as noted in the preventative action; moving forward, the Principal Investigator (PI) will enter his initials to the source document confirming he completed the Physical Exams (PEs). The Principal Investigator will also create a Note to file confirming he conducted all prior Physical Exams. 3a-d. For Participants 10151001, 10151002, 10151003, 10151006, the date of the assessment is noted in the header but the rater did not date his initials. The action is as noted in the Corrective Action; moving forward, as the Pfizer-provided worksheets (e.g. SALT, EBA/ELA, C-SSRS, PGI-C, P-SAT) do not contain a space for Rater ID/initials. The site will ensure that the rater’s ID and the rater’s dated initials are documented directly in the source document at the time the assessment is completed.The PI will create a Note to File to document the corrective action for not dating his initials when entering them onto the Pfizer provided worksheets (SALT/ELA/EBA, C-SSRS). 4. The PI confirmed final eligibility, and randomization does not occur until all data is received/reviewed against the inclusion/ exclusion criteria. The Baseline source document clearly notes, "By signing below, the PI has reviewed the inclusion/exclusion criteria, medical history and concomitant medications as well as other source documents completed during the visits and confirms subject's eligibility and enrollment in the study." The action is as noted in the preventive action. Moving forward, the source will only capture the final eligibility confirmation for randomization at the baseline visit after all assessments are completed and results available for review. 5. For participant 10151003- the (Severity of Alopecia Tool (SALT) worksheet for Baseline Day 1 did include the Rater ID/ initials. But a late entry will be added for the Eyelash Assessment (ELA), Eyebrow Assessment (EBA), and Columbia-Suicide Severity Rating Scale (C-SSRS), confirming the rater ID, initials, date of assessments. -For week 4: The (Severity of Alopecia Tool (SALT), Eyelash Assessment (ELA), and Columbia-Suicide Severity Rating Scale (C-SSRS) worksheet did include the Rater ID/ initials. A late entry will be added for the Eyebrow Assessment (EBA), confirming the rater ID, initials, date of assessments.6. For participant 10151001, the study coordinator corrected errors on worksheets originally made by the Principal Investigator (PI), and the PI co-signed these corrections. 7. At the Week 4 study visit (21 May 2025), the time of the Investigational Product (IP) administration was recorded in the source. At the Week 24 study visit (09 Oct 2025), on page 3 of 4 of the study visit worksheets, the header was completed. For Week 28 (05 Nov 2025), the rater conducting the Columbia-Suicide Severity Rating Scale (CSSR-S) questionnaire did not initial the document; however, it was initialed by the coordinator. The coordinator initialed her correction since she entered Rater ID #38 instead of # 39 in error. The error was corrected. The SC will add late entries to the incomplete fields on the Dosing Diaries.7a. For Participant 10151002, under the screening visit: the investigator will add a late entry explaining the date the ECG was initially reviewed was not noted in error. The Canfield eligibility report will be filed in the chart. 7b. A late entry was added to the source to clarify the discrepancy in dosing on 30MAY2025 and the adverse event reported on 12JUL2025 versus the response at week 12 for “any changes in health since last visit”.8. For Participant 10151003, The PI did not complete Item 13 on the screening eligibility worksheet but did complete this at Baseline which is clearly noted in the source. The site clarified the field "other AA" indicates the type of current episode of Alopecia Areata which is equivalent to “Alopecia Areata”, not "Totalis" or "Universalis"8b. The Week 4 (11 Jul 2025) repeat chemistry safety laboratory results and the investigator’s review will be filed in the participant’s chart. The investigator will add late entry and any relevant notes related to the elevated lab values and the instructions to the participant to restart the IP on July 19, 2025. 8c. Under week 12 source documents, a late entry will be entered to answer the questions, "were any doses missed" section of the source documents, and to complete the missing fields on the dosing diary.9. For Participant 10151006: under the screening visit, the investigator will add a late entry explaining the ECG was reviewed by PI, initialed by PI, but was not dated in error. The Canfield eligibility report will be filed in the chart. -The individual who obtained consent will add late entry to explain their added note "subject declined photo consent" on the informed consent process documentation was not initialed or dated in error.-There was documentation in the source explaining participant was contacted for a repeat CK test. Participant was not told to hold IP but was instructed to refrain from strenuous activity and drink plenty of water for 3-4 days before returning.1-9. The Clinical Research Associate will review the source documents to confirm corrections were made per ALCOAC (attributable, legible, contemporaneous, original, accurate, complete) principles. Responsible Roles: Principal Investigator/ Site Personnel/Clinical Research Associate | Jennifer Wysocki |  | - | Jennifer Wysocki | Approved - In CAPA | Closed | Data Collection and Management | Inadequate source data/documentation | NOT APPLICABLE; NOT APPLICABLE | SITE PERSONNEL | MODEL 1 - INSOURCED | Inflammation & Immunology | Wysocki, Jennifer Marie | GSSO | 84 | AMERICAS
AIA-008469 | QE-215066 | 2026-03-16 | 2026-03-13 |  | Completed On Time |  | Major |  | Jonathan Wolfe, Jonathan Wolfe | UNITED STATES | B7981094_1015 | GCP Site Audit | 2025-12-16 |  | For 4 of 4 participant records reviewed, source documentation practices did not consistently adhere to ALCOAC (attributable, legible, contemporaneous, original, accurate, complete) principles. [Pfizer Protocol B7981094 (07 Jan 2025), ICH E6 (R3) 2.12.2].&nbsp; Examples include, but are not limited to:&nbsp; 1. For 4 of 4 participant records reviewed, the time questionnaires were administered and/or completed was not documented on the source records for the following visits:&nbsp; a. Participant 10151001: Week 4 (21 May 2025), Week 12 (14 Jul 2025) b. Participant 10151002: Week 4 (30 May 2025) c. Participant 10151003: Week 12 (05 Sep 2025) d. Participant 10151006: Screening (16 Jul 2025), Day 1 (01 Aug 2025), Week 4 (29 Aug 2025), Week 12 (24 Oct 2025) Note: the auditor was unable to verify if questionnaires were completed prior to other evaluations as the site generated source documents did not include a designated field to capture the time of administration.&nbsp; 2. For 4 of 4 participant records reviewed, the targeted Physical Exam (PE) was not initialed or signed by the person conducting the PE in the source documents for the following visits:&nbsp; a. Participant 10151001: Week 4 (21 May 2025),&nbsp; b. Participant 10151002: Week 4 (30 May 2025), Week 12 (23 Jul 2025), Week 28 (12 Nov 2024).&nbsp; c. Participant 10151003: Screening (22 May 2025),&nbsp; d. Participant 10151006: Screening (16 Jul 2025), Day 1 (01 Aug 2025), Week 4 (29 Aug 2025), Week 12 (24 Oct 2025) Note: the site generated source document lacked a section for the investigator to attest, via signature or initials, that they performed the PE.&nbsp; 3. For 4 of 4 participant records reviewed, the Clinical Assessment forms (Severity of Alopecia Tool (SALT), Eyelash Assessment (ELA), Eyebrow Assessment (EBA), or Columbia-Suicide Severity Rating Scale (C-SSRS)) had the rater ID and rater's initials; however, the date of the assessment was not documented by the rater for the following visits:&nbsp; a. &nbsp; &nbsp;Participant 10151001:&nbsp; a1. Week 4 (21 May 2025): SALT, ELA, EBA, C-SSRS a2. Week 12 (14 Jul 2025): EBA, ELA, C-SSRS a3. Week 24 (09 Oct 2025): EBA, ELA, C-SSRS a4. Week 28 (05 Nov 2025): EBA, ELA, C-SSRS b. &nbsp; &nbsp;Participant 10151002:&nbsp; b1. Week 4 (30 May 2025): EBA, ELA, SALT, C-SSRS.&nbsp; c. &nbsp; &nbsp;Participant 10151003:&nbsp; c1. Screening (22 May 2025): EBA, ELA, SALT, C-SSRS c2. Day 1 (13 Jun 2025): EBA, ELA, SALT, C-SSRS c3. Week 4 (11 Jul 2025): ELA, SALT, C-SSRS c4. Week 12 (05 Sep 2025): EBA, SALT, C-SSRS d. &nbsp; &nbsp;Participant 10151006:&nbsp; d1. Screening (16 Jul 2025): SALT, EBA, ELA d2. Day 1 (01 Aug 2025):SALT, EBA, ELA, C-SSRS d3. Week 4 (29 Aug 2025): SALT, C-SSRS d4. Week 12 (24 Oct 2025): SALT, EBA, ELA, C-SSRS 4. For 3 of 4 participant records reviewed (10151001, 10151002, 10151003), the Screening eligibility review worksheets were signed confirming participant eligibility prior to required safety laboratory result availability and review.&nbsp; Note: The safety laboratory results were available after the screening visit and were part of the eligibility review on Day 1 by the investigator. There were no laboratory results that were exclusionary.&nbsp; 5. For 1 of 4 participants reviewed (10151003), the Clinical Assessment forms (ELA, EBA, and/or CSSRS) did not have the rater ID, initials, or date documented on the forms for the following visits: Day 1 Study Visit (13 Jun 2025), Week 4 (11 Jul 2025).&nbsp; 6. For Participant 10151001: a. Corrections were not performed by the individual who made the documentation error; the study coordinator corrected errors on worksheets originally made by the Principal Investigator (PI), and the PI co-signed these corrections.&nbsp; b. At the Week 4 study visit (21 May 2025), the time of administration of the Investigational Product (IP) was not recorded in the participant dosing diary.&nbsp; c. At the Week 24 study visit (09 Oct 2025), on page 3 of 4 of the study visit worksheets, the header had an incomplete date recorded.&nbsp; d. For Week 28 (05 Nov 2025), the rater of the CSSR questionnaire did not initial the document; however, it was initialed by the coordinator.&nbsp; e. The Dosing Diary for 23 Apr - 22 May 2025 was missing the following information (page 1): Study Clinic (Contact, Name, Telephone Number) and Next Scheduled Visit (Date, Time).&nbsp; f . The Dosing Diary for 23 May - 14 July 2025 was missing the following information (page 1): Participant Information (Subject ID, Date Dispensed), Study Clinic (Contact, Name, Telephone Number).&nbsp; g. The Dosing Diary for 09 Oct - 04 Nov 2025 was missing the following information (page 1): Participant Information (Subject ID, Date Dispensed), Study Clinic (Contact, Name, Telephone Number) and Next Scheduled Visit (Date, Time).&nbsp; 7. Participant 10151002:&nbsp; a. Screening Visit (09 Apr 2025): a1. The review of the screening Electrocardiogram (ECG) was initialed, but was not dated by the investigator.&nbsp; a2. The Certified copy of the screening ECG was initialed and dated with a delay on 07 May 2025 by the investigator.&nbsp; a3. The Canfield Eligibility Report was not filed in the participant chart.&nbsp; b. Week 12 (23 Jul 2025):&nbsp; b1. The 30 May 2025 dose was documented as being missed in the source documents under "accountability 50mg" and "accountability 100mg" sections of the study visit worksheets; however, the IP dose was taken in clinic on 30 May 2025 as documented in the dosing diary.&nbsp; b2. "Any changes in health since the last visit" was documented as "no" in the source documents; however, the participant had an Adverse Event (AE) on 12 Jul 2025 as documented in the source records.&nbsp; 8. Participant 10151003:&nbsp; a. Screening (22 May 2025):&nbsp; a1. The "Screening" eligibility review worksheet did not have the last item (item 13) in the exclusion criteria reviewed by the investigator.&nbsp; Note: the participant did not meet the exclusion criteria.&nbsp; a2. The Type of current episode of AA - "Other AA" was not documented in the Alopecia Areata History in the study visit worksheet.&nbsp; b. Week 4 (11 Jul 2025):&nbsp; b1. The participant was asked to return to the site to repeat chemistry safety laboratory tests due to elevated values; however, the repeated chemistry lab results and the investigator’s review were not filed in the participant’s chart. Additionally, while the investigator instructed the participant to hold IP from July 15 to July 18, 2025, the communication to restart IP on July 19, 2025 was not documented in the participant’s source records. Note: there was no Adverse Event associated with the elevated laboratory results as per PI assessment.&nbsp; c. Week 12 (05 Sep 2025):&nbsp; c1. The "were any doses missed" was not completed for the "Accountability 50mg" and "Accountability 100mg" sections of the source documents.&nbsp; c2. The Dosing Diary was missing the following information (page 1): Participant Information (Subject ID, Date Dispensed) and Study Clinic (Contact, Name, Telephone Number).&nbsp; 9. Participant 10151006:&nbsp; a. Screening (16 Jul 2025):&nbsp; a1. The review of the screening Electrocardiogram (ECG) was initialed, but was not dated by the investigator.&nbsp; a2. The Canfield Eligibility Report was not filed in the participant chart.&nbsp; a3. The added note of "subject declined photo consent" on the informed consent process documentation was not initialed or dated.&nbsp; b. Week 12 (24 Oct 2024):&nbsp; b1. The participant was asked to return to the site for repeat chemistry safety laboratory tests; however, the documentation in the participant chart did not clearly indicate whether the participant was instructed to hold IP due to elevated laboratory test values.&nbsp; Note: As per interview with the study coordinator, IP was not held. &nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Refer to Issue ID #1-A59W2MB on the attached Clinical Trial Management System Issue Action log confirming all corrections/updates were completed for this finding. Also refer to and Contact Report dated 02MAR2026. | The Site Care Partner retrained the Study Coordinator during an onsite visit on 09Jan2026, on source documentation practices per Good Clinical Practice (GCP) ALCOAC (attributable, legible, contemporaneous, original, accurate, complete) principles, using the Site Initiation Visit Required Activities training slides (Version 1.0, 3-Mar-2025). The Principal Investigator (PI) was unable to attend the visit. The Clinical Research Associate (CRA) will provide retraining to the PI during the follow-up phone call. Moving forward, as the Pfizer-provided worksheets (e.g. SALT, EBA/ELA, C-SSRS, PGI-C, P-SAT) do not contain fields for Rater ID/initials, the site will ensure that the rater’s ID and the rater’s dated initials are documented directly in the source document at the time the assessment is completed. The CRA will confirm all corrections have been made and for any documentation issues that cannot be retroactively corrected in the source, a Note to File will be created to explain site process and corrective action moving forward (For example: Performing Physical Exams, Timing of administering PROs)Responsible Roles: Site Care Partner/ Clinical Research Associate | Jennifer Wysocki |  | - | Jennifer Wysocki | Approved - In CAPA | Closed | Data Collection and Management | Inadequate source data/documentation | NOT APPLICABLE; NOT APPLICABLE | SITE PERSONNEL | MODEL 1 - INSOURCED | Inflammation & Immunology | Wysocki, Jennifer Marie | GSSO | 84 | AMERICAS
AIA-008469 | QE-215066 | 2026-03-16 | 2026-03-13 |  | Completed On Time |  | Major |  | Jonathan Wolfe, Jonathan Wolfe | UNITED STATES | B7981094_1015 | GCP Site Audit | 2025-12-16 |  | For 4 of 4 participant records reviewed, source documentation practices did not consistently adhere to ALCOAC (attributable, legible, contemporaneous, original, accurate, complete) principles. [Pfizer Protocol B7981094 (07 Jan 2025), ICH E6 (R3) 2.12.2].&nbsp; Examples include, but are not limited to:&nbsp; 1. For 4 of 4 participant records reviewed, the time questionnaires were administered and/or completed was not documented on the source records for the following visits:&nbsp; a. Participant 10151001: Week 4 (21 May 2025), Week 12 (14 Jul 2025) b. Participant 10151002: Week 4 (30 May 2025) c. Participant 10151003: Week 12 (05 Sep 2025) d. Participant 10151006: Screening (16 Jul 2025), Day 1 (01 Aug 2025), Week 4 (29 Aug 2025), Week 12 (24 Oct 2025) Note: the auditor was unable to verify if questionnaires were completed prior to other evaluations as the site generated source documents did not include a designated field to capture the time of administration.&nbsp; 2. For 4 of 4 participant records reviewed, the targeted Physical Exam (PE) was not initialed or signed by the person conducting the PE in the source documents for the following visits:&nbsp; a. Participant 10151001: Week 4 (21 May 2025),&nbsp; b. Participant 10151002: Week 4 (30 May 2025), Week 12 (23 Jul 2025), Week 28 (12 Nov 2024).&nbsp; c. Participant 10151003: Screening (22 May 2025),&nbsp; d. Participant 10151006: Screening (16 Jul 2025), Day 1 (01 Aug 2025), Week 4 (29 Aug 2025), Week 12 (24 Oct 2025) Note: the site generated source document lacked a section for the investigator to attest, via signature or initials, that they performed the PE.&nbsp; 3. For 4 of 4 participant records reviewed, the Clinical Assessment forms (Severity of Alopecia Tool (SALT), Eyelash Assessment (ELA), Eyebrow Assessment (EBA), or Columbia-Suicide Severity Rating Scale (C-SSRS)) had the rater ID and rater's initials; however, the date of the assessment was not documented by the rater for the following visits:&nbsp; a. &nbsp; &nbsp;Participant 10151001:&nbsp; a1. Week 4 (21 May 2025): SALT, ELA, EBA, C-SSRS a2. Week 12 (14 Jul 2025): EBA, ELA, C-SSRS a3. Week 24 (09 Oct 2025): EBA, ELA, C-SSRS a4. Week 28 (05 Nov 2025): EBA, ELA, C-SSRS b. &nbsp; &nbsp;Participant 10151002:&nbsp; b1. Week 4 (30 May 2025): EBA, ELA, SALT, C-SSRS.&nbsp; c. &nbsp; &nbsp;Participant 10151003:&nbsp; c1. Screening (22 May 2025): EBA, ELA, SALT, C-SSRS c2. Day 1 (13 Jun 2025): EBA, ELA, SALT, C-SSRS c3. Week 4 (11 Jul 2025): ELA, SALT, C-SSRS c4. Week 12 (05 Sep 2025): EBA, SALT, C-SSRS d. &nbsp; &nbsp;Participant 10151006:&nbsp; d1. Screening (16 Jul 2025): SALT, EBA, ELA d2. Day 1 (01 Aug 2025):SALT, EBA, ELA, C-SSRS d3. Week 4 (29 Aug 2025): SALT, C-SSRS d4. Week 12 (24 Oct 2025): SALT, EBA, ELA, C-SSRS 4. For 3 of 4 participant records reviewed (10151001, 10151002, 10151003), the Screening eligibility review worksheets were signed confirming participant eligibility prior to required safety laboratory result availability and review.&nbsp; Note: The safety laboratory results were available after the screening visit and were part of the eligibility review on Day 1 by the investigator. There were no laboratory results that were exclusionary.&nbsp; 5. For 1 of 4 participants reviewed (10151003), the Clinical Assessment forms (ELA, EBA, and/or CSSRS) did not have the rater ID, initials, or date documented on the forms for the following visits: Day 1 Study Visit (13 Jun 2025), Week 4 (11 Jul 2025).&nbsp; 6. For Participant 10151001: a. Corrections were not performed by the individual who made the documentation error; the study coordinator corrected errors on worksheets originally made by the Principal Investigator (PI), and the PI co-signed these corrections.&nbsp; b. At the Week 4 study visit (21 May 2025), the time of administration of the Investigational Product (IP) was not recorded in the participant dosing diary.&nbsp; c. At the Week 24 study visit (09 Oct 2025), on page 3 of 4 of the study visit worksheets, the header had an incomplete date recorded.&nbsp; d. For Week 28 (05 Nov 2025), the rater of the CSSR questionnaire did not initial the document; however, it was initialed by the coordinator.&nbsp; e. The Dosing Diary for 23 Apr - 22 May 2025 was missing the following information (page 1): Study Clinic (Contact, Name, Telephone Number) and Next Scheduled Visit (Date, Time).&nbsp; f . The Dosing Diary for 23 May - 14 July 2025 was missing the following information (page 1): Participant Information (Subject ID, Date Dispensed), Study Clinic (Contact, Name, Telephone Number).&nbsp; g. The Dosing Diary for 09 Oct - 04 Nov 2025 was missing the following information (page 1): Participant Information (Subject ID, Date Dispensed), Study Clinic (Contact, Name, Telephone Number) and Next Scheduled Visit (Date, Time).&nbsp; 7. Participant 10151002:&nbsp; a. Screening Visit (09 Apr 2025): a1. The review of the screening Electrocardiogram (ECG) was initialed, but was not dated by the investigator.&nbsp; a2. The Certified copy of the screening ECG was initialed and dated with a delay on 07 May 2025 by the investigator.&nbsp; a3. The Canfield Eligibility Report was not filed in the participant chart.&nbsp; b. Week 12 (23 Jul 2025):&nbsp; b1. The 30 May 2025 dose was documented as being missed in the source documents under "accountability 50mg" and "accountability 100mg" sections of the study visit worksheets; however, the IP dose was taken in clinic on 30 May 2025 as documented in the dosing diary.&nbsp; b2. "Any changes in health since the last visit" was documented as "no" in the source documents; however, the participant had an Adverse Event (AE) on 12 Jul 2025 as documented in the source records.&nbsp; 8. Participant 10151003:&nbsp; a. Screening (22 May 2025):&nbsp; a1. The "Screening" eligibility review worksheet did not have the last item (item 13) in the exclusion criteria reviewed by the investigator.&nbsp; Note: the participant did not meet the exclusion criteria.&nbsp; a2. The Type of current episode of AA - "Other AA" was not documented in the Alopecia Areata History in the study visit worksheet.&nbsp; b. Week 4 (11 Jul 2025):&nbsp; b1. The participant was asked to return to the site to repeat chemistry safety laboratory tests due to elevated values; however, the repeated chemistry lab results and the investigator’s review were not filed in the participant’s chart. Additionally, while the investigator instructed the participant to hold IP from July 15 to July 18, 2025, the communication to restart IP on July 19, 2025 was not documented in the participant’s source records. Note: there was no Adverse Event associated with the elevated laboratory results as per PI assessment.&nbsp; c. Week 12 (05 Sep 2025):&nbsp; c1. The "were any doses missed" was not completed for the "Accountability 50mg" and "Accountability 100mg" sections of the source documents.&nbsp; c2. The Dosing Diary was missing the following information (page 1): Participant Information (Subject ID, Date Dispensed) and Study Clinic (Contact, Name, Telephone Number).&nbsp; 9. Participant 10151006:&nbsp; a. Screening (16 Jul 2025):&nbsp; a1. The review of the screening Electrocardiogram (ECG) was initialed, but was not dated by the investigator.&nbsp; a2. The Canfield Eligibility Report was not filed in the participant chart.&nbsp; a3. The added note of "subject declined photo consent" on the informed consent process documentation was not initialed or dated.&nbsp; b. Week 12 (24 Oct 2024):&nbsp; b1. The participant was asked to return to the site for repeat chemistry safety laboratory tests; however, the documentation in the participant chart did not clearly indicate whether the participant was instructed to hold IP due to elevated laboratory test values.&nbsp; Note: As per interview with the study coordinator, IP was not held. &nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Refer to Issue ID # 1-A59W2MB, 1-A59W2MG, 1-A59W2MK, 1-A59W2NI, 1-AFQF47A on the attached Clinical Trial Management System Issue Action log confirming all corrections/updates were completed for this finding. | The Site will update their Source Document Template (for example, capture all required protocol elements and proper attribution fields, including the date/time). The template will clearly designate tasks that are delegated for the Principal Investigator (for example but not limited to Physical Exams.)Responsible Roles: Site Personnel | Jennifer Wysocki |  | - | Jennifer Wysocki | Approved - In CAPA | Closed | Data Collection and Management | Inadequate source data/documentation | NOT APPLICABLE; NOT APPLICABLE | SITE PERSONNEL | MODEL 1 - INSOURCED | Inflammation & Immunology | Wysocki, Jennifer Marie | GSSO | 84 | AMERICAS
AIA-008469 | QE-218208 | 2026-03-16 | 2026-02-20 |  | Completed On Time |  | Minor |  | Jonathan Wolfe, Jonathan Wolfe | UNITED STATES | B7981094_1015 | GCP Site Audit | 2025-12-16 |  | The study coordinator conducted activities that were not formally delegated to them but fell under investigator responsibilities. (ICH GCP E6 (R3) 2.3.3). For 4 of 4 participant records reviewed (10151001, 10151002, 10151003, 10151006), the study coordinator attested to the following, "does the patient meet all the above inclusion/exclusion criteria for the study?" with a "yes" or "no" on the Eligibility worksheets; however, the study coordinator was not delegated to "Determine Eligibility of Subjects".&nbsp; Note: The Principal Investigator co-signed the following, "By signing below the Principal Investigator [redacted] has reviewed the Inclusion/Exclusion criteria, medical history and concomitant medications and as well as all the other source documents completed during this visit confirms subject's eligibility and enrollment into the study".&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Refer to Issue ID # 1-AFQF48C on the attached Clinical Trial Management System Issue Action log confirming all corrections/updates were completed. | The study coordinator and Principal investigator will create a note to file (NTF) to clarify site’s process for reviewing and determining Final Eligibility prior to randomization per protocol. The Clinical Research Associate will confirm the NTF is created and filed in the Investigator Site File (ISF)Responsible Roles: Prinicipal Investigator/ Study Coordinator | Jennifer Wysocki |  | - | Jennifer Wysocki | Closed | Closed | Quality Oversight | Inadequate Principal Investigator quality oversight | NOT APPLICABLE; NOT APPLICABLE | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Inflammation & Immunology | Wysocki, Jennifer Marie | GSSO | 84 | AMERICAS