## Standard_Quality_Dashboard - QE
Observation ID | Study ID | Targeted | PR ID | Site(s) | principal Investigator | EX Comp? | QE Threshold | Status | Observation Description (as submitted) | Awareness Date | Submission Date | Assessment Date | Title/Short Description | Business CAPA Plan Endorsed On | CAPA Plan in Place | Last Action Due Date | Investigation Summary and Conclusion | Effectiveness Check Required | Effectiveness Check Rationale | Investigation Completion Date | Closed On | PDAL Decision | Level 1 | Level 2 | Quality CAPA Plan Endorsed On | Quality Reviewer Approved On | Business Process | Submitter | Confirmed Serious Breach | Remediation Actions Taken (when QE was submitted) | CAPA Action Details | CAPA Action Owner | Root Cause Description | Root Cause Level 1 | Root Cause Level 2 | Root Cause Level 3 | Rapid Model | Business Category
QE-170278 | B7981094 | (Empty) | QE-170278 |  | PFIZER | N | Minor | Closed | One Site had access to financial information of another Site due to ICL mixed up the email's chain | 2025-03-13 | 2025-03-17 | 2025-03-18 16:57 | GCP_Minor_Mar-2025_B7981094: Site Confidentiality_Pfizer_USA |  | NO |  |  | No |  |  | 2025-03-18 |  | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) |  |  | CP411 | Melina Melendez |  | ICL requested the Site to confirm the deletion of the email containing information not related to them. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-201634 | B7981094 | (Empty) | QE-201634 |  | ICON PLC, PFIZER | N | Major | Closed | Participant's samples from Polish sites were sent to a US ICON referral laboratory (which was not IVDR compliant lab) instead of the ICON Certe referral lab located within EU. These samples for the Varicella-Zoster Virus Antibody, IgG test that were supposed to be analyzed within Europe were sent and analyzed in the USA lab due to an ICON error setting. ICON used the wrong study cohort in their system. ICON sent the wrong materials, i.e collection/transportation forms and labels instead of the IVDR Cohort materials to the active sites. The study team is unsure if there will be any impact to the study data. See below list of impacted participants that had their samples sent and analyzed by non IVDR ICON referral Lab in US:Investigator Country Subject Number Visit NamePoland 10051014 ScreenPoland 10051015 ScreenPoland 10121001 ScreenPoland 10121002 ScreenPoland 10121003 ScreenPoland 10121004 ScreenPoland 10121007 ScreenPoland 10121011 ScreenPoland 10141002 ScreenPoland 10141003 ScreenPoland 10141004 ScreenPoland 10141005 ScreenPoland 10561002 ScreenPoland 10561007 ScreenPoland 10621003 ScreenPoland 10621004 ScreenPoland 10621006 ScreenPoland 10621007 ScreenPoland 10621009 ScreenPoland 10621010 ScreenPoland 10621011 ScreenPoland 10621014 ScreenPoland 10641007 ScreenPoland 10641009 ScreenPoland 10641012 ScreenPoland 10701001 ScreenPoland 10701002 ScreenPoland 10701003 ScreenPoland 10751001 ScreenPoland 10751002 ScreenPoland 10751003 ScreenPoland 10751004 ScreenPoland 10751005 ScreenPoland 11431001 ScreenPoland 11431002 ScreenPoland 11431003 ScreenPoland 11431004 ScreenPoland 11431005 ScreenPoland 11431006 ScreenPoland 11431007 ScreenPoland 11431008 ScreenPoland 11431009 ScreenPoland 11431010 ScreenPoland 11431011 Screen&lt;table&gt;&lt;tbody&gt;&lt;tr&gt;&lt;td&gt;&lt;br&gt;&lt;/br&gt;&lt;/td&gt;&lt;td&gt;&lt;br&gt;&lt;/br&gt;&lt;/td&gt;&lt;td&gt;&lt;br&gt;&lt;/br&gt;&lt;/td&gt;&lt;/tr&gt;&lt;/tbody&gt;&lt;/table&gt; | 2025-09-09 | 2025-09-16 | 2025-12-18 13:42 | GCP_Major_Sep-2025_B7981094: Biospecimen Management: IVDR Non-Compliant_ICON Central Lab_POL, UK, ESP, Czech Rep, Pfizer |  | YES |  | <p>The In Vitro Diagnostic Regulation (EU) 2017/746, known as IVDR is the comprehensive European Union law that sets stricter, uniform standards for the safety, performance, and quality of in vitro diagnostic medical devices (like pregnancy tests, blood glucose monitors, COVID tests) sold in the EU, replacing the older directive to align with scientific advancements and improve clinical safety through robust oversight, performance requirements, and risk-based classification (Class A-D).</p><p>&nbsp;</p><p>On 09 September 2025, ICON notified Pfizer that Varicella‑Zoster Virus Antibody (VZV) laboratory samples from 54 participants across ten sites in Poland were mistakenly sent to ARUP, a U.S.-based ICON referral laboratory that is not IVDR‑compliant. These samples should have been routed to the ICON Certe referral laboratory within the European Union (EU). Of the affected samples, 24 were from adolescent participants. Per protocol, VZV testing is required only for adolescent participants.</p><p>&nbsp;</p><p>Separately, in the Czech Republic, one site sent two adult participant samples to ARUP. ICON was instructed to discard these samples, VZV testing is not required for adult participants. In the United Kingdom, five sites sent five adult VZV samples to ARUP; this resulted in no impact to the study. Additionally, five sites in Spain incorrectly received standard sample collections kits. However, because these sites had not yet been activated, there was no impact.</p><p>&nbsp;</p><p>All affected samples were intended for VZV (IgG) testing in adolescents and were required to be analyzed within the EU to ensure adherence to IVDR requirements.</p><p>&nbsp;</p><p>A historical review of Quality Events (QEs) documented in the Spotfire Tool was conducted using the following criteria:<br>&nbsp;Keywords: IVDR, kit, central lab, samples<br>&nbsp;Timeframe: 23 September 2023 – 16 December 2025</p><p>Each identified historical QE—including associated details, root causes, and corrective and preventive actions (CAPAs)—was thoroughly reviewed. Based on this assessment, it was determined that the current event (QE‑201634) does not represent a recurring issue.</p> | No | Other | 2025-12-19 | 2025-12-19 |  | Equipment, Facility and Sample/Specimens, Quality Oversight | Inadequate Principal Investigator quality oversight, Inadequate sample/specimen collection and management |  | 2025-12-19 20:31 | CT29-Management of Clinical Study BioSpecimens, QMS09-Vendor Engagement | Marilia Marchiori | FALSE | ICON submitted a Quality Event on their system and are further investigating it.ICON are also sending new kits with correct forms and labels to the sites and are manually re-directing any VZV participant sample to the correct ICON referral lab in Europe (Certe).Study team also requested Regulatory colleagues to assess the impact of this issue and still awaiting their feedback. |  |  | The ICON Project Coordinator referenced the incorrect SOLAR section when directing Client Service Support (CSS) on site entry, due to insufficient training. and although copied on the communication, the Project Manager (PM) did not identify the error. As a result, ICON Central Lab entered the wrong study cohort for B7981094 sites in Poland, Spain, the UK, and the Czech Republic. This led to sites receiving standard cohort materials for the Varicella‑Zoster Virus Antibody, IgG test instead of the required EU IVDR‑compliant materials. Consequently, samples from sites in Poland (6), the Czech Republic (2), and the UK (2) were sent to the U.S. central lab, ARUP, rather than the EU IVDR‑compliant central lab, Certe. | Method/Procedure | Procedure/Form/Plan | Inconsistency Between Documents (Document Standard Lacking/Incorrect Standard Content) | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-205261 | B7981094 | (Empty) | QE-205261 |  | PFIZER, SYNEOS HEALTH LLC | N | Minor | Closed | Study B7981094 - I was sent a medical record for SSID 10351022 which was not properly redacted (black boxes had been placed over the text in the PDF, but were not proper redactions). As the document was in Korean, I asked Copilot to translate the document and then realized that the document had not been properly redacted as the participant's name and full date of birth were included in the translation. | 2025-10-06 | 2025-10-06 | 2025-10-06 21:35 | GCP_Minor_Oct-2025_B7981094: Participant Confidentiality / Data Privacy_Syneos Health; Pfizer_KOR |  | NO |  |  | No |  |  | 2025-10-06 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Deborah Woodworth |  | Asked Copilot to remove the document and translation from the cloud and my history. However, Copilot stated that it couldn't remove the translation from my history. Requested the monitor to re-send a properly redacted translated document. |  |  | NA | Human Performance | Decision Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-206092 | B7981094 | N | QE-206092 | 1127, 1152 | cheng zhou (B7981094-1152), xiang nong (B7981094-1127) | N | Major | Approved - In Effectiveness Check | Study B7981094, two patients（11521003 and 11271003）with HBcAb postive and HBsAb negative results were enrolled, which meet the exclusion criteria.11521003 subject dosed from 29-Aug-2025 to 27-Sep-202511271003 subject dosed from 25-Sep-2025 to 27-Sep-2025 | 2025-10-10 | 2025-10-10 | 2025-10-10 16:09 | GCP_Major_Oct-2025_B7981094: Protocol Deviation: Inclusion /Exclusion Criteria with Dosing_Pfizer_ICON; Zhou, Cheng; Nong, Xiang_CHN |  | YES |  | <p>A protocol deviation (PD) was identified in the B7981094 study at sites 1152 and 1127 in China, where two participants (11521003 and 11271003) were enrolled despite meeting exclusion criteria. Both participants had positive Hepatitis B Core Antibody (HBcAb) and negative Hepatitis B Surface Antibody (HBsAb) results.&nbsp;</p><p><br></p><p>The PD was first discovered by the principal investigator (PI) at site 1152 on 26-Sep-2025 during a review of laboratory reports to determine which participants required Hepatitis B Virus (HBV) deoxyribonucleic acid (DNA) testing every three months for visit scheduling as per the Schedule of Activities (SOA) in the B7981094 protocol. Following this identification, the China study team instructed all B7981094 China sites to self-check for similar PDs, which led to the identification of the same issue at site 1127.</p><p>&nbsp;</p><p>On the same day, 26-Sep-2025, the primary Clinical Research Associate (CRA) also identified that exclusionary alerts were not sent for participant 11521003 during a review of laboratory reports. This finding revealed that the lab alert system, configured by ICON, was incorrectly set up, resulting in no exclusionary alerts for participants in China with negative HBsAb results.</p><p><br></p><p>A historical review was conducted of Quality Events in the eQMS database to identify QEs that meet the following search criteria: Keywords: &nbsp;Protocol Deviation, B7981094, Inclusion/Exclusion Criteria with Dosing, Pfizer, Zhou, Cheng; Nong, Xiang, China. Timeframe 2 years (Dec 2023 - Jan 2026)</p><p><br></p><p>Each historical QE was reviewed along with the QE Details, Root Causes, and Corrective and Preventive Action(s). Through this review, it was concluded that the current QE (QE-206092) is not a repeat occurrence.</p> | Yes |  | 2026-02-02 |  |  | Protocol Deviations, Quality Oversight | Failure to comply with protocol inclusion/exclusion criteria, Lack of quality assurance program (e.g., independent quality assurance function, missing Quality Plan) |  | 2026-02-04 17:11 | CT40-Management of Protocol Deviations, CT42 | Chunyun Zhao | FALSE | 1.Communicated with Global Clinician and following their instructions that those 2 patients discontinued treatment on 27 Sep 2025 2.Investigators followed with subjects' safety closely and confirm no AE occured till now3. All screening patients with HBcAb postive and HBsAb negative are screened failed in China on 27 Sep 20254. Global clinician had resent email with correct HBsAB result on 27 Sep 20255. Site staffs had been retraning about this exclusion criteria |  |  | The clinical team believed that lab alerts were properly configured to flag ineligible participants for the China cohort, just as they were for other countries. While the HBV-DNA alert was set up correctly, the alert for HBsAb was never set up for China. The emails sent by the global clinician to sites 1152 and 1127 referenced the two participant's HBsAb results without previously checking the actual results in ICOLabs. &nbsp;, The lab alert system failed to generate exclusionary alerts for negative HBsAb results in China because the SOLAR (ICON Statement of Work) document was not user-friendly, lacked version control, and was difficult to review. This, combined with an unclear assignment of responsibility for quality checking between Pfizer and ICON, led to misconfiguration of alerts for country-specific test names and requirements., The PIs at sites 1152 and 1127 did not follow protocol requirements for verifying participant eligibility. Instead, they relied on the global clinician’s email and did not raise a query for the discrepancy between the protocol requirement and the email which resulted in incorrect enrollment. | Human Performance, Method/Procedure | Decision Error, Procedure/Form/Plan | Consequences of Decision Was not Known/Understood - Impact of Deviations/Variance in Process/Task not Known, Inadequate/Inaccurate/Confusing (Document Standard Lacking/Incorrect Standard Content) | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-206092 | B7981094 | (Empty) | QE-206092 |  | ICON PLC, PFIZER | N | Major | Approved - In Effectiveness Check | Study B7981094, two patients（11521003 and 11271003）with HBcAb postive and HBsAb negative results were enrolled, which meet the exclusion criteria.11521003 subject dosed from 29-Aug-2025 to 27-Sep-202511271003 subject dosed from 25-Sep-2025 to 27-Sep-2025 | 2025-10-10 | 2025-10-10 | 2025-10-10 16:09 | GCP_Major_Oct-2025_B7981094: Protocol Deviation: Inclusion /Exclusion Criteria with Dosing_Pfizer_ICON; Zhou, Cheng; Nong, Xiang_CHN |  | YES |  | <p>A protocol deviation (PD) was identified in the B7981094 study at sites 1152 and 1127 in China, where two participants (11521003 and 11271003) were enrolled despite meeting exclusion criteria. Both participants had positive Hepatitis B Core Antibody (HBcAb) and negative Hepatitis B Surface Antibody (HBsAb) results.&nbsp;</p><p><br></p><p>The PD was first discovered by the principal investigator (PI) at site 1152 on 26-Sep-2025 during a review of laboratory reports to determine which participants required Hepatitis B Virus (HBV) deoxyribonucleic acid (DNA) testing every three months for visit scheduling as per the Schedule of Activities (SOA) in the B7981094 protocol. Following this identification, the China study team instructed all B7981094 China sites to self-check for similar PDs, which led to the identification of the same issue at site 1127.</p><p>&nbsp;</p><p>On the same day, 26-Sep-2025, the primary Clinical Research Associate (CRA) also identified that exclusionary alerts were not sent for participant 11521003 during a review of laboratory reports. This finding revealed that the lab alert system, configured by ICON, was incorrectly set up, resulting in no exclusionary alerts for participants in China with negative HBsAb results.</p><p><br></p><p>A historical review was conducted of Quality Events in the eQMS database to identify QEs that meet the following search criteria: Keywords: &nbsp;Protocol Deviation, B7981094, Inclusion/Exclusion Criteria with Dosing, Pfizer, Zhou, Cheng; Nong, Xiang, China. Timeframe 2 years (Dec 2023 - Jan 2026)</p><p><br></p><p>Each historical QE was reviewed along with the QE Details, Root Causes, and Corrective and Preventive Action(s). Through this review, it was concluded that the current QE (QE-206092) is not a repeat occurrence.</p> | Yes |  | 2026-02-02 |  |  | Protocol Deviations, Quality Oversight | Failure to comply with protocol inclusion/exclusion criteria, Lack of quality assurance program (e.g., independent quality assurance function, missing Quality Plan) |  | 2026-02-04 17:11 | CT40-Management of Protocol Deviations, CT42 | Chunyun Zhao | FALSE | 1.Communicated with Global Clinician and following their instructions that those 2 patients discontinued treatment on 27 Sep 2025 2.Investigators followed with subjects' safety closely and confirm no AE occured till now3. All screening patients with HBcAb postive and HBsAb negative are screened failed in China on 27 Sep 20254. Global clinician had resent email with correct HBsAB result on 27 Sep 20255. Site staffs had been retraning about this exclusion criteria |  |  | The clinical team believed that lab alerts were properly configured to flag ineligible participants for the China cohort, just as they were for other countries. While the HBV-DNA alert was set up correctly, the alert for HBsAb was never set up for China. The emails sent by the global clinician to sites 1152 and 1127 referenced the two participant's HBsAb results without previously checking the actual results in ICOLabs. &nbsp;, The lab alert system failed to generate exclusionary alerts for negative HBsAb results in China because the SOLAR (ICON Statement of Work) document was not user-friendly, lacked version control, and was difficult to review. This, combined with an unclear assignment of responsibility for quality checking between Pfizer and ICON, led to misconfiguration of alerts for country-specific test names and requirements., The PIs at sites 1152 and 1127 did not follow protocol requirements for verifying participant eligibility. Instead, they relied on the global clinician’s email and did not raise a query for the discrepancy between the protocol requirement and the email which resulted in incorrect enrollment. | Human Performance, Method/Procedure | Decision Error, Procedure/Form/Plan | Consequences of Decision Was not Known/Understood - Impact of Deviations/Variance in Process/Task not Known, Inadequate/Inaccurate/Confusing (Document Standard Lacking/Incorrect Standard Content) | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-207121 | B7981094 | N | QE-207121 | 1080 | Brandon Coakley (B7981094-1080) | N | Minor | Closed | During routine communication, I received an email chain that included the name of a potential participant who had been referred to a site. The site user was attempting to contact the referral but noted that no phone number had been provided. To resolve this, the site user emailed the Site Care Partner (SCP) requesting the missing contact information. The SCP then forwarded the email to me for assistance.Importantly, only the potential participant’s name was disclosed in the email. No referral or patient IDs were included, and there is no way to link the name to any other data in our system. While the disclosure was limited, it still involved identifiable information being shared across parties, which may constitute a privacy concern under Pfizer’s data handling policies. | 2025-10-14 | 2025-10-16 | 2025-10-16 16:54 | GCP_Minor_Oct-2025_B7981094: Participant Confidentiality_Coakley, Brandon_USA |  | NO |  |  | No |  |  | 2025-10-16 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Tania Lerma Rodriguez |  | Upon receiving the email chain, I immediately informed the Site Care Partner (SCP) that I am not authorized to view any personally identifiable information (PII). The SCP acknowledged the concern, apologized for the oversight, and confirmed that the site had resolved their initial request independently. The SCP also assured that such disclosures would not occur again.To mitigate any potential privacy risk, I promptly deleted the email chain from both my personal inbox and the shared sitesupportandengagement@pfizer.com mailbox where the message had been copied. No further communication on this matter was initiated or received following this action. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-209002 | B7981094 | N | QE-209002 | 1002, 1004, 1016, 1030, 1034, 1035, 1037, 1063, 1068, 1076, 1086, 1087, 1091, 1106, 1109, 1119, 1126, 1141, 1152, 1155, 1158, 1160, 1163, 1166, 1214, 1252, 1293, 1294, 1401, 33018, 81019, 86004 | Atsuro Sawada (C5731001-81019), Ayala Hubert (C3651021-1076), Buhle Nxumalo-Toba (C4591048-1158), Camilla Thellenberg Karlsson (C3441021-1160), cheng zhou (B7981094-1152), Chia-Jen Liu (C1071015-1035), Ge Tan (C4951063-1086), George Medvedev (C4951063-1068), Grant McArthur (C4901001-1068), Heather West (C4391024-1401), Huailian Guo (C4951063-1087), Ildefonso Rodriguez Rivera (C5951001-1004), John O'Mahony (C4951063-1030), Jose luis Velasco garrido (C4531029-1109), Junzhen Gao (C4531029-1163), Laurent Greillier (C5751003-1214), Lu Li (C5751002-86004), Miroslav Stoyanov (C4921003-1034), Nan Su (C4531029-1155), Norman Lepor (C4921003-1016), Sabrina Falkowski (C5731001-33018), Sandra Basic-Kinda (C1071032-1293), Seung Soo Yoo (C5751003-1119), Soyun Cho (B7981094-1037), Steinbjoern Hansen (C2321003-1294), Takuya Shintani (C4921003-1126), Tokuya Omi (B7451031-1063), Tulio Rodriguez (C1071032-1166), Yanqiu Zhao (C5851005-1106), Yi-Tsung Lin (C5091018-1002), You Sook Cho (C4531029-1091), Yusuke Fujikawa (C4921003-1141), Zhangzhou Huang (C5751003-1252) | N | Critical | In Investigation |  Background: On 17 Oct 2025, I received a SIRIUS ticket from a Korean Site care partner. The ticket, originally submitted on 30 Sep 2025, asked why Protocol B7981094 Site 1037 did not have the latest SUSAR reports posted in their SIRIUS portal folder. Investigation Findings:The site status was “Ongoing,” but the “Send SUSAR” flag for the Principal Investigator was set to “N” (No).Normally, for ongoing sites, this flag should be “Y” (Yes), and it cannot be manually changed to “N.”This suggested a technical issue. Actions Taken:On 20 Oct 2025, I contacted the GPDIP team and submitted a ticket.On 21 Oct 2025, GPDIP confirmed that the “susar_Send” flag was “Y” in MDM and GPDIP Intermediate but not updated in GPDIP CDM.On 23 Oct 2025, GPDIP performed a “retrigger” to correct the flag for the site.On 24 Oct 2025, GPDIP provided analysis containing 30 sites with the Send SUSAR flag = Y in Siebel but incorrectly showing as N in GPDIP. Additionally, 2 sites in Siebel have the Send SUSAR flag = N and in GPDIP they show as Y. Ongoing Concerns:I requested GPDIP not to close the ticket, as a backend search is needed to see if other sites are affected.The PIs impacted have been identified but the start date of the issue impacting each PI is unknown.The data for the 32 impacted sites needs to be refreshed so the Send SUSAR flag can correctly populate in downstream systems.The Korean site missed multiple SUSAR reports, which now must be submitted late to the Principal Investigator.It is not yet known how many SUSARs have missed being reported to the impacted PIs, so it is not yet known how many reports will need to be sent to them late. Summary: This is a quality event (QE) causing SUSAR reports not to be sent to Principal Investigators. The full impact is still unclear. This issue is related to QE-200578 and QE-196243. | 2025-10-21 | 2025-10-24 | 2025-10-27 18:40 | GCP_Critical_Oct-2025_Enterprise Level: SUSAR Report Distribution_GPDIP MDM Veeva Clinical_Pfizer_Global UPGRADE |  | NO | [7 empty] | IT Systems, Safety surveillance and reporting by Sponsor | Inadequate Data Conversion / Data Migration / Data Extension / Report Configuration, Inadequate/incomplete reporting, failure/delay in reporting safety event to regulators, authorities, IRB/investigators by Pfizer |  |  | AEM01-Adverse Event Monitoring | C Anna Breen |  | The GPDIP group has been requested to investigate and verify if any other sites have set the Send SUSAR flag incorrectly. They have also been asked to report on when this issue began. The Korean DSU team has been notified that, once further information is available, they will need to send or remediate late reports outside of SIRIUS for this principal investigator. | [6 empty] | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-209002 | B7981094 | (Empty) | QE-209002 |  | PFIZER | N | Critical | In Investigation |  Background: On 17 Oct 2025, I received a SIRIUS ticket from a Korean Site care partner. The ticket, originally submitted on 30 Sep 2025, asked why Protocol B7981094 Site 1037 did not have the latest SUSAR reports posted in their SIRIUS portal folder. Investigation Findings:The site status was “Ongoing,” but the “Send SUSAR” flag for the Principal Investigator was set to “N” (No).Normally, for ongoing sites, this flag should be “Y” (Yes), and it cannot be manually changed to “N.”This suggested a technical issue. Actions Taken:On 20 Oct 2025, I contacted the GPDIP team and submitted a ticket.On 21 Oct 2025, GPDIP confirmed that the “susar_Send” flag was “Y” in MDM and GPDIP Intermediate but not updated in GPDIP CDM.On 23 Oct 2025, GPDIP performed a “retrigger” to correct the flag for the site.On 24 Oct 2025, GPDIP provided analysis containing 30 sites with the Send SUSAR flag = Y in Siebel but incorrectly showing as N in GPDIP. Additionally, 2 sites in Siebel have the Send SUSAR flag = N and in GPDIP they show as Y. Ongoing Concerns:I requested GPDIP not to close the ticket, as a backend search is needed to see if other sites are affected.The PIs impacted have been identified but the start date of the issue impacting each PI is unknown.The data for the 32 impacted sites needs to be refreshed so the Send SUSAR flag can correctly populate in downstream systems.The Korean site missed multiple SUSAR reports, which now must be submitted late to the Principal Investigator.It is not yet known how many SUSARs have missed being reported to the impacted PIs, so it is not yet known how many reports will need to be sent to them late. Summary: This is a quality event (QE) causing SUSAR reports not to be sent to Principal Investigators. The full impact is still unclear. This issue is related to QE-200578 and QE-196243. | 2025-10-21 | 2025-10-24 | 2025-10-27 18:40 | GCP_Critical_Oct-2025_Enterprise Level: SUSAR Report Distribution_GPDIP MDM Veeva Clinical_Pfizer_Global UPGRADE |  | NO | [7 empty] | IT Systems, Safety surveillance and reporting by Sponsor | Inadequate Data Conversion / Data Migration / Data Extension / Report Configuration, Inadequate/incomplete reporting, failure/delay in reporting safety event to regulators, authorities, IRB/investigators by Pfizer |  |  | AEM01-Adverse Event Monitoring | C Anna Breen |  | The GPDIP group has been requested to investigate and verify if any other sites have set the Send SUSAR flag incorrectly. They have also been asked to report on when this issue began. The Korean DSU team has been notified that, once further information is available, they will need to send or remediate late reports outside of SIRIUS for this principal investigator. | [6 empty] | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-210614 | B7981094 | (Empty) | QE-210614 |  | PFIZER | N | Minor | Closed | The Program B798 PEOI (Potential Events of Interests) are captured differently in the Clario 'Communication &amp; Process Plan' vs. the Clario "Adjudication Charter". For DM and Clinical Reconciliation listings, the "Adjudication Charter" PEOI list is being utilized. However, the vendor Clario (at Pfizer's Clinical direction) is utilizing the PEOIs embedded in an excel file in Clario 'Communication &amp; Process Plan'. This incongruence is causing reconciliation fallout and documentation that is confusing and not in alignment. | 2025-10-30 | 2025-11-03 | 2025-11-05 22:31 | GCP_Minor_Nov-2025_B798 Protocols: Potential Events of Interest (PEoI)_Pfizer_Global |  | NO |  |  | No |  |  | 2025-11-05 |  | Quality Oversight/Documentation | Inadequate quality documentation |  |  | CT22-Independent Oversight Committees | Ammber Dunn |  | Ammber initially met with B798 Clinical Lead Amy Freyman and Illeana to discuss this nonconformance in May 2025. It was decided at that time to no update to PEOI list was needed and that Charter should be updated. Charter has not been updated as agreed upon. |  |  | NA | Personnel | Inadequate Information for Determination |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-213607 | B7981094 | N | QE-213607 | 1001 | Taisuke Ito (B7981094-1001) | N | Minor | Closed | Event: The thermal paper attached to the worksheet was missing# 3/Sep/2025: Informed consent obtained# 1/Oct/2025: Study drug administration started # 29/Oct/2025: The subject visit to site for Week 4. The subject measured systolic blood pressure/diastolic blood pressure and pulse rate using an automatic blood pressure monitor. The study coordinator(SC) confirmed the measurement results recorded on thermal paper output from the automatic blood pressure monitor were within normal range, wrote the subject number on the thermal paper, and attached it to the worksheet on the spot. During the examination, the investigator confirmed from the attached thermal paper to the worksheet, he judged the subject’s blood pressure and pulse rate measurement results were within normal range and recorded it in worksheet.# 31/Oct/2025: When the SC tried to enter data into the EDC, the thermal paper attached to the worksheet was missing. The principal investigator determined there was no safety concern and that re-examination was not necessary. Cause: The thermal paper was insufficiently attached due to SC's carelessness. Preventive Measures: Instead of attaching the thermal paper on the spot, it will be filed on the spot and attached after the all assessments for clinical trial are completed. | 2025-11-12 | 2025-11-19 | 2025-11-19 20:28 | GCP_Minor_Nov-2025_B7981094: Source Documentation_Ito, Taisuke_JPN |  | NO |  |  | No |  |  | 2025-11-19 |  | Document Management | Missing document |  |  | No Process Assigned | Takashi Akiba |  | The principal investigator determined there was no safety concern and that re-examination was not necessary. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-214203 | B7981094 | N | QE-214203 | 1064 | Aleksandra Okuniewska (B7981094-1064) | N | Minor | Closed | .0pt;"Retained research samples for genetics (Prep D1) collected on D1 although the Informed Consent for Optional Research Samples was not obtained. CRA identified it on MV 8-14Oct2025 and reported PDs regarding patients: 10641001 (D1 on 21Aug2025), 10641008 (D1 on 24Sep2025), 10641009 (D1 on 23Sep2025), 10641010 (D1 on 30Sep2025). Collected RRS will be destroyed. | 2025-11-18 | 2025-11-21 | 2025-11-24 20:36 | GCP_Minor_Nov-2025_B7981094: Biospecimen Collection; Informed Consent_Okuniewska, Aleksandra_POL |  | NO |  |  | No |  |  | 2025-11-24 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens | Patryk Komorowski |  | Issue discussed with the PI and SC and site staff was retrained. CRA asked site staff to contact the patients and describe it in source data. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-217053 | B7981094 | (Empty) | QE-217053 |  | PFIZER | N | Minor | Closed | Participant’s home address which is personal identifiable information (PII) was contained on an email which was sent to study team, GSM and clinician. | 2025-12-03 | 2025-12-08 | 2025-12-08 19:55 | GCP_Minor_Dec-2025_B7981094: Participant Confidentiality / Data Privacy_Pfizer_KOR |  | NO |  |  | No |  |  | 2025-12-08 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Shinwon Park |  | The emails was deleted once detected. Reminded of the regulation |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-217812 | B7981094 | N | QE-217812 | 1056 | Tadeusz Debniak (B7981094-1056) | N | Minor | Closed | Retained research sample for genetics (Prep D1) was collected on Day1 visit although the Informed Consent for Optional Research Samples was not obtained from subject before this procedures.Mismatch in data collected between EDC status for RR optional consent and laboratory samples status was identified by central study team.The issue was identified for subjects: 10561003, 10561006, 10561008 and local study team was requested for verification with the site.After investigation and revision for all subjects isssue was confirmed for all initially listed subjects. In addition was found out that subject 10561002 is also affected by this issue.10561002, Day1 03Sep202510561003, Day1 08Sep202510561006, Day1 10Sep202510561008, Day1 24Sep2025 | 2025-12-05 | 2025-12-09 | 2025-12-17 17:35 | GCP_Minor_Dec-2025_B7981094: Biospecimen Sample Management; Informed Consent_Debniak, Tadeusz_POL |  | NO |  |  | No |  |  | 2025-12-17 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens | Lena Zajko |  | Revision data related to RR consent for all randomized patients.Issue discussed with assigned CRA, PI and SC.Site staff was retrained by CRA.CRA was requested to ask site staff to contact the impacted patients and describe it in source data. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-218430 | B7981094 | N | QE-218430 | 1108 | Christos Tziotzios (B7981094-1108) | N | Minor | Closed | Site 1108.Screening and Visit one SALT and CSSRS assessments were performed by a untrained rater. Site was trained on the rater qualification process during the SIV. PI completed the rater qualification process and received a rater ID. The Sub Investigator did not complete this process.The participants affected were:11081001, 11081002, 11081003 | 2025-11-26 | 2026-02-02 | 2026-02-02 19:16 | GCP_Minor_Jan-2026_B7981094: Rater Qualifications_Tziotzios, Christos_GBR |  | NO |  |  | No |  |  | 2026-02-02 |  | Training & Qualifications | Training not completed or documented in a timely manner |  |  | CT33-Study Training | Helen McKennedy |  | During the MV01 the CRA could not see which staff member conducted the assessments. CRA requested a meeting with the site staff to discuss. Site was not responsive. CRA spoke with the PI once he had returned from sick leave and discussed the issue, the PI confirmed the Sub I had completed the assessments. The CRA informed the PI of the process required before becoming a rater. The CRA informed the PI that he will need to complete the assessments until the Sub I can get trained. The CRA phoned the Sub I and showed him how to complete the training. The training certifications and the CV were sent to the appropriate team for review. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-218890 | B7981094 | N | QE-218890 | 1028 | Sameh Hanna (B7981094-1028) | N | Minor | Closed | Site accidentally shared a document (an ECG) which contained patient identifying information to the contracted cardiologist. The patient affected is patient 10281013 from Study B7981094 who was made aware of this error yesterday, and did not have any questions/concerns. The ECG was uploaded to the cardiologist portal for analysis on 02-DEC-2025, and site was made aware of the patient identifying information yesterday, the 11-DEC-2025. Only the cardiologist's coordinator was exposed to the information (the patient's name and date of birth) prior to alerting site. The original ECG has now been deleted and a redacted copy has been uploaded (both actions taken 11-DEC-2025). | 2025-12-12 | 2025-12-15 | 2025-12-17 17:25 | GCP_Minor_Dec-2025_B7981094: Participant Confidentiality / Data Privacy_Hanna, Sameh_CAN |  | NO |  |  | No | Minor/Unrated Quality Event |  | 2025-12-17 |  | Data Privacy | Data privacy/confidentiality |  |  | REG09-Protecting the Privacy of Personal Information | Hélène Filion |  | The original ECG has now been deleted and a redacted copy has been uploaded (both actions taken 11-DEC-2025). |  |  | None.&nbsp; | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-219539 | B7981094 | N | QE-219539 | 1062 | Pawel Brzewski (B7981094-1062) | N | Minor | Closed | Retained research samples for genetics (Prep D1) collected on D1 although the Informed Consent for Optional Research Samples was not obtained. CRA identified it during MV on 17-18Dec2025 and reported PDs regarding patients: 10621014 (D1 on 06Oct2025), 10621015 (D1 on 07Oct2025). Collected RRS will be destroyed. | 2025-12-17 | 2025-12-18 | 2025-12-18 17:37 | GCP_Minor_Dec-2025_B7981094: Biospecimen Management; Informed Consent_Brzewski, Pawel_POL |  | NO |  |  | No |  |  | 2025-12-18 |  | Equipment, Facility and Sample/Specimens, Informed Consent | Inadequate consent process at the investigator site, Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens | Patryk Komorowski |  | .0pt"Issue discussed with the PI and SCs and site staff was retrained. CRA asked site staff to contact the patients and describe it in source data. |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-219573 | B7981094 | N | QE-219573 | 1005 | Anna Kozera (B7981094-1005), Patrycja Napiórkowska (B7981094-1005), Witold Owczarek (B7981094-1005) | N | Critical | Approved - In CAPA | Retained research samples for genetics (Prep D1) collected on D1 although the Informed Consent for Optional Research Samples was not obtained. CRA identified it during MV on 11Dec2025 and reported PD regarding patient 10051020 (D1 on 10Nov2025). Collected RRS will be destroyed. | 2025-12-17 | 2025-12-18 | 2025-12-22 20:16 | GCP_Critical_Dec-2025_B7981094: Reoccurrence: Biospecimen Management; Informed Consent_Owczarek, Witold; Kozera, Anna; Napiorkowska, Patrycja_POL UPGRADE |  | YES |  | <p>It was reported on 18 Dec 2025 by the site monitor that site 1005 for the B7981094 study collected optional retained research samples (RRS) for a participant during the randomization Day 1 study visit on 10 Nov 2025. The participant had not signed the optional consent section within the Informed Consent Form permitting the collection of RRS however the study nurse collected samples for all the tubes included within the study kit which included tubes for optional RRS collection.&nbsp;</p><p>&nbsp;</p><p>This issue was reported as a Serious Breach <span style="text-align: left;"><span style="color: rgb(29, 29, 29); font-family: Arial; background-color: rgb(255, 255, 255);">to the European Medicines Agency (EMA)&nbsp;</span></span>on 23 Dec 2025.&nbsp;</p><p>&nbsp;</p><p>An historic review was conducted of Quality Events in the eQMS database to identify QEs that meet the following search criteria:&nbsp;</p><p>Keywords: Retained Sample; Informed Consent; Biospecimen&nbsp;</p><p>Timeframe: 2 years (20 Dec 2023- 30 Dec 2025)&nbsp;</p><p>Each historical QE was reviewed along with the QE Details, Root Causes, and Corrective and Preventative Action(s). Through this review, it was concluded that the current QE (QE-219573) is not a repeat occurrence of QE-210262 and QE-219008.</p> | No | Other | 2026-01-30 | 2025-12-18 |  | Equipment, Facility and Sample/Specimens, Informed Consent | Inadequate consent process at the investigator site, Inadequate sample/specimen collection and management |  | 2026-01-30 19:58 | CT05-Informed Consent Document, CT29-Management of Clinical Study BioSpecimens | Patryk Komorowski | TRUE | .0pt"Issue discussed with the PI and SC and site staff was retrained. CRA asked site staff to contact the patients and describe it in source data. |  |  | The site’s process was dependent on the presence of an individual rather than a checklist or documentation with reminders to ensure the refraining of collection of optional research samples &nbsp;(RRS) from participants who had not consented to RRS collection. | Method/Procedure | Procedure/Form/Plan | Inadequate/Inaccurate/Confusing (Document Standard Lacking/Incorrect Standard Content) | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-219767 | B7981094 | N | QE-219767 | 1080 | Brandon Coakley (B7981094-1080), Cameorn Clements (B7981094-1080) | N | Minor | Closed | Site 1080 sub-I was used to completed patient assessments even though she had not completed the training or been assigned a rater ID. SCP has retrained the site multiple time but SUb-I continues to complete assessments without the training. | 2025-08-25 | 2025-12-18 | 2025-12-19 18:34 | GCP_Minor_Dec-2025_B7981094: Rater Qualification_ Coakley, Brandon , Clements, Cameorn_USA |  | NO |  |  | No | Minor/Unrated Quality Event |  | 2025-12-19 |  | Quality Oversight | Quality Management System issue |  |  | QMS07-Training and Qualifications | Toni Sokol |  | SCP and CRA informed site that this staff member did not have training and had not been cleared to perform the rater assessments at the first IMV conducted at the site. Site was told that the staff member must not complete any additional assessment until all training was completed and a rater ID was assigned. SCP continued to ask the site for training to be completed. SCP also had a call with the PI and SC to discuss the non-compliance issue and retrain site on the correct process. SC confirmed that he understood sub-i was not allowed to do any additional assesment. |  |  | N/A | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-219945 | B7981094 | Y | QE-219945 | 1020, 1067 | Iftikhar Hussain (B7981094-1020), Stephanie Mehlis (B7981094-1067) | N | Minor | Closed | After discussion with Study Team it was found that site was not including time Rater Assessments were completed, only the date and rater number was provided. While recording the time is not specifically outlined in the Protocol, the SALT assessment is to be completed at a certain timepoint prior to IRT completion. As part of the discussion, because it is not specifically included in the Protocol, it is not a Protocol Deviation, it has been determined to be a Quality Event based on a previous audit finding. | 2025-12-18 | 2025-12-19 | 2025-12-19 22:26 | GCP_Minor_Dec-2025_B7981094: Rater Assessment Process_Hussain, Iftikhar; Mehlis, Stephanie; Pfizer_USA |  | NO |  |  | No |  |  | 2025-12-19 |  | Data Collection and Management | Inadequate source data/documentation |  |  | CT02-Protocol Development for Interventional Studies, No Process Assigned | Apryl Thomas |  | Site re-educated that going forward, times are to be recorded on all Rater Assessments. Study Team notified. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-219945 | B7981094 | (Empty) | QE-219945 |  | PFIZER | N | Minor | Closed | After discussion with Study Team it was found that site was not including time Rater Assessments were completed, only the date and rater number was provided. While recording the time is not specifically outlined in the Protocol, the SALT assessment is to be completed at a certain timepoint prior to IRT completion. As part of the discussion, because it is not specifically included in the Protocol, it is not a Protocol Deviation, it has been determined to be a Quality Event based on a previous audit finding. | 2025-12-18 | 2025-12-19 | 2025-12-19 22:26 | GCP_Minor_Dec-2025_B7981094: Rater Assessment Process_Hussain, Iftikhar; Mehlis, Stephanie; Pfizer_USA |  | NO |  |  | No |  |  | 2025-12-19 |  | Data Collection and Management | Inadequate source data/documentation |  |  | CT02-Protocol Development for Interventional Studies, No Process Assigned | Apryl Thomas |  | Site re-educated that going forward, times are to be recorded on all Rater Assessments. Study Team notified. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-222232 | B7981094 | Y | QE-222232 | 1067 | Stephanie Mehlis (B7981094-1067) | N | Minor | Closed | Site did not enter SAE into PSSA reporting system within 24 hours of awareness of the SAE. Site did notify and shared the information with the Clinical Team within the 24-hour notification period and entered into Inform EDC, just did not get put into PSSA. | 2026-01-06 | 2026-01-12 | 2026-01-12 18:31 | GCP_Minor_Jan-2026_B7981094: SAE Reporting_Mehlis, Stephanie_USA |  | NO |  |  | No | Minor/Unrated Quality Event |  | 2026-01-12 |  | Safety Information Communication | Failure/Incomplete safety communication |  |  | AEM01-Adverse Event Monitoring | Apryl Thomas |  | Site was instructed to complete a paper SAE form and submit. Once site staff has access to PSSA system, the site will transcribe the information from the paper SAE form to PSSA. Site was re-educated on the importance of PSSA entry of SAE within 24-hours of awareness. |  |  | N/A | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-223421 | B7981094 | N | QE-223421 | 1087 | Nisha Desai (B7981094-1087) | N | Minor | Closed | B7981094 Site 1087 had 2 sub-investigators who were not approved to conduct Columbia-Suicide Severity Rating Scale (C-SSRS) assessments on patients. One sub-investigator completed one assessment on 03Sep2025 and the other sub-investigator completed two assessments on 02Oct2025 and 27Oct2025. | 2026-01-14 | 2026-01-16 | 2026-01-16 22:05 | GCP_Minor_Jan-2026_B7981094: Rater Qualification_Desai, Nisha_USA |  | NO |  |  | No |  |  | 2026-01-16 |  | Protocol Deviations | Failure to follow protocol |  |  | CT40-Management of Protocol Deviations | Michelle Krocka |  | Certificates of training were sent to the clinical research associate (CRA) and approval process was started. Both raters were approved on 24Nov2025. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-223425 | B7981094 | N | QE-223425 | 1087 | Nisha Desai (B7981094-1087) | N | Minor | Closed | The site accidentally logged Week 12 for SSID 10871002 under SSID 10871003 in the Impala 2.0 system. Incorrect investigational medicinal product (IMP) was dispensed to patient 10871002. Patient took this IMP for 2 days before site realized he was dispensed the wrong bottles of IMP. | 2026-01-16 | 2026-01-16 | 2026-01-16 21:52 | GCP_Minor_Jan-2026_B7981094: Medication Error: Dispensing Error_Desai, Nisha_USA |  | NO |  |  | No |  |  | 2026-01-16 |  | Medicinal Product | Inadequate preparation, dosing, dispensing error |  |  | CT13-Investigational Product | Michelle Krocka |  | Site called patient 10871002 on 24Dec2025 and told the patient to discontinue taking the IMP. Site staff then scheduled a visit on 26Dec2025 for the patient to come in and return the erroneous bottles of IMP. Site then provided the patient with the correct bottles of IMP. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-224466 | B7981094 | (Empty) | QE-224466 |  | PFIZER | N | Minor | Closed | It was identified that one of the roles (Database Builder_Production) in several InForm studies had incorrect permissions enabled including permissions to enter/edit data. | 2026-01-16 | 2026-01-23 | 2026-01-23 18:56 | GCP_Minor_Jan-2026_Multiple Studies: System Access Controls_Pfizer_IND |  | NO |  |  | No |  |  | 2026-01-23 |  | IT Systems | Inadequate system access or account management |  |  | CP403 | Jennifer DelSanto |  | Updated the role to have the correct permissions enabled according to the InForm Rights and Roles matrix, performed QC and generated audit trail report to ensure no unexpected transactions occurred. |  |  | NA | Equipment/System/Facility | System/Application |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-224909 | B7981094 | N | QE-224909 | 1005, 1035, 1042, 1054, 1105, 1108, 1121, 1141, 1143, 1179, 1297 | ALICIA GONZALEZ QUESADA (B7981041-1042), Jennifer Cather (B7981041-1121), Katharina Kreutzer (B7981080-1141), Lawrence Sher (B7981080-1297), Nicolas Leitz (B7981041-1054), OHSANG KWON (B7981094-1035), Serap Ozturkcan (B7981041-1108), Shireen Sidhu (B7981041-1105), Snejina Vassileva (B7981041-1179), Witold Owczarek (B7981094-1005), Xiaowei Shi (B7981041-1143) | N | Critical | In Investigation | In study B7981080 at Site 1009 the SC mistakenly entered the wrong responder status in Impala on 08 Jan 2026 for participant 10091002. The correct data is 'Sub-threshold responder' instead of 'responder'. The site also missed to enter the Responer Status into SIgnant Health. The event was discovered by the monitor during routine monitoring visit on 21Jan2026.. The monitor requested access to Veeva Quality on 22Jan2026 to report the case, but as of today she was not yet granted access, therefore the SCP is reporting the event. on behalf of the CRA | 2026-01-21 | 2026-01-27 | 2026-01-27 19:20 | GCP_Critical_Jan-2026_B798 Program: Incorrect Responder Status_Multiple PIs; Pfizer_Multiple Countries UPGRADE |  | NO | [7 empty] | Medicinal Product, Quality Procedures | Failure to detect or document issue (quality control), Inadequate preparation, dosing, dispensing error |  |  | IP13-Investigational Medicinal Product | Zsuzsa Lieber |  | The monitor called and emailed the site on 22 Jan 2026 to immediately call and request the patient stop the IP administration. CRA informed the Study Team via email on 22 Jan 2026.. | [6 empty] | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-224909 | B7981094 | Y | QE-224909 | 1004, 1009, 1018, 1027, 1109, 1178, 1202 | Aleksandra Lesiak (B7981041-1202), Andrea Szegedi (B7981080-1009), Athanasios Tsianakas (B7981041-1027), Boyka Stoyanova (B7981041-1178), Claudia Ledesma de la Torre (B7981041-1109), Juan Ruano Ruiz (B7981041-1018), Seth Forman (B7981041-1004) | N | Critical | In Investigation | In study B7981080 at Site 1009 the SC mistakenly entered the wrong responder status in Impala on 08 Jan 2026 for participant 10091002. The correct data is 'Sub-threshold responder' instead of 'responder'. The site also missed to enter the Responer Status into SIgnant Health. The event was discovered by the monitor during routine monitoring visit on 21Jan2026.. The monitor requested access to Veeva Quality on 22Jan2026 to report the case, but as of today she was not yet granted access, therefore the SCP is reporting the event. on behalf of the CRA | 2026-01-21 | 2026-01-27 | 2026-01-27 19:20 | GCP_Critical_Jan-2026_B798 Program: Incorrect Responder Status_Multiple PIs; Pfizer_Multiple Countries UPGRADE |  | NO | [7 empty] | Medicinal Product, Quality Procedures | Failure to detect or document issue (quality control), Inadequate preparation, dosing, dispensing error |  |  | IP13-Investigational Medicinal Product | Zsuzsa Lieber |  | The monitor called and emailed the site on 22 Jan 2026 to immediately call and request the patient stop the IP administration. CRA informed the Study Team via email on 22 Jan 2026.. | [6 empty] | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-226684 | B7981094 | N | QE-226684 | 1143 | Leszek Bartoszak (B7981094-1143) | N | Minor | Closed | Retained research sample for genetics (Prep D1) was collected on Day1 visit although the Informed Consent for Optional Research Samples was not obtained from the participants before this procedure. A mismatch in data collected between EDC status for RR optional consent and laboratory samples status was identified by central study team. The issue was identified for subject 11431016. Local study team was requested for verification with the site. After investigation and revision, the issue was confirmed for the patient. 11431016, Day1 06 Nov 2025 | 2026-02-04 | 2026-02-05 | 2026-02-05 19:06 | GCP_Minor_Feb-2026_B7981094: Biospecimen Sample Management; Informed Consent_Bartoszak, Leszek_POL |  | NO |  |  | No |  |  | 2026-02-05 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens | Zaneta Wilicka-Swiercz |  | Revision of data related to RR consent was done for all randomized participants. Issue was discussed with assigned CRA, PI and SC. Site staff was retrained by CRA. CRA was requested to ask site staff to contact the impacted participants and describe it in source data. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-229829 | B7981094 | N | QE-229829 | 1029 | Sheetal Sapra (B7981094-1029) | N | Minor | Closed | The site coordinator at site1029 submitted source documents to TAP for subject10291001 because there was an query that was opened in which the source was required. The site coordinator uploaded source documents for subject; however, they didn't redacted subject information from the documents. | 2026-02-17 | 2026-02-23 | 2026-02-23 19:31 | GCP_Minor_Feb-2026_B7981094: CMCD: Participant Confidentiality_Sapra, Sheetal_CAN |  | NO |  |  | No |  |  | 2026-02-23 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Natasha Sharma |  | The site will be re-trained on privacy requirements. The site will be re-directed to PHI/PII Redaction Guidelines QRF within TAP's Training page. |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-231668 | B7981094 | N | QE-231668 | 1105 | PATRICIA LEE (B7981094-1105) | N | Minor | Closed | site inquired to the monitor on 03FEB26 that Subject 11051001 presented for V5/WK24 today and it was noticed by the coordinator that the “platelet sticker” was in the visit kit but no tube. The site uses in house supplies to add the correct tube and sticks the platelet label on it. The site confirmed that this occurred during the Screening visit, Baseline visit, and Visit 5 for 1 subject 11051001 only. The kits corresponding to these visits did not have a platelet tube. Site was retrained next monitoring visit about the platelets already being drawn and that there was no need for additional lab draws. | 2026-02-23 | 2026-03-04 | 2026-03-04 20:14 | GCP_Minor_Mar-2026_B7981094: Biospecimen Sample Management_Lee, Patricia_USA |  | NO |  |  | No |  |  | 2026-03-04 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens | Lauryn Brown |  | Monitor retrained site on using correct lab kits to utilize for lab procedures during the study. Non study supply collection tubes should not be used for remaining of the study. Site was informed platelets are collected within cbc panel. |  |  | NA | Human Performance | Inconsistency Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-231698 | B7981094 | N | QE-231698 | 1027 | Jamie Rhoads (B7981094-1027) | N | Minor | Closed | Retained research sample was taken by mistake as the subject 10271001 did not consent to the retained research sample collection | 2026-03-04 | 2026-03-04 | 2026-03-04 20:25 | GCP_Minor_Mar-2026_B7981094: Biospecimen Sample Management; Informed Consent_Rhoads, Jamie_USA |  | NO |  |  | No |  |  | 2026-03-04 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens | Lauryn Brown |  | Monitor retrained site by going over the table of schedule of activities in the protocol to ensure the site understands the lab protocol for the remaining of the study. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-234629 | B7981094 | (Empty) | QE-234629 |  | ICON PLC | N | Minor | Closed | Issue identified on 16 March 2026 affecting the display of high flags for AST (adult) and GGT (paediatric) results.On 09 March 2026, AST and GGT reference ranges were updated in accordance with Scientific Updates 805v2 and 848. During this update, the associated high‑result thresholds were not applied in ICON’s laboratory system (ICOLIMS). As a result, AST and GGT results released between 09 March 2026 and 16 March 2026 did not display high flags when result values were above the applied reference range. | 2026-03-16 | 2026-03-19 | 2026-03-20 18:08 | GCP_Minor_Mar-2026_Multiple Studies: Vendor Responsibilities: High-Flag Thresholds_ICON_Global |  | NO |  |  | No |  |  | 2026-03-20 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | No Process Assigned | Jeremy Vire |  | Issue was corrected in ICOLIMS on 16 March 2026, and the high‑flag thresholds are now active. Impacted accessions will be reprocessed to apply the appropriate result flagging, and corrected laboratory reports will be reissued through the standard distribution channels. A quality investigation has been initiated under sCAPA‑03079, and a full CAPA report will be provided upon completion. |  |  | NA | Equipment/System/Facility | System/Application |  | MODEL 1 - INSOURCED | Inflammation & Immunology