## Standard_Quality_Dashboard - SQ
Case ID | Case Status | Observation ID | Obs Status | Submission Date | Issue Audit Report (Actual) | Center Number | principal investigator | Country | Description | Study ID | Protocol ID | Title Short Description | Drug Program Code | Rating | Event Type | Case CAPA Approved Due Date | Case CAPA Approved On | CAPA Plan In Place Timely | Obs CAPA Approved Due Date | Obs CAPA Approved On | Obs Target Completion Date | Obs Actual Completion Date | Case CAPA Closure Timely | Case Target Completion Date | Case Actual Completion Date | Obs CAPA Closure Timely | Selected Business Process | Taxonomy Level 1 | Taxonomy Level 2 | Study Status | Business Category | Study Phase | Study Priority | Asset | Dev China | Dev Japan | Rapid Model | Business Category
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1010 | shusen wang (C4891001-1010) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1016 | Huiqiang Huang (A8081075-1016) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1017 | shusen wang (C4891002-1017) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1022 | Yaping Yang (A5481173-1022) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1025 | shusen wang (A5481027-1025) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1025 | Weidong Zhang (A5481027-1025) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1032 | Zhongjun XIA (C1071015-1032) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1035 | Peiying Feng (B7981118-1035) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1054 | Ruihua Xu (C6461003-1054) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1054 | Yanhong Deng (C6461016-1054) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1055 | shusen wang (C4551001-1055) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1079 | shusen wang (C4891026-1079) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1091 | Yugang Dong (C4921003-1091) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1142 | Yanhong Deng (C6461003-1142) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1209 | Zhongjun Xia (C1071006-1209) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1237 | shusen wang (C4551002-1237) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1259 | Yonghong Li (C2321008-1259) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1309 | Zhongjun XIA (C1071005-1309) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1315 | shusen wang (C4391024-1315) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1319 | Zhongjun XIA (C1071007-1319) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 86001 | Yanhong Deng (C5831001-86001) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 86002 | Jian Huang (C5701003-86002) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 86002 | shusen wang (C4251001-86002) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 86010 | Yanhong Deng (C4251008-86010) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | (Empty) | PFIZER | (Empty) | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | B7981118 | B7981118 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | B798 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-224942 | In Investigation | QE-224942 | In Investigation | 2026-01-27 | (Empty) | (Empty) | PFIZER | (Empty) | This event relates to sync issues involving Pfizer Siebel to Reltio resulting in missing sites from SIRIUS through a Dynatrace relate which never appeared on the Business Continuity Plan (BCP) put in place post Veeva CTMS issues.A new QE has been raised per management request due to a potential different cause separate from the existing Veeva CTMS issues impacting SUSARs downstream (QE-169243, QE-209002, QE-212408)(T. Houck) UPDATED to the following per instruction from submitter on 28 Jan 2026:This event relates to sync issues involving Pfizer Siebel to Reltio resulting in missing sites from SIRIUS which never appeared on the Business Continuity Plan (BCP) put in place post Veeva CTMS issues.A new QE has been raised per management request due to a potential different cause separate from the existing Veeva CTMS issues impacting SUSARs downstream (QE-169243, QE-209002, QE-212408) | B7981118 | B7981118 | GCP_Major_Jan-2026_Multiple Protocols: System-Level, CTMS / GPD IP Business Continuity Plan (BCP) and SIRIUS Reporting_Pfizer_Global | B798 | Major | SQE | 2026-03-14 | (Empty) | N | 2026-03-14 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | AEM01 - Adverse Event Monitoring | Safety surveillance and reporting by Sponsor | Inadequate/incomplete reporting, failure/delay in reporting safety event to regulators, authorities, IRB/investigators by Pfizer | ONGOING | Inflammation & Immunology | PHASE IIB | MAINTAIN | Ritlecitinib CSU | China Global | JP_Global | MODEL 1 - INSOURCED | Inflammation & Immunology