## Standard_Quality_Dashboard - QE
Observation ID | Study ID | Targeted | PR ID | Site(s) | principal Investigator | EX Comp? | QE Threshold | Status | Observation Description (as submitted) | Awareness Date | Submission Date | Assessment Date | Title/Short Description | Business CAPA Plan Endorsed On | CAPA Plan in Place | Last Action Due Date | Investigation Summary and Conclusion | Effectiveness Check Required | Effectiveness Check Rationale | Investigation Completion Date | Closed On | PDAL Decision | Level 1 | Level 2 | Quality CAPA Plan Endorsed On | Quality Reviewer Approved On | Business Process | Submitter | Confirmed Serious Breach | Remediation Actions Taken (when QE was submitted) | CAPA Action Details | CAPA Action Owner | Root Cause Description | Root Cause Level 1 | Root Cause Level 2 | Root Cause Level 3 | Rapid Model | Business Category
QE-194748 | B7981119 | (Empty) | QE-194748 |  | PFIZER | N | Minor | Closed | Vendor (IQVIA) contact was granted access to a specific folder in SP by Pfizer clinician, to be able to load slides urgently for a KOM. Vendor circulated the link to the rest of the internal team to confirm KOM slides were uploaded. GSM did not see the original teams chat about this and was confused why Vendor circulated a SP link to the folder and asked how the vendor had access to this folder. Vendor then saw a link circulated from GSM for another file and requested access to this file. CSTL saw the request and declined. | 2025-08-07 | 2025-08-08 | 2025-08-11 15:11 | GCP_Minor_Aug-2025_B7981119: System Access Controls_Pfizer_Global |  | NO |  |  | No |  |  | 2025-08-11 |  | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) |  |  | CP403 | Charlotte Epsley |  | Team investigated and CSTA created a new Vendor collaboration folder - for single access for the vendor to collaborate with the team. Access for the vendor has been granted to the new folder and the other folder deleted. Team will continue to use this folder managed by the CSTA moving forward. |  |  | NA | Human Performance | Decision Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-200197 | B7981119 | (Empty) | QE-200197 |  | PFIZER | N | Major | Approved - In CAPA | The PRS Prediction tool (Protocol Risk Score) is a machine learning algorithm run against 31 data points (primarily Registry) pulled from the GPDIP database to provide a PRS for study team and RQA set up and planning. It was recently noted that the tool has been generating final PRS scores for users based upon incomplete and/or stale data. The PRS scores are used by:.25in;"Study Management for development of the SDV/SDR percentage in the Study Monitoring Plan per INV02-INV04-GSOP-RF04 and INV04-GSOP-RF17. Data Management for SDV requirements during the EDC database build as per DMB07-GSOP-RF27.Study teams for contract and budgeting purposes at the endorsed study outline time pointRegulatory Quality Assurance for their audit strategy development The PRS is provided automatically twice during a study; an ‘at risk’ PRS score is provided at Study Outline, and Final PRS is provided at Study FAP (within 24-48hrs of those dates being received in GPDIP). A review of data shows:that 43/60 studies receiving a Final PRS since the prediction tool was implemented had at least 4 of the 31 required fields missing.Some studies had more than 15 missing data points at the time their PRS was calculated.All 60 studies were missing the same 3 data points – which were retired several years ago from the Registry. The replacement field is not used in the calculation..25in;" Lastly, study teams submitting updates to the Registry have noticed that their updates are not reflected in revised PRS scores. This led to the discovery that data from 2 GPDIP databases are not flowing to the PRS Prediction Tool. – so the tool is using stale data to make calculations. 17 studies have had Final PRS calculated with stale data. 2 support tickets were submitted by Pan Liu, which remained open last week. It might be as much as a month ago that the stale data were identified. It does not appear that RQA nor any study teams are aware of the stale data issue, or the potential impact of using a PRS generated from incomplete data.The start date would be the launch date of the PRS Prediction Tool (Confirm with Tarin McTague or Sheri Kuss). The awareness date would be 8Sep2025, when AQLs met with Ivan Walrath and Tarin McTague to discuss and confirm concerns. | 2025-09-08 | 2025-09-08 | 2025-09-09 15:30 | GCP_Major_Sep-2025_Multiple Protocols: PRS Prediction tool (Protocol Risk Score)_Pfizer_Global |  | YES |  | <p style="margin-left: 0in;"><span style="font-size: small;">On 08 September 2025, a Pfizer Asset Quality Lead (AQL) identified stale data impacting the Protocol Risk Score (PRS) Tool. Updated data from upstream systems had not flowed into the PRS Tool since 01 May 2025, meaning calculations performed by the tool during this period were based on outdated information.</span></p><p style="margin-left: 0in;"><span style="font-size: small;">&nbsp;</span></p><p style="margin-left: 0in;"><span style="font-size: small;">The PRS Tool is a machine learning algorithm that calculates a study-level risk score using 31 data points entered by study teams into various source systems. These data points are aggregated by the PRS Tool and processed through the algorithm to generate an overall risk classification (i.e., low, medium, or high). This score informs study teams of the study’s risk profile and supports decisions on risk mitigation activities such as monitoring plans, Source Document Review (SDR), and Source Data Verification (SDV).</span></p><p style="margin-left: 0in;"><span style="font-size: small;">&nbsp;</span></p><p style="margin-left: 0in;"><span style="font-size: small;">The PRS Tool automatically calculates scores at two key time points:</span></p><ul type="disc"><li style="margin-left: 0.5in; font-size: small;">Post-Study Outline: Provides an initial risk score based on limited early data.</li><li style="margin-left: 0.5in; font-size: small;">Post-Final Approved Protocol (FAP): Generates a comprehensive risk score using a more complete dataset.</li></ul><p style="margin-left: 0.3in;"><span style="font-size: small;">&nbsp;</span></p><p style="margin-left: 0in;"><span style="font-size: small;">Additionally, study teams may request ad hoc PRS scores at any time.</span></p><p style="margin-left: 0in;"><span style="font-size: small;">&nbsp;</span></p><p style="margin-left: 0in;"><span style="font-size: small;">Data flow to the PRS Tool was restored on 15 September 2025. During the outage period, PRS scores were calculated for 16 studies at the FAP time point.</span></p><p style="margin-left: 0in;"><span style="font-size: small;">&nbsp;</span></p><p style="margin-left: 0in;"><span style="font-size: small;">A historical review of Quality Events (QEs) in the electronic Quality Management System (eQMS) database was conducted for the period 08 September 2023 – 18 December 2025, using the keywords “Protocol Risk Score Tool” and “PRS Score Tool.” No historical QEs were identified. Based on this review, the current QE (QE-208430) is not considered a repeat occurrence.</span></p> | No | CAPA Plan included error proofing that will prevent reoccurrence | 2026-01-06 |  |  | IT Systems | Inadequate IT system (eg. planning, definitions, design, development, testing, validation, support) per regulatory requirements |  | 2026-01-07 18:19 | QMS06-Risk Management for Clinical Development | Walter Sauer | FALSE | 4Aug2025 AQL JS noted gaps in data set for B7981118 upon completion of ad hoc update. AQL JS downloaded full data set from PRS Prediction Tool to perform personal review of data. Consulted over the next week or so with AQLs HW and MG. 18Aug2025 AQL MG Requested meeting with technical and process SMEs/BPOs - scheduled for 10Sep 2025. 28Aug2025 AQL JS and HW met with Registry team to review processes and data requirements. 8 Sep 2025 AQL JS presented investigation results to QMS06 BPO and Head, Risk Quality and Operations. Agreement that QE submission was warranted even without full impact assessment and/or BPO identification |  |  | A lack of awareness of the relationship between CT27 "Clinical Trial Registry" data entry and PRS tool automated score within study teams can cause updated data to be missing from the Clinical Trial Registry during PRS automated score calculation., An update associated with the Siebel CTMS to Veeva transition caused a value within Siebel CTMS to become unrecognized by GPDIP and prevented updated data from flowing into GPDIP. The PRS tool was then pulling stale data from GPDIP. | Equipment/System/Facility | System/Application | Failure or Malfunction, Signals Unavailable or Ineffective | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-210606 | B7981119 | (Empty) | QE-210606 |  | PFIZER | N | Minor | Closed | Protocol Captures that "Participants will use a participant-completed eDiary to record the date and time of their study intervention dosing " However it also says "The date and time of each dose of study intervention administered in the clinic will be recorded by the participant in the eDiary. The date and time of each dose on visits when PK samples are collected must also be recorded in the CRF." The Study Team during Build decided to move forward with eDiary collection only. Thus, we did not go live with a Dosing CRF (as this data would have been duplication). However, there was no PACL to correct the Protocol language that requested duplication of data. | 2025-10-16 | 2025-11-03 | 2025-11-03 18:09 | GCP_Minor_Nov-2025_B7981119; B7981118: Database Design; Protocol_Pfizer_Global |  | NO |  |  | No |  |  | 2025-11-03 |  | IT Systems | Inadequate IT system (eg. planning, definitions, design, development, testing, validation, support) per regulatory requirements |  |  | DMB07-Study Data Set Design and Setup | Ammber Dunn |  | CDS has met with Quality, Clin Pharm, SDSA and Clinical to make a decision to either create the PACL or add a Dosing CRF. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-210614 | B7981119 | (Empty) | QE-210614 |  | PFIZER | N | Minor | Closed | The Program B798 PEOI (Potential Events of Interests) are captured differently in the Clario 'Communication &amp; Process Plan' vs. the Clario "Adjudication Charter". For DM and Clinical Reconciliation listings, the "Adjudication Charter" PEOI list is being utilized. However, the vendor Clario (at Pfizer's Clinical direction) is utilizing the PEOIs embedded in an excel file in Clario 'Communication &amp; Process Plan'. This incongruence is causing reconciliation fallout and documentation that is confusing and not in alignment. | 2025-10-30 | 2025-11-03 | 2025-11-05 22:31 | GCP_Minor_Nov-2025_B798 Protocols: Potential Events of Interest (PEoI)_Pfizer_Global |  | NO |  |  | No |  |  | 2025-11-05 |  | Quality Oversight/Documentation | Inadequate quality documentation |  |  | CT22-Independent Oversight Committees | Ammber Dunn |  | Ammber initially met with B798 Clinical Lead Amy Freyman and Illeana to discuss this nonconformance in May 2025. It was decided at that time to no update to PEOI list was needed and that Charter should be updated. Charter has not been updated as agreed upon. |  |  | NA | Personnel | Inadequate Information for Determination |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-217000 | B7981119 | (Empty) | QE-217000 |  | CLARIO, PFIZER | N | Minor | Closed | FSFV reached for B7981118 Oct 30th and B79810119 13th Nov 2025, the study teams I understand have been meeting with Clario as the selected adjudication event processing vendor. However, Clario is not yet contracted to support this service type. There is a program level WO for B798, but the WO has not yet been updated to include these new trials.There have been no events adjudicated at this time, and the Adjudication Committee charter is updated to include the new studies.CO2 is in process to increase the scope to add '1118' and '1119" and is expected to be in place in the coming business days (likely by/before Dec 8th pending funding).AC Charter updated/effective 11Aug2025 (selected this date as the Date Occurred) | 2025-12-02 | 2025-12-04 | 2025-12-05 13:42 | GCP_Minor_Dec-2025_B7981118, B7981119: Vendor Management: Contract_Pfizer_Global |  | NO |  |  | No |  |  | 2025-12-05 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | QMS09-Vendor Engagement | Timothy Ferris |  | Team shared a CO to include the additional trials is in process and the contracting colleague expressed expectation that CO to be fully executed in the coming business days. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-217484 | B7981119 | (Empty) | QE-217484 |  | PFIZER | N | Minor | Closed | dISRP not completed prior to site activation for site 1007 | 2025-11-25 | 2025-12-08 | 2025-12-08 19:36 | GCP_Minor_Dec-2025_B7981119: Investigator Site Recruitment Plan (ISRP)_Pfizer_USA |  | NO |  |  | No |  |  | 2025-12-08 |  | Site Management and Monitoring | Failure to follow study specific monitoring plan/ requirements |  |  | INV03-Study Participant Recruitment and Retention Planning | Toni Sokol |  | ISRP was completed once the dISRP was available in the new My Trial system after the study team confirmed the guidance in INV03 |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-221724 | B7981119 | N | QE-221724 | 1007 | Ali Moiin (B7981119-1007) | N | Minor | Closed | Site completed CSSRS on paper, due to IQVIA portal not working correctly, which is a violation of Site User Manual for the study. | 2026-01-07 | 2026-01-07 | 2026-01-07 21:21 | GCP_Minor_Jan-2026_B7981119: eCOA Data Collection_Moiin, Ali_USA |  | NO |  |  | No |  |  | 2026-01-07 |  | Data Collection and Management | Inadequate source data/documentation |  |  | No Process Assigned | Anna Hayryan |  | Site informed that the paper copy cannot be used. Site will complete when the portal issue will be fixed. |  |  | NA | Equipment/System/Facility | System/Application |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-221725 | B7981119 | (Empty) | QE-221725 |  | IQVIA RDS INC | N | Minor | Closed | During screening of subject the IQVIA SCRIBE application did not load the required baseline CSSRs questionnaire for the CSSRS rater to complete. The site called the IQVIA HD and registered that issue and attempted to trigger an unscheduled visit to complete the questionnaire, however that functionality failed as well. | 2026-01-07 | 2026-01-07 | 2026-01-08 15:20 | GCP_Minor_Jan-2026_B7981119: Vendor Responsibilities: eCOA Data Collection_IQVIA_USA |  | NO |  |  | No |  |  | 2026-01-08 |  | Data Collection and Management | Data management error |  |  | No Process Assigned | Reena Patel |  | vendor helpdesk contacted to register a ticket. Issues was further escalated to IQVIA PM to investigate and find resolution. |  |  | na | Equipment/System/Facility | System/Application |  | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-224942 | B7981119 | (Empty) | QE-224942 |  | PFIZER | N | Major | In Investigation | This event relates to sync issues involving Pfizer Siebel to Reltio resulting in missing sites from SIRIUS through a Dynatrace relate which never appeared on the Business Continuity Plan (BCP) put in place post Veeva CTMS issues.A new QE has been raised per management request due to a potential different cause separate from the existing Veeva CTMS issues impacting SUSARs downstream (QE-169243, QE-209002, QE-212408)(T. Houck) UPDATED to the following per instruction from submitter on 28 Jan 2026:This event relates to sync issues involving Pfizer Siebel to Reltio resulting in missing sites from SIRIUS which never appeared on the Business Continuity Plan (BCP) put in place post Veeva CTMS issues.A new QE has been raised per management request due to a potential different cause separate from the existing Veeva CTMS issues impacting SUSARs downstream (QE-169243, QE-209002, QE-212408) | 2026-01-23 | 2026-01-27 | 2026-01-28 20:12 | GCP_Major_Jan-2026_Multiple Protocols: System-Level, CTMS / GPD IP Business Continuity Plan (BCP) and SIRIUS Reporting_Pfizer_Global |  | NO | [7 empty] | Safety surveillance and reporting by Sponsor | Inadequate/incomplete reporting, failure/delay in reporting safety event to regulators, authorities, IRB/investigators by Pfizer |  |  | AEM01-Adverse Event Monitoring | C Anna Breen |  | SUSAR reports not previously submitted to PIs were identified and distributed outside of SIRIUS by the respective Local DSUs. | [6 empty] | MODEL 1 - INSOURCED | Inflammation & Immunology
QE-233305 | B7981119 | (Empty) | QE-233305 |  | PFIZER | N | Minor | Closed | ISPR not done before activationB7981119 Site 1060Not done due to ISRP system not working | 2026-03-10 | 2026-03-12 | 2026-03-13 20:47 | GCP_Minor_Mar-2026_B7981119: Site Activation Documentation_Pfizer_USA |  | NO |  |  | No | Minor/Unrated Quality Event |  | 2026-03-13 |  | Quality Oversight | Lack of quality assurance program (e.g., independent quality assurance function, missing Quality Plan) |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Kristi Wright |  | opened a help ticketB7981119 Site 1060 |  |  | N/A | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Inflammation & Immunology