## Standard_Quality_Dashboard - QE
Observation ID | Study ID | Targeted | PR ID | Site(s) | principal Investigator | EX Comp? | QE Threshold | Status | Observation Description (as submitted) | Awareness Date | Submission Date | Assessment Date | Title/Short Description | Business CAPA Plan Endorsed On | CAPA Plan in Place | Last Action Due Date | Investigation Summary and Conclusion | Effectiveness Check Required | Effectiveness Check Rationale | Investigation Completion Date | Closed On | PDAL Decision | Level 1 | Level 2 | Quality CAPA Plan Endorsed On | Quality Reviewer Approved On | Business Process | Submitter | Confirmed Serious Breach | Remediation Actions Taken (when QE was submitted) | CAPA Action Details | CAPA Action Owner | Root Cause Description | Root Cause Level 1 | Root Cause Level 2 | Root Cause Level 3 | Rapid Model | Business Category
2192376 | C1071004 | (Empty) | 2192308 |  |  | N | Major | Closed - Superseded | Product Protocol Number: B8011011 / PPD B9991004 / PPD B9991046/ PAREXEL C1071004 / ICON C3671013 / ICON C4591031/ ICON Involved Party / Country: Pfizer / Global Quality Event Description: Three oncology studies (B8011001, B9991046, C1071004) were developed and implemented using a master protocol, umbrella study design. However, Pfizer systems including those for data reporting, clinical trial registry, and public disclosure, are not designed to support independent reporting of sub-studies under the Master Protocol (MP) and sub-study (SS) structure. Specifically, complex interventional clinical trial study designs (umbrella, basket, platform) are not supported by current SOPs, processes, and systems. B8011011 is a Phase 1B/2 Open Label Umbrella Study of Sasanlimab Combined with Anti-Cancer Therapies Targeting Multiple Molecular Mechanisms in Participants with Non-Small Cell Lung Cancer (NSCLC). Compound: Sasanlimab (PF-06801591). Protocol Amendment #3_28-April-2021 B9991046 is the Avelumab Master Protocol: An open-label continuation study for participants continuing from Pfizer Sponsored Avelumab clinical studies. Compound: Avelumab (PF-06834635 MSB0010718C) Protocol _28-April-2021; CT B999bk B9991046 Avelumab Master Study C1071004 (alias MagnetisMM-4 - Substudy A + Substudy B) is a phase 1B/2, open label umbrella study of elranatamab (PF-06863135), a B-Cell maturation antigen (BCMA) CD3 bispecific antibody, in combination with other anti-cancer treatments in participants with multiple myeloma. Substudy A + SubStudy B_Protocol Amendment #2_17-Jun-2021; CT C107h C1071004 Ph2 Ph1-2 POC MagnetisMM-4 Combination Umbrella MM Study On 24-Aug-2021, 3 additional clinical trials were added to the investigation. B9991004 is a phase 1B/2 open-label study to evaluate safety, clinical activity, pharmacokinetics and pharmacodynamics of avelumab (MSB0010718C) in combination with other cancer immunotherapies in patients with advance malignancies. Protocol Amendment #8; CT B999u B9991004 C3671013 is a phase 3 study to evaluate the efficacy, immunogenicity, and safety of respiratory syncytial virus (RSV) prefusion F subunit vaccine in adults. Protocol_07-Jul-2021 (FSFV 01-Sep-2021); CT C367a C3671013 Phase 3 RSV Adult. C4591031 is a phase 3 master protocol to evaluate additional dose(s) of BNT162B2 in healthy individuals previously vaccinated with BNT162B2. Protocol 13-May-2021 (FSFV 01-Jul-2021) CT C459a C4591031 Booster & Efficacy. | 2021-05-27 | 2021-07-27 | 2021-07-28 | GCP_T2_Jul-2021_Mulitiple Protocols: CMCD: Master Protocol Design_Pfizer_Global |  | YES | 2022-12-19 | Root Cause Analysis-A root cause analysis (RCA) was conducted, Brainstorming and Five Whys methodologies were used to determine the underlying causes and identify Corrective and Preventative Actions (CAPA).-4 oncology clinical trials (B8011011, B9991004, B9991046, C1071004) and 2 vaccines Pfizer clinical trials (C3671013, C4591021) are currently ongoing and have implemented the Master Protocol. These 6 Study Teams were notified for awareness and served to support the investigation of details.-Not Required | Yes |  | 2021-08-27 | 2022-12-15 19:30 |  | Quality Procedures | Requirement/process not met |  | 2022-03-24 22:10 | CT02-Protocol Development for Interventional Studies, CT27-Corporate Clinical Trials Registry, CT28-Public Disclosure of Pfizer-Sponsored Studies | Christa Allen | Not Applicable | TBD. This is intended to be raised to the risk hub to progress further | Document CMCD deviations (post WTL) to document agreement and to record completion of (any) process updates to support the WTL go-forward strategy. | Allen, Christa |  |  |  |  | MODEL 1 - INSOURCED | Oncology
2197977 | C1071004 | (Empty) | 2197685 |  |  | N | Minor | Closed | Product Protocol Number: C1071004 (Alias: Umbrella study) Involved Party / Country: Pfizer / United States Awareness Date: 08-Nov-2021 Quality Event Description: On 04-Nov-2021 we unexpectedly received FDA feedback on Protocol Amendment (PA) #4 for new sub-study B protocol which was sent to them on 13-Aug-2021. (FDA had for almost 12 weeks for review). FDA gave us 2 business days to respond and also required tracked-change amendment to illustrate that we are making the changes they are requiring for approval. This timeline does not allow team to draft response and submit to SCiOPs before sending back to FDA per CT02. We have held initiation of the study for almost 3 months which is important for registration study start in the BCMA Lightspeed 2.0 program, thus there is a significant impact on further delays. What Should Have Happened: Per SOP, any changes to protocol should be reviewed by SciOps before submitting to agency. Why Did This Event Happen: Unexpected response and short timeline provided from FDA. Immediate Actions Taken: CD&O Governance representative and the Governance administrators were informed immediately by CSTL after the Rapid Response Team met on Thursday, 04-Nov-2021. CT02 BPOs and the CQL were also informed. The Regulatory Lead suggested submitting a draft, tracked-change amendment to FDA while responses were being negotiated. An exception was submitted via UIMS ticket on 04-Nov-2021 but was rejected due to late notice and timeline. The team was directed to resubmit as QE. In addition, a summary of changes and the FDA response were provided to Governance on 04-Nov-2021 for added background and clarity. All FDA changes were agreed to (these are non-negotiable) with exception of one request that the team is negotiating with the FDA to keep as-is. Once all changes are endorsed by the FDA; the draft protocol will be submitted to SciOps for review/endorsement prior to finalizing. Once final and published, PA#6 will be sent to the FDA accordingly. CMCD Information: Start Date: 04-Nov-2021 End Date: 08-Nov-2021 Reason for Start/End Date: NA CMCD Requirement Not Met: Unable to accommodate full SciOps review prior to sending draft amendment to FDA on Monday, 08-Nov-2021. Instead of CMCD Requirement: Final changes will be submitted to SciOps as soon as there is alignment with FDA on and before finalization as agreed. Historical Review: Protocol Search: There is 1 previous similar Quality Event identified for this Protocol upon review of quality database. PR 2197394_GCP_Nov-2021_C1071004: CMCD Exception Intended: Protocol Amendment_Pfizer (Cancelled due to CMCD Exception intended) Assessment Comments: This quality event represents CMCD non-conformance. The CMCD that is referenced by the event reporter is: CT02-GSOP 12.0 Protocol Development for Interventional Studies 03-May-2021 The submission indicates that in response to an FDA request for quick turnaround on changes for protocol amendment, the study team was unable to accommodate the CT02 required full SciOps review prior to sending draft amendment to FDA on Monday, 08-Nov-2021. It is noted that actions were taken to address this including informing Governance administrators, CT02 BPO, and CQL of the situation; Regulatory Lead suggested submitting a draft, tracked-change amendment to FDA while responses were being negotiated; summary of changes and the FDA response were provided to Governance on 04-Nov-2021 for added background and clarity, which should decrease risk from not having the full SciOps review at this time. Further, final changes will be submitted to SciOps as soon as there is alignment with FDA before finalization as agreed. With these actions taken and plan for submitting final changes to SciOps as soon as there is alignment with FDA before finalization, there is no indication in the submission of significant adverse impact due to this event. The event appears to be appropriate for the study team to continue to manage. As such, the event does not appear to materially or have a substantial likelihood to impact participant safety, rights, confidentiality, and well-being; data integrity and/or scientific rigor; compliance with regulatory requirements; license obligations; or trust in the clinical research enterprise per QMS01 criteria (Significant Quality Event). This quality event represents a nonconformity to applicable policy, procedure, protocol or Good Practices Quality Guidelines and Regulations (GxP). Therefore, this is a T1 Quality Event, and the study team should continue to manage and document the Quality Event and the actions taken to address the issue. Please discuss as necessary with study Clinician, Clinical Scientist and/or CPM/CSTL, and if they consider this event to have potential or material (significant) adverse impact to any of the criteria noted above due to this event, or if the issue persists post-remediation, please resubmit providing detail on the impact. | 2021-11-08 | 2021-11-08 | 2021-11-10 | GCP_T1_Nov-2021_C1071004: CMCD: Protocol Amendment; SciOps Review_Pfizer_USA |  | NO |  | --- |  |  |  | 2021-11-10 19:36 |  | Quality Procedures | Requirement/process not met |  |  | CT02-Protocol Development for Interventional Studies | Cynthia Green |  | Heather Riley and the Governance administrators were informed immediately by CSTL after the Rapid Response Team met on Thursday, Nov. 4th. CT02 BPOs and the CQL were also informed. The Regulatory Lead suggested submitting a draft, tracked-change amendment to FDA while responses were being negotiated. An exception was submitted via UIMS ticket on Nov. 4th but was rejected due to late notice and timeline. The team was directed to resubmit as QE. In addition, A summary of changes and the FDA response were provided to Governance on Nov. 5th for added background and clarity. All FDA changes were agreed to (these are non-negotiable) with exception of one request that the team is negotiating with the FDA to keep as-is. Once all changes are endorsed by the FDA; the draft protocol will be submitted to SciOps for review/endorsement prior to finalizing. Once final and published, PA#6 will be sent to the FDA accordingly. | [6 empty] | MODEL 1 - INSOURCED | Oncology
2208756 | C1071004 | (Empty) | 2208746 |  |  | N | Minor | Closed | Product Protocol Number: C1071004 (Alias: Umbrella Study) Involved Party / Country: Vendor: Pfizer / Global Awareness Date: 31-May-2022 Quality Event Description: Incorrect deployment package 'C1071004_PPC_17May' was deployed from Central Designer Prod to InForm Prod C1071004 trial. What Should Have Happened: Deployment package 'C1071004_25May2022' should have been deployed from Central Designer Prod to InForm Prod C1071004 trial. Why Did This Event Happen: Database Builder selected the incorrect deployment package. Immediate Actions Taken: Oracle rolled back the study and the correct deployment package was deployed. Historical Review: Protocol Search: There were no previous Quality Events identified for this Protocol upon review of quality database. Assessment Comments: This appears to be a first occurrence, isolated event for this protocol. The submission indicates that the incorrect deployment package was deployed to InForm production due to the Pfizer Database Builder’s error. It is noted that the correct package was later deployed. There is no indication in the submission of significant adverse impact to study participants or study data, due to this event. The event appears to be appropriate for the study team to continue to manage. As such, the event does not appear to materially or have a substantial likelihood to impact participant safety, rights, confidentiality, and well-being; data integrity and/or scientific rigor; compliance with regulatory requirements; license obligations; or trust in the clinical research enterprise per QMS01 criteria (Significant Quality Event). This quality event represents a nonconformity to applicable policy, procedure, protocol or Good Practices Quality Guidelines and Regulations (GxP). Therefore, this is a T1 Quality Event, rather than T2, and the monitor/study team should continue to manage and document the Quality Event and the actions taken to address the issue Please discuss as necessary with study Clinician, Clinical Scientist and/or CPM/CSTL, and if they consider this event to have potential or material (significant) adverse impact to any of the criteria noted above due to this event, or if the issue persists post-remediation, please resubmit providing detail on the impact. | 2022-05-31 | 2022-06-01 | 2022-06-01 | GCP_T1_Jun-2022_C1071004: Database Post Production Change (PPC)_Pfizer_Global |  | NO |  | --- |  |  |  | 2022-06-01 19:11 |  | Data Collection and Management | Data management error |  |  | DMB07-Study Data Set Design and Setup | Kelly Vandale |  | Oracle rollback the study and the correct deployment package was deployed. | [6 empty] | MODEL 1 - INSOURCED | Oncology
2214565 | C1071004 | N | 2214524 | 1011 | Landgren, Carl Ola | N | Major | Closed | Product Protocol Number: C1071004 (Alias: Umbrella Study) Involved Party / Country: PI: Landgren, Carl Ola (Site Number: 1011) / United States Awareness Date: 23-Sep-2022 A Phase 1B/2, open label Umbrella Study of Elranatamab (PF-06863135), a B-cell Maturation Antigen (BCMA) CD3 (Cluster of Differentiation 3) bispecific antibody, in combination with other anti-cancer treatments in participants with multiple myeloma. This Quality Event (QE) was initiated due to a late SAE (Serious Adverse Event) reported by site 1011 on C1071004.The late SAE for prolongation of hospitalization was reported by the site on Mon 29-Aug-2022, with an awareness date of Saturday, 27-Aug-2022. On Monday, 29-Aug-2022, the Study Coordinator (SC) who reported the SAE realized the participant was not discharged on Friday, 26-Aug-2022 until they returned to the site on Monday, 29-Aug-2022. The SAE should have been reported within 24 hours of the Sub-Investigators awareness that the reporting requirements were met for prolongation of hospitalization. The participant experienced GI issue for which the Sub-Investigator requested a GI consult on Friday 26-Aug-2022. The treating physician later confirmed on (23-Sep-2022) that the participant was otherwise well but remained in the hospital pending review of the GI workup. The participant remained in hospital over the weekend for GI workup and the Day 8 dosing which would occur on Monday, 29-Aug-2022. The GI event was not considered related to the study drug. The Sub-Investigator was aware the participant remained in the hospital through the weekend; however, did not report the potential SAE to the Primary Investigator and SC until Monday, 29-Aug-2022 when the SAE was formally reported. The late SAE report was the third instance for late SAE reporting and the second intervention for late SAE reporting (clinician letter sent to Site 1011 on 08-Jul-2022) at site 1011. The late SAE reporting was limited to only this site of C1071004. | 2022-09-23 | 2022-09-23 | 2022-09-26 | GCP_T2_Sep-2022_C1071004: CMCD: SAE Reporting_Landgren, Carl Ola_USA |  | YES | 2023-01-09 | Root Cause Analysis-A Root Cause Analysis was conducted. Brainstorming and 5-Whys analysis were used to determine the underlying causes of the issues and identify Corrective and Preventive Actions (CAPAs).-The PI (Primary Investigator) was associated with three Ongoing and two Proposed studies in the corporate clinical trials registry. An awareness email was sent to the respective study team members on 26-Sep-2022 informing them of the issue, requesting them to consider the impact to their study and if appropriate take and document action for their study.-Not Required | No | Late SAE Reporting | 2022-10-18 | 2023-01-05 21:28 |  | AE reporting to Sponsor | Delayed SAE reporting |  | 2022-10-21 19:37 | AEM01-Adverse Event Monitoring | Komal Changela | Not Applicable | CRA has trained the site on SAE reporting and study clinician sent a Late SAE Letter to the PI per SOP. Site is aware to report any potential SAE immediately even if it is unclear whether it meets the SAE criteria for reporting. | Conduct refresher training with the site on the use of the alternate SAE submission process, the need to report first in all situations and the need to report within 24 hours. | Gonzalez, Marisol |  |  |  |  | MODEL 1 - INSOURCED | Oncology
2216807 | C1071004 | (Empty) | 2216756 |  |  | N | Minor | Closed | Product Protocol Number: ELRANATAMAB (C107) Involved Party / Country: Pfizer / Global Awareness Date: 02-Nov-2022 Quality Event Description: As a follow-up action to a previously raised QE (T1 PR 2216074) with regards to a PI and sub-I for a selected site on several studies on the BCMA (C107) program not meeting one of the requirements listed on the Protocol-Specific-Requirement form (PSR), further investigation to check other sites compared to the completed PSRs revealed that several investigators may not have met the required board certification (in the US) as listed in the PSRs. Several sites/PIs were selected based on PSRs indicating all requirements were met, to include board-certification in Hematology or Oncology while it was not the case (either no current board-certification was found or no certification at all could be confirmed). The rest of the requirements regarding experience in Multiple Myeloma and Clinical research were met as noted in completed PSR forms and CVs. In addition, similar requirements were noted to be needed for Sub-Investigators, but complete list of sub-Investigators may not have been known at time of site selection and focus was on sub-Is that were known to support PIs. Clarification from the Medical line has confirmed that this requirement (board-certification) should not have applied to sub-Investigators. What Should Have Happened: Confirmation of board-certification should have been done at time of site activation. Why Did This Event Happen: Unknown at this time. Of note, some PIs may have had a board-certification in the past but did not maintain it and did not have a current one. Immediate Actions Taken: Immediate actions: clarification with clinical line that board-certification was indeed intended for US PIs and review of equivalent qualifications was conducted for ex-US PIs. Additional clarification was obtained that requirements for sub-Investigators to be board-certified should not have been included. Follow-up actions: For studies with site selection complete at this time: review of all the sites and documentation of site selection to confirm requirements were met List of US PIs with no or no current board certifications compiled (attached to submission) - verification ongoing to see if some may have had current certification at time of initial site selection. For studies with ongoing site selection: revision of study-level PSR to account for updated criteria. For Studies with sites pending site activation (site is selected but PI may not meet board-certification requirement): consultation with BPO to verify best course of action in documenting approval of PIs who are otherwise qualified based on specialization and experience. CMCD Information: Start Date: 01-Feb-2021 End Date: 03-Nov-2022 Reason for Start/End Date: NA CMCD Requirement Not Met: PSR forms documented board-certification that may not have been present/confirmed for PIs. Instead of CMCD Requirement: Revision of PSR for studies with ongoing site selection; evaluation of PI's qualifications to confirm they met all other requirements outside of board certification. Historical Review: Program and Keyword Search: There were 4 Quality events identified upon review of the quality data base PR 2216074_GCP_T1_Oct-2022_C1071003; C1071007; C1071017: Protocol-Specific Site Requirements (PSR)_Syneos Health_USA (Niesvizky and Monge) PR 2216030_GCP_T1_Oct-2022_C1071017: CMCD: Project Specific Site Requirement (PSSR)_Pfizer; ICON_USA (Niesvizky and Monge) PR 2202429_GCP_T1_Feb-2022_C1071009: CMCD: Protocol-Specific Site Requirements_Pfizer_USA, GBR (sites selected with PSR requirement checked: NO) PR 2192025_GCP_T1_Jul-2021_C1071005: CMCD: Protocol-Specific Site Requirements_Pfizer_Global (28 sites selected with NAP boxes checked in PSR) Assessment Comments: This quality event represents CMCD non-conformance. The CMCD that is referenced by the event reporter is: INV02-GSOP 5.0 Investigational Site Selection, Preparation, and Initiation 01-Jun-2022. The submission indicates that due to a follow up from a previous quality event, further investigation was conducted across the C107 program. It is currently unknown why it was indicated all requirements were met for site/PIs selected, including the requirement for board-certification in Hematology or Oncology while it was not the case (either no current board-certification was found or no certification at all could be confirmed). Similar requirements were also noted for the SI; however, it was later confirmed by the medical line that board certification for SI should not have been required. It is noted that clarification from the clinical line was obtained in regards to board certification requirements for US and exUS PIs and SIs. For sites / studies where site selection is complete a review of all the sites documentation of site selection to confirm if requirements were met. For studies in ongoing site selection a revision of study level PSR to account for the updated criteria. For sites with pending site activation, a consultation with the BPO to verify the best course of action in documenting approval of PIs based on specialization and experience. There is no indication in the submission of significant adverse impact to study participants or study data, due to this event. The event appears to be appropriate for the monitor/study team to continue to manage. As such, the event does not appear to materially or have a substantial likelihood to impact participant safety, rights, confidentiality, and well-being; data integrity and/or scientific rigor; compliance with regulatory requirements; license obligations; or trust in the clinical research enterprise per QMS01 criteria (Significant Quality Event). This quality event represents a nonconformity to applicable policy, procedure, protocol or Good Practices Quality Guidelines and Regulations (GxP). Therefore, this is a T1 Quality Event, rather than T2, and the monitor/study team should continue to manage and document the Quality Event and the actions taken to address the issue. Please discuss as necessary with study Clinician, Clinical Scientist and/or CPM/CSTL, and if they consider this event to have potential or material (significant) adverse impact to any of the criteria noted above due to this event, or if the issue persists post-remediation, please resubmit providing detail on the impact. | 2022-11-02 | 2022-11-03 | 2022-11-04 | GCP_T1_Nov-2022_ELRANATAMAB (C107): CMCD: PSR and Due Diligence_Pfizer_Global |  | NO |  | --- |  |  |  | 2022-11-04 15:48 |  | Quality Procedures | Requirement/process not met |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Annick Hartman |  | Immediate actions: clarification with clinical line that board-certification was indeed intended for US PIs and review of equivalent qualifications was conducted for ex-US PIs. Additional clarification was obtained that requirements for sub-Investigators to be board-certified should not have been included. Follow-up actions: For studies with site selection complete at this time: review of all the sites and documentation of site selection to confirm requirements were met List of US PIs with no or no current board certifications compiled (attached to submission) - verification ongoing to see if some may have had current certification at time of initial site selection. For studies with ongoing site selection: revision of study-level PSR to account for updated criteria For Studies with sites pending site activation (site is selected but PI may not meet board-certification requirement): consultation with BPO to verify best course of action in documenting approval of PIs who are otherwise qualified based on specialization and experience. | [6 empty] | MODEL 1 - INSOURCED | Oncology
2222689 | C1071004 | (Empty) | 2222652 |  |  | Y | Minor | Closed | Product Protocol Number: C1071004 (Alias: Umbrella Study) C1071005 (Alias: MAGNETISMM-5) C1071006 C1071020 Involved Party / Country: Pfizer / Global Awareness Date: 07-Feb-2023 Quality Event Description: CT05 Section 4.1 (Develop or amend study-level ICD) references “The Study Level ICD or A Study-Level ICD”. It has been identified that multiple studies in the program have used more than one study-level ICD for various reasons (e.g., different study phases, different cohorts, different treatments or visit schedules, master protocols with sub-studies, stage of study). What Should Have Happened: There was the risk that updates (e.g., for future protocol amendments, Required Safety Text [RST] updates) would have not been made to all the ICDs and/or that study participants would had signed the wrong ICD. Why Did This Event Happen: In the SOP there is no language that explicitly do not permits multiple study-level ICDs. Immediate Actions Taken: Not applicable. CMCD Information: Start Date: 15-Dec-2020 End Date: 27-Feb-2024 Reason for Start/End Date: NA CMCD Requirement Not Met: CT05 Section 4.1 (Develop or amend study-level ICD) Instead of CMCD Requirement: The studies are using multiple study-level ICDs, although there is no language in the SOP that explicitly permits multiple study-level ICDs. Historical Review: Protocol Search (C1071005): There is 1 Consent related Quality Event identified for this Protocol upon review of quality database. PR 2216267_GCP_T1_Oct-2022_C1071005: Informed Consent Document_Pfizer_CZE Protocol Search (C1071004, C1071006, C1071020): There are no previous similar Quality Events identified for this Protocol upon review of quality database. Assessment Comments: This quality event represents CMCD non-conformance. The CMCD that is referenced by the event reporter is: CT05-GSOP 8.0 Informed Consent Document 06-Dec-2021. For this CMCD QE, the past component occurred during the dates of 15-Dec-2020 to date of QE submission (28-Feb-2023), whereby start date represents is the first ICDs that were approved using 2 study level ICDs in this program (study C1071004). The submission indicates that because it was perceived that the that the CMCD does not have language that explicitly does not permit multiple study-level ICDs, 4 Studies on the C107 program used multiple study level ICDs for various reasons. It is noted that no remediation actions have been taken as an exception was requested. It is not clear to the assessor how many participants were impacted based on the submission, however there is no indication in the submission of significant adverse impact to study participants or study data, due to this event. The event appears to be appropriate for the monitor/study team to continue to manage. As such, the event does not appear to materially or have a substantial likelihood to impact participant safety, rights, confidentiality, and well-being; data integrity and/or scientific rigor; compliance with regulatory requirements; license obligations; or trust in the clinical research enterprise per QMS01 criteria (Significant Quality Event). This quality event represents a nonconformity to applicable policy, procedure, protocol or Good Practices Quality Guidelines and Regulations (GxP). Therefore, this is a T1 Quality Event, and the monitor/study team should continue to manage and document the Quality Event and the actions taken to address the issue. Please discuss as necessary with study Clinician, Clinical Scientist and/or CPM/CSTL, and if they consider this event to have potential or material (significant) adverse impact to any of the criteria noted above due to this event, or if the issue persists post-remediation, please resubmit providing detail on the impact. | 2023-02-07 | 2023-02-28 | 2023-02-28 | GCP_T1_Feb-2023_C1071004; C1071005; C1071006; C1071020: CMCD: Study Level Consent_Pfizer_Global |  | NO |  | --- |  |  |  | 2023-02-28 17:58 |  | Quality Procedures | Requirement/process not met |  |  | CT05-Informed Consent Document | Elisa Dall'O' |  | Not applicable | [6 empty] | MODEL 1 - INSOURCED | Oncology
2225045 | C1071004 | (Empty) | 2225040 |  |  | N | Minor | Closed | Product Protocol Number: C1071004 (Alias: Umbrella Study) Involved Party / Country: Vendor: ICON / United States; Canada Awareness Date: 13-Apr-2023 Quality Event Description: All investigators listed on the 1572 must be trained on Pfizer's process for reporting SAEs. Lead Pfizer Study Manager requested CRO to complete training reconciliation from Firecrest portal. CRO notified Pfizer that sites 1007 and 1022 had incomplete training records for SAE Reporting Responsibilities for multiple sub-investigators. Both site PIs had completed the training. On 13-Apr-2023, back-up Study Manager met with site SRPs, CRO CTM, CRO PM, and CRO CRA to discuss reasoning behind lack of training records and to understand site process for training record keeping. It was discovered that site SOPs dictate the sites will not complete training records for sponsor specific training despite sponsor/CRO requests. What Should Have Happened: Both sites should not have been activated until all sub-investigators completed the SAE Responsibilities training. If sites' SOPs do not allow for the site to complete this training, then documentation of this decision should have been approved and filed in TMF by sponsor. Sponsor needs to confirm sites SAE Reporting capabilities are up to safety and sponsor's standards. Why Did This Event Happen: Lack of reconciliation and oversight for sites' training processes and understanding of sites' SOPs and documentation of decision regarding activating sites without SAE training records. Immediate Actions Taken: Review of site SOPs and information gathering from Pfizer and CRO. Requested site to complete training and provide record of training completion. Neither of these two sites have screened or randomized any patients. Historical Review: Vendor Search: There are no previous similar Quality Events identified for this Vendor in this protocol upon review of quality database. Assessment Comments: A Based on eForm entries, there was no system set auto-threshold for this event. The submission indicates that due to a misunderstanding of two sites training processes and SOPs, two sites were activated without investigative staff completing the required SAE Responsibilities training. It is noted that a review of the sites SOPs and information gathering from Pfizer and CRO. Requested the sites to complete training and provide record of training completion. Neither of these two sites have screened or randomized any patients. It is not clear to the Assessor from the submission if either of the two sites plan to enroll participants in the near future. There is no indication in the submission of significant adverse impact to study participants or study data, due to this event. The event appears to be appropriate for the monitor/study team to continue to manage. As such, the event does not appear to materially or have a substantial likelihood to impact participant safety, rights, confidentiality, and well-being; data integrity and/or scientific rigor; compliance with regulatory requirements; license obligations; or trust in the clinical research enterprise per QMS01 criteria (Significant Quality Event). This quality event represents a nonconformity to applicable policy, procedure, protocol or Good Practices Quality Guidelines and Regulations (GxP). Therefore, this is a T1 Quality Event, and the monitor/study team should continue to manage and document the Quality Event and the actions taken to address the issue. Please discuss as necessary with study Clinician, Clinical Scientist and/or CPM/CSTL, and if they consider this event to have potential or material (significant) adverse impact to any of the criteria noted above due to this event, or if the issue persists post-remediation, please resubmit providing detail on the impact. | 2023-04-13 | 2023-04-14 | 2023-04-14 | GCP_T1_Apr-2023_C1071004: Site Activation_ICON_USA |  | NO |  | --- |  |  |  | 2023-04-14 20:14 |  | Quality Procedures, Training & Qualifications | Failure to detect or document issue (quality control), Training not completed or documented in a timely manner |  |  | CT33-Study Training, INV02-Investigational Site Selection, Preparation, and Initiation | Avdyl Gjonbalaj |  | Review of site SOPs and information gathering from Pfizer and CRO. Requested site to complete training and provide record of training completion. | [6 empty] | MODEL 1 - INSOURCED | Oncology
2225706 | C1071004 | (Empty) | 2225671 |  |  | N | Minor | Closed | Product Protocol Number: C1071004 (Alias: Umbrella Study) C1071020 Involved Party / Country: Vendor: ICON / Canada, United States Awareness Date: 01-May-2023 Quality Event Description: All sites should have received the Supplemental Safety Gap Pack when the IIP was sent to the sites and likewise, at the time of IIP approval a second set of Safety Gap Pack is to be sent to the sites, generated in SIRIUS by the CRO/Vendor delegate for CRO managed sites or Site Activation Partner for Pfizer managed sites. CRO PM notified Pfizer Lead Study Manager on 28-Apr-2023 that his team identified that the INVO2 outlined process for distributing the safety reports was not followed accordingly by ICON start-up team and not reviewed or confirmed during the Site Initiation Visit by monitor for C1071004 study. For study C1071020 sites did not receive the safety gap pack when IIP was sent but an updated IB was distributed with the new IIP documents appropriately. On 01-May-2023, Lead Study Manager discussed with Pfizer team including Safety Process Lead and Quality Lead and confirmed that ICON safety team is aware of the Pfizer process requirements and the current assigned CRO team staff was not compliant. This is a deviation from the Pfizer process. What Should Have Happened: ICON team should have reviewed the INV02 requirements, and the details outlined in the Investigator Initiation Package Letter and also monitor should have confirmed during the SIV, based on the SIV required activities/completeness of ISF section, that safety letters were provided and received by sites. Why Did This Event Happen: Lack of oversight and understanding of Pfizer’s processes by the assigned team. Immediate Actions Taken: Review of Pfizer's SOPs and requested CRO ICON to complete training and provide record of training completion. CMCD Information: Start Date: 01-May-2023 End Date: 01-May-2023 Reason for Start/End Date: NA CMCD Requirement Not Met: Per INV02-INV04-WI- GL02 Managing Investigational Site documents the Pfizer documents required to be sent to the site are listed in INV02-INV04-WI-GL02-RF01 Investigational Site Documents and Changes at the Site. The following documents are required to be assembled and distributed by the site essential document manager to the site for the investigator initiation package (IIP): Single Reference Safety Document (SRSD) (e.g. Investigators Brochure [IB] and if applicable IB Annual Memo) and; If applicable, any Clinical Trial Safety Update Reports (CTSURs) distributed since the cut-off date of the safety data in the SRSD(s), and; If applicable, any suspected unexpected serious adverse reactions (SUSARs) distributed since the cut-off date of last distributed CTSUR, and; If applicable, any special safety concerns (SSCs) distributed since the cut-off date of the safety data in the SRSD(s). Instead of CMCD Requirement: Currently all sites on C1071004 were activated and the most recent IB was distributed to the sites. All sites have access to SIRIUS and they can access the safety letters in the portal. Currently for C1071020 one site activated and the Safety letters were received per the process - that were distributed by the Pfizer SAP team. The new sites in activation received the most recent IB and the plan is at the IIP approval a Supplemental Safety Gap Pack will be provided, monitor will ensure at SIV all documents were received. Historical Review: Vendor and Protocol Search: There were no previous similar Quality Events identified for the vendor in these Protocols upon review of quality database. Assessment Comments: This quality event represents CMCD non-conformance. The CMCD that is referenced by the event reporter is: INV02-GSOP 5.0 Investigational Site Selection, Preparation, and Initiation 01-Jun-2022. The submission indicates that the safety report distribution process was not followed by the ICON start-up team and C1071004 monitors did not review and confirm safety letter receipt during SIVs. Sites did not receive a Supplemental Safety Gap Pack when the IIP was sent to the sites, nor did they receive a second Safety Gap Pack at the time of IIP approval. It is noted that the CRO has reviewed and been trained on the relevant Pfizer SOP, C1071004 sites were activated and received the most recent IB; and all sites have access to SIRIUS. One C1071020 site is activated and received the safety letters from the SAP team. In addition, new sites in activation have received the current IB and a Supplemental Safety Gap Pack will be provided upon IIP approval. There is no indication in the submission of significant adverse impact to study participants or study data, due to this event. The event appears to be appropriate for the monitor/study team to continue to manage. As such, the event does not appear to materially or have a substantial likelihood to impact participant safety, rights, confidentiality, and well-being; data integrity and/or scientific rigor; compliance with regulatory requirements; license obligations; or trust in the clinical research enterprise per QMS01 criteria (Significant Quality Event). This quality event represents a nonconformity to applicable policy, procedure, protocol or Good Practices Quality Guidelines and Regulations (GxP). Therefore, this is a T1 Quality Event, rather than T2, and the monitor/study team should continue to manage and document the Quality Event and the actions taken to address the issue. Please discuss as necessary with study Clinician, Clinical Scientist and/or CPM/CSTL, and if they consider this event to have potential or material (significant) adverse impact to any of the criteria noted above due to this event, or if the issue persists post-remediation, please resubmit providing detail on the impact. | 2023-05-01 | 2023-05-01 | 2023-05-02 | GCP_T1_May-2023_C1071004, C1071020: CMCD: Safety Gap Pack Distribution_ICON_CAN; USA |  | NO |  | --- |  |  |  | 2023-05-02 18:43 |  | Quality Procedures | Requirement/process not met |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Ramona Barac |  | Review of Pfizer's SOPs and requested CRO ICON to complete training and provide record of training completion. | [6 empty] | MODEL 1 - INSOURCED | Oncology
2226333 | C1071004 | (Empty) | 2226319 |  |  | N | Major | Closed | Product Protocol Number: B3461087; B7981031; B7981040; C1071004; C1071005; C1071006; C1071007; C1071009; C1071020; C3441052; C4151002; C4161001; C4221022; C4391001; C5341021, C5341026; AREN1721 (WI237422-14) Involved Party / Country: Vendor: ICON Laboratory Services / Global Quality Event Description: Between Sep 2021 and Apr 2023 during supply shortages stemming from the COVID pandemic, the ICON Central Lab (ICL) provided study sites with replacement blood collection vacutainer tubes manufactured by Jiangsu Kangjie Medical Devices Co Ltd (JKMD) and Jiangsu Maik Medical Apparatus Co Ltd (JMMA) in convenience kits. These tubes were incorrectly registered with the Food & Drug Administration (FDA) as Class 1 Medical Devices instead of the required Class 2 designation and did not undergo sterilization after production, thereby deviating from Clinical & Laboratory Standards Institute guidelines. | 2023-05-15 | 2023-05-16 | 2023-05-16 | GCP_T2_May-2023_Multiple Protocols: Blood Collection Tube Registration_ICON Laboratory Services_Global |  | YES | 2024-03-30 | Root Cause Analysis-Root Cause Analysis investigation using Brainstorming and Five Whys methodologies identified the underlying Root Causes and Corrective and Preventative Actions (CAPAs):-• On 16-May-2023, the Pfizer Central Labs & ECG Oversight (CLEO) group sent an awareness notification to the Study Managers (SMs) of all 17 potentially impacted Pfizer study teams. • On 10-May-2023, the ICL Medical Director completed an extensive study participant safety evaluation using the International Organization for Standardization (ISO) 14971: 2019 risk acceptability matrix. Overall, the ICL processed more than 70,000 study participant visits using 190000 non-sterile blood collection tubes. No Adverse Events were identified and overall study participant infection risk was deemed very low when compared to sterilized blood collection tube usage. • In their 09-May-2023 memo, the ICL verified that no potential impact resulted from blood collection vacutainer tubes released into the European Union because they were correctly classified and Conformite Europeenne (CE) marked as Class A in vitro diagnostic medical devices. • In Jun 2021, the FDA announced a Sodium Citrate blue-top blood collection tube shortage that was extended in Jan 2022 to include all blood collection tubes. The sudden shortage required procurement of alternate blood collection vacutainer tubes via a third-party ICL kit assembly partner, BioTouch, through distributors JKMD and JMMA.-Not required | Yes |  | 2023-06-14 | 2024-03-22 16:38 |  | Compliance Requirements - Country Specific Requirements, Equipment, Facility and Sample/Specimens | Failure to follow country-specific requirements, Inadequate equipment/lab supply mgmt. |  | 2023-06-23 21:09 | No Process Assigned | Karen Barrett | Not Applicable | ICON Central Lab stopped sourcing those tubes and conducted a thorough safety evaluation and conducted a risk assessment with regard to patient safety, lab data integrity and regulatory compliance. | GBT will submit a FDA application to obtain the correct Class II Medical Device certification for the blood collection vacutainer tubes. The ICL Project Managers will contact all identified study teams, providing the estimated 6 to 12 months timeline for the tube reclassification approval and agree an action plan for handling of kits already at Investigator sites that contain JKMD and JMMA blood collection tubes. Study teams will be resupplied with approved tubes if requested. | Carreras, Isabel |  |  |  |  | MODEL 1 - INSOURCED | Oncology
2226703 | C1071004 | N | 2226642 | 1011 | Landgren, C. Ola Ola | N | Minor | Closed | Product Protocol Number: C1071004 (Alias: Umbrella Study) Involved Party / Country: Vendor: Marken / United States Vendor: Onco360 / United States Awareness Date: 28-Apr-2023 Quality Event Description: A shipment of Non-Investigational Medicinal Product (Redacted) was shipped from Onco360 direct to a participant from site 1011 in the C1071004 study utilizing a non-functioning temp tale. The shipment left the Onco360 facility on 03-Apr-2023, arriving to the participant on 05-Apr-2023. The shipment included a temperature monitor that had previously been used and was therefore unable to capture temperature data. The temp tale was provided by Marken to Onco360 for use. It was determined by Marken on 28-Apr-2023 that there was no temp data to retrieve. The participant had already completed treatment of the medication received in said shipment as of 28-Apr-2023. This issue was discussed at an operational call and the SCL and SM were made aware of the situation. What Should Have Happened: The shipment should have originated with a conditioned credo cube and a functioning temp tale set to record temperatures. When the credo cube is received by Onco360 they confirm it had a temp tale and then packed the Non-Investigational Medicinal Product (Redacted) in the cube and arranged for the Marken pick-up. When the delivery driver arrives at the participant's residence, they should confirm there is no alarm on the temp tale prior to delivering it to the participant. Why Did This Event Happen: Delayed credo cube shipment and temp tale from Philadelphia’s distribution center to Onco360 and the Marken pickup driver provided a non-conditioned cube and previously used temp tale to Onco360. Onco360 did not identify the non-functioning temp tale and Marken delivery driver did not identify the marking on the temp tale indicating it was previously used and that it was not recording properly. Marken DtP team delayed in acknowledging there was no temp data to provide to Onco360 and Pfizer. Immediate Actions Taken: Marken opened a CAPA to investigate the event and provided it to Onco360 for review. Pfizer met with Marken DtP colleagues to identify the corrective actions. Historical Review: Vendor / Protocol Search (Marken): There are no previous similar Quality Events identified for this Vendor in this protocol upon review of quality database. Vendor / Protocol Search (Onco360): There are no previous similar Quality Events identified for this Vendor in this protocol upon review of quality database. Assessment Comments: The submission indicates that a shipment of Non-Investigational Medicinal Product (Redacted) was shipped from Onco360 direct to a participant study utilizing a non-functioning temp tale and the participant had already completed treatment of the medication received as of 28-Apr-2023. There was approximately 45hours elapsed from collection to delivery and dosing. It is noted that Marken opened a CAPA to investigate the event and provided it to Onco360 for review. Pfizer met with Marken DtP colleagues to identify the corrective actions. It is not clear from the submission if the excursion was submitted to GCS and if GCS determined if it was acceptable for use. The submission indicates there was no significant adverse impact to participant safety, nor other medical concerns. The event appears to be appropriate for the monitor/study team to continue to manage. As such, the event does not appear to pose a potential or material (significant) impact to participant safety, rights, confidentiality, and well-being; data integrity and/or scientific rigor; compliance with regulatory requirements; license obligations; or trust in the clinical research enterprise per QMS01 criteria (Significant Quality Event). Therefore, this is a T1 Quality Event, rather than T2, and the monitor/study team should continue to manage and document the Quality Event and the actions taken to address the issue. Please discuss as necessary with study Clinician, Clinical Scientist and/or CPM/CSTL, and if they consider this event to have potential or material (significant) adverse impact to participant safety or to any of the criteria noted above due to this event, or if the issue persists post-remediation, please resubmit providing detail on the impact. There was no reported significant adverse effect to participant safety due to the potential IP temperature excursion, and no indication on whether IP was reported as “Acceptable-for-Use”, or not by Medicinal Sciences GCS or is pending. • Please re-submit if the following situation is identified: IP has had temperature excursion, and IP was dispensed to participant(s) who took the IP, and the IP was confirmed to be ‘Unacceptable-for-Use’ by Medicinal Sciences GCS. • Please do not re-submit if Medicinal Sciences GCS determines the IP was “Acceptable-for-use”. Note: It is noted that the eForm submitted contained box checked 'yes' to the question indicating that "PD could result in SAE/EDP", which is intended for events where a Protocol Deviation Alert Letter (PDAL) may be required (Protocol Deviation that may affect the safe use of study drug that results in or could result in an SAE [Serious Adverse Event] or EDP [Exposure During Pregnancy]). CT40-GSOP-Management of Protocol Deviations: PDAL Criteria: Criterion 1: The PD affected the safe use of study drug in a manner that directly resulted in a Serious Adverse Event (SAE) or Exposure During Pregnancy (EDP). Criterion 2: The PD is likely to recur, and if so, could affect the safe use of study drug in a manner that would be likely to result in an SAE or EDP, as initially assessed by the Clinician. It appears that this box may have been checked in error as no SAE or EDP has occurred based on submitted information, and it is not known to the Assessor whether SAE/EDP could be a likely result if this event were to reoccur. Please discuss with study Clinician, Clinical Scientist and/or CPM/Clinical Study Team Lead (CSTL); if the study team feels that potential PDAL may be needed for this study due to this event or that SAE/EDP may be a likely result if it were to reoccur, please resubmit including detail and clarifying the likely impact in the submitted text. Otherwise, it is not necessary to respond with clarification. | 2023-04-28 | 2023-05-23 | 2023-05-24 | GCP_T1_May-2023_C1071004: Potential Temperature Excursion with Dosing_Marken; Onco360_USA |  | NO |  | --- |  |  |  | 2023-05-24 19:39 |  | Equipment, Facility and Sample/Specimens | Inadequate equipment/lab supply mgmt. |  |  | QMS09-Vendor Engagement | Sonya Yohn |  | Marken opened a CAPA to investigate the event and provided it to Onco360 for review. Pfizer met with Marken DtP colleagues to identify the corrective actions. | [6 empty] | MODEL 1 - INSOURCED | Oncology
2226703 | C1071004 | (Empty) | 2226642 |  |  | N | Minor | Closed | Product Protocol Number: C1071004 (Alias: Umbrella Study) Involved Party / Country: Vendor: Marken / United States Vendor: Onco360 / United States Awareness Date: 28-Apr-2023 Quality Event Description: A shipment of Non-Investigational Medicinal Product (Redacted) was shipped from Onco360 direct to a participant from site 1011 in the C1071004 study utilizing a non-functioning temp tale. The shipment left the Onco360 facility on 03-Apr-2023, arriving to the participant on 05-Apr-2023. The shipment included a temperature monitor that had previously been used and was therefore unable to capture temperature data. The temp tale was provided by Marken to Onco360 for use. It was determined by Marken on 28-Apr-2023 that there was no temp data to retrieve. The participant had already completed treatment of the medication received in said shipment as of 28-Apr-2023. This issue was discussed at an operational call and the SCL and SM were made aware of the situation. What Should Have Happened: The shipment should have originated with a conditioned credo cube and a functioning temp tale set to record temperatures. When the credo cube is received by Onco360 they confirm it had a temp tale and then packed the Non-Investigational Medicinal Product (Redacted) in the cube and arranged for the Marken pick-up. When the delivery driver arrives at the participant's residence, they should confirm there is no alarm on the temp tale prior to delivering it to the participant. Why Did This Event Happen: Delayed credo cube shipment and temp tale from Philadelphia’s distribution center to Onco360 and the Marken pickup driver provided a non-conditioned cube and previously used temp tale to Onco360. Onco360 did not identify the non-functioning temp tale and Marken delivery driver did not identify the marking on the temp tale indicating it was previously used and that it was not recording properly. Marken DtP team delayed in acknowledging there was no temp data to provide to Onco360 and Pfizer. Immediate Actions Taken: Marken opened a CAPA to investigate the event and provided it to Onco360 for review. Pfizer met with Marken DtP colleagues to identify the corrective actions. Historical Review: Vendor / Protocol Search (Marken): There are no previous similar Quality Events identified for this Vendor in this protocol upon review of quality database. Vendor / Protocol Search (Onco360): There are no previous similar Quality Events identified for this Vendor in this protocol upon review of quality database. Assessment Comments: The submission indicates that a shipment of Non-Investigational Medicinal Product (Redacted) was shipped from Onco360 direct to a participant study utilizing a non-functioning temp tale and the participant had already completed treatment of the medication received as of 28-Apr-2023. There was approximately 45hours elapsed from collection to delivery and dosing. It is noted that Marken opened a CAPA to investigate the event and provided it to Onco360 for review. Pfizer met with Marken DtP colleagues to identify the corrective actions. It is not clear from the submission if the excursion was submitted to GCS and if GCS determined if it was acceptable for use. The submission indicates there was no significant adverse impact to participant safety, nor other medical concerns. The event appears to be appropriate for the monitor/study team to continue to manage. As such, the event does not appear to pose a potential or material (significant) impact to participant safety, rights, confidentiality, and well-being; data integrity and/or scientific rigor; compliance with regulatory requirements; license obligations; or trust in the clinical research enterprise per QMS01 criteria (Significant Quality Event). Therefore, this is a T1 Quality Event, rather than T2, and the monitor/study team should continue to manage and document the Quality Event and the actions taken to address the issue. Please discuss as necessary with study Clinician, Clinical Scientist and/or CPM/CSTL, and if they consider this event to have potential or material (significant) adverse impact to participant safety or to any of the criteria noted above due to this event, or if the issue persists post-remediation, please resubmit providing detail on the impact. There was no reported significant adverse effect to participant safety due to the potential IP temperature excursion, and no indication on whether IP was reported as “Acceptable-for-Use”, or not by Medicinal Sciences GCS or is pending. • Please re-submit if the following situation is identified: IP has had temperature excursion, and IP was dispensed to participant(s) who took the IP, and the IP was confirmed to be ‘Unacceptable-for-Use’ by Medicinal Sciences GCS. • Please do not re-submit if Medicinal Sciences GCS determines the IP was “Acceptable-for-use”. Note: It is noted that the eForm submitted contained box checked 'yes' to the question indicating that "PD could result in SAE/EDP", which is intended for events where a Protocol Deviation Alert Letter (PDAL) may be required (Protocol Deviation that may affect the safe use of study drug that results in or could result in an SAE [Serious Adverse Event] or EDP [Exposure During Pregnancy]). CT40-GSOP-Management of Protocol Deviations: PDAL Criteria: Criterion 1: The PD affected the safe use of study drug in a manner that directly resulted in a Serious Adverse Event (SAE) or Exposure During Pregnancy (EDP). Criterion 2: The PD is likely to recur, and if so, could affect the safe use of study drug in a manner that would be likely to result in an SAE or EDP, as initially assessed by the Clinician. It appears that this box may have been checked in error as no SAE or EDP has occurred based on submitted information, and it is not known to the Assessor whether SAE/EDP could be a likely result if this event were to reoccur. Please discuss with study Clinician, Clinical Scientist and/or CPM/Clinical Study Team Lead (CSTL); if the study team feels that potential PDAL may be needed for this study due to this event or that SAE/EDP may be a likely result if it were to reoccur, please resubmit including detail and clarifying the likely impact in the submitted text. Otherwise, it is not necessary to respond with clarification. | 2023-04-28 | 2023-05-23 | 2023-05-24 | GCP_T1_May-2023_C1071004: Potential Temperature Excursion with Dosing_Marken; Onco360_USA |  | NO |  | --- |  |  |  | 2023-05-24 19:39 |  | Equipment, Facility and Sample/Specimens | Inadequate equipment/lab supply mgmt. |  |  | QMS09-Vendor Engagement | Sonya Yohn |  | Marken opened a CAPA to investigate the event and provided it to Onco360 for review. Pfizer met with Marken DtP colleagues to identify the corrective actions. | [6 empty] | MODEL 1 - INSOURCED | Oncology
QE-081356 | C1071004 | N | QE-081356 | 1011 | C. Ola Landgren (C1071004-1011) | N | Minor | Closed | During Monitoring Visit on 15 Nov 2023 CRA reviewed the eSAE form and noted that the patient's last name was entered into the free text field. | 2023-11-15 | 2023-11-15 | 2023-11-15 21:54 | GCP_Minor_Nov-2023_C1071004: Participant Confidentiality_Landgren, Carl Ola_USA |  | NO |  |  | No |  |  | 2023-11-15 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Harald Singer |  | CRA asked Data Coordinator to remove the last name from the eSAE free text field, but the Data Coordinator was unable to edit it. CRA retrained the Data Coordinator on not using any patient identifying information in CRFs and plans to retrain the investigator team during the monitoring exit meeting on 16 Nov 2023. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Oncology
QE-082473 | C1071004 | N | QE-082473 | 1011 | C. Ola Landgren (C1071004-1011) | N | Minor | Closed | During a routine monitoring visit the site data coordinator emailed the CRA a screenshot of a site tracker that included patient names.This is a similar issue to QE-081356 however these events are attributed to 2 different data coordinators. | 2023-11-16 | 2023-11-20 | 2023-11-21 15:01 | GCP_Minor_Nov-2023_C1071004: Participant Confidentiality_Landgren, C. Ola_USA |  | NO |  |  | No |  |  | 2023-11-21 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Sarah Barkin |  | CRA retrained the data coordinator during the monitoring visit and submitted an IT ticket to have the email deleted from ICON servers. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Oncology
QE-084808 | C1071004 | N | QE-084808 | 1001, 1003, 1004, 1006, 1007, 1009, 1010, 1011, 1012, 1014, 1016, 1025 | Andrzej Jakubowiak (C1071004-1006), C. Ola Landgren (C1071004-1011), Carolina Schinke (C1071004-1014), Leyla Shune (C1071004-1007), Michael Tomasson (C1071004-1025), Nizar Bahlis (C1071004-1012), Noopur Raje (C1071004-1001), Robert Vescio (C1071004-1009), Sarah Holstein (C1071004-1016), Sumit Madan (C1071004-1004), Suzanne Trudel (C1071004-1003), Syed Abbas Ali (C1071004-1010) | N | Minor | Closed | Delinquent protocol and SAE reporting trainings for multiple sites across the study. Training was not completed within Firecrest or another acceptable method in line with CT33. Multiple sites also refuse to complete sponsor-specific training or utilize Firecrest per their institutional SOPs. | 2023-11-30 | 2023-12-01 | 2023-12-01 19:54 | GCP_Minor_Dec-2023_C1071004: Study Training Documentation_Multiple Sites_USA, CAN |  | NO |  |  | No |  |  | 2023-12-01 |  | Training & Qualifications | Training not completed or documented in a timely manner |  |  | CT33-Study Training | Sarah Barkin |  | Study team provided sponsor-approved training slides to sites, requesting confirmation of offline review and understanding to satisfy Firecrest modules.Site training SOPs requested for review and confirmation if they align with CT33.Pending trainings captured on issues and actions logs and MV reports. |  |  | NA | Personnel | Lack of or Inadequate Oversight |  | MODEL 1 - INSOURCED | Oncology
QE-084808 | C1071004 | Y | QE-084808 | 1005 | Arleigh McCurdy (C1071004-1005) | N | Minor | Closed | Delinquent protocol and SAE reporting trainings for multiple sites across the study. Training was not completed within Firecrest or another acceptable method in line with CT33. Multiple sites also refuse to complete sponsor-specific training or utilize Firecrest per their institutional SOPs. | 2023-11-30 | 2023-12-01 | 2023-12-01 19:54 | GCP_Minor_Dec-2023_C1071004: Study Training Documentation_Multiple Sites_USA, CAN |  | NO |  |  | No |  |  | 2023-12-01 |  | Training & Qualifications | Training not completed or documented in a timely manner |  |  | CT33-Study Training | Sarah Barkin |  | Study team provided sponsor-approved training slides to sites, requesting confirmation of offline review and understanding to satisfy Firecrest modules.Site training SOPs requested for review and confirmation if they align with CT33.Pending trainings captured on issues and actions logs and MV reports. |  |  | NA | Personnel | Lack of or Inadequate Oversight |  | MODEL 1 - INSOURCED | Oncology
QE-084828 | C1071004 | N | QE-084828 | 1001 | Noopur Raje (C1071004-1001) | N | Minor | Closed | Site and IRB failed to have timely, efficient, and effective review of new ICD information and changes. Approximately 6 months elapsed from the time the site received elranatamab IB v8 and the associated consent revisions (March 2023) and when the IRB approved the documents (August 2023). | 2023-12-01 | 2023-12-01 | 2023-12-01 20:06 | GCP_Minor_Dec-2023_C1071004: IRB Submission and Approval_Noopur, Raje; Pfizer_USA |  | NO |  |  | No |  |  | 2023-12-01 |  | Ethics Oversight, Quality Procedures | Lacks evidence of ethics oversight, Requirement/process not met |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Sarah Barkin |  | Study team completed weekly follow up with site to reuest updates and remind site to check for updates on the IRB submission/review/approval. Unresponsiveness was escalated to sponsor for assistance. |  |  | NA | Human Performance | Inconsistency Error |  | MODEL 1 - INSOURCED | Oncology
QE-084828 | C1071004 | (Empty) | QE-084828 |  | PFIZER | N | Minor | Closed | Site and IRB failed to have timely, efficient, and effective review of new ICD information and changes. Approximately 6 months elapsed from the time the site received elranatamab IB v8 and the associated consent revisions (March 2023) and when the IRB approved the documents (August 2023). | 2023-12-01 | 2023-12-01 | 2023-12-01 20:06 | GCP_Minor_Dec-2023_C1071004: IRB Submission and Approval_Noopur, Raje; Pfizer_USA |  | NO |  |  | No |  |  | 2023-12-01 |  | Ethics Oversight, Quality Procedures | Lacks evidence of ethics oversight, Requirement/process not met |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Sarah Barkin |  | Study team completed weekly follow up with site to reuest updates and remind site to check for updates on the IRB submission/review/approval. Unresponsiveness was escalated to sponsor for assistance. |  |  | NA | Human Performance | Inconsistency Error |  | MODEL 1 - INSOURCED | Oncology
QE-090603 | C1071004 | N | QE-090603 | 1001, 1003, 1011 | C. Ola Landgren (C1071004-1011), Noopur Raje (C1071004-1001), Suzanne Trudel (C1071004-1003) | N | Minor | Closed | In study C1071004, lab samples have been collected although not required. In the C1071004 trial, patients with multiple myeloma are included. Blood for circulating free(cf) DNA are only required for Part2 only and only part 1 (dose escalation part) is currently enrolling participants. The sample is whole blood and collected using the cycle kits (kits include both part 1 and part 2 tubes). The lab manual identifies the samples to be taken for Part2 (expansion only).4 sites from 2 countries sent cfDNA samples to ICON Central Lab (A total of 49 samples were taken for 13 participants across 4 sites as shown on an ICON lab report dated 03 Jan 2024). The samples are in storage at ICON facility and have not been analyzed. This was found through data management reconciliation process and shared during the Data surveillance Meeting on 3-Jan-24 - it had been happening since November 2022 but was not detected before though monthly reconciliations have been conducted. Monitoring visits have been conducted also regularly at these 4 sites and this was also not detected through this process. | 2024-01-03 | 2024-01-04 | 2024-01-04 22:48 | GCP_Minor_Jan-2024_C1071004: Biospecimen Sample Management_Multiple Sites; ICON_CAN, USA |  | NO |  |  | No |  |  | 2024-01-04 |  | Equipment, Facility and Sample/Specimens, Site Management and Monitoring | Failure to detect/document, Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens, INV04-Investigational Site Management and Monitoring | Annick Perrot |  | Study team, including Monitors were alerted; blast email will be sent to sites, retraining the sites and CRA.PDs will be raised for every incorrectly sent sample. Central lab will be instructed to destroy samples. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Oncology
QE-090603 | C1071004 | Y | QE-090603 | 1005 | Arleigh McCurdy (C1071004-1005) | N | Minor | Closed | In study C1071004, lab samples have been collected although not required. In the C1071004 trial, patients with multiple myeloma are included. Blood for circulating free(cf) DNA are only required for Part2 only and only part 1 (dose escalation part) is currently enrolling participants. The sample is whole blood and collected using the cycle kits (kits include both part 1 and part 2 tubes). The lab manual identifies the samples to be taken for Part2 (expansion only).4 sites from 2 countries sent cfDNA samples to ICON Central Lab (A total of 49 samples were taken for 13 participants across 4 sites as shown on an ICON lab report dated 03 Jan 2024). The samples are in storage at ICON facility and have not been analyzed. This was found through data management reconciliation process and shared during the Data surveillance Meeting on 3-Jan-24 - it had been happening since November 2022 but was not detected before though monthly reconciliations have been conducted. Monitoring visits have been conducted also regularly at these 4 sites and this was also not detected through this process. | 2024-01-03 | 2024-01-04 | 2024-01-04 22:48 | GCP_Minor_Jan-2024_C1071004: Biospecimen Sample Management_Multiple Sites; ICON_CAN, USA |  | NO |  |  | No |  |  | 2024-01-04 |  | Equipment, Facility and Sample/Specimens, Site Management and Monitoring | Failure to detect/document, Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens, INV04-Investigational Site Management and Monitoring | Annick Perrot |  | Study team, including Monitors were alerted; blast email will be sent to sites, retraining the sites and CRA.PDs will be raised for every incorrectly sent sample. Central lab will be instructed to destroy samples. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Oncology
QE-090603 | C1071004 | (Empty) | QE-090603 |  | ICON PLC | N | Minor | Closed | In study C1071004, lab samples have been collected although not required. In the C1071004 trial, patients with multiple myeloma are included. Blood for circulating free(cf) DNA are only required for Part2 only and only part 1 (dose escalation part) is currently enrolling participants. The sample is whole blood and collected using the cycle kits (kits include both part 1 and part 2 tubes). The lab manual identifies the samples to be taken for Part2 (expansion only).4 sites from 2 countries sent cfDNA samples to ICON Central Lab (A total of 49 samples were taken for 13 participants across 4 sites as shown on an ICON lab report dated 03 Jan 2024). The samples are in storage at ICON facility and have not been analyzed. This was found through data management reconciliation process and shared during the Data surveillance Meeting on 3-Jan-24 - it had been happening since November 2022 but was not detected before though monthly reconciliations have been conducted. Monitoring visits have been conducted also regularly at these 4 sites and this was also not detected through this process. | 2024-01-03 | 2024-01-04 | 2024-01-04 22:48 | GCP_Minor_Jan-2024_C1071004: Biospecimen Sample Management_Multiple Sites; ICON_CAN, USA |  | NO |  |  | No |  |  | 2024-01-04 |  | Equipment, Facility and Sample/Specimens, Site Management and Monitoring | Failure to detect/document, Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens, INV04-Investigational Site Management and Monitoring | Annick Perrot |  | Study team, including Monitors were alerted; blast email will be sent to sites, retraining the sites and CRA.PDs will be raised for every incorrectly sent sample. Central lab will be instructed to destroy samples. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Oncology
QE-090608 | C1071004 | N | QE-090608 | 1012 | Nizar Bahlis (C1071004-1012) | N | Minor | Closed | In study C1071004, electronic Patient Reported Outcomes(ePRO) questionnaires EORTC QLQ-C30 and MY20 have been collected although not required. In the C1071004 trial, patients with multiple myeloma are included. ePRO questionnaires are only required for Substudy A (SSA)Part2-(expansion only and Substudy B(SSB) - dose escalation Part1 and dose expansion-Part 2. The ePRO questionnaires are collected using a slate , each site was provided with a TrialMax Slate (tablet) to administer the ePRO to patients for SSA or SSB . 3 sites from 2 countries collected the questionaries (multiple questionnaires EORTC QLQ-C30 and MY20 varying from C0 to C9 cycles were administrated to 4 patients from December 2022 to September 2023) - This was identified during data management reconciliation process and shared during the Data Surveillance Meeting on 3-Jan-24. | 2024-01-03 | 2024-01-04 | 2024-01-04 23:14 | GCP_Minor_Jan-2024_C1071004: Data Collection: Outcomes Questionnaires_Multiple Sites; Signant Health; Pfizer_CAN, USA |  | NO |  |  | No |  |  | 2024-01-04 |  | Data Collection and Management, IT Systems | Inadequate IT system (eg. planning, definitions, design, development, testing, validation, support) per regulatory requirements, Inadequate source data/documentation |  |  | CT40-Management of Protocol Deviations, No Process Assigned | Annick Perrot |  | Study team, including Monitors were alerted; blast email will be sent to sites, retraining the sites and CRA. PDs will be raised for every incorrectly sent sample. |  |  | NA | Method/Procedure | Procedure/Form/Plan |  | MODEL 1 - INSOURCED | Oncology
QE-090608 | C1071004 | Y | QE-090608 | 1005, 1026 | Afshin Gabayan (C1071004-1026), Arleigh McCurdy (C1071004-1005) | N | Minor | Closed | In study C1071004, electronic Patient Reported Outcomes(ePRO) questionnaires EORTC QLQ-C30 and MY20 have been collected although not required. In the C1071004 trial, patients with multiple myeloma are included. ePRO questionnaires are only required for Substudy A (SSA)Part2-(expansion only and Substudy B(SSB) - dose escalation Part1 and dose expansion-Part 2. The ePRO questionnaires are collected using a slate , each site was provided with a TrialMax Slate (tablet) to administer the ePRO to patients for SSA or SSB . 3 sites from 2 countries collected the questionaries (multiple questionnaires EORTC QLQ-C30 and MY20 varying from C0 to C9 cycles were administrated to 4 patients from December 2022 to September 2023) - This was identified during data management reconciliation process and shared during the Data Surveillance Meeting on 3-Jan-24. | 2024-01-03 | 2024-01-04 | 2024-01-04 23:14 | GCP_Minor_Jan-2024_C1071004: Data Collection: Outcomes Questionnaires_Multiple Sites; Signant Health; Pfizer_CAN, USA |  | NO |  |  | No |  |  | 2024-01-04 |  | Data Collection and Management, IT Systems | Inadequate IT system (eg. planning, definitions, design, development, testing, validation, support) per regulatory requirements, Inadequate source data/documentation |  |  | CT40-Management of Protocol Deviations, No Process Assigned | Annick Perrot |  | Study team, including Monitors were alerted; blast email will be sent to sites, retraining the sites and CRA. PDs will be raised for every incorrectly sent sample. |  |  | NA | Method/Procedure | Procedure/Form/Plan |  | MODEL 1 - INSOURCED | Oncology
QE-090608 | C1071004 | (Empty) | QE-090608 |  | PFIZER, SIGNANT HEALTH GLOBAL SOLUTIONS LIMITED | N | Minor | Closed | In study C1071004, electronic Patient Reported Outcomes(ePRO) questionnaires EORTC QLQ-C30 and MY20 have been collected although not required. In the C1071004 trial, patients with multiple myeloma are included. ePRO questionnaires are only required for Substudy A (SSA)Part2-(expansion only and Substudy B(SSB) - dose escalation Part1 and dose expansion-Part 2. The ePRO questionnaires are collected using a slate , each site was provided with a TrialMax Slate (tablet) to administer the ePRO to patients for SSA or SSB . 3 sites from 2 countries collected the questionaries (multiple questionnaires EORTC QLQ-C30 and MY20 varying from C0 to C9 cycles were administrated to 4 patients from December 2022 to September 2023) - This was identified during data management reconciliation process and shared during the Data Surveillance Meeting on 3-Jan-24. | 2024-01-03 | 2024-01-04 | 2024-01-04 23:14 | GCP_Minor_Jan-2024_C1071004: Data Collection: Outcomes Questionnaires_Multiple Sites; Signant Health; Pfizer_CAN, USA |  | NO |  |  | No |  |  | 2024-01-04 |  | Data Collection and Management, IT Systems | Inadequate IT system (eg. planning, definitions, design, development, testing, validation, support) per regulatory requirements, Inadequate source data/documentation |  |  | CT40-Management of Protocol Deviations, No Process Assigned | Annick Perrot |  | Study team, including Monitors were alerted; blast email will be sent to sites, retraining the sites and CRA. PDs will be raised for every incorrectly sent sample. |  |  | NA | Method/Procedure | Procedure/Form/Plan |  | MODEL 1 - INSOURCED | Oncology
QE-099310 | C1071004 | (Empty) | QE-099310 |  | PFIZER | N | Minor | Closed | For Study C1071004, while performing “TMF Quality Review for Study FSFV+2Ys” Functional Line Document Owners review by the CDS, it was found that few documents were missing or not completed as per the process requirement. We couldn't backtrack and search for the documents because the Clinical Data Scientist (CDS) responsible for the documentation in the past had moved out from the organization. Investigated all available resources such as CDS portfolio folder, study SharePoint and UIMS tickets, however, the below documents could not be located. Missing documents:87.01: DM QC for PPC 3, 4, 5, 6, L2_Snapshot_JUN2022 are missing693.01: Study definition report for Initial set-up, PPC 1, 2, 3 and 10 are missing331.03: Blank CRF is missing for V5 (ASB V5 dated 25May2022 is present).331.08 &amp; 331.03: ASB and Blank CRF_dated 16Aug2021 and 27Aug2021 are not versioned correctly. System generated document shows that it is version 3, however it was required to increment the version.85.01: EDS/VC production report for Initial set-up, PPC 1, 3, 7, 8, 10 are missing.231.01 &amp; 726.01: L3_snapshot_APR2022 documents are missing.86.02: Data Review Tracking log for SM for L2 snapshot_JUN2022 is missing.612.03: Missing Documents (i) EORTC QLQ CIPN20: Version 1 and 2 are missing. (ii)EORTC QLQC30 and QLQ-MY20: Version 1, 2, 3 are missing. | 2024-02-21 | 2024-02-21 | 2024-02-21 15:20 | GCP_Minor_Feb-2024_C1071004: CMCD: Pfizer Trial Master Files: DMB Documents_Pfizer_USA; CAN |  | NO |  |  | No |  |  | 2024-02-21 |  | Document Management | Document filed late |  |  | CT01-Trial Master Files | Kalpesh Patel |  | The quality of the database release is not impacted because of above missing documents and once QE process completed, the placeholder in PTMF for the respective documents will be satisfied with the QE reference in the Reason Satisfied Notes field. |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Oncology
QE-104261 | C1071004 | (Empty) | QE-104261 |  | ICON PLC, PAREXEL INTERNATIONAL | N | Major | Closed | During Wave 2 transitions to Model 1 from CROs ICON and PXL, Pfizer teams are taking over approx. 40 studies which were previously managed by the CRO. As part of the transition process from outgoing CRO to incoming Pfizer SAP team member it has been discovered that the CROs may not have been aware of Safety Gap Package processes. SIRIUS only sends SUSAR and CTSUR safety info to PIs automatically AFTER IIP approval. Process is to then send what we call the Gap package at the time of IIP approval to provide any safety reports which have been filed between the sending of the initial IB and the site's IIP approval date (the SSU period) to ensure PIs have all safety info prior to seeing their first patient. We believe this was not done and potentially for thousands of sites on these studies over the past 5 years or so. It is difficult to confirm the volume at this time but it not definitely appears to be a widespread non-complaince by both ICON and PXL pCROs. | 2024-03-15 | 2024-03-15 | 2024-03-15 16:57 | GCP_Major_Mar-2024_Enterprise Level: Safety Gap Packs_ICON PL; Parexel International_Global |  | YES |  | <p><span style='font-size: 16px; font-family: "Times New Roman", serif;'><span style="font-family: Calibri, sans-serif;">Involved Party / Country: Enterprise Level</span></span></p><p><span style='font-size: 16px; font-family: "Times New Roman", serif;'><span style="font-family: Calibri, sans-serif;">&nbsp;</span></span></p><p><span style='font-size: 16px; font-family: "Times New Roman", serif;'><span style="font-family: Calibri, sans-serif;">Vendor: &nbsp;ICON PL / Global</span></span></p><p><span style='font-size: 16px; font-family: "Times New Roman", serif;'><span style="font-family: Calibri, sans-serif;">&nbsp;</span></span></p><p><span style='font-size: 16px; font-family: "Times New Roman", serif;'><span style="font-family: Calibri, sans-serif;">Vendor: Parexel International / Global</span></span></p><p><span style='font-size: 16px; font-family: "Times New Roman", serif;'><span style="font-family: Calibri, sans-serif;">&nbsp;</span></span></p><p><span style='font-size: 16px; font-family: "Times New Roman", serif;'><span style="font-family: Calibri, sans-serif;">Description of the Issue(s):</span></span></p><p><span style='font-size: 16px; font-family: "Times New Roman", serif;'><span style="font-family: Calibri, sans-serif;">This quality event was identified during a Model 1 study transition from contract research organizations (CROs) ICON and PAREXEL management to Pfizer study team management. Pfizer study teams are taking over approximately 40 studies which were previously managed by the CRO. &nbsp;As part of the transition process from outgoing CRO to incoming Pfizer site activation partner (SAP) team member it has been discovered that the CROs were not aware or did not adhere to the Safety Gap Package processes for some studies. The safety gap process is to send the gap package at the time of Investigator Initiation Package (IIP) approval to provide any safety reports which have been filed between the sending of the initial investigator brochure (IB) and the site's IIP approval date (the study start-up period) to ensure investigators have all safety info prior to seeing their first patient.&nbsp;</span></span></p><p><span style='font-size: 16px; font-family: "Times New Roman", serif;'><span style="font-family: Calibri, sans-serif;">&nbsp;</span></span></p><p><span style='font-size: 16px; font-family: "Times New Roman", serif;'><span style="font-family: Calibri, sans-serif;">This affects the following 17 studies: B1791094, B1931036, B7841007, B7981040, B7981041, B7981080, C0371002, C0371017, C1071004, C1071020, C1071030, C2321001, C4221016, C4221023, C4601012, C4771001, C4971006. All studies impacted were reviewed and will be sent updated safety information if required. &nbsp;</span></span></p><p><span style="font-size: 11pt;">&nbsp;</span></p><p><br></p> | No | Quality Event only required gap analysis investigation | 2024-06-21 | 2025-03-18 |  | Safety Information Communication | Failure/Incomplete safety communication |  | 2024-08-12 21:11 | INV02-Investigational Site Selection, Preparation, and Initiation | Micaiah Lambright | FALSE | Assessment as best we can with the outgoing CRO teams whether or not they did provide gap packages and whether or not they can provide any evidence to that effect. Preparing to send them immediately following Pfizer takeover after the transition completes. Due date for all transitions and all studies in 12-Apr but many have concluded their transitions already. |  |  | Gap Analysis | Human Performance | Omission Error | Inadequate Information for Determination | MODEL 1 - INSOURCED | Oncology
QE-119628 | C1071004 | (Empty) | QE-119628 |  | ICON PLC | N | Minor | Closed | All sites should have received the IIP Investigator Initiation Package Letter after were selected and SAP should filed the sites notification in a pTMF in a timely manner.On June 05,2024 the pTMF owner Min Ai mentioned the notification pTMF ID #720.02 for 7 US sites 1010, 1004, 1014,1016,1009,1022 1025 are missing in pTMF and asked the global study manager to submit a quality event for the finding per process requirement. The study C1071004 was transition to the insourced model in Apr 2024 form ICON CRO to Pfizer team. During the transition the Site Activation Partner (SAP) Akele Carter noted in her documentation tracker that were missing the IIP notification.ICON CRO clarified that they don’t have the documentation since many of their ICON colleagues no longer at the company and ICON don’t have access to the previous correspondence. After further investigation, ICON and Pfizer reach out to sites if ask to provide a copy, sites didn’t have any emails or correspondence since many sites staff departed the institution.All sites listed above were IIP approved therefore the Site Essential Documents were retrieved and filed in pTMF. | 2024-06-05 | 2024-06-06 | 2024-06-07 16:42 | GCP_Minor_Jun-2024_C1071004: CMCD: Pfizer Trial Master File (PTMF): Essential Documents_ICON_USA |  | NO |  |  | No |  |  | 2024-06-07 |  | Document Management | Document filed late |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Ramona Barac |  | Review of Pfizer's SOPs and requested Pfizer team to complete training. The study complet activation for all sites in Apr 2023, this finding will not occur. The Pfizer SAP have an solid process for submitting site documentation to pTMF. |  |  | NA | Personnel | Lack of or Inadequate Oversight |  | MODEL 1 - INSOURCED | Oncology
QE-120192 | C1071004 | (Empty) | QE-120192 |  | PFIZER | N | Major | Closed | Several site organizations across Pfizer study programs are following their own site standard training processes/SOPs. Site training processes are being assessed for equivalency to CT33-GSOP and marked as "Completed" in Firecrest when the following CT33-GSOP criteria may not be met: The PI must be trained by Pfizer process for protocol amendments after being trained by Pfizer process for initial PST (e.g., IM, SIV, Firecrest, online meeting). The PI will follow its organization's training process after the initial Pfizer PST training.The site is not providing a confirmation that current/approved training materials are reviewed in their entirety. The site-specific training record provides a confirmation that staff have read &amp; understood the study training material. | 2024-06-10 | 2024-06-10 | 2024-06-11 15:11 | GCP_Major_Jun-2024_Enterprise Level; Multiple Studies: CMCD: Trend: Study Training Process_Multiple Sites; Pfizer_Global, CAN |  | YES | 2025-01-21 | <p>Product Protocol Number:</p><p>C1071007</p><p>&nbsp;</p><p>Involved Party / Country:</p><p>Multiple Sites / Canada</p><p><span><br></span></p><p><span>Protocol Title(s):</span></p><p><span>C1071007: a Phase 3, open-label, randomized, 2-arm study of elranatamab monotherapy vs lenalidomide in participants with newly diagnosed multiple myeloma after undergoing ASCT.</span></p><p><span><br></span></p><p><span>Description of the Issue(s):</span></p><p><span>On 9-Jun-2024, a training documentation review was conducted by Site Care Partners for Study C1071007 where it was identified principal Investigator (PI) training documentation appeared to have inconsistencies with the expectations of Standard Operating Procedure (SOP), CT33-GSOP-RF03 Pfizer GCP Training Requirement - Investigators while adhering to the Study Training Plan (STP), Protocol #:C1071007, Version 4.0 (18-Mar-2024), Section 2; Specifically bullets 1 and 3.&nbsp;</span></p><p><span><br></span></p><p><span>Site training processes are being assessed for equivalency to CT33-GSOP-RF03 Pfizer GCP (Good Clinical Practice) Training Requirement - Investigators and marked as "Completed" in Firecrest when the following CT33-GSOP-RF03 Pfizer GCP Training Requirement - Investigators criteria may not be met:</span></p><p><span>&nbsp;</span></p><p><span>-&nbsp; &nbsp;&nbsp;The PI must be trained by Pfizer process for protocol amendments after being trained by Pfizer process for initial PST (e.g., IM, SIV, Firecrest, online meeting). The PI will follow its organization's training process after the initial Pfizer PST training.&nbsp;</span></p><p><span><br></span></p><p><span>-&nbsp; &nbsp;&nbsp;The site does not provide confirmation that current/approved training materials are reviewed in their entirety. The site-specific training record provides confirmation that staff have read &amp; understood the study training material.&nbsp;</span></p><p><span><br></span></p><p><span>There was no impact to training requirements or study data due to the inconsistencies; however, more training than required was being completed by site PI’s and was not reflected in Firecrest.&nbsp;</span></p><p><br></p><p><br></p> | No | CAPA Plan included error proofing that will prevent reoccurrence | 2024-07-31 | 2025-07-30 |  | Quality Procedures | Requirement/process not met |  | 2024-08-01 15:13 | CT33-Study Training | Chantal Leduc | FALSE | Informed study team C1071007 of discrepancy between CT33-GSOP requirement, site 1070 training process and completion record in Firecrest. |  |  | Inconsistency between CT33-GSOP-RF03, Section 2: Pre-Trial Assessment Guidance and the Study Training Plan led to confusion on the site’s need to complete more training than required. &nbsp; | Method/Procedure | Procedure/Form/Plan | Inconsistency Between Documents (Document Standard Lacking/Incorrect Standard Content) | MODEL 1 - INSOURCED | Oncology
QE-131401 | C1071004 | (Empty) | QE-131401 |  | PFIZER | N | Minor | Closed | Digital ads were run at the program level in June on an advocacy group/vendors Meta platform (FB/IG). During an audit of the ads, it was determined that the way the ad files were submitted to the IRB submission was incorrect. Multiple documents were submitted to the IRB and approved as standalone documents (an image library and ad copy) but were ultimately used together to create an ad. Standard process is to submit a complete media board which contains images and ad copy. In this case the media board contained only headline copy and images, the ad body copy was contained in different but accompanying files in the same submission. Since the ads were run above study level to create awareness of all enrolling MagnetisMM studies the following studies are involved in the QE:C1071004, C1071007, C1071020, C1071030, C1071032. | 2024-08-07 | 2024-08-08 | 2024-08-08 14:48 | GCP_Minor_Aug-2024_C107: Digital Advocacy Campaign Submission_Pfizer_United States |  | NO |  |  | No |  |  | 2024-08-08 |  | Ethics Oversight | Lacks evidence of ethics oversight |  |  | INV03-Study Participant Recruitment and Retention Planning | Melinda Boutsikakis |  | Since the finding was after the ad flight concluded at the end of June and the error was found in August we validated that no enrolled subjects came from the June campaign, Next we are moving the ad content from multiple documents to one document to be resubmitted to the IRB with an explanation. The next media campaign with the ads is in September. Additionally, the supervisor of the Patient Recruitment Specialist who incorrectly created the submission was notified and will perform training with the entire PRS team as well as have a discussion with the party involved. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Oncology
QE-138667 | C1071004 | (Empty) | QE-138667 |  | PFIZER | N | Major | Closed | Multiple PRS scores were not uploaded into eQRM per process and multiple AQLs were not notified of a PRS score change. This has resulted in discrepancies between documentation and the study level RBM monitoring approach (SDV and SDR). In some cases, it has taken 6 months or more to identify that there was a discrepancy in the score, which is a considerable delay for the study teams to take the appropriate actions where needed. Discrepancies now exist between the eQRM system, scores provided to the study teams, Risk Steering Committee and the overall risk-based approach for RBM (including SDV and SDR) for the studies and examples below. C5681001 - manual PRS was calculated in January 2024 as low. This score was not uploaded into eQRM. The PRS was calculated in March based off the approved IQMP and uploaded into eQRM as Medium. As this was the first version to be uploaded to eQRM it did not flag as a change and thus it was not communicated to the AQL or the study team as a change. In 2Q 2024, the PRS was updated to high. The AQL/Study Team were notified of the score change, but the team was operating off of the ‘low’ score provided in January. They were unaware that they should have been operating off of a medium score. QE was previously submitted (before it was realized to be a broader issue).C5241007 - score was calculated as high in August 2023. It was subsequently re-calculated as low in January 2024 and July 2024. The AQL and study team were not informed of the change to low and have been operating off of a high risk score. Change on the PRS was discovered by chance by the Study Manager. Same process steps as above, but the score was reversed (high to low in this situation). C4841001 – Similar situation as above, the score as manually calculated to be low. That score was not uploaded into the eQRM system. The study team wanted to implement medium level SDV. The DRP and SMP were not aligned in regards to the % SDV and a QE was submitted (QE-129179). The study team requested the Risk Steering Committee to permit an increase %SDV to medium, which was approved. The first score uploaded into the eQRM system was recorded as medium (not as low, which was manually calculated previously). The AQL/study team was not informed of this difference/change in score. The study team was operating off the low score provided. The request to the Risk Steering Committee to increase SDV to a medium level would not have been needed with this new score. When the team was informed about the Medium PRS, the SDV was already increased following RSC approval. SDR remains as a low approach. Now there is a discrepancy in the RSC documentation request for a change and the approach of SDV (med) /SDR (low).C4591048 – The statistician calculating the PRS informed the AQL in Nov 2022 that the PRS increased to High. This was not uploaded into the eQRM system/not showing in eQRM dashboard history in November 2022. PRS increase to high is first reported in eQRM in April 2024. In Nov 22, the study team discussed the PRS score change and they made a decision log entry not to change their RBM approach in Nov 22. While there is no RBM impact from the April 2024 increase, there was an 18 month delay in having the correct scoring showing within the validated eQRM system. The decision log entry is only based on the email from the statistician and has no audit trail within eQRM for the Nov 22 change. .25in;".25in;"Additionally, on a related note, it is not clear if there were erroneous PRS scores calculated, specifically those calculated in January and March 2024. These scores were found on the eQRM spotfire viewer on the PRS history tab; however, they were not provided to the Asset Quality Leads (AQLs) or the study teams in a timely fashion (i.e., in January or March 2024 at the time of calculation).Aside from the specific study examples cited above, there are at least 6 other instances where PRS changed (off cycle of the quarterly updates) and the changes were not communicated to the AQL. They were discovered on the eQRM spotfire viewer. It is not clear if these changes were errors as the scores reverted back to the previous scores in the next quarterly calculation. Examples of when the score changed to a different ranking (H/M/L) and back again are as follows: .346153846153847%" valign="top".25pt;"Study number.65384615384616%" valign="top".25pt;"Score fluctuation.346153846153847%" valign="top".25pt;"B7841007.65384615384616%" valign="top".25pt;"High (Oct 23) changed to Medium in Jan 24, back to High in Q1 (Apr 24) and Q2 (Jul 24).346153846153847%" valign="top".25pt;"B7841008.65384615384616%" valign="top".25pt;"Medium (Oct 23) changed to Low (Jan 24) back to Medium in Q1 and Q2.346153846153847%" valign="top".25pt;"C1071020.65384615384616%" valign="top".25pt;"High (Oct 23) changed to Low (Mar24) back to High in 1Q, 2Q.346153846153847%" valign="top".25pt;"C1071030.65384615384616%" valign="top".25pt;"Med (Oct23) changed to Low (Jan 24) back to Medium in 1Q, 2Q.346153846153847%" valign="top".25pt;"C1071004.65384615384616%" valign="top".25pt;"High (Oct 23) to Med (Jan 24) back to High in Q1 and Q2.346153846153847%" valign="top".25pt;"C4591054.65384615384616%" valign="top".25pt;"Med (Oct23) to Low (Mar24) to Med in Q1 | 2024-09-11 | 2024-09-17 | 2024-09-18 15:30 | GCP_Major_Sep-2024_Multiple: CMCD: Protocol Risk Score; Source Document Verification / Review_Pfizer_Global |  | YES |  | <p>Product Protocol Number(s): C4591048 , C4841001, C5681001, C5241007, Z0021001, B7841007, B7841008, C1071020, C1071030, C1071004, C4591054</p><p>&nbsp;</p><p>Involved Party / Country: Pfizer/Global&nbsp;</p><p>&nbsp;</p><p>Discrepancies were identified in five (C4591048 , C4841001, C5681001, C5241007, Z0021001)&nbsp;studies; between the Protocol Risk Scores (PRS) in the eQRM system and the scores provided to the study teams, and Risk Steering Committee. These scores contribute to the overall risk-based approach for Risk Based Monitoring (RBM) including source data verification/source data review (SDV and SDR) for multiple studies.</p><p>&nbsp;</p><p>There may have been erroneous PRS scores calculated, specifically those calculated in January and March 2024. These potentially erroneous changes were not communicated to the Asset Quality Leads (AQLs) or the study teams in a timely manner. &nbsp;Additionally, manually calculated PRS scores are not automatically entered in eQRM.</p><p><br></p><p>In six (B7841007, B7841008, C1071020, C1071030, C1071004, C4591054) other studies the PRS changed (off cycle of the quarterly updates) and the changes were not communicated to the AQL. &nbsp;These were discovered on the eQRM spotfire viewer. It is not clear if these changes were errors as the scores reverted to the previous scores in the next quarterly calculation.</p> | No | Other | 2024-12-20 | 2025-06-03 |  | Quality Procedures | Requirement/process not met |  | 2024-12-20 16:12 | QMS06-Risk Management for Clinical Development | Sheri Kuss | FALSE | Asset Quality Leads (AQLs) notified. AQLs are addressing specific examples in 1-4 above. Discussions with the study teams need to occur and decisions will need to be made regarding each team’s RBM monitoring approach, including SDV and SDR, which has a potential impact on the Study Monitoring Plans, the Data Management Plans, SDV reports, resourcing and cost.RQA will be notified as the PRS score is a key driver in their audit approach. Related QEs were reported for C5681001 and C4841001. |  |  | Discrepancies were noted in the PRS reports utilized to inform SDV/SDR and audit strategies. This was due to multiple factors; transition of PRS calculation to a new group, old application used for PRS calculation, no documented process for the creation of the PRS, no documented communication pathway to/from the involved parties and multiple group involvement with silos and lack of overall process ownership’. | Method/Procedure | Procedure/Form/Plan | Inadequate/Inaccurate/Confusing (Document Standard Lacking/Incorrect Standard Content) | MODEL 1 - INSOURCED | Oncology
QE-140973 | C1071004 | N | QE-140973 | 1014 | Carolina Schinke (C1071004-1014), Samer Al Hadidi (C1071020-1014) | N | Minor | Closed | Site signature and delegation of duties log does not contain all elements required by INV02-INV04-GSOP-RF09. Site delegation log does not contain document title, version control, PI initials and dates for each delegation, or start dates specific to the study. The start date listed on the Master Signature Pages in use by the site are not study-specific, and many pre-date the start date of study. This site has been activated on study and using this process since 15Mar2024. | 2024-09-25 | 2024-09-30 | 2024-10-01 17:36 | GCP_Minor_Oct-2024_C1071004, C1071020: CMCD: Signature Sheet and Delegation of Duties Log (SSDDL) _Schinke, Carolina; Al Hadidi, Samer_USA |  | NO |  |  | No |  |  | 2024-10-01 |  | Quality Procedures | Failure to use adequate controls (e.g., Required Forms, templates) |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Brandi Evans |  | Upon identifying issue during routine Site Management Visit, SCP escalated to study team and BPO. |  |  | NA | Method/Procedure | Procedure/Form/Plan |  | MODEL 1 - INSOURCED | Oncology
QE-153021 | C1071004 | (Empty) | QE-153021 |  | PFIZER | N | Minor | Closed | Study C1071004 Site 1003 was inadvertently given wrong dosing assignment on 25Nov2024 by a Pfizer team member.3 minutes later the site was given the correct assignment.The site had already updated Impala with the wrong dosing assignment.Study team was unaware of the phone number change to IGOT and gave a disconnected phone number to the site initially. New number was identified and the site was able to contact IGOT. The issue was resolved by completing a DCF with IGOT within 2 hours. | 2024-11-25 | 2024-12-03 | 2024-12-03 16:32 | GCP_Minor_Dec-2024_C1071004: IP Assignment Error_Pfizer_CAN |  | NO |  |  | No |  |  | 2024-12-03 |  | Medicinal Product | Inadequate preparation, dosing, dispensing error |  |  | IP13-Investigational Medicinal Product | Isaac Caudillo |  | Informed site to speak with IGOT to update dosing assignment. Followed up with site afterwards to confirm DCF has been updated and patient dosed. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Oncology
QE-196243 | C1071004 | (Empty) | QE-196243 |  | PFIZER | N | Critical | Approved - In CAPA | Multiple Centers for multiple protocols to not feed into SIRIUS since 15Aug2025. This is causing SUSARs not to be distributed to Pfizer Investigators. | 2025-08-15 | 2025-08-18 | 2025-08-18 20:57 | GCP_Critical_Aug-2025_Multiple Protocols: SIRIUS Report Distribution / Veeva Clinical_Pfizer_Global UPGRADE |  | YES |  | <p style="margin-left: 0in;"><span style="font-size: small;">On 15 Aug 2025, Pfizer Global Drug Safety Unit became aware of a data flow failure affecting multiple protocols. Multiple centers stopped feeding into SIRIUS, Pfizer’s system used to distribute safety notifications, including Suspected Unexpected Serious Adverse Reactions (SUSARs), to investigators. As a direct result, SUSARs were not distributed to Principal Investigators (PIs) for impacted centers. Initial analysis identified that the International Organization for Standardization (ISO) country code field was missing in affected site records, rendering PI information null and preventing ingestion by SIRIUS. At identification, 146 centers were impacted. An immediate high‑urgency ticket was submitted to the Global Product Development Information Platform (GPDIP) support group by the responsible operations team.</span></p><p style="margin-left: 0in;"><span style="font-size: small;">&nbsp;</span></p><p style="margin-left: 0in;"><span style="font-size: small;">The impact spanned Pfizer’s Clinical Operations portfolio and was not limited to one study. The investigation traced the data path from upstream sources, through integration, to distribution. GPDIP functions as the integration layer brokering study, site, and investigator master data to downstream systems. Upstream sources included Siebel, a legacy customer relationship management and clinical operations system, and Veeva Clinical Trial Management System (CTMS), a vendor‑provided platform contracted to manage study, site, and investigator operational data. Downstream, SIRIUS relies on complete site and PI attributes, including ISO country code, to distribute SUSAR letters.</span></p><p style="margin-left: 0in;"><span style="font-size: small;">&nbsp;</span></p><p style="margin-left: 0in;"><span style="font-size: small;">As a result of these data flow issues 372 Individual Case Safety Report (ICSR) SUSARs and 22 Clinical Trial Safety Update Reports (CTSURs) were manually submitted late to PIs by the Drug Safety Unit (DSU).</span></p><p style="margin-left: 0in;"><span style="font-size: small;">&nbsp;</span></p><p><span style="font-size: small;">A historical review of Quality Events (QEs) in the electronic Quality Management System (eQMS) database was conducted for the period 15 Aug 2023 – 03 Mar 2026, using the keyword “SUSAR” and “Veeva.” No historical QEs were identified as previous occurrences. Based on this review, the current QE (QE-196243) is not considered a repeat occurrence.</span></p> | No | Other | 2026-03-06 | 2025-08-18 |  | Safety surveillance and reporting by Sponsor | Inadequate/incomplete internal safety surveillance, risk management and safety reporting |  | 2026-03-06 18:17 | AEM01-Adverse Event Monitoring | C Anna Breen | FALSE | A high urgency ticket was submitted to GPDIP group by Aaron Croteau. Otherwise, unable to remediate via BCP until the PI information is present in the system. |  |  | A lack of robust testing, documentation, clear roles and responsibilities led to unidentified compatibility issues from CTMS Veeva implementation within GPDIP which led to cascading data flow issues within downstream systems., An error while performing support issue trouble shooting caused duplicate data to be uploaded to the incorrect data bucket which caused the pipeline to stop processing. While restoring the pipeline, a number of PI records were not provided causing an incomplete set of SUSAR recipients to the SIRIUS system. | Equipment/System/Facility, Human Performance | Application Error, System/Application | Complexity (e.g. Procedures, Forms, Plans, Contracts, Agreements, Training Material), Lack of or Inadequate Validation/Installation | MODEL 1 - INSOURCED | Oncology
QE-219824 | C1071004 | (Empty) | QE-219824 |  | ORACLE | N | Minor | Closed | Inform LNMT is a separate functionality within Inform EDC which is used to set-up Local Labs and configure the lab normal ranges which are associated to corresponding Studies and Sites. MedTech team has access to Inform LNMT to perform these functions.Inform is a product of Oracle. And Oracle identified that, if multiple users are working in the LNMT and making updates in it, it is causing the audit to capture the username of another user. Oracle notified Pfizer about this identified issue and the action they have taken on 3/Dec/2025.Please note, this issue only affected the username attribution in the LNMT audit trail; all other clinical trial audit data remains accurate. Additionally, users were never able to perform actions outside of their authorized permissions. | 2025-12-03 | 2025-12-19 | 2025-12-19 20:22 | GCP_Minor_Dec-2025_Multiple Studies: InForm LNMT User Audit Trail_Oracle_Global |  | NO |  |  | No |  |  | 2025-12-19 |  | Data Collection and Management | Data management error |  |  | DMB07-Study Data Set Design and Setup | Prathamesh Patil |  | Oracle has implemented preventative fixes to prevent incorrect user attribution in the LNMT audit going forward. Please note that Oracle is unable to retroactively correct past occurrences of this issue. |  |  | NA | Equipment/System/Facility | System/Application |  | MODEL 1 - INSOURCED | Oncology
QE-232848 | C1071004 | N | QE-232848 | 1003 | Suzanne Trudel (C1071004-1003) | N | Minor | Closed | The site was entering data related to long-term disease assessments in Inform after Subject 10031009 had withdrawn consent. Per source, the subject withdrew the study consent on 19Sep2025 and agreed to be followed up only for survival. However, the site continued capturing data (lab results) for LTDA (Long Term Disease Assessment) in EDC - that was for LTDA5 (29Sep2025), LTDA6 (06Nov2025) and LTDA7 (18Dec2025). | 2026-03-10 | 2026-03-10 | 2026-03-11 15:28 | GCP_Minor_Mar-2026_C1071004: Protocol Deviation: Withdrawal of Consent; Data Entry_Trudel, Suzanne_CAN |  | NO |  |  | No |  |  | 2026-03-11 |  | Data Collection and Management | Data management error |  |  | DMB08-Study Data Set Review Release and Archive | Olaide Olowe |  | Monitor instructed site to remove all data entered in EDC after becoming aware of withdrawal of consent by the Subject. |  |  | NA | Human Performance | Decision Error |  | MODEL 1 - INSOURCED | Oncology