## Standard_Quality_Dashboard - SQ
Case ID | Case Status | Observation ID | Obs Status | Submission Date | Issue Audit Report (Actual) | Center Number | principal investigator | Country | Description | Study ID | Protocol ID | Title Short Description | Drug Program Code | Rating | Event Type | Case CAPA Approved Due Date | Case CAPA Approved On | CAPA Plan In Place Timely | Obs CAPA Approved Due Date | Obs CAPA Approved On | Obs Target Completion Date | Obs Actual Completion Date | Case CAPA Closure Timely | Case Target Completion Date | Case Actual Completion Date | Obs CAPA Closure Timely | Selected Business Process | Taxonomy Level 1 | Taxonomy Level 2 | Study Status | Business Category | Study Phase | Study Priority | Asset | Dev China | Dev Japan | Rapid Model | Business Category
2192308 | Closed - Superseded | 2192376 | Closed - Superseded | 2021-07-27 | (Empty) | (Empty) | (Empty) | (Empty) | Product Protocol Number: B8011011 / PPD B9991004 / PPD B9991046/ PAREXEL C1071004 / ICON C3671013 / ICON C4591031/ ICON Involved Party / Country: Pfizer / Global Quality Event Description: Three oncology studies (B8011001, B9991046, C1071004) were developed and implemented using a master protocol, umbrella study design. However, Pfizer systems including those for data reporting, clinical trial registry, and public disclosure, are not designed to support independent reporting of sub-studies under the Master Protocol (MP) and sub-study (SS) structure. Specifically, complex interventional clinical trial study designs (umbrella, basket, platform) are not supported by current SOPs, processes, and systems. B8011011 is a Phase 1B/2 Open Label Umbrella Study of Sasanlimab Combined with Anti-Cancer Therapies Targeting Multiple Molecular Mechanisms in Participants with Non-Small Cell Lung Cancer (NSCLC). Compound: Sasanlimab (PF-06801591). Protocol Amendment #3_28-April-2021 B9991046 is the Avelumab Master Protocol: An open-label continuation study for participants continuing from Pfizer Sponsored Avelumab clinical studies. Compound: Avelumab (PF-06834635 MSB0010718C) Protocol _28-April-2021; CT B999bk B9991046 Avelumab Master Study C1071004 (alias MagnetisMM-4 - Substudy A + Substudy B) is a phase 1B/2, open label umbrella study of elranatamab (PF-06863135), a B-Cell maturation antigen (BCMA) CD3 bispecific antibody, in combination with other anti-cancer treatments in participants with multiple myeloma. Substudy A + SubStudy B_Protocol Amendment #2_17-Jun-2021; CT C107h C1071004 Ph2 Ph1-2 POC MagnetisMM-4 Combination Umbrella MM Study On 24-Aug-2021, 3 additional clinical trials were added to the investigation. B9991004 is a phase 1B/2 open-label study to evaluate safety, clinical activity, pharmacokinetics and pharmacodynamics of avelumab (MSB0010718C) in combination with other cancer immunotherapies in patients with advance malignancies. Protocol Amendment #8; CT B999u B9991004 C3671013 is a phase 3 study to evaluate the efficacy, immunogenicity, and safety of respiratory syncytial virus (RSV) prefusion F subunit vaccine in adults. Protocol_07-Jul-2021 (FSFV 01-Sep-2021); CT C367a C3671013 Phase 3 RSV Adult. C4591031 is a phase 3 master protocol to evaluate additional dose(s) of BNT162B2 in healthy individuals previously vaccinated with BNT162B2. Protocol 13-May-2021 (FSFV 01-Jul-2021) CT C459a C4591031 Booster & Efficacy. | C1071004 | C1071004 | GCP_T2_Jul-2021_Mulitiple Protocols: CMCD: Master Protocol Design_Pfizer_Global | C107 | Major | SQE | 2022-04-08 | 2022-03-24 | Y | 2022-04-08 | 2022-03-24 22:10 | 2022-12-19 | 2022-12-15 | Y | 2022-12-19 | 2022-12-15 | Y | CT02 - CLINICAL PROTOCOLS | Quality Procedures | Requirement/process not met | TERMINATED | Oncology | PHASE II | STREAMLINE | ELREXFIO MM Umb | (Empty) | (Empty) | MODEL 1 - INSOURCED | Oncology
2192308 | Closed - Superseded | 2192376 | Closed - Superseded | 2021-07-27 | (Empty) | (Empty) | (Empty) | (Empty) | Product Protocol Number: B8011011 / PPD B9991004 / PPD B9991046/ PAREXEL C1071004 / ICON C3671013 / ICON C4591031/ ICON Involved Party / Country: Pfizer / Global Quality Event Description: Three oncology studies (B8011001, B9991046, C1071004) were developed and implemented using a master protocol, umbrella study design. However, Pfizer systems including those for data reporting, clinical trial registry, and public disclosure, are not designed to support independent reporting of sub-studies under the Master Protocol (MP) and sub-study (SS) structure. Specifically, complex interventional clinical trial study designs (umbrella, basket, platform) are not supported by current SOPs, processes, and systems. B8011011 is a Phase 1B/2 Open Label Umbrella Study of Sasanlimab Combined with Anti-Cancer Therapies Targeting Multiple Molecular Mechanisms in Participants with Non-Small Cell Lung Cancer (NSCLC). Compound: Sasanlimab (PF-06801591). Protocol Amendment #3_28-April-2021 B9991046 is the Avelumab Master Protocol: An open-label continuation study for participants continuing from Pfizer Sponsored Avelumab clinical studies. Compound: Avelumab (PF-06834635 MSB0010718C) Protocol _28-April-2021; CT B999bk B9991046 Avelumab Master Study C1071004 (alias MagnetisMM-4 - Substudy A + Substudy B) is a phase 1B/2, open label umbrella study of elranatamab (PF-06863135), a B-Cell maturation antigen (BCMA) CD3 bispecific antibody, in combination with other anti-cancer treatments in participants with multiple myeloma. Substudy A + SubStudy B_Protocol Amendment #2_17-Jun-2021; CT C107h C1071004 Ph2 Ph1-2 POC MagnetisMM-4 Combination Umbrella MM Study On 24-Aug-2021, 3 additional clinical trials were added to the investigation. B9991004 is a phase 1B/2 open-label study to evaluate safety, clinical activity, pharmacokinetics and pharmacodynamics of avelumab (MSB0010718C) in combination with other cancer immunotherapies in patients with advance malignancies. Protocol Amendment #8; CT B999u B9991004 C3671013 is a phase 3 study to evaluate the efficacy, immunogenicity, and safety of respiratory syncytial virus (RSV) prefusion F subunit vaccine in adults. Protocol_07-Jul-2021 (FSFV 01-Sep-2021); CT C367a C3671013 Phase 3 RSV Adult. C4591031 is a phase 3 master protocol to evaluate additional dose(s) of BNT162B2 in healthy individuals previously vaccinated with BNT162B2. Protocol 13-May-2021 (FSFV 01-Jul-2021) CT C459a C4591031 Booster & Efficacy. | C1071004 | C1071004 | GCP_T2_Jul-2021_Mulitiple Protocols: CMCD: Master Protocol Design_Pfizer_Global | C107 | Major | SQE | 2022-04-08 | 2022-03-24 | Y | 2022-04-08 | 2022-03-24 22:10 | 2022-12-19 | 2022-12-15 | Y | 2022-12-19 | 2022-12-15 | Y | CT27 - CLINICAL TRIAL REGISTRY | Quality Procedures | Requirement/process not met | TERMINATED | Oncology | PHASE II | STREAMLINE | ELREXFIO MM Umb | (Empty) | (Empty) | MODEL 1 - INSOURCED | Oncology
2192308 | Closed - Superseded | 2192376 | Closed - Superseded | 2021-07-27 | (Empty) | (Empty) | (Empty) | (Empty) | Product Protocol Number: B8011011 / PPD B9991004 / PPD B9991046/ PAREXEL C1071004 / ICON C3671013 / ICON C4591031/ ICON Involved Party / Country: Pfizer / Global Quality Event Description: Three oncology studies (B8011001, B9991046, C1071004) were developed and implemented using a master protocol, umbrella study design. However, Pfizer systems including those for data reporting, clinical trial registry, and public disclosure, are not designed to support independent reporting of sub-studies under the Master Protocol (MP) and sub-study (SS) structure. Specifically, complex interventional clinical trial study designs (umbrella, basket, platform) are not supported by current SOPs, processes, and systems. B8011011 is a Phase 1B/2 Open Label Umbrella Study of Sasanlimab Combined with Anti-Cancer Therapies Targeting Multiple Molecular Mechanisms in Participants with Non-Small Cell Lung Cancer (NSCLC). Compound: Sasanlimab (PF-06801591). Protocol Amendment #3_28-April-2021 B9991046 is the Avelumab Master Protocol: An open-label continuation study for participants continuing from Pfizer Sponsored Avelumab clinical studies. Compound: Avelumab (PF-06834635 MSB0010718C) Protocol _28-April-2021; CT B999bk B9991046 Avelumab Master Study C1071004 (alias MagnetisMM-4 - Substudy A + Substudy B) is a phase 1B/2, open label umbrella study of elranatamab (PF-06863135), a B-Cell maturation antigen (BCMA) CD3 bispecific antibody, in combination with other anti-cancer treatments in participants with multiple myeloma. Substudy A + SubStudy B_Protocol Amendment #2_17-Jun-2021; CT C107h C1071004 Ph2 Ph1-2 POC MagnetisMM-4 Combination Umbrella MM Study On 24-Aug-2021, 3 additional clinical trials were added to the investigation. B9991004 is a phase 1B/2 open-label study to evaluate safety, clinical activity, pharmacokinetics and pharmacodynamics of avelumab (MSB0010718C) in combination with other cancer immunotherapies in patients with advance malignancies. Protocol Amendment #8; CT B999u B9991004 C3671013 is a phase 3 study to evaluate the efficacy, immunogenicity, and safety of respiratory syncytial virus (RSV) prefusion F subunit vaccine in adults. Protocol_07-Jul-2021 (FSFV 01-Sep-2021); CT C367a C3671013 Phase 3 RSV Adult. C4591031 is a phase 3 master protocol to evaluate additional dose(s) of BNT162B2 in healthy individuals previously vaccinated with BNT162B2. Protocol 13-May-2021 (FSFV 01-Jul-2021) CT C459a C4591031 Booster & Efficacy. | C1071004 | C1071004 | GCP_T2_Jul-2021_Mulitiple Protocols: CMCD: Master Protocol Design_Pfizer_Global | C107 | Major | SQE | 2022-04-08 | 2022-03-24 | Y | 2022-04-08 | 2022-03-24 22:10 | 2022-12-19 | 2022-12-15 | Y | 2022-12-19 | 2022-12-15 | Y | CT28 - PUBLIC DISCLOSURE OF STUDY INFORMATION | Quality Procedures | Requirement/process not met | TERMINATED | Oncology | PHASE II | STREAMLINE | ELREXFIO MM Umb | (Empty) | (Empty) | MODEL 1 - INSOURCED | Oncology
2214524 | Closed | 2214565 | Closed | 2022-09-23 | (Empty) | 1011 | Landgren, Carl Ola | UNITED STATES | Product Protocol Number: C1071004 (Alias: Umbrella Study) Involved Party / Country: PI: Landgren, Carl Ola (Site Number: 1011) / United States Awareness Date: 23-Sep-2022 A Phase 1B/2, open label Umbrella Study of Elranatamab (PF-06863135), a B-cell Maturation Antigen (BCMA) CD3 (Cluster of Differentiation 3) bispecific antibody, in combination with other anti-cancer treatments in participants with multiple myeloma. This Quality Event (QE) was initiated due to a late SAE (Serious Adverse Event) reported by site 1011 on C1071004.The late SAE for prolongation of hospitalization was reported by the site on Mon 29-Aug-2022, with an awareness date of Saturday, 27-Aug-2022. On Monday, 29-Aug-2022, the Study Coordinator (SC) who reported the SAE realized the participant was not discharged on Friday, 26-Aug-2022 until they returned to the site on Monday, 29-Aug-2022. The SAE should have been reported within 24 hours of the Sub-Investigators awareness that the reporting requirements were met for prolongation of hospitalization. The participant experienced GI issue for which the Sub-Investigator requested a GI consult on Friday 26-Aug-2022. The treating physician later confirmed on (23-Sep-2022) that the participant was otherwise well but remained in the hospital pending review of the GI workup. The participant remained in hospital over the weekend for GI workup and the Day 8 dosing which would occur on Monday, 29-Aug-2022. The GI event was not considered related to the study drug. The Sub-Investigator was aware the participant remained in the hospital through the weekend; however, did not report the potential SAE to the Primary Investigator and SC until Monday, 29-Aug-2022 when the SAE was formally reported. The late SAE report was the third instance for late SAE reporting and the second intervention for late SAE reporting (clinician letter sent to Site 1011 on 08-Jul-2022) at site 1011. The late SAE reporting was limited to only this site of C1071004. | C1071004 | C1071004 | GCP_T2_Sep-2022_C1071004: CMCD: SAE Reporting_Landgren, Carl Ola_USA | C107 | Major | SQE | 2022-11-07 | 2022-10-21 | Y | 2022-11-07 | 2022-10-21 19:37 | 2023-01-09 | 2023-01-05 | Y | 2023-01-09 | 2023-01-05 | Y | AEM01 - Adverse Event Monitoring | AE reporting to Sponsor | Delayed SAE reporting | TERMINATED | Oncology | PHASE II | STREAMLINE | ELREXFIO MM Umb | (Empty) | (Empty) | MODEL 1 - INSOURCED | Oncology
2226319 | Closed | 2226333 | Closed | 2023-05-16 | (Empty) | (Empty) | (Empty) | (Empty) | Product Protocol Number: B3461087; B7981031; B7981040; C1071004; C1071005; C1071006; C1071007; C1071009; C1071020; C3441052; C4151002; C4161001; C4221022; C4391001; C5341021, C5341026; AREN1721 (WI237422-14) Involved Party / Country: Vendor: ICON Laboratory Services / Global Quality Event Description: Between Sep 2021 and Apr 2023 during supply shortages stemming from the COVID pandemic, the ICON Central Lab (ICL) provided study sites with replacement blood collection vacutainer tubes manufactured by Jiangsu Kangjie Medical Devices Co Ltd (JKMD) and Jiangsu Maik Medical Apparatus Co Ltd (JMMA) in convenience kits. These tubes were incorrectly registered with the Food & Drug Administration (FDA) as Class 1 Medical Devices instead of the required Class 2 designation and did not undergo sterilization after production, thereby deviating from Clinical & Laboratory Standards Institute guidelines. | C1071004 | C1071004 | GCP_T2_May-2023_Multiple Protocols: Blood Collection Tube Registration_ICON Laboratory Services_Global | C107 | Major | SQE | 2023-06-30 | 2023-06-23 | Y | 2023-06-30 | 2023-06-23 21:09 | 2024-03-30 | 2024-03-22 | Y | 2024-03-30 | 2024-03-22 | Y | NOT APPLICABLE | Compliance Requirements - Country Specific Requirements | Failure to follow country-specific requirements | TERMINATED | Oncology | PHASE II | STREAMLINE | ELREXFIO MM Umb | (Empty) | (Empty) | MODEL 1 - INSOURCED | Oncology
2226319 | Closed | 2226333 | Closed | 2023-05-16 | (Empty) | (Empty) | (Empty) | (Empty) | Product Protocol Number: B3461087; B7981031; B7981040; C1071004; C1071005; C1071006; C1071007; C1071009; C1071020; C3441052; C4151002; C4161001; C4221022; C4391001; C5341021, C5341026; AREN1721 (WI237422-14) Involved Party / Country: Vendor: ICON Laboratory Services / Global Quality Event Description: Between Sep 2021 and Apr 2023 during supply shortages stemming from the COVID pandemic, the ICON Central Lab (ICL) provided study sites with replacement blood collection vacutainer tubes manufactured by Jiangsu Kangjie Medical Devices Co Ltd (JKMD) and Jiangsu Maik Medical Apparatus Co Ltd (JMMA) in convenience kits. These tubes were incorrectly registered with the Food & Drug Administration (FDA) as Class 1 Medical Devices instead of the required Class 2 designation and did not undergo sterilization after production, thereby deviating from Clinical & Laboratory Standards Institute guidelines. | C1071004 | C1071004 | GCP_T2_May-2023_Multiple Protocols: Blood Collection Tube Registration_ICON Laboratory Services_Global | C107 | Major | SQE | 2023-06-30 | 2023-06-23 | Y | 2023-06-30 | 2023-06-23 21:09 | 2024-03-30 | 2024-03-22 | Y | 2024-03-30 | 2024-03-22 | Y | NOT APPLICABLE | Equipment, Facility and Sample/Specimens | Inadequate equipment/lab supply mgmt. | TERMINATED | Oncology | PHASE II | STREAMLINE | ELREXFIO MM Umb | (Empty) | (Empty) | MODEL 1 - INSOURCED | Oncology
AIA-001227 | Closed | QE-071636 | Closed | (Empty) | 2023-10-24 | 1011 | (Empty) | UNITED STATES | For five of five participants reviewed, informed consent was not adequately obtained and documented [ICH E6 (R2) 4.8.2, 4.8.5, 4.8.8]. The&nbsp;following&nbsp;examples&nbsp;were&nbsp;noted: 1. For one of five participants reviewed, re-consent was not obtained at the next in-person study visit after approval of the informed consent document. Participant 10111025 was reconsented on 17May2023 with the English Main Informed Consent and addendum effective on 18Apr2023. However, the participant had a study visit on 03May2023.&nbsp; 2.&nbsp; For three of five participants reviewed, the informed consent forms were incomplete or were not adequately completed: a. Participant 10111005: i. Re-consent obtained on 25Oct2022 (English main consent sub-study A effective 24 Oct 2022): The participant did not include a printed name on the designated line of the form. ii. Re-consent obtained Jun2023 (English main consent sub-study A effective 05 Jan 2023). The participant's date on the informed consent document was illegible. It could not be determined if the participant signed the document on the 25th or 29th of Jun2023, as the day of the month was a write-over. The person who obtained consent signed the document on 29Jun2023. b. Participant 10111008: i. Re-consent obtained on 16May2023: The handwriting for the date entered on the participant's date line on the English main consent sub-study A form (effective 18 Apr 2023) consent section (page 32) was not consistent with the handwriting of the participant's date in the Health Insurance Portability and Accountability Act (HIPAA) section on page 36 or with the handwriting on page 12 of the addendum consent. The participant's date on page 32 of the main consent was consistent with the handwriting of the sub-investigator who obtained consent. ii. Re-consent obtained on 13Jun2023: The person who obtained consent did not sign or date the English main consent sub-study A document effective 05 Jun 2023. On the same day, the English addendum consent for sub- study A was signed and dated by sub-investigator S.M. c. Participant 10111026, Re-consent on 14Jun2023: The participant signed the English informed consent sub-study A document (effective on 05 Jun 2023) on 14Jun2023. However, sub-investigator J.H. signed the form on 17Jun2023. The sub-investigator signed the English addendum for sub-study A (effective 05 Jun 2023) on the same day as the participant (i.e., 14Jun2023). 3. For five of five participants reviewed, the informed consent note was either not documented or was not documented contemporaneously: a. Participant 10111005: i. The 31Jan2022 initial informed consent process was not documented in the medical notes until 01Feb2022. ii. The 01Mar2022 re-consent process was not documented in the medical notes. iii. The 25Oct2022 re-consent process was not documented in the medical notes. iv. The 25Apr2023 re-consent process was not documented in the medical notes until 03May2023. v. The Jun 2023 re-consent process was not documented in the medical notes until 27Jul2023. b. Participant 10111008: &nbsp; i. The 25Feb2022 initial consent process was not documented in the medical notes. ii. The 25Oct2022 re-consent process was not documented in the medical notes. iii. The 16May2023 re-consent process was not documented in the medical notes. iv. The 13Jun2023 re-consent process was not documented in the medical notes until 18Jun2023. c. Participant 10111020: i. The 23Aug2022 initial consent process was not documented in the medical notes until 24Aug2022. ii. The 02May2022 re-consent process was not documented in the medical notes until 05May2023. d. Participant 10111025: i. The 17May2023 re-consent process was not documented in the medical notes. ii. The 14Jun2023 re-consent process was incomplete in the medical notes. The signature status of the note was pending/incomplete as of 16Jun2023. e. Participant 10111026: i. The 28Mar2023 initial consent process on was not documented in the medical notes until 31Mar2023. ii. The 26Apr2023 re-consent process was not documented in the medical notes until 28Apr2023. iii. The 05Jun2023 re-consent process was not documented in the medical notes until 16Jun2023 and was documented by a different sub-inve stigator than the one who signed the informed consent document. | C1071004 | C1071004 | A Routine Investigator Site Audit of Study C1071004, Site 1011, Dr. C. Ola Landgren, Miami, FL USA | (Empty) | Major | AUDIT | 2023-12-05 | (Empty) | N | (Empty) | (Empty) | 2024-03-31 | 2024-03-27 | N | 2024-06-30 | 2025-04-14 | Y | CT05 - Informed Consent Documents | Informed Consent | Inadequate consent process at the investigator site | TERMINATED | Oncology | PHASE II | STREAMLINE | ELREXFIO MM Umb | (Empty) | (Empty) | MODEL 1 - INSOURCED | Oncology
AIA-001227 | Closed | QE-071639 | Closed | (Empty) | 2023-10-24 | 1011 | (Empty) | UNITED STATES | For five of five participants reviewed, electrocardiograms (ECG) were not reviewed by a delegated study physician [Pfizer Protocol C1071004 (Amendment: 7, 28 Jul 2022); ICH E6 (R2) 4.3.1]. Physician reviews of the ECG tracings were documented in the electronic medical record (EMR) by study physicians not listed on the Delegation of Authority Log.&nbsp; No physician reviews were documented on the printed ECG tracings. &nbsp; | C1071004 | C1071004 | A Routine Investigator Site Audit of Study C1071004, Site 1011, Dr. C. Ola Landgren, Miami, FL USA | (Empty) | Major | AUDIT | 2023-12-05 | (Empty) | N | (Empty) | (Empty) | 2024-03-31 | 2024-03-14 | N | 2024-06-30 | 2025-04-14 | Y | NOT APPLICABLE; NOT APPLICABLE | Quality Oversight | Inadequate Principal Investigator quality oversight | TERMINATED | Oncology | PHASE II | STREAMLINE | ELREXFIO MM Umb | (Empty) | (Empty) | MODEL 1 - INSOURCED | Oncology
AIA-001227 | Closed | QE-071641 | Closed | (Empty) | 2023-10-24 | 1011 | (Empty) | UNITED STATES | For five of 34 delegated staff reviewed training was not found or was found to be expired [ICH E6 (R2) 4.1.5, 4.2.3, 4.2.4]. 1.&nbsp; Good Clinical &nbsp;Practice (GCP) training:&nbsp; a. GCP training was not found for the following &nbsp;three staff members:&nbsp; i. Sub-investigator: I.L. ii. Sub-investigator J.A. iii. Sub-investigator C.M. b. GCP training was expired for the following two staff members: i. Sub-investigator M.B., expired 06Apr2023 ii. Regulatory staff member A.M., expired 10Sep2023 2. Protocol training for amendment 7 was not found for two of the 34 delegated staff: a. Sub-investigator C.M. b. Sub-investigator M.B. | C1071004 | C1071004 | A Routine Investigator Site Audit of Study C1071004, Site 1011, Dr. C. Ola Landgren, Miami, FL USA | (Empty) | Minor | AUDIT | 2023-12-05 | (Empty) | N | (Empty) | (Empty) | 2024-01-31 | 2023-11-16 | N | 2024-06-30 | 2025-04-14 | Y | CT33 - Study-Specific Training | Training & Qualifications | Training not completed or documented in a timely manner | TERMINATED | Oncology | PHASE II | STREAMLINE | ELREXFIO MM Umb | (Empty) | (Empty) | MODEL 1 - INSOURCED | Oncology
AIA-001227 | Closed | QE-071643 | Closed | (Empty) | 2023-10-24 | 1011 | (Empty) | UNITED STATES | For three of 39 investigational product (IP) shipments reviewed, the drug receipt inspection was either not documented or was incorrectly documented to indicate that IP was received damaged [C1071004 Investigational Product Manual, version 6.0 dated 30 Sep2022]. 1.&nbsp; Shipment ID 1789289 (shipment date 27 Mar 2023) did not have drug receipt inspection documented. 2. Shipment ID 1751907 (shipment date 18 Apr 2022) did not have drug receipt inspection documented. 3. Shipment ID 1798153 (shipment date 12 Jun 2023) was marked "yes," that IP was received damaged. Per interview with a site pharmacist, this response was marked in error. | C1071004 | C1071004 | A Routine Investigator Site Audit of Study C1071004, Site 1011, Dr. C. Ola Landgren, Miami, FL USA | (Empty) | Minor | AUDIT | 2023-12-05 | (Empty) | N | (Empty) | (Empty) | 2024-03-31 | 2024-02-20 | N | 2024-06-30 | 2025-04-14 | Y | IP13 - Study Investigational Product Supplies | Medicinal Product | Inadequate accountability/record keeping | TERMINATED | Oncology | PHASE II | STREAMLINE | ELREXFIO MM Umb | (Empty) | (Empty) | MODEL 1 - INSOURCED | Oncology
AIA-001227 | Closed | QE-071644 | Closed | (Empty) | 2023-10-24 | 1011 | (Empty) | UNITED STATES | Eight Essential documents were absent from the Investigator Site File (ISF) [ICH E6 (R2) 4.9.4]. The&nbsp;following&nbsp;examples&nbsp;were&nbsp;noted: 1. Two C1071004 Protocols: a. Protocol amendment 4, version date 09Aug2021 b. Protocol amendment 5, version date 08Nov2021 2. Two Protocol Administrative Clarification Letters (PACLs):&nbsp; a. Protocol administrative clarification letter dated 16Nov2022 b. Protocol administrative clarification letter dated 15May2023 3. Two Protocol Acceptance Forms: a. Protocol amendment 4, version date 09Aug2021 b. Protocol amendment 5, version date 08Nov2021 4. Financial disclosure form for sub-investigator J.A. signed on 08Dec2021 5. Wet-ink initials and signatures were not included on the electronic Delegation of Authority Log. Staff initials and signatures could not be verified. | C1071004 | C1071004 | A Routine Investigator Site Audit of Study C1071004, Site 1011, Dr. C. Ola Landgren, Miami, FL USA | (Empty) | Minor | AUDIT | 2023-12-05 | (Empty) | N | (Empty) | (Empty) | 2024-06-30 | 2025-04-14 | N | 2024-06-30 | 2025-04-14 | N | CT01 - Trial Master Files | Document Management | Missing document | TERMINATED | Oncology | PHASE II | STREAMLINE | ELREXFIO MM Umb | (Empty) | (Empty) | MODEL 1 - INSOURCED | Oncology
AIA-001227 | Closed | QE-071646 | Closed | (Empty) | 2023-10-24 | 1011 | (Empty) | UNITED STATES | Essential documents in the Pfizer Trial Master File (PTMF) were not found [SOP CT01 GSOP 8.0 Trial Master File (Effective 03 Oct 2022), ICH E6 (R2) 8]. The&nbsp;following&nbsp;examples&nbsp;were&nbsp;noted: 1. The following documents were absent: a. English Sub-study A Research Participant Consent Form, effective date 24Oct2022 b. Institutional Review Board (IRB) approvals: i. Initial approval dated 24Sep2021 ii. Continuing review approval dated 26Jul2022 iii. Continuing review approval dated 22May2023 c. University of Miami local institutional review board (IRB) rosters for the IRB-B and IRB-C panels d. Form FDA-1572s signed by the Principal Investigator on the following dates: i. 21Aug2021 ii. 07Dec2021 iii. 05Oct2022 iv. 06Nov2022&nbsp; v. 02Dec2022 vi.&nbsp;30Jun2023 e. The following financial disclosure forms: i. Sub-investigator D.C. signed on 01Nov2022 ii. Sub-investigator F.M. signed on 16Nov2022 iii. Sub-investigator F.S. signed on 13Aug2023 &nbsp; | C1071004 | C1071004 | A Routine Investigator Site Audit of Study C1071004, Site 1011, Dr. C. Ola Landgren, Miami, FL USA | (Empty) | Minor | AUDIT | 2023-12-05 | (Empty) | N | (Empty) | (Empty) | 2024-03-31 | 2024-03-26 | N | 2024-06-30 | 2025-04-14 | Y | CT01 - Trial Master Files | Document Management | Missing document | TERMINATED | Oncology | PHASE II | STREAMLINE | ELREXFIO MM Umb | (Empty) | (Empty) | MODEL 1 - INSOURCED | Oncology
QE-104261 | Closed | QE-104261 | Closed | 2024-03-15 | (Empty) | (Empty) | ICON PLC | (Empty) | During Wave 2 transitions to Model 1 from CROs ICON and PXL, Pfizer teams are taking over approx. 40 studies which were previously managed by the CRO. As part of the transition process from outgoing CRO to incoming Pfizer SAP team member it has been discovered that the CROs may not have been aware of Safety Gap Package processes. SIRIUS only sends SUSAR and CTSUR safety info to PIs automatically AFTER IIP approval. Process is to then send what we call the Gap package at the time of IIP approval to provide any safety reports which have been filed between the sending of the initial IB and the site's IIP approval date (the SSU period) to ensure PIs have all safety info prior to seeing their first patient. We believe this was not done and potentially for thousands of sites on these studies over the past 5 years or so. It is difficult to confirm the volume at this time but it not definitely appears to be a widespread non-complaince by both ICON and PXL pCROs. | C1071004 | C1071004 | GCP_Major_Mar-2024_Enterprise Level: Safety Gap Packs_ICON PL; Parexel International_Global | C107 | Major | SQE | 2024-04-29 | 2024-08-12 | N | 2024-04-29 | 2024-08-12 21:11 | (Empty) | 2025-03-19 | (Empty) | (Empty) | 2025-03-19 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Safety Information Communication | Failure/Incomplete safety communication | TERMINATED | Oncology | PHASE II | STREAMLINE | ELREXFIO MM Umb | (Empty) | (Empty) | MODEL 1 - INSOURCED | Oncology
QE-104261 | Closed | QE-104261 | Closed | 2024-03-15 | (Empty) | (Empty) | PAREXEL INTERNATIONAL | (Empty) | During Wave 2 transitions to Model 1 from CROs ICON and PXL, Pfizer teams are taking over approx. 40 studies which were previously managed by the CRO. As part of the transition process from outgoing CRO to incoming Pfizer SAP team member it has been discovered that the CROs may not have been aware of Safety Gap Package processes. SIRIUS only sends SUSAR and CTSUR safety info to PIs automatically AFTER IIP approval. Process is to then send what we call the Gap package at the time of IIP approval to provide any safety reports which have been filed between the sending of the initial IB and the site's IIP approval date (the SSU period) to ensure PIs have all safety info prior to seeing their first patient. We believe this was not done and potentially for thousands of sites on these studies over the past 5 years or so. It is difficult to confirm the volume at this time but it not definitely appears to be a widespread non-complaince by both ICON and PXL pCROs. | C1071004 | C1071004 | GCP_Major_Mar-2024_Enterprise Level: Safety Gap Packs_ICON PL; Parexel International_Global | C107 | Major | SQE | 2024-04-29 | 2024-08-12 | N | 2024-04-29 | 2024-08-12 21:11 | (Empty) | 2025-03-19 | (Empty) | (Empty) | 2025-03-19 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Safety Information Communication | Failure/Incomplete safety communication | TERMINATED | Oncology | PHASE II | STREAMLINE | ELREXFIO MM Umb | (Empty) | (Empty) | MODEL 1 - INSOURCED | Oncology
QE-120192 | Closed | QE-120192 | Closed | 2024-06-10 | (Empty) | (Empty) | PFIZER | (Empty) | Several site organizations across Pfizer study programs are following their own site standard training processes/SOPs. Site training processes are being assessed for equivalency to CT33-GSOP and marked as "Completed" in Firecrest when the following CT33-GSOP criteria may not be met: The PI must be trained by Pfizer process for protocol amendments after being trained by Pfizer process for initial PST (e.g., IM, SIV, Firecrest, online meeting). The PI will follow its organization's training process after the initial Pfizer PST training.The site is not providing a confirmation that current/approved training materials are reviewed in their entirety. The site-specific training record provides a confirmation that staff have read &amp; understood the study training material. | C1071004 | C1071004 | GCP_Major_Jun-2024_Enterprise Level; Multiple Studies: CMCD: Trend: Study Training Process_Multiple Sites; Pfizer_Global, CAN | C107 | Major | SQE | 2024-07-26 | 2024-08-01 | N | 2024-07-26 | 2024-08-01 15:13 | 2025-01-21 | 2025-07-30 | N | 2025-01-21 | 2025-07-30 | N | CT33 - Study-Specific Training | Quality Procedures | Requirement/process not met | TERMINATED | Oncology | PHASE II | STREAMLINE | ELREXFIO MM Umb | (Empty) | (Empty) | MODEL 1 - INSOURCED | Oncology
QE-138667 | Closed | QE-138667 | Closed | 2024-09-17 | (Empty) | (Empty) | PFIZER | (Empty) | Multiple PRS scores were not uploaded into eQRM per process and multiple AQLs were not notified of a PRS score change. This has resulted in discrepancies between documentation and the study level RBM monitoring approach (SDV and SDR). In some cases, it has taken 6 months or more to identify that there was a discrepancy in the score, which is a considerable delay for the study teams to take the appropriate actions where needed. Discrepancies now exist between the eQRM system, scores provided to the study teams, Risk Steering Committee and the overall risk-based approach for RBM (including SDV and SDR) for the studies and examples below. C5681001 - manual PRS was calculated in January 2024 as low. This score was not uploaded into eQRM. The PRS was calculated in March based off the approved IQMP and uploaded into eQRM as Medium. As this was the first version to be uploaded to eQRM it did not flag as a change and thus it was not communicated to the AQL or the study team as a change. In 2Q 2024, the PRS was updated to high. The AQL/Study Team were notified of the score change, but the team was operating off of the ‘low’ score provided in January. They were unaware that they should have been operating off of a medium score. QE was previously submitted (before it was realized to be a broader issue).C5241007 - score was calculated as high in August 2023. It was subsequently re-calculated as low in January 2024 and July 2024. The AQL and study team were not informed of the change to low and have been operating off of a high risk score. Change on the PRS was discovered by chance by the Study Manager. Same process steps as above, but the score was reversed (high to low in this situation). C4841001 – Similar situation as above, the score as manually calculated to be low. That score was not uploaded into the eQRM system. The study team wanted to implement medium level SDV. The DRP and SMP were not aligned in regards to the % SDV and a QE was submitted (QE-129179). The study team requested the Risk Steering Committee to permit an increase %SDV to medium, which was approved. The first score uploaded into the eQRM system was recorded as medium (not as low, which was manually calculated previously). The AQL/study team was not informed of this difference/change in score. The study team was operating off the low score provided. The request to the Risk Steering Committee to increase SDV to a medium level would not have been needed with this new score. When the team was informed about the Medium PRS, the SDV was already increased following RSC approval. SDR remains as a low approach. Now there is a discrepancy in the RSC documentation request for a change and the approach of SDV (med) /SDR (low).C4591048 – The statistician calculating the PRS informed the AQL in Nov 2022 that the PRS increased to High. This was not uploaded into the eQRM system/not showing in eQRM dashboard history in November 2022. PRS increase to high is first reported in eQRM in April 2024. In Nov 22, the study team discussed the PRS score change and they made a decision log entry not to change their RBM approach in Nov 22. While there is no RBM impact from the April 2024 increase, there was an 18 month delay in having the correct scoring showing within the validated eQRM system. The decision log entry is only based on the email from the statistician and has no audit trail within eQRM for the Nov 22 change. .25in;".25in;"Additionally, on a related note, it is not clear if there were erroneous PRS scores calculated, specifically those calculated in January and March 2024. These scores were found on the eQRM spotfire viewer on the PRS history tab; however, they were not provided to the Asset Quality Leads (AQLs) or the study teams in a timely fashion (i.e., in January or March 2024 at the time of calculation).Aside from the specific study examples cited above, there are at least 6 other instances where PRS changed (off cycle of the quarterly updates) and the changes were not communicated to the AQL. They were discovered on the eQRM spotfire viewer. It is not clear if these changes were errors as the scores reverted back to the previous scores in the next quarterly calculation. Examples of when the score changed to a different ranking (H/M/L) and back again are as follows: .346153846153847%" valign="top".25pt;"Study number.65384615384616%" valign="top".25pt;"Score fluctuation.346153846153847%" valign="top".25pt;"B7841007.65384615384616%" valign="top".25pt;"High (Oct 23) changed to Medium in Jan 24, back to High in Q1 (Apr 24) and Q2 (Jul 24).346153846153847%" valign="top".25pt;"B7841008.65384615384616%" valign="top".25pt;"Medium (Oct 23) changed to Low (Jan 24) back to Medium in Q1 and Q2.346153846153847%" valign="top".25pt;"C1071020.65384615384616%" valign="top".25pt;"High (Oct 23) changed to Low (Mar24) back to High in 1Q, 2Q.346153846153847%" valign="top".25pt;"C1071030.65384615384616%" valign="top".25pt;"Med (Oct23) changed to Low (Jan 24) back to Medium in 1Q, 2Q.346153846153847%" valign="top".25pt;"C1071004.65384615384616%" valign="top".25pt;"High (Oct 23) to Med (Jan 24) back to High in Q1 and Q2.346153846153847%" valign="top".25pt;"C4591054.65384615384616%" valign="top".25pt;"Med (Oct23) to Low (Mar24) to Med in Q1 | C1071004 | C1071004 | GCP_Major_Sep-2024_Multiple: CMCD: Protocol Risk Score; Source Document Verification / Review_Pfizer_Global | C107 | Major | SQE | 2024-11-02 | 2024-12-20 | N | 2024-11-02 | 2024-12-20 16:12 | (Empty) | 2025-06-03 | (Empty) | (Empty) | 2025-06-03 | (Empty) | QMS06 - Quality Risk Management for Clinical Development | Quality Procedures | Requirement/process not met | TERMINATED | Oncology | PHASE II | STREAMLINE | ELREXFIO MM Umb | (Empty) | (Empty) | MODEL 1 - INSOURCED | Oncology
QE-196243 | Approved - In CAPA | QE-196243 | Approved - In CAPA | 2025-08-18 | (Empty) | (Empty) | PFIZER | (Empty) | Multiple Centers for multiple protocols to not feed into SIRIUS since 15Aug2025. This is causing SUSARs not to be distributed to Pfizer Investigators. | C1071004 | C1071004 | GCP_Critical_Aug-2025_Multiple Protocols: SIRIUS Report Distribution / Veeva Clinical_Pfizer_Global UPGRADE | C107 | Critical | SQE | 2025-11-12 | 2026-03-06 | N | 2025-11-12 | 2026-03-06 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | AEM01 - Adverse Event Monitoring | Safety surveillance and reporting by Sponsor | Inadequate/incomplete internal safety surveillance, risk management and safety reporting | TERMINATED | Oncology | PHASE II | STREAMLINE | ELREXFIO MM Umb | (Empty) | (Empty) | MODEL 1 - INSOURCED | Oncology