## Standard_Quality_Dashboard - QE
Observation ID | Study ID | Targeted | PR ID | Site(s) | principal Investigator | EX Comp? | QE Threshold | Status | Observation Description (as submitted) | Awareness Date | Submission Date | Assessment Date | Title/Short Description | Business CAPA Plan Endorsed On | CAPA Plan in Place | Last Action Due Date | Investigation Summary and Conclusion | Effectiveness Check Required | Effectiveness Check Rationale | Investigation Completion Date | Closed On | PDAL Decision | Level 1 | Level 2 | Quality CAPA Plan Endorsed On | Quality Reviewer Approved On | Business Process | Submitter | Confirmed Serious Breach | Remediation Actions Taken (when QE was submitted) | CAPA Action Details | CAPA Action Owner | Root Cause Description | Root Cause Level 1 | Root Cause Level 2 | Root Cause Level 3 | Rapid Model | Business Category
QE-136468 | C1071015 | (Empty) | QE-136468 |  | PFIZER | N | Minor | Closed | C1071015 2 subjects have reached Cycle 13 visit which is not yet available to enter in EDC for site to enter Date of Visit and dosing. | 2024-09-05 | 2024-09-05 | 2024-09-06 14:25 | GCP_Minor_Sep-2024_C1071015: EDC Data Entry_Pfizer_Global |  | NO |  |  | No |  |  | 2024-09-06 |  | Data Collection and Management | Data management error |  |  | DMB07-Study Data Set Design and Setup | Carrie Niemes |  | A PPC has been initiated to urgently add cycle visits for entry of dosing. |  |  | NA | Human Performance | Omission Error |  | MODEL 2 - HYBRID | Oncology
QE-163016 | C1071015 | N | QE-163016 | 1011 | Michael Chu (C1071015-1011) | N | Minor | Closed | Study C1071015, Site 1011, Subject 10111001. Principal Investigator casebook annual signature was not applied for 2024 by 31Jan2025. The PI stated when he tried to sign on 01Jan2025, he received an error message with support ID 8448849230557370657. The helpdesk contact information was provided. The PI tried again on 22Jan2025 by logging in via the Oracle option instead of ExoStar; however, the signature prompt asked for ExoStar credentials again. The helpdesk stated there is a known issue with Exostar login but no solution. Their instructions were for the PI to use a link on that screen that allows for Oracle ID to be used instead. These instructions were provided but the study team has been unable to obtain a response from the PI, his assistant, or the study coordinator. Currently, the PI's voicemail indicates he is out of the office. | 2025-02-03 | 2025-02-03 | 2025-02-03 19:18 | GCP_Minor_Feb-2025_C1071015: CMCD: Investigator Attestation_Chu, Michael_CAN |  | NO |  |  | No |  |  | 2025-02-03 |  | Data Collection and Management | Inadequate source data/documentation |  |  | DMB08-Study Data Set Review Release and Archive | Seth Ferguson |  | Multiple requests to PI were made. The Inform helpdesk was contacted. Escalation was made to CSTL. |  |  | NA | Human Performance | Application Error |  | MODEL 2 - HYBRID | Oncology
QE-191787 | C1071015 | (Empty) | QE-191787 |  | PFIZER | N | Minor | Closed | Three subjects who rolled over from MM8 (China) should have been enrolled under Protocol Amendment 1, however PA1 was not available in the protocol version code list at the time of enrollment. A QE will be entered for these three subjects. | 2025-07-21 | 2025-07-22 | 2025-07-22 20:59 | GCP_Minor_Jul-2025_C1071015: CMCD: Post Production Change (PPC)_Pfizer_CHN |  | NO |  |  | No |  |  | 2025-07-22 |  | IT Systems | Inadequate system access or account management |  |  | DMB07-Study Data Set Design and Setup | Ashley Blatsioris |  | PPC opened to add PA1 to PV TRIG CRF. |  |  | NA | Human Performance | Omission Error |  | MODEL 2 - HYBRID | Oncology
QE-194650 | C1071015 | (Empty) | QE-194650 |  | PFIZER | N | Minor | Closed | C1071015 had a PPC opened to update the database CRF PV TRIG codelist and DMB07-DMB08- WI-GL03 was not followed as DM QC was not completed prior to DBA. The PPC was a minor update to a single codelist, had no impact to the SDS outside of revision history to reflect the ASB update, did not impact critical data or SDV'd data, and we believe there is no impact to safety or data integrity due to the DM QC step being missed. | 2025-08-07 | 2025-08-07 | 2025-08-08 11:56 | GCP_Minor_Aug-2025_C1071015: CMCD: Post Production Change (PPC) QC_Pfizer_Global |  | NO |  |  | No |  |  | 2025-08-08 |  | IT Systems | Inadequate IT system (eg. planning, definitions, design, development, testing, validation, support) per regulatory requirements |  |  | DMB07-Study Data Set Design and Setup | Ashley Blatsioris |  | Re-education with Quality lead |  |  | NA | Human Performance | Learning Error |  | MODEL 2 - HYBRID | Oncology
QE-196615 | C1071015 | N | QE-196615 | 1010, 1016, 1017, 1022, 1025, 1032, 1035, 1054, 1055, 1079, 1091, 1142, 1209, 1237, 1259, 1309, 1315, 1319, 86001, 86002, 86010 | Huiqiang Huang (A8081075-1016), Jian Huang (C5701003-86002), Peiying Feng (B7981118-1035), Ruihua Xu (C6461003-1054), shusen wang (A5481027-1025), shusen wang (C4251001-86002), shusen wang (C4391024-1315), shusen wang (C4551001-1055), shusen wang (C4551002-1237), shusen wang (C4891001-1010), shusen wang (C4891002-1017), shusen wang (C4891026-1079), Weidong Zhang (A5481027-1025), Yanhong Deng (C4251008-86010), Yanhong Deng (C5831001-86001), Yanhong Deng (C6461003-1142), Yanhong Deng (C6461016-1054), Yaping Yang (A5481173-1022), Yonghong Li (C2321008-1259), Yugang Dong (C4921003-1091), Zhongjun XIA (C1071005-1309), Zhongjun Xia (C1071006-1209), Zhongjun XIA (C1071007-1319), Zhongjun XIA (C1071015-1032) | N | Major | Approved - In CAPA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | 2025-08-15 | 2025-08-19 | 2026-02-02 15:09 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN |  | YES |  | <p>Description of Issue(s):</p><p>On 01 Aug 2025 while conducting a due diligence check of Investigator Weidong Zhang in China, the Due Diligence Lead received an ‘Approved’ pass through the Pfizer Restricted Party Screening (RPS) tool. At the time of the due diligence check, Investigator Zhang’s Status was ‘Available,’ so the Investigator was designated as having passed due diligence given that there were no findings. On 14 Aug 2025, a Pfizer Trade Controls Specialist advised the Due Diligence Lead that the Investigator’s affiliated institution, Sun Yat-Sen University in China, was a ‘restricted entity’ requiring an exception for the site to be used. As such, Investigator Zhang should not have been considered as having passed due diligence. Investigators Shusen Wang and Fei Xu, who also worked at Sun Yat Sen Cancer Center and had due diligence checks on 31 Jul 2025 and 01 Aug 2025, respectively, also should have failed the RPS checks and therefore the Due Diligence review.&nbsp;</p><p><br></p><p>An historical review was conducted of Quality Events in the eQMS database to identify QEs that meet the following search criteria:&nbsp;</p><p>Keywords: “restricted party,” “global trade,” “trade control”</p><p>Timeframe: 22 Nov 2023 – 29 Nov 2025</p><p>Each historical QE was reviewed along with the QE Details, Root Causes, and Corrective and Preventive Action(s). Through this review, it was concluded that the current QE (QE-196615) is not a repeat occurrence.</p><p><br></p> | Yes |  | 2026-02-13 |  |  | Quality Procedures | Requirement/process not met |  | 2026-02-17 15:07 | INV02-Investigational Site Selection, Preparation, and Initiation | Carla Moses-Bradley | FALSE | QE opened to investigate |  |  | The specificity of RPS tool search criteria used was insufficient to identify Investigator affiliation with a restricted institution resulting in multiple Investigators erroneously passing due diligence (though additional investigation later confirmed the institutions were not restricted, the institution was believed to be restricted at the time of the RPS search). Counter to the RPS OnDemand Instructions , addresses were not included in RPS tool searches, and a separate search of Investigator institutions was not completed. | Method/Procedure | Procedure/Form/Plan | Conflicting or Unclear Roles and Responsibilities (Document Standard Lacking /Incorrect Standard Content) | MODEL 2 - HYBRID | Oncology
QE-196615 | C1071015 | (Empty) | QE-196615 |  | PFIZER | N | Major | Approved - In CAPA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | 2025-08-15 | 2025-08-19 | 2026-02-02 15:09 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN |  | YES |  | <p>Description of Issue(s):</p><p>On 01 Aug 2025 while conducting a due diligence check of Investigator Weidong Zhang in China, the Due Diligence Lead received an ‘Approved’ pass through the Pfizer Restricted Party Screening (RPS) tool. At the time of the due diligence check, Investigator Zhang’s Status was ‘Available,’ so the Investigator was designated as having passed due diligence given that there were no findings. On 14 Aug 2025, a Pfizer Trade Controls Specialist advised the Due Diligence Lead that the Investigator’s affiliated institution, Sun Yat-Sen University in China, was a ‘restricted entity’ requiring an exception for the site to be used. As such, Investigator Zhang should not have been considered as having passed due diligence. Investigators Shusen Wang and Fei Xu, who also worked at Sun Yat Sen Cancer Center and had due diligence checks on 31 Jul 2025 and 01 Aug 2025, respectively, also should have failed the RPS checks and therefore the Due Diligence review.&nbsp;</p><p><br></p><p>An historical review was conducted of Quality Events in the eQMS database to identify QEs that meet the following search criteria:&nbsp;</p><p>Keywords: “restricted party,” “global trade,” “trade control”</p><p>Timeframe: 22 Nov 2023 – 29 Nov 2025</p><p>Each historical QE was reviewed along with the QE Details, Root Causes, and Corrective and Preventive Action(s). Through this review, it was concluded that the current QE (QE-196615) is not a repeat occurrence.</p><p><br></p> | Yes |  | 2026-02-13 |  |  | Quality Procedures | Requirement/process not met |  | 2026-02-17 15:07 | INV02-Investigational Site Selection, Preparation, and Initiation | Carla Moses-Bradley | FALSE | QE opened to investigate |  |  | The specificity of RPS tool search criteria used was insufficient to identify Investigator affiliation with a restricted institution resulting in multiple Investigators erroneously passing due diligence (though additional investigation later confirmed the institutions were not restricted, the institution was believed to be restricted at the time of the RPS search). Counter to the RPS OnDemand Instructions , addresses were not included in RPS tool searches, and a separate search of Investigator institutions was not completed. | Method/Procedure | Procedure/Form/Plan | Conflicting or Unclear Roles and Responsibilities (Document Standard Lacking /Incorrect Standard Content) | MODEL 2 - HYBRID | Oncology
QE-209002 | C1071015 | N | QE-209002 | 1002, 1004, 1016, 1030, 1034, 1035, 1037, 1063, 1068, 1076, 1086, 1087, 1091, 1106, 1109, 1119, 1126, 1141, 1152, 1155, 1158, 1160, 1163, 1166, 1214, 1252, 1293, 1294, 1401, 33018, 81019, 86004 | Atsuro Sawada (C5731001-81019), Ayala Hubert (C3651021-1076), Buhle Nxumalo-Toba (C4591048-1158), Camilla Thellenberg Karlsson (C3441021-1160), cheng zhou (B7981094-1152), Chia-Jen Liu (C1071015-1035), Ge Tan (C4951063-1086), George Medvedev (C4951063-1068), Grant McArthur (C4901001-1068), Heather West (C4391024-1401), Huailian Guo (C4951063-1087), Ildefonso Rodriguez Rivera (C5951001-1004), John O'Mahony (C4951063-1030), Jose luis Velasco garrido (C4531029-1109), Junzhen Gao (C4531029-1163), Laurent Greillier (C5751003-1214), Lu Li (C5751002-86004), Miroslav Stoyanov (C4921003-1034), Nan Su (C4531029-1155), Norman Lepor (C4921003-1016), Sabrina Falkowski (C5731001-33018), Sandra Basic-Kinda (C1071032-1293), Seung Soo Yoo (C5751003-1119), Soyun Cho (B7981094-1037), Steinbjoern Hansen (C2321003-1294), Takuya Shintani (C4921003-1126), Tokuya Omi (B7451031-1063), Tulio Rodriguez (C1071032-1166), Yanqiu Zhao (C5851005-1106), Yi-Tsung Lin (C5091018-1002), You Sook Cho (C4531029-1091), Yusuke Fujikawa (C4921003-1141), Zhangzhou Huang (C5751003-1252) | N | Critical | In Investigation |  Background: On 17 Oct 2025, I received a SIRIUS ticket from a Korean Site care partner. The ticket, originally submitted on 30 Sep 2025, asked why Protocol B7981094 Site 1037 did not have the latest SUSAR reports posted in their SIRIUS portal folder. Investigation Findings:The site status was “Ongoing,” but the “Send SUSAR” flag for the Principal Investigator was set to “N” (No).Normally, for ongoing sites, this flag should be “Y” (Yes), and it cannot be manually changed to “N.”This suggested a technical issue. Actions Taken:On 20 Oct 2025, I contacted the GPDIP team and submitted a ticket.On 21 Oct 2025, GPDIP confirmed that the “susar_Send” flag was “Y” in MDM and GPDIP Intermediate but not updated in GPDIP CDM.On 23 Oct 2025, GPDIP performed a “retrigger” to correct the flag for the site.On 24 Oct 2025, GPDIP provided analysis containing 30 sites with the Send SUSAR flag = Y in Siebel but incorrectly showing as N in GPDIP. Additionally, 2 sites in Siebel have the Send SUSAR flag = N and in GPDIP they show as Y. Ongoing Concerns:I requested GPDIP not to close the ticket, as a backend search is needed to see if other sites are affected.The PIs impacted have been identified but the start date of the issue impacting each PI is unknown.The data for the 32 impacted sites needs to be refreshed so the Send SUSAR flag can correctly populate in downstream systems.The Korean site missed multiple SUSAR reports, which now must be submitted late to the Principal Investigator.It is not yet known how many SUSARs have missed being reported to the impacted PIs, so it is not yet known how many reports will need to be sent to them late. Summary: This is a quality event (QE) causing SUSAR reports not to be sent to Principal Investigators. The full impact is still unclear. This issue is related to QE-200578 and QE-196243. | 2025-10-21 | 2025-10-24 | 2025-10-27 18:40 | GCP_Critical_Oct-2025_Enterprise Level: SUSAR Report Distribution_GPDIP MDM Veeva Clinical_Pfizer_Global UPGRADE |  | NO | [7 empty] | IT Systems, Safety surveillance and reporting by Sponsor | Inadequate Data Conversion / Data Migration / Data Extension / Report Configuration, Inadequate/incomplete reporting, failure/delay in reporting safety event to regulators, authorities, IRB/investigators by Pfizer |  |  | AEM01-Adverse Event Monitoring | C Anna Breen |  | The GPDIP group has been requested to investigate and verify if any other sites have set the Send SUSAR flag incorrectly. They have also been asked to report on when this issue began. The Korean DSU team has been notified that, once further information is available, they will need to send or remediate late reports outside of SIRIUS for this principal investigator. | [6 empty] | MODEL 2 - HYBRID | Oncology
QE-209002 | C1071015 | (Empty) | QE-209002 |  | PFIZER | N | Critical | In Investigation |  Background: On 17 Oct 2025, I received a SIRIUS ticket from a Korean Site care partner. The ticket, originally submitted on 30 Sep 2025, asked why Protocol B7981094 Site 1037 did not have the latest SUSAR reports posted in their SIRIUS portal folder. Investigation Findings:The site status was “Ongoing,” but the “Send SUSAR” flag for the Principal Investigator was set to “N” (No).Normally, for ongoing sites, this flag should be “Y” (Yes), and it cannot be manually changed to “N.”This suggested a technical issue. Actions Taken:On 20 Oct 2025, I contacted the GPDIP team and submitted a ticket.On 21 Oct 2025, GPDIP confirmed that the “susar_Send” flag was “Y” in MDM and GPDIP Intermediate but not updated in GPDIP CDM.On 23 Oct 2025, GPDIP performed a “retrigger” to correct the flag for the site.On 24 Oct 2025, GPDIP provided analysis containing 30 sites with the Send SUSAR flag = Y in Siebel but incorrectly showing as N in GPDIP. Additionally, 2 sites in Siebel have the Send SUSAR flag = N and in GPDIP they show as Y. Ongoing Concerns:I requested GPDIP not to close the ticket, as a backend search is needed to see if other sites are affected.The PIs impacted have been identified but the start date of the issue impacting each PI is unknown.The data for the 32 impacted sites needs to be refreshed so the Send SUSAR flag can correctly populate in downstream systems.The Korean site missed multiple SUSAR reports, which now must be submitted late to the Principal Investigator.It is not yet known how many SUSARs have missed being reported to the impacted PIs, so it is not yet known how many reports will need to be sent to them late. Summary: This is a quality event (QE) causing SUSAR reports not to be sent to Principal Investigators. The full impact is still unclear. This issue is related to QE-200578 and QE-196243. | 2025-10-21 | 2025-10-24 | 2025-10-27 18:40 | GCP_Critical_Oct-2025_Enterprise Level: SUSAR Report Distribution_GPDIP MDM Veeva Clinical_Pfizer_Global UPGRADE |  | NO | [7 empty] | IT Systems, Safety surveillance and reporting by Sponsor | Inadequate Data Conversion / Data Migration / Data Extension / Report Configuration, Inadequate/incomplete reporting, failure/delay in reporting safety event to regulators, authorities, IRB/investigators by Pfizer |  |  | AEM01-Adverse Event Monitoring | C Anna Breen |  | The GPDIP group has been requested to investigate and verify if any other sites have set the Send SUSAR flag incorrectly. They have also been asked to report on when this issue began. The Korean DSU team has been notified that, once further information is available, they will need to send or remediate late reports outside of SIRIUS for this principal investigator. | [6 empty] | MODEL 2 - HYBRID | Oncology
QE-215440 | C1071015 | (Empty) | QE-215440 |  | PFIZER, SYNEOS HEALTH LLC | N | Minor | Closed | On 26 Jun 2025 Pfizer China Sr. Clinical Operation Group Lead requested the Syneos PM to check if the Pfizer local requirement training curricula were assigned to the C1071015 study personnel. On 27 Jun 2025 Syneos PM requested to the Syneos Training Team the assignment of the Local China training curriculum to the C1071015 team. The existence of the China local training curriculum was not known to Syneos Training Team as it was not listed in the local requirement tracker that Pfizer Global Training Team maintains for reference and provides to the CRO.On 27 Jun 2025 Syneos Training Team initiated a conversation with Pfizer Global Training Team that included also Pfizer China local Training team. On 18 Jul 2025 Pfizer China Local Training team confirmed the requirement to assign all CRAs and CTMs located in China the following training curricula:Site Monitor: 9902C DC Core and 9902C DC CTM CoreClinical Trial Manager: DC Core, 9902C DC CTM Core and 9902C DC Study ManagerOn same day Pfizer China Local Training Team asked Pfizer Global Training Team to inform other CROs working in China about the same requirement and confirmed to Syneos Health the training assignment of China Local training curricula falls under the CROs assignment remit | 2025-07-18 | 2025-11-27 | 2025-12-01 15:55 | GCP_Minor_Nov-2025_Multiple Studies: Local China Training Curriculum_Syneos Health_CHN |  | NO |  |  | No |  |  | 2025-12-01 |  | Training & Qualifications | Training not completed or documented in a timely manner |  |  | QMS07-Training and Qualifications | Francesca Landolfi |  | On 18 Jul 2025 Syneos Training Team notified the Clinical Monitoring Leadership the need of additional training assignment and on 1 Aug 2025 the plan for training assignment was agreed internally at Syneos Health. On 4 Aug 2025 local China curriculum assignment started and on 5 Aug 2025 the plan for remediation was shared with Pfizer Global and China local training team. The remediation plan was composed by 2 batches of training assignments. The decision of making two separate batches for training assignment was taken for the following reasons:Significant amount of trainings were required (40 trainings for Site Monitors and 78 trainings for Clinical Trial Managers) to fill the training gap in China local trainingAt the time of issue discovery, impacted personnel was already working on clinical trials with associated deadlines and deliverablesThe issue was already ongoing for a for undetermined period of timeUpcoming summer and public Holidays in ChinaFirst Batch of training assignment was done on 4 Aug 2025 and Training assignment was completed with a second batch of training assigned on 15 Oct 2025. |  |  | NA | Human Performance | Omission Error |  | MODEL 2 - HYBRID | Oncology
QE-234134 | C1071015 | (Empty) | QE-234134 |  | SYNEOS HEALTH LLC | N | Major | In Investigation | Several gaps were identified for subcontractor approvals that were not obtained per QMS09. A total of 17 gaps were identified across 9 subcontractors that were engaged between Jul-2020 and Sep-2025, across 14 studies. The gaps fall under two main categories: “vendor approval is project specific and does not include the project” (7 instances), and “service contracted is not an approved service type for the vendor” (10 instances). Given that the root causes are portfolio-level rather than study-level, we are submitting a portfolio-level QE including all projects/vendors impacted, per the below list.C1071015 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C3651032 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C4991001 Part 2 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C4541011 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.C5001004 - Advarra Inc. (Commercial IRB/IEC): Vendor approval is project specific and does not include this project.B7451023 - Ametris (Digital Devices Bundled with Service): Vendor approval is project specific and does not include this project.C4951002 - Lionbridge Technologies LLC (Translations Services): Vendor approval is project specific and does not include this project.B7461039 - ClinPlus (Study Coordination Support Services): Service contracted is not an approved service type for this vendor.B7451031 - ICON Clinical Research Limited (Translations Services, Scales Only): Service contracted is not an approved service type for this vendor. C4541011 - HealthCarePoint.com Public Benefit Corporation (Rater Training): Service contracted is not an approved service type for this vendor.C4541011 - ICON Clinical Research Limited (Translations Services, Scales Only): Service contracted is not an approved service type for this vendor. C4951002 - Endpoint Clinical L.P. (Interactive Response Technology): Service contracted is not an approved service type for this vendor.B7471015 - ICON Clinical Research Limited (Medical Imaging - Central Reader): Service contracted is not an approved service type for this vendor.C4851001 - Marken Ltd. (Biospecimen Management): Service contracted is not an approved service type for this vendor.B7981027 - eResearch Technology (Rater Training): Service contracted is not an approved service type for this vendor.B7981028 - eResearch Technology (Rater Training): Service contracted is not an approved service type for this vendor.C4951063 - ICON Clinical Research Limited (Translations Services, Scales Only): Service contracted is not an approved service type for this vendor. | 2026-03-16 | 2026-03-17 | 2026-03-18 17:58 | GCP_Major_Mar-2026_Process/Enterprise Level: CMCD: Vendor Responsibilities: Sub-Contractor Approval_Syneos Health; Pfizer_Global |  | NO | [7 empty] | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | QMS09-Vendor Engagement | Lourdes Arnillas |  | Re-formatting of tools to ensure relevant information is included – completed 25Feb2026Rollout of a new process training across the portfolio – completed 03Mar2026Submission of subcontractor approval requests to close all 17 gaps – completed 13Mar2026Submission of this Quality Event (flagged for action on 16Mar2026) | [6 empty] | MODEL 2 - HYBRID | Oncology