## Standard_Quality_Dashboard - SQ
Case ID | Case Status | Observation ID | Obs Status | Submission Date | Issue Audit Report (Actual) | Center Number | principal investigator | Country | Description | Study ID | Protocol ID | Title Short Description | Drug Program Code | Rating | Event Type | Case CAPA Approved Due Date | Case CAPA Approved On | CAPA Plan In Place Timely | Obs CAPA Approved Due Date | Obs CAPA Approved On | Obs Target Completion Date | Obs Actual Completion Date | Case CAPA Closure Timely | Case Target Completion Date | Case Actual Completion Date | Obs CAPA Closure Timely | Selected Business Process | Taxonomy Level 1 | Taxonomy Level 2 | Study Status | Business Category | Study Phase | Study Priority | Asset | Dev China | Dev Japan | Rapid Model | Business Category
QE-188342 | Approved - In Effectiveness Check | QE-188342 | Approved - In Effectiveness Check | 2025-07-02 | (Empty) | (Empty) | PFIZER | (Empty) | RQA Process Audit of the CT05-GSOP process which occurred November 2024 highlighted as part of a major finding that the Study team Decision Log was not always being updated when new information arose which has a potential to impact the ICD on a study. CT05-GSOP specifically states “ The impact to the ICD, based on the new information, is assessed and the outcome is documented in the study’s decision log and relayed to the ICD author for possible action.” As a result of the audit, the following Corrective and Preventative actions were taken: Corrective Action – Remind study teams of the need and request they check their study team decision log to ensure documentation of the outcome of their assessment of new study information that may have an impact on a participant’s willingness to continue in the study and an impact to the study ICD has been noted in the study team decision log. Provide training and reminders to ICD authors and supportive roles in the study team (CSTA, CSTL) emphasizing the need to document the results of their assessment of new study information that may have an impact on a participant’s willingness to continue in the study and an impact to the study ICD in the study team decision log. Training and reminders include:A reminder to all those involved with the CT05 GSOP via the CT05 Newsletter, The Informed. The CT05 newsletter is distributed quarterly to those that have completed CT05 training and archived on the CT05 SP site (completed Dec 2024). Training with CT05 Office Hours. The slide included a question and answer, where the response reminded study teams of the need for the documentation in the study team decision log on the impact and actions to be taken regarding the informed consents when new study information presents that may impact participants participation occurs (completed 13 Dec 2024).Training for clinicians via the Clinical Community Connection (presentation completed on 12 Dec 2024).Reminder will be presented by Ruth Bailey during training for Vaccines Clinical Team scheduled on Friday, 17 Jan 2025 CSTAs are including a reminder for the documentation requirement in the study team decision log in their Jan newsletter (circulated at the end of January), and adding it to their TEAMS chat (before end of January).Mass mailer to be sent to those trained on CT05 reminding them of the need for the documentation in the study team decision log on the impact and actions to be taken regarding the informed consents when new study information presents that may impact participants participation occurs, and requesting they check their log and make late entries if any are missing. Estimated completion date is 24 Jan 2025. Preventive Action - The BPOs will communicate the audit finding(s) to the Process Oversight Board, and the CT05 ICD Core Team to raise awareness. Additional preventive activities include: Protocol Feasibility Committee and Pfizer Oncology Division protocol governance have added or will be adding a reminder statement to their Summary of Changes document which is requested with amendment submissions. Example of the reminder “Please note the decision to update or not to update the ICD must be documented in the study decision log as per CT05 GSOP.”The SToD guidance will be updated by Hongyan and CSTA team to specifically call out ICDs (and PAs) to remind study teams of the need for the documentation in the study team decision log on the impact and actions to be taken regarding the informed consents when new study information presents that may impact participants participation occurs (Planned for end of Feb)Responses to CMCD queries by the CT05 BPOs, Process Lead and /or Process and Procedural Document Specialist that are relevant to this matter will include a reminder to document their decision in the study team decision log. An Effectiveness check was also put in place but this check was not successful: Method: A sample of approximately 15 studies with amendments will have their study team decision spot checked for completion of the documentation. Criteria/Threshold for Success: The EC will be deemed successful if 100% of the sample demonstrates 100% compliance with documentation. The Effectiveness was broadened to include 60 studies. Of the 60 studies reviewed, 27 had the information added to their STDL with 8 studies not being applicable as these studies fall under ClinPharm. For all other studies, this information has now been updated retrospectively in their STDL except one study ( C4761001). The clinician is no longer with Pfizer and there is no confirmed date of the assessment occurring although the ICD itself was updated. As the Effectiveness check was not met, CT05-GSOP is now required to submit a QE. | C2321008 | C2321008 | GCP_Major_Jul-2025_Multiple: ICD Updates and Decision Log Entries_Pfizer_Global | C232 | Major | SQE | 2025-08-16 | 2026-02-04 | N | 2025-08-16 | 2026-02-04 22:59 | (Empty) | 2025-11-21 | (Empty) | (Empty) | 2025-11-21 | (Empty) | CT48 - Study Operational Management | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1010 | shusen wang (C4891001-1010) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1016 | Huiqiang Huang (A8081075-1016) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1017 | shusen wang (C4891002-1017) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1022 | Yaping Yang (A5481173-1022) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1025 | shusen wang (A5481027-1025) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1025 | Weidong Zhang (A5481027-1025) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1032 | Zhongjun XIA (C1071015-1032) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1035 | Peiying Feng (B7981118-1035) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1054 | Ruihua Xu (C6461003-1054) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1054 | Yanhong Deng (C6461016-1054) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1055 | shusen wang (C4551001-1055) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1079 | shusen wang (C4891026-1079) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1091 | Yugang Dong (C4921003-1091) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1142 | Yanhong Deng (C6461003-1142) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1209 | Zhongjun Xia (C1071006-1209) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1237 | shusen wang (C4551002-1237) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1259 | Yonghong Li (C2321008-1259) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1309 | Zhongjun XIA (C1071005-1309) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1315 | shusen wang (C4391024-1315) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 1319 | Zhongjun XIA (C1071007-1319) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 86001 | Yanhong Deng (C5831001-86001) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 86002 | Jian Huang (C5701003-86002) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 86002 | shusen wang (C4251001-86002) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | 86010 | Yanhong Deng (C4251008-86010) | CHINA | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-196615 | Approved - In CAPA | QE-196615 | Approved - In CAPA | 2025-08-19 | (Empty) | (Empty) | PFIZER | (Empty) | Weidong Zhang CCTR ID 390542 is affiliated with a site at Sun Yat-Sen University, China. He is currently Available in CTMS. He is currently associated with one study that is "completed" but not yet closed. DD for this study/site was automatically triggered from Siebel to Centaur- for Perpetual Due Diligence.Due Diligence was completed for Weidong Zhang on 01AUG2025. He was "approved" by RPS (the Restricted Party Screening tool) and there were no findings. On 14AUG2025, we were advised with an email from RPS, specifically, Bob Cal, Trade Controls Specialist to advise: From: Cal, Bob &lt;.Cal@pfizer.com"Bob.Cal@pfizer.com&gt; Sent: 14 August 2025 22:18 To: Poffley, Thomas &lt;.Poffley@pfizer.com"Thomas.Poffley@pfizer.com&gt; Cc: Restricted Party Screening &lt;.com"RestrictedPartyScreening@pfizer.com&gt; Subject: RPS on Demand Request: Weidong Zhang Hello Thomas,I see that you submitted a RPS on Demand request Weidong Zhang (POFFLT20250731092921/ 5607519). Zhang Weidong is affiliated with Sun Yat Sen University, which is matching to a Restricted Party. There is a current exception process in place where the below statement must be confirmed before transactions with this BP can take place: "If the business is willing to accept any risks in engaging with thisbusiness partner, please confirm that no U.S. origin product ortechnology will be shared with the HCP or the University and that theonly engagement is to provide payment for services provided by the HCP”. Once a confirmation has been provided, then the transaction (payment, PO, sales order) can be approved on our side. This BP will be blocked on our end. Note: Due Diligence was completed 01AUG2025 for Shusen Wang (PI) and 10JUL2025 for Fei Xu (SubI) at the same study/site and other studies/sites with no similar notification from RPS. I have emailed RPS to further inquire about the status of these 2 investigators. Response pending | C2321008 | C2321008 | GCP_Major_Aug-2025_A5481027: Investigator Availability Status_Multiple Investigators; Sun Yat-Sen University_Pfizer_CHN | C232 | Major | SQE | 2026-02-13 | 2026-02-17 | N | 2026-02-13 | 2026-02-17 15:07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-222180 | In Investigation | QE-222180 | In Investigation | 2026-01-09 | (Empty) | (Empty) | NPHASE INC (REDCAP CLOUD) | (Empty) | We are raising this event to please request that the minor assessment for QE-219754 be reconsidered. To again summarize the what occured, a legitimate query was raised in the C4601019 study by our medical monitor. However in RCC this query changed to a different user name and role (LabTech). That different user is a real person at Pfizer, but they never requested access to C4601019 and they are not on our Site User Report. This user does not have access to the C4601019 study in RCC, as confirmed by the RCC Admin team's review of the study's audit logs. Further, the Lab Tech role does NOT have access to issue a query in RCC. As a result, the RCC system does not clearly link back to user who issued the query, which we believe violates FDA guidance per CFR 21 Part 11, likely with guidance from EMA and other regulators similarly breached. When this QE was initally submitted, there were 3 such known issues across 2 RCC studies. There are now 9 known issues across 6 RCC studies. | C2321008 | C2321008 | GCP_Major_Jan-2026_System/Enterprise Level_System Access Controls Redcap Cloud (RCC): Broader Issue_Pfizer; NPHASE INC (REDCAP CLOUD)_Global | C232 | Major | SQE | 2026-02-26 | (Empty) | N | 2026-02-26 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CP403 - Acceptable Use of Information | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-222180 | In Investigation | QE-222180 | In Investigation | 2026-01-09 | (Empty) | (Empty) | PFIZER | (Empty) | We are raising this event to please request that the minor assessment for QE-219754 be reconsidered. To again summarize the what occured, a legitimate query was raised in the C4601019 study by our medical monitor. However in RCC this query changed to a different user name and role (LabTech). That different user is a real person at Pfizer, but they never requested access to C4601019 and they are not on our Site User Report. This user does not have access to the C4601019 study in RCC, as confirmed by the RCC Admin team's review of the study's audit logs. Further, the Lab Tech role does NOT have access to issue a query in RCC. As a result, the RCC system does not clearly link back to user who issued the query, which we believe violates FDA guidance per CFR 21 Part 11, likely with guidance from EMA and other regulators similarly breached. When this QE was initally submitted, there were 3 such known issues across 2 RCC studies. There are now 9 known issues across 6 RCC studies. | C2321008 | C2321008 | GCP_Major_Jan-2026_System/Enterprise Level_System Access Controls Redcap Cloud (RCC): Broader Issue_Pfizer; NPHASE INC (REDCAP CLOUD)_Global | C232 | Major | SQE | 2026-02-26 | (Empty) | N | 2026-02-26 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CP403 - Acceptable Use of Information | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-224942 | In Investigation | QE-224942 | In Investigation | 2026-01-27 | (Empty) | (Empty) | PFIZER | (Empty) | This event relates to sync issues involving Pfizer Siebel to Reltio resulting in missing sites from SIRIUS through a Dynatrace relate which never appeared on the Business Continuity Plan (BCP) put in place post Veeva CTMS issues.A new QE has been raised per management request due to a potential different cause separate from the existing Veeva CTMS issues impacting SUSARs downstream (QE-169243, QE-209002, QE-212408)(T. Houck) UPDATED to the following per instruction from submitter on 28 Jan 2026:This event relates to sync issues involving Pfizer Siebel to Reltio resulting in missing sites from SIRIUS which never appeared on the Business Continuity Plan (BCP) put in place post Veeva CTMS issues.A new QE has been raised per management request due to a potential different cause separate from the existing Veeva CTMS issues impacting SUSARs downstream (QE-169243, QE-209002, QE-212408) | C2321008 | C2321008 | GCP_Major_Jan-2026_Multiple Protocols: System-Level, CTMS / GPD IP Business Continuity Plan (BCP) and SIRIUS Reporting_Pfizer_Global | C232 | Major | SQE | 2026-03-14 | (Empty) | N | 2026-03-14 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | AEM01 - Adverse Event Monitoring | Safety surveillance and reporting by Sponsor | Inadequate/incomplete reporting, failure/delay in reporting safety event to regulators, authorities, IRB/investigators by Pfizer | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-234307 | In Investigation | QE-234307 | In Investigation | 2026-03-18 | (Empty) | 1018 | EFRAT BROIDE (C5041018-1018) | ISRAEL | Cyber attack reported at Shamir Medical Center in Israel | C2321008 | C2321008 | GCP_Major_Mar-2026_Multiple Protocols: Cyber Security Incident_Shamir Medical Center_ISR | C232 | Major | SQE | 2026-05-02 | (Empty) | (Empty) | 2026-05-02 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CP411 - Information Incident Response Policy | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-234307 | In Investigation | QE-234307 | In Investigation | 2026-03-18 | (Empty) | 1195 | Carmell Fink (C5851005-1195) | ISRAEL | Cyber attack reported at Shamir Medical Center in Israel | C2321008 | C2321008 | GCP_Major_Mar-2026_Multiple Protocols: Cyber Security Incident_Shamir Medical Center_ISR | C232 | Major | SQE | 2026-05-02 | (Empty) | (Empty) | 2026-05-02 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CP411 - Information Incident Response Policy | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-234307 | In Investigation | QE-234307 | In Investigation | 2026-03-18 | (Empty) | 1330 | Raya Leibowitz (C2321008-1330) | ISRAEL | Cyber attack reported at Shamir Medical Center in Israel | C2321008 | C2321008 | GCP_Major_Mar-2026_Multiple Protocols: Cyber Security Incident_Shamir Medical Center_ISR | C232 | Major | SQE | 2026-05-02 | (Empty) | (Empty) | 2026-05-02 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CP411 - Information Incident Response Policy | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology
QE-234307 | In Investigation | QE-234307 | In Investigation | 2026-03-18 | (Empty) | 1403 | Carmell Fink (C6461001-1403) | ISRAEL | Cyber attack reported at Shamir Medical Center in Israel | C2321008 | C2321008 | GCP_Major_Mar-2026_Multiple Protocols: Cyber Security Incident_Shamir Medical Center_ISR | C232 | Major | SQE | 2026-05-02 | (Empty) | (Empty) | 2026-05-02 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CP411 - Information Incident Response Policy | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) | ONGOING | Oncology | PHASE III | ACCELERATE | EZH2 +Xtandi 1L mCSPC | China Global | JP_Global | MODEL 1 - INSOURCED | Oncology