## Standard_Quality_Dashboard - QE
Observation ID | Study ID | Targeted | PR ID | Site(s) | principal Investigator | EX Comp? | QE Threshold | Status | Observation Description (as submitted) | Awareness Date | Submission Date | Assessment Date | Title/Short Description | Business CAPA Plan Endorsed On | CAPA Plan in Place | Last Action Due Date | Investigation Summary and Conclusion | Effectiveness Check Required | Effectiveness Check Rationale | Investigation Completion Date | Closed On | PDAL Decision | Level 1 | Level 2 | Quality CAPA Plan Endorsed On | Quality Reviewer Approved On | Business Process | Submitter | Confirmed Serious Breach | Remediation Actions Taken (when QE was submitted) | CAPA Action Details | CAPA Action Owner | Root Cause Description | Root Cause Level 1 | Root Cause Level 2 | Root Cause Level 3 | Rapid Model | Business Category
QE-164348 | C3671058 | (Empty) | QE-164348 |  | PFIZER | N | Minor | Closed | Study C3671058 Site 1034/Newberg site selection letter was sent and FSSF completed while no due diligence was on file. | 2025-01-29 | 2025-02-10 | 2025-02-13 15:05 | GCP_Minor_Feb-2025_C3671058: Investigator Due Diligence_Pfizer_USA |  | NO |  |  | No |  |  | 2025-02-13 |  | Quality Procedures | Requirement/process not met |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Erin Palm |  | As soon as the discrepancy was found, Feasibility team reached out to SIS for the completion of due diligence. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-178439 | C3671058 | N | QE-178439 | 1046 | Samar Hameed (C3671058-1046) | N | Minor | Closed | All subjects screened (10461001-10461013) for the study were not provided and did not sign the IRB approved VCT Authorization form. Site was trained on VCT during SIV and IM meeting. | 2025-05-06 | 2025-05-07 | 2025-05-07 18:28 | GCP_Minor_May-2025_C3671058: Verified Clinical Trials (VCT) Authorization Form_Hameed, Samar_USA |  | NO |  |  | No |  |  | 2025-05-07 |  | Informed Consent | Inadequate consent process at the investigator site |  |  | CT05-Informed Consent Document | Ciara Chacon |  | Site Monitor re-educated the site staff during on-site MV conducted on 06May2025. Site was instructed to have subjects returning for V2 visits to sign the VCT authorization form and document the erroneous error. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-178655 | C3671058 | N | QE-178655 | 1037 | David DeAtkine (C3671058-1037) | N | Minor | Closed | Subject 10371008 was taking a Immunosuppressive/Cytotoxic medication for an existing medical issue that was overlooked during the screening and enrollment. Subject was enrolled in the study and was dosed with the study IP. | 2025-04-30 | 2025-05-08 | 2025-05-08 20:02 | GCP_Minor_May-2025_C3671058: CMCD: Protocol Deviation: Inclusion / Exclusion Criteria_DeAtkine, David_USA |  | NO |  |  | No |  |  | 2025-05-08 |  | Protocol Deviations | Failure to comply with protocol inclusion/exclusion criteria |  |  | CT40-Management of Protocol Deviations | Mehrzad Khodavandi |  | Site discontinued the subject from the study after the clinician's feedback. A Protocol Deviation was submitted to IRB and was entered in CTMS as well. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-178655 | C3671058 | (Empty) | QE-178655 |  |  | N | Minor | Closed | Subject 10371008 was taking a Immunosuppressive/Cytotoxic medication for an existing medical issue that was overlooked during the screening and enrollment. Subject was enrolled in the study and was dosed with the study IP. | 2025-04-30 | 2025-05-08 | 2025-05-08 20:02 | GCP_Minor_May-2025_C3671058: CMCD: Protocol Deviation: Inclusion / Exclusion Criteria_DeAtkine, David_USA |  | NO |  |  | No |  |  | 2025-05-08 |  | Protocol Deviations | Failure to comply with protocol inclusion/exclusion criteria |  |  | CT40-Management of Protocol Deviations | Mehrzad Khodavandi |  | Site discontinued the subject from the study after the clinician's feedback. A Protocol Deviation was submitted to IRB and was entered in CTMS as well. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-180099 | C3671058 | N | QE-180099 | 1041 | Abid Chaudhry (C3671058-1041) | N | Minor | Closed | Site 1041 completed the Verified Clinical Trials (VCT) verification process with the first two participants at FSFV. One participant signed the Main study ICD and the second participant did not complete the Main study ICD. The site uses electronic source CRFs and terminated the study visits when the site staff discovered that source was not available to complete the visit. At the time the site terminated the study visits, the site did not register the participants in IRT, an SSID was not generated for IRT or InForm EDC for the two participants. | 2025-05-15 | 2025-05-16 | 2025-05-16 14:32 | GCP_Minor_May-2025_C3671058: Participant Registration_Chaudhry, Abid_USA |  | NO |  |  | No |  |  | 2025-05-16 |  | Protocol Deviations | Failure to follow protocol |  |  | CT40-Management of Protocol Deviations | Ezinna Anosike |  | Site instructed to submit a DCR to IRT to create SSIDs for the subjects. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-182028 | C3671058 | N | QE-182028 | 1017 | Patrick Dennis (C3671058-1017) | N | Minor | Closed | Site used incorrect cryovial for sample collection for 7 subjects. A total of 28 samples were sent in the wrong cryovials. | 2025-05-21 | 2025-05-28 | 2025-05-28 17:36 | GCP_Minor_May-2025_C3671058: Sample Collection_Dennis, Patrick_USA |  | NO |  |  | No |  |  | 2025-05-28 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | No Process Assigned | Diandra Browne |  | After TruLab notified sponsor team of incorrect supplies. Site reviewed to ensure that correct samples were sent to the lab despite being placed into the incorrect cryovials. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-182295 | C3671058 | (Empty) | QE-182295 |  | PFIZER | N | Minor | Closed | Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | 2025-04-28 | 2025-05-29 | 2025-05-30 14:58 | GCP_Minor_May-2025_C3671058, C6271001: Sample Collection Data_Pfizer_USA |  | NO |  |  | No |  |  | 2025-05-30 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | No Process Assigned | Amber Haugeto |  | Summary of data discrepancies generated for each study via Dashboard downloads, FMS-Vax team consulted by Study Managers/VRD SLS reps, Laboratory Manuals and Investigator meeting training materials reviewed for accuracy. Sites demonstrating discrepant data capture requested to assess whether they have supporting documentation to generate Data Change tickets with TruLab. For discrepant sites that do not have additional source documentation to support collection and aliquot times, requested that sites prepare Note to File memos confirming proper sample processing per laboratory manual, noting any samples that were improperly processed, and outlining steps taken to re-educate staff on proper ‘real-time’ use of the TruLab app during biospecimen collection. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-182467 | C3671058 | N | QE-182467 | 1001, 1006, 1008, 1015, 1017, 1019, 1024, 1025, 1027, 1028, 1032, 1033, 1035, 1037, 1040, 1043, 1055, 1061, 1062 | Alejandro DeLaCruz (C3671058-1015), Alton Walters (C6271001-1001), Barton Williams (C6271001-1027), Christopher Romero (C6271001-1035), Daniel Brune (C3671058-1040), David DeAtkine (C3671058-1037), Harry Studdard (C3671058-1043), James Clark (C6271001-1006), Jose Cardona (C6271001-1019), Joseph Surber (C3671058-1024), Orlando Puente (C6271001-1008), Patrick Dennis (C3671058-1017), Sridhar Guduri (C3671058-1055), Sridhar Guduri (C6271001-1025), Stacey Layle (C6271001-1033), Stephan Sharp (C6271001-1028), Timothy Jennings (C3671058-1062), Timothy Jennings (C6271001-1032), William Towner (C3671058-1061) | N | Major | Approved - In CAPA | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | 2025-04-28 | 2025-05-30 | 2025-05-30 19:53 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA |  | YES |  | <p>It was reported on 30 May 2025 that multiple sites on protocols C6271001 and C3671058 were not utilizing the TruLab Application (App) in real time while processing study participant lab samples. This issue was identified by site facing study team members during review of sample processing data as part of the routine monitoring and oversight activities for protocols C6271001 and C3671058. &nbsp;The study team for C4851001 became aware of impact to C4851001 for the same issue via the Quality Event Awareness Notification sent on 02 Jun 2025.&nbsp;</p><p>&nbsp;</p><p>The TruLab App is a mobile-based data capture application for biospecimens that eliminates the need to capture sample collection information in the Electronic Sample Tracking Case Report Form (CRF). &nbsp;Information related to the samples and sample tracking is available in data transfers from the TruLab vendor and via site-facing dashboards. &nbsp;The TruLab mobile devices were employed at sites for the impacted protocols and users were instructed to utilize the application as source data for participant sample collection and processing. &nbsp;</p><p><br></p><p>The non-contemporaneous use of the TruLab Application by site users impacted the data integrity of the corresponding samples, as the data was not aligned with the protocol required sample processing procedures. The total samples impacted per study, where no other source for sample processing data existed is as follows: 3.5% of samples for protocol C3671058, 1% of samples for protocol C6271001 and no samples for C4851001.</p><p><br></p><p>An historical review was conducted of Quality Events (QEs) in the eQMS database to identify QEs that meet the following search criteria:&nbsp;</p><ul><li>Keywords: Sample</li><li>Timeframe: 2 years; 01 Jun 2023 – 19 Nov 2025</li></ul><p>Each historical QE was reviewed along with the QE Details, Root Causes, and Corrective and Preventive Action(s). Through this review, it was concluded that the current QE (QE-182467) is not a repeat occurrence. &nbsp;</p><p><br></p> | Yes |  | 2025-11-20 |  |  | Equipment, Facility and Sample/Specimens, Quality Oversight | Inadequate or incorrect test performance/analysis, Inadequate Principal Investigator quality oversight |  | 2025-11-21 17:21 | CT29-Management of Clinical Study BioSpecimens, QMS09-Vendor Engagement | Amber Haugeto | FALSE | Summary of data discrepancies generated for each study via Dashboard downloads, FMS-Vax team consulted by Study Managers/VRD SLS reps, Laboratory Manuals and Investigator meeting training materials reviewed for accuracy. Sites demonstrating discrepant data capture requested to assess whether they have supporting documentation to generate Data Change tickets with TruLab. For discrepant sites that do not have additional source documentation to support collection and aliquot times, requested that sites prepare Note to File memos confirming proper sample processing per laboratory manual, noting any samples that were improperly processed, and outlining steps taken to re-educate staff on proper ‘real-time’ use of the TruLab app during biospecimen collection. |  |  | Some site laboratory personnel are utilizing the TruLab Application to scan sample collection tubes and/or aliquots in bulk either prior to or following processing of laboratory samples, rather than as each processing step is completed, as required by protocol. &nbsp;The training provided to site users for this new technology did not adequately outline the requirement to use this new technology in real time.&nbsp;, The Study Monitoring Plan (SMP) requirements for review of TruLab data by the monitoring team, in combination with the rate of enrolment per site and time between first subject visit and first on site monitoring visit prevented the timely detection that sites were not utilizing TruLab in real time for sample processing. | Human Performance, Method/Procedure | Inconsistency Error, Procedure/Form/Plan | Inconsistent with Pfizer Requirements (Document Standard Lacking/Incorrect Standard Content), Lack of or Inadequate Review and Approval (Document Standard Lacking/Incorrect Standard Content) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | C3671058 | Y | QE-182467 | 1003, 1056 | David Fitz-Patrick (C6271001-1003), Lisa Usdan (C3671058-1056) | N | Major | Approved - In CAPA | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | 2025-04-28 | 2025-05-30 | 2025-05-30 19:53 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA |  | YES |  | <p>It was reported on 30 May 2025 that multiple sites on protocols C6271001 and C3671058 were not utilizing the TruLab Application (App) in real time while processing study participant lab samples. This issue was identified by site facing study team members during review of sample processing data as part of the routine monitoring and oversight activities for protocols C6271001 and C3671058. &nbsp;The study team for C4851001 became aware of impact to C4851001 for the same issue via the Quality Event Awareness Notification sent on 02 Jun 2025.&nbsp;</p><p>&nbsp;</p><p>The TruLab App is a mobile-based data capture application for biospecimens that eliminates the need to capture sample collection information in the Electronic Sample Tracking Case Report Form (CRF). &nbsp;Information related to the samples and sample tracking is available in data transfers from the TruLab vendor and via site-facing dashboards. &nbsp;The TruLab mobile devices were employed at sites for the impacted protocols and users were instructed to utilize the application as source data for participant sample collection and processing. &nbsp;</p><p><br></p><p>The non-contemporaneous use of the TruLab Application by site users impacted the data integrity of the corresponding samples, as the data was not aligned with the protocol required sample processing procedures. The total samples impacted per study, where no other source for sample processing data existed is as follows: 3.5% of samples for protocol C3671058, 1% of samples for protocol C6271001 and no samples for C4851001.</p><p><br></p><p>An historical review was conducted of Quality Events (QEs) in the eQMS database to identify QEs that meet the following search criteria:&nbsp;</p><ul><li>Keywords: Sample</li><li>Timeframe: 2 years; 01 Jun 2023 – 19 Nov 2025</li></ul><p>Each historical QE was reviewed along with the QE Details, Root Causes, and Corrective and Preventive Action(s). Through this review, it was concluded that the current QE (QE-182467) is not a repeat occurrence. &nbsp;</p><p><br></p> | Yes |  | 2025-11-20 |  |  | Equipment, Facility and Sample/Specimens, Quality Oversight | Inadequate or incorrect test performance/analysis, Inadequate Principal Investigator quality oversight |  | 2025-11-21 17:21 | CT29-Management of Clinical Study BioSpecimens, QMS09-Vendor Engagement | Amber Haugeto | FALSE | Summary of data discrepancies generated for each study via Dashboard downloads, FMS-Vax team consulted by Study Managers/VRD SLS reps, Laboratory Manuals and Investigator meeting training materials reviewed for accuracy. Sites demonstrating discrepant data capture requested to assess whether they have supporting documentation to generate Data Change tickets with TruLab. For discrepant sites that do not have additional source documentation to support collection and aliquot times, requested that sites prepare Note to File memos confirming proper sample processing per laboratory manual, noting any samples that were improperly processed, and outlining steps taken to re-educate staff on proper ‘real-time’ use of the TruLab app during biospecimen collection. |  |  | Some site laboratory personnel are utilizing the TruLab Application to scan sample collection tubes and/or aliquots in bulk either prior to or following processing of laboratory samples, rather than as each processing step is completed, as required by protocol. &nbsp;The training provided to site users for this new technology did not adequately outline the requirement to use this new technology in real time.&nbsp;, The Study Monitoring Plan (SMP) requirements for review of TruLab data by the monitoring team, in combination with the rate of enrolment per site and time between first subject visit and first on site monitoring visit prevented the timely detection that sites were not utilizing TruLab in real time for sample processing. | Human Performance, Method/Procedure | Inconsistency Error, Procedure/Form/Plan | Inconsistent with Pfizer Requirements (Document Standard Lacking/Incorrect Standard Content), Lack of or Inadequate Review and Approval (Document Standard Lacking/Incorrect Standard Content) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | C3671058 | (Empty) | QE-182467 |  | PFIZER, TRULAB INC | N | Major | Approved - In CAPA | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | 2025-04-28 | 2025-05-30 | 2025-05-30 19:53 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA |  | YES |  | <p>It was reported on 30 May 2025 that multiple sites on protocols C6271001 and C3671058 were not utilizing the TruLab Application (App) in real time while processing study participant lab samples. This issue was identified by site facing study team members during review of sample processing data as part of the routine monitoring and oversight activities for protocols C6271001 and C3671058. &nbsp;The study team for C4851001 became aware of impact to C4851001 for the same issue via the Quality Event Awareness Notification sent on 02 Jun 2025.&nbsp;</p><p>&nbsp;</p><p>The TruLab App is a mobile-based data capture application for biospecimens that eliminates the need to capture sample collection information in the Electronic Sample Tracking Case Report Form (CRF). &nbsp;Information related to the samples and sample tracking is available in data transfers from the TruLab vendor and via site-facing dashboards. &nbsp;The TruLab mobile devices were employed at sites for the impacted protocols and users were instructed to utilize the application as source data for participant sample collection and processing. &nbsp;</p><p><br></p><p>The non-contemporaneous use of the TruLab Application by site users impacted the data integrity of the corresponding samples, as the data was not aligned with the protocol required sample processing procedures. The total samples impacted per study, where no other source for sample processing data existed is as follows: 3.5% of samples for protocol C3671058, 1% of samples for protocol C6271001 and no samples for C4851001.</p><p><br></p><p>An historical review was conducted of Quality Events (QEs) in the eQMS database to identify QEs that meet the following search criteria:&nbsp;</p><ul><li>Keywords: Sample</li><li>Timeframe: 2 years; 01 Jun 2023 – 19 Nov 2025</li></ul><p>Each historical QE was reviewed along with the QE Details, Root Causes, and Corrective and Preventive Action(s). Through this review, it was concluded that the current QE (QE-182467) is not a repeat occurrence. &nbsp;</p><p><br></p> | Yes |  | 2025-11-20 |  |  | Equipment, Facility and Sample/Specimens, Quality Oversight | Inadequate or incorrect test performance/analysis, Inadequate Principal Investigator quality oversight |  | 2025-11-21 17:21 | CT29-Management of Clinical Study BioSpecimens, QMS09-Vendor Engagement | Amber Haugeto | FALSE | Summary of data discrepancies generated for each study via Dashboard downloads, FMS-Vax team consulted by Study Managers/VRD SLS reps, Laboratory Manuals and Investigator meeting training materials reviewed for accuracy. Sites demonstrating discrepant data capture requested to assess whether they have supporting documentation to generate Data Change tickets with TruLab. For discrepant sites that do not have additional source documentation to support collection and aliquot times, requested that sites prepare Note to File memos confirming proper sample processing per laboratory manual, noting any samples that were improperly processed, and outlining steps taken to re-educate staff on proper ‘real-time’ use of the TruLab app during biospecimen collection. |  |  | Some site laboratory personnel are utilizing the TruLab Application to scan sample collection tubes and/or aliquots in bulk either prior to or following processing of laboratory samples, rather than as each processing step is completed, as required by protocol. &nbsp;The training provided to site users for this new technology did not adequately outline the requirement to use this new technology in real time.&nbsp;, The Study Monitoring Plan (SMP) requirements for review of TruLab data by the monitoring team, in combination with the rate of enrolment per site and time between first subject visit and first on site monitoring visit prevented the timely detection that sites were not utilizing TruLab in real time for sample processing. | Human Performance, Method/Procedure | Inconsistency Error, Procedure/Form/Plan | Inconsistent with Pfizer Requirements (Document Standard Lacking/Incorrect Standard Content), Lack of or Inadequate Review and Approval (Document Standard Lacking/Incorrect Standard Content) | MODEL 1 - INSOURCED | Vaccines
QE-186049 | C3671058 | N | QE-186049 | 1015 | Alejandro DeLaCruz (C3671058-1015) | N | Minor | Closed | Sub-I completed task for which they were not delegated. | 2025-06-17 | 2025-06-20 | 2025-06-23 16:32 | GCP_Minor_Jun-2025_C3671058: Delegation of Duties; Training_DeLaCruz, Alejandro_USA |  | NO |  |  | No |  |  | 2025-06-23 |  | Training & Qualifications | Personnel inadequately trained to perform their assigned job function |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Diandra Browne |  | PI has updated the SSDDL to reflect the delegation of task to sub-I. Site has documented issue in an NTF. Monitor verified sub-I training, for IP handling, was completed on 9APR2025 |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Vaccines
QE-187977 | C3671058 | N | QE-187977 | 1025 | Sarah Freeman (C6271001-1025), Sridhar Guduri (C6271001-1025) | N | Critical | Closed | Departing Study Coordinator (last day 02Jul2025) raised the following concerns to the SCP and Site Monitor during the onsite visit which occurred 26Jun2025: Site Management requesting blinded site staff to perform unblinded study tasks, Site Management requesting site staff to not process subject payments, indications that Site Network may be experiencing significant financial challenges. | 2025-06-26 | 2025-07-01 | 2025-07-01 16:20 | GCP_Critical_Jul-2025_C6271001, C3671058: Potential Allegation, PI Oversight_Guduri, Sridhar, Freeman, Sarah_USA PRIVILEDGED AND CONFIDENTIAL |  | YES |  | <p><br></p><p>On 26-Jun-2025, during a routine monitoring visit, the Pfizer Site Care Partner (SCP) and Clinical Research Associate (CRA) received an unsolicited comment from a Clinical Research Coordinator (CRC), SS, raising concerns about practices at the site. &nbsp;The CRC (SS) had resigned the site as of 02-Jul-2025, but noted:</p><p>&nbsp;</p><ul><li>Unblinded activities: CRC reported that the site manager (SF) had requested that blinded staff perform unblinded tasks for protocol C6271001</li><li>Participant reimbursement: CRC reported that the site manager (SF) had requested staff to withhold participant reimbursements from study participants.&nbsp;</li></ul><p>&nbsp;</p><p>A Due Diligence investigation was conducted via a non-routine RQA Audit for C6271001 from 25-27 Aug-2025. The audit was unable to substantiate the allegations.&nbsp;</p><p>&nbsp;</p><p>During the QE investigation, an additional issue was identified for Principal Investigator (PI) Guduri pertaining to site conduct for protocol C3671058. &nbsp;The SCP and CRA identified during monitoring visits conducted in July 2025 that multiple Adverse events (AEs) and Medical History events were recorded in the site source documentation but not present in the electronic Case Report Form (eCRF). &nbsp; In addition, oversight of participant e-diary, source documentation practices and PI signature contemporaneity was not maintained per Good Clinical Practice (GCP) requirements. &nbsp;</p> | No | Study/Program/Activity ended and issue does not impact other studies/programs/activities | 2025-10-10 | 2025-11-25 |  | Potential allegation of Falsification or misconduct, Quality Oversight | Inadequate Principal Investigator quality oversight, Potential allegation of Scientific fraud, falsification or misconduct |  | 2025-10-10 19:23 | No Process Assigned | Anna Murad | FALSE | SCP escalated to DSMM. |  |  | Due Diligence, Site management change at the Columbus Centricity clinical site has resulted in staff turnover of both Sub-investigators and study coordinators. &nbsp;New staff have been added to the site team that have less experience in conducting clinical trials and are less familiar with GCP and ALCOA+ requirements. | Due Diligence, Personnel | N/A, Turnover/Attrition | N/A, Turnover/Attrition | MODEL 1 - INSOURCED | Vaccines
QE-188294 | C3671058 | N | QE-188294 | 1025, 1055 | Sridhar Guduri (C3671058-1055), Sridhar Guduri (C6271001-1025) | N | Minor | Closed | Subject 10251044 on C6271001 reported an SAE (Case ID: 1353068) to the site on 30Jun2025. Site submitted the initial SAE report via PSSA on 02Jul2025.Subject 10551028 on C3671058 reported an SAE (Case ID: 1353846) to the site on 30Jun2025. Site submitted the initial SAE report via PSSA on 02Jul2025. | 2025-07-02 | 2025-07-02 | 2025-07-02 15:38 | GCP_Minor_ Jul-2025_C6271001; C3671058: SAE Reporting_Guduri, Sridhar_USA |  | NO |  |  | No |  |  | 2025-07-02 |  | AE reporting to Sponsor | Delayed SAE reporting |  |  | AEM01-Adverse Event Monitoring | Anna Murad |  | SCP instructed the site to contact PSSA HelpDesk. PSSA HelpDesk confirmed there were no access issues. When site staff logged in on 02Jul2025 AM, they were able to access and submit the report. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-188341 | C3671058 | N | QE-188341 | 1034 | Joseph Newberg (C3671058-1034) | N | Minor | Closed | C3671058 site 1034, PI Joseph Newberg - numerous documentation quality issues have been noted. As of 02July25, the site has accumulated a large volume of InForm CRF queries which lists the site as a particular outlier relative to other sites i.e. 332 queries raised to date (18.9 queries per subject) in comparison to the next highest queried site with 179 queries (5.8 queries per subject). The site has flagged in Central monitoring outputs as accumulating a high number of SAEs (2) and has failed to resolve SAE related queries appropriately and within expected timelines within InForm and PSSA, hence the majority of InForm queries are in relation to the 10341006 SAE . Additionally it has been noted that of the SAE narrative reported 10Jun25 (subject 10341006), despite being reported on time, this narrative has revealed 15 medical histories which was not previously transcribed into the InForm CRF by site. | 2025-07-02 | 2025-07-02 | 2025-07-02 18:47 | GCP_Minor_Jul-2025_C3671058: CMCD: Data Entry Timeliness; Site Documentation Quality_Newberg, Joseph_USA |  | NO |  |  | No |  |  | 2025-07-02 |  | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry |  |  | INV04-Investigational Site Management and Monitoring | Shaun Godwin |  | Training records indicate site staff have completed required training for study specific InForm data entry &amp; Protocol Specific training. A teleconference with the C3671058 study team has been completed with the PI and site staff 09June25 to explain Pfizer requirements and queries relating to the SAE reported 10Jun25. Onsite monitoring visits and Site Management Visits have been completed by the Site Monitor (26Jun25) and Site Care Partner (02July25) and communication is ongoing with site to schedule regular weekly teleconferences between the site staff and Site Monitor/Site Care Partner to guide the site in query resolution and expectations for SAE report updates. A temporary increase in SDV is underway as per the C3671058 Study Monitoring Plan to perform additional SDV on subject 10341006 to identify any other data that has not been transcribed to InForm. The site has proved unresponsive to follow up requests and escalation to the site director has been completed to encourage the site to improve query resolution timelines. Ongoing study team oversight proceeds to track the status of InForm CRF queries and the SAE report narrative and additional onsite monitoring visits will occur with the next monitoring visit scheduled 8Jul25. Further investigations are ongoing to ascertain any potential impact resulting from competing studies, and an open dialogue between site staff and the study team is under consideration to facilitate query resolution. A request for a site audit has been placed and is under investigation. |  |  | NA | Personnel | Lack of or Inadequate Oversight |  | MODEL 1 - INSOURCED | Vaccines
QE-188521 | C3671058 | Y | QE-188521 | 1042 | Jon Finley (C3671058-1042) | N | Minor | Closed | Power loss at site and delayed generator activation caused a temperature excursion that may have impact on stored biological samples.Temperatures for lab samples went below -15 from 0800-1130. The generator was back on but went off again that day and temp went below -15 from 14:14-17:45. | 2025-06-30 | 2025-07-03 | 2025-07-03 19:21 | GCP_Minor_Jun-2025_C3671058: Sample Management: Temperature Excursion_Finley, Jon_USA |  | NO |  |  | No |  |  | 2025-07-03 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | No Process Assigned | Diandra Browne |  | Site staff notified SCP and monitor. Site shipped samples adhoc to VRD. 10 samples shipped. |  |  | NA | Equipment/System/Facility | Equipment |  | MODEL 1 - INSOURCED | Vaccines
QE-195266 | C3671058 | (Empty) | QE-195266 |  | PFIZER | N | Minor | Closed | The study C3671058 build activity began in December 2024 with Alexa Brownfield as the Clinical Data Scientist (CDS). At that time, Madhan Babu supported the study as the Senior Data Manager. Due to unplanned leave, Alexa was replaced by Jennifer Riddle as CDS. Subsequently, Jennifer also went on unplanned leave, and Madhan Babu assumed the CDS responsibilities as a backup.Given the ongoing study requirements, Madhan Babu continued to serve as the CDS for the study. The CDS task transition plan was not documented at the time of transition due to unplanned leaves of both assigned CDS personnel and need to maintain study continuity and oversight. | 2025-06-24 | 2025-08-12 | 2025-08-12 16:21 | GCP_Minor_Aug-2025_C3671058: CMCD: Transition Documentation_Pfizer_Global |  | NO |  |  | No |  |  | 2025-08-12 |  | Quality Procedures | Failure to use adequate controls (e.g., Required Forms, templates) |  |  | CT48-Study Operational Management | Madhan Babu |  | Requested C3671058 studyTMF owner to create a new placeholder for the missing documents and request will be raised to satisfy the placeholder with an appropriate reason. The documentation from that SQE to be filed in TMF. |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Vaccines
QE-196047 | C3671058 | N | QE-196047 | 1009, 1013, 1021, 1041 | Abid Chaudhry (C3671058-1041), Abid Chaudhry (C4771001-1021), Abid Chaudhry (C4931001-1013), Abid Chaudhry (C6271001-1009) | N | Minor | Closed | Alliance for Multispecialty Research, Miami (AMR-Miami) has Ongoing site status on C6271001 and other Pfizer studies including: C3671058, C4771001, and C4931001. Between 12Jun2025 and 08Aug2025, up to 4 study coordinators (SCs) have left the organization resulting in slowed responsiveness and cases of unresponsiveness to Sponsor communications. There has been delayed completion of study activities and delayed data entry reconciliation putting the site at risk to meet in-window participant follow up visits and data cleaning timelines across the studies listed – for example:Delayed confirmation of treatment and risk for out of window follow up visits (C4771001). PI and Site Manager have been making efforts to resolve their resourcing issues. SCP has engaged with the PI, Site Manager, Regulatory Coordinator, and SCs through phone calls and email communications to provide support and guidance. The site has been delayed to provide updated SSDDLs accurately reflecting roles and task changes. SCP review of SIP and SSDDLs during role and task changes have yielded compounding findings including inconsistencies between SIP roles and SSDDL roles and tasks – for example:Multiple tasks have not been delegated to any site staff (C6271001 and C3671058).A staff with a blinded SC role in SIP and an unblinded SC role on the SSDDL – staff never completed any unblinded study activities – SCP notified site of discrepancy and site has been delayed to correct the SSDDL (C4931001).Site has been delayed to add updated SSDDL to eISF after multiple requests (C4771001). SCP continues to work with the site to bridge gaps in site performance on the studies; however, the site continues to struggle to close the gaps. | 2025-08-13 | 2025-08-15 | 2025-08-15 20:21 | GCP_Minor_Aug-2025_Multiple Protocols: PI Oversight, Delgation; Data Entry Timeliness, Site Staff Resourcing_Chaudhry, Abid_USA |  | NO |  |  | No |  |  | 2025-08-15 |  | Data Collection and Management, Protocol Deviations, Quality Oversight | Failure to follow protocol, Inadequate Principal Investigator quality oversight, Incomplete or inaccurate data transcription and/or entry |  |  | CT40-Management of Protocol Deviations, INV02-Investigational Site Selection, Preparation, and Initiation, INV04-Investigational Site Management and Monitoring | Ezinna Anosike |  | Study teams were notified of staff turnover and impact to study activities. SCP met with PI and site to ascertain site plan to fill positions and ensure continuity of study activities at the site. |  |  | NA | Personnel | Turnover/Attrition |  | MODEL 1 - INSOURCED | Vaccines
QE-199192 | C3671058 | N | QE-199192 | 1069 | Jay Sandberg (C3671058-1069) | N | Minor | Closed | Missing transcription of Adverse Events, Medical History and Medications for multiple patients (40-50% of participants) | 2025-08-27 | 2025-09-03 | 2025-09-03 15:55 | GCP_Minor_Sep-2025_C3671058: Data Entry Timeliness_Sandberg, Jay_USA |  | NO |  |  | No |  |  | 2025-09-03 |  | Data Collection and Management | Inadequate source data/documentation |  |  | DMB08-Study Data Set Review Release and Archive | Judith Pride |  | Site monitor made study team aware of the issue, refresher training provided by site. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-218970 | C3671058 | (Empty) | QE-218970 |  | TRULAB INC | N | Minor | Closed | TruLab Application (App) is a Software as a Service (SaaS) platform that enables the digital collection and processing of biospecimen samples. As per the playbook, once the final data transfer has been received and confirmed by Clinical Data Sciences (CDS) as complete and accurate, the Final Data Transfer Form (TMP-SYS-003) is sent from TruLab. CDS then completes the form and returns it to TruLab for further processing. However, we were informed that this form has become obsolete at TruLab’s end and is no longer required; an email confirmation is now considered sufficient. TruTech has retired the Final Data Transfer Form, which is still required by Pfizer’s process to proceed with final study close-out activities and to be filed in the Trial Master File (TMF). At the study team’s request, a memo was created by TruLab to document a temporary deviation allowing the continued use of TMP-SYS-003 in place of the newly created work forms. This deviation is necessary to fulfill Pfizer’s documentation requirements for the TMF.CDS has completed TMP-SYS-003 for final data transfer confirmation and form will be filed in the TMF as per Pfizer requirements. Please find the memo attached for further reference. | 2025-11-17 | 2025-12-16 | 2025-12-16 18:43 | GCP_Minor_Dec-2025_C3671058: DM Documentation_Pfizer; TruLab_USA; PRI |  | NO |  |  | No |  |  | 2025-12-16 |  | Quality Oversight/Documentation | Inadequate quality documentation |  |  | DMB08-Study Data Set Review Release and Archive, QMS09-Vendor Engagement | Madhan Babu |  | CDS has completed TMP-SYS-003 for final data transfer confirmation, and the form will be filed in the TMF as per Pfizer requirements. |  |  | NA | Human Performance | Decision Error |  | MODEL 1 - INSOURCED | Vaccines