## Standard_Quality_Dashboard - SQ
Case ID | Case Status | Observation ID | Obs Status | Submission Date | Issue Audit Report (Actual) | Center Number | principal investigator | Country | Description | Study ID | Protocol ID | Title Short Description | Drug Program Code | Rating | Event Type | Case CAPA Approved Due Date | Case CAPA Approved On | CAPA Plan In Place Timely | Obs CAPA Approved Due Date | Obs CAPA Approved On | Obs Target Completion Date | Obs Actual Completion Date | Case CAPA Closure Timely | Case Target Completion Date | Case Actual Completion Date | Obs CAPA Closure Timely | Selected Business Process | Taxonomy Level 1 | Taxonomy Level 2 | Study Status | Business Category | Study Phase | Study Priority | Asset | Dev China | Dev Japan | Rapid Model | Business Category
AIA-007556 | Closed | QE-198623 | Closed | (Empty) | 2025-09-02 | 1069 | (Empty) | UNITED STATES | For 7 of 7 participants records reviewed, source documentation practices were not complete, attributable, or accurate (ICH GCP E6 (R3) 2.12.2). 1. For 7 of 7 participants records reviewed (10691002,10691012, 10691014, 10691025, 10691027, 10691030, 10691034), the time of the pre-vaccination oral body temperature collection was not recorded in the source records for the study intervention administration visits.&nbsp; Please note: as per an interview with the site staff; the oral body temperature measurement was recorded prior to study intervention administration as indicated by the flow of the study visit worksheet; however, since the time of the temperature collection was not recorded, the auditor was not able to verify if the temperature was recorded prior to study intervention. &nbsp; 2. Participant 10691002: a. On the Eligibility worksheet (Inclusion and Exclusion review), the investigator had answered "yes" for exclusions 1 thru 6 (protocol version date 19 Dec 2024); however, had answered "yes" to the question "inclusion/exclusion reviewed and subject is eligible to randomize".&nbsp; Please note: per interview with the site staff, the participant met criteria and the investigator had answered "yes" to exclusions 1 thru 6 in error.&nbsp; b. For Visit 2 (15 May 2025), the temperature was recorded as 36.5 degrees Fahrenheit instead of Celsius in the participant chart in error.&nbsp; 3. Participant 10691012: a. The Adverse Event and Prior and Concomitant Medications Logs were not filed in the participant chart.&nbsp; b. For Visit 3 (05 Jun 2025), the temperature was recorded as 36.5 degrees Fahrenheit instead of Celsius in the participant chart in error.&nbsp; 4. Participant 10691014: a. The blank Prior and Concomitant Medications Log had been crossed out, but was not initialed or dated.&nbsp; b. For Visit 3 (05 Jun 2025), the temperature was recorded as 36.5 degrees Fahrenheit instead of Celsius in the participant chart in error.&nbsp; 5. Participant 10691025:&nbsp; a. The blank Medical and Surgical History Log was crossed out, but was not initialed or dated.&nbsp; b. The blank Prior and Concomitant Medications Log was crossed out and dated, but it was not initialed.&nbsp; 6. Participant 10691027: a. For Visit 2 (13 May 2025), the temperature was recorded as 36.5 degrees Fahrenheit instead of Celsius in the participant chart in error.&nbsp; b. For the Visit 2 (13 May 2025), 30 minutes post observational time was recorded as 10:02; however, the time of study intervention was 10:31.&nbsp; 7. Participant 10691030: a. The Symptoms Resolution Diary for 19 Apr 2025 had a note that stated, "All symptoms Resolved'; however, it was not initialed or dated.&nbsp; b. Page 2 of 2 was not filed for the Progress Note.&nbsp; c. The Investigator signature was missing from the Visit 4 (23 July 2025) source document on page 3.&nbsp; 8. Participant 10691034: a. For Visit 1 (11 Apr 2025), the following questions were marked as "no" in error:&nbsp; a1. "Provide Patient Instructions for completion of ediary on Day 1 to Day 7" a2. "Provide patients measuring device and thermometer for recording daily temperatures" b. For Visit 2 (12 May 2025), page 3 of 4 of the visit worksheet was crossed out, but was not initialed or dated.&nbsp; c. For Visit 2 (12 May 2025), "was a urine sample collected for pregnancy test?" was not answered "N/A" in error.&nbsp; &nbsp; | C3671058 | C3671058 | A Routine Investigator Site Audit of Pfizer Study C3671058, Site 1069, Dr. Sandberg, Troy, Michigan, USA | (Empty) | Major | AUDIT | 2025-10-14 | (Empty) | N | (Empty) | (Empty) | 2025-11-30 | 2025-09-12 | Y | 2025-11-30 | 2025-09-25 | Y | NOT APPLICABLE; NOT APPLICABLE | Data Collection and Management | Inadequate source data/documentation | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-007556 | Closed | QE-198716 | Closed | (Empty) | 2025-09-02 | 1069 | (Empty) | UNITED STATES | Three essential documents in the Investigator Site File (ISF) were incomplete and/or not filed (ICH E6 (R3) C2.3, C2.5).&nbsp; 1. The Subject Identification Code List was not completed or filed in the ISF.&nbsp; 2. The Screening and Enrollment Log was not updated to reflect the current participant statuses. &nbsp; 3. A Note to File to explain the qualifications, training, and vaccine experience of the site staff that were delegated to administer Investigational Product (IP) as they were not healthcare professionals was not filed in the ISF.&nbsp; Please Note: As per the protocol, "Study interventions should be prepared and dispensed by an appropriately qualified and experienced member of the study staff (eg, physician, nurse, physician’s assistant, nurse practitioner, pharmacy assistant/technician, or pharmacist) as allowed by local, state, and institutional guidance"; however, the delegated staff were not medical professionals.&nbsp; | C3671058 | C3671058 | A Routine Investigator Site Audit of Pfizer Study C3671058, Site 1069, Dr. Sandberg, Troy, Michigan, USA | (Empty) | Minor | AUDIT | 2025-10-14 | (Empty) | N | (Empty) | (Empty) | 2025-11-30 | 2025-09-25 | Y | 2025-11-30 | 2025-09-25 | Y | CT01 - Trial Master Files | Document Management | Missing document | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-007556 | Closed | QE-198719 | Closed | (Empty) | 2025-09-02 | 1069 | (Empty) | UNITED STATES | Documentation related to Investigational Product handling was inadequate (Pfizer Study C3671058 Investigational Product Manual (version 2: 05 Jun 2025).&nbsp; For 40 of 40 participants randomized, the "Disposition" columns (Returned or Destroyed, Date of Disposition, Staff Initials), were not completed on the Investigational Product Accountability Log (IPAL).&nbsp; | C3671058 | C3671058 | A Routine Investigator Site Audit of Pfizer Study C3671058, Site 1069, Dr. Sandberg, Troy, Michigan, USA | (Empty) | Minor | AUDIT | 2025-10-14 | (Empty) | N | (Empty) | (Empty) | 2025-11-30 | 2025-09-10 | Y | 2025-11-30 | 2025-09-25 | Y | IP13 - Study Investigational Product Supplies | Medicinal Product | Inadequate accountability/record keeping | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-007556 | Closed | QE-198728 | Closed | (Empty) | 2025-09-02 | 1069 | (Empty) | UNITED STATES | For 3 of 7 participant records reviewed, the investigator site did not consistently adhere to the protocol (Pfizer Study C3671058 (19 Dec 2024)). 1. For 3 of 7 participants records reviewed (10691012, 10691014, 10691027), the male participants agreeing to refrain from donating sperm was not documented in the participant charts. Please note: As per the reproductive criteria, male participants are eligible to participate if they agree to refrain from donating sperm.&nbsp; 2. For Participant 10691012, the Visit 3 (2 Month Follow Up), the vaccination electronic diary was not completed during the required 7-day post vaccination period. There was no documentation to confirm if a follow up call was conducted by the site personnel. | C3671058 | C3671058 | A Routine Investigator Site Audit of Pfizer Study C3671058, Site 1069, Dr. Sandberg, Troy, Michigan, USA | (Empty) | Minor | AUDIT | 2025-10-14 | (Empty) | N | (Empty) | (Empty) | 2025-11-30 | 2025-09-24 | Y | 2025-11-30 | 2025-09-25 | Y | CT40 - Protocol Deviations | Protocol Deviations | Failure to follow protocol | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-007559 | Closed | QE-179449 | Closed | (Empty) | 2025-05-16 | 1048 | (Empty) | UNITED STATES | For 4 of 8 participant files reviewed, source documentation practices were not in accordance with ALCOACCEA (Attributable, Legible, Contemporaneous, Original, Accurate, Complete, Consistent, Enduring, and Available) [Pfizer Protocol C3671058 (Final: 19 Dec 2024); ICH E6 (R2) 2.10; 4.9.0]. 1. &nbsp;Participant 10481001 did not have type 1 or type II checked for their type of diabetes recorded in the source records. 2. &nbsp;For Participant 10481003 the 04 Apr 2025 progress note for the unplanned visit had Participant #10481004 recorded in the body of the memo. 3. &nbsp;For Participant 10481008, the randomization number was recorded as 10077 on the site’s Visit 1 worksheet; however, the randomization number was documented as 10027 in Interactive Response Technology (IRT). 4. &nbsp;For Participant 10481034, the randomization number was not recorded on the site’s Visit 1 worksheet; however, the randomization number was documented as 10692 in Interactive Response Technology (IRT). | C3671058 | C3671058 | A Routine Investigator Site Audit of Study C3671058 Site 1048, Dr David Mishkin, Fort Lauderdale, FL, USA | (Empty) | Minor | AUDIT | 2025-06-27 | (Empty) | N | (Empty) | (Empty) | 2025-07-25 | 2025-07-15 | Y | 2025-07-25 | 2025-07-15 | Y | NOT APPLICABLE; NOT APPLICABLE | Data Collection and Management | Inadequate source data/documentation | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-007559 | Closed | QE-179450 | Closed | (Empty) | 2025-05-16 | 1048 | (Empty) | UNITED STATES | For 1 of 8 participant files reviewed a discrepancy was noted between the electronic Case Report Form (eCRF) and source documentation [C3671058 CRF Completion Requirements Version 1, 06 Mar 2025]. For Participant 10481003, the site's source worksheet for ' Pre-Specified Significant Medical History Risk Factors' did not have "Chronic Lung Disease" checked; however, the participant had sleep apnea which qualified as "Chronic Lung Disease" per the eCRF Requirements.&nbsp; | C3671058 | C3671058 | A Routine Investigator Site Audit of Study C3671058 Site 1048, Dr David Mishkin, Fort Lauderdale, FL, USA | (Empty) | Minor | AUDIT | 2025-06-27 | (Empty) | N | (Empty) | (Empty) | 2025-07-25 | 2025-07-15 | Y | 2025-07-25 | 2025-07-15 | Y | DMB07 - CRF and Database Design | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-007559 | Closed | QE-179451 | Closed | (Empty) | 2025-05-16 | 1048 | (Empty) | UNITED STATES | For 1 of 8 participant files reviewed, data available in the electronic Case Report Form (eCRF) was not supported by source documentation [ICH GCP E6 [R2] 4.9.0]. Participant 10481003: 1. &nbsp; &nbsp;Allergies were checked as N/A&nbsp; in the medical history source documentation; however, an oyster (shellfish) allergy was listed in the eCRF with a start date of "UNK/UNK/2012". 2.&nbsp; &nbsp;There was no stroke recorded in medical history source documentation; however, a stroke was listed in the eCRF with a start date of "UNK/UNK/2012". | C3671058 | C3671058 | A Routine Investigator Site Audit of Study C3671058 Site 1048, Dr David Mishkin, Fort Lauderdale, FL, USA | (Empty) | Minor | AUDIT | 2025-06-27 | (Empty) | N | (Empty) | (Empty) | 2025-07-25 | 2025-07-15 | Y | 2025-07-25 | 2025-07-15 | Y | NOT APPLICABLE; NOT APPLICABLE | Data Collection and Management | Inadequate source data/documentation | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-007559 | Closed | QE-179454 | Closed | (Empty) | 2025-05-16 | 1048 | (Empty) | UNITED STATES | One essential document was missing from the Pfizer Trial Master File (PTMF) [CT01-GSOP 8.0 Trial Master Files 03-Oct-2022; ICH GCP E6 (R2) Section 4.9.4]. The Pfizer study C3671058 Case Report Form (CRF) Completion Requirements was not available in the PTMF. | C3671058 | C3671058 | A Routine Investigator Site Audit of Study C3671058 Site 1048, Dr David Mishkin, Fort Lauderdale, FL, USA | (Empty) | Minor | AUDIT | 2025-06-27 | (Empty) | N | (Empty) | (Empty) | 2025-05-20 | 2025-05-20 | Y | 2025-07-25 | 2025-07-15 | Y | CT01 - Trial Master Files | Document Management | Missing document | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-007559 | Closed | QE-179457 | Closed | (Empty) | 2025-05-16 | 1048 | (Empty) | UNITED STATES | One essential document was inaccurate in the electronic Investigator Site File (e-ISF) [ICH GCP E6 (R2) Section 4.9.4]. There were two (2) copies of the Financial Disclosure Form (FDF) signed by the Sub-Investigator. The first FDF was signed on 10 Feb 2025; however, the "Yes or No" questions were not completed. The second FDF was signed on 12 Feb 2025 with the "Yes or No" questions completed; however, the box for an "Initial FDF" was checked instead of the box for an "Updated FDF".&nbsp; | C3671058 | C3671058 | A Routine Investigator Site Audit of Study C3671058 Site 1048, Dr David Mishkin, Fort Lauderdale, FL, USA | (Empty) | Minor | AUDIT | 2025-06-27 | (Empty) | N | (Empty) | (Empty) | 2025-07-25 | 2025-07-15 | Y | 2025-07-25 | 2025-07-15 | Y | CT01 - Trial Master Files | Document Management | Missing document | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1001 | Alton Walters (C6271001-1001) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1001 | Alton Walters (C6271001-1001) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1003 | David Fitz-Patrick (C6271001-1003) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1003 | David Fitz-Patrick (C6271001-1003) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1006 | James Clark (C6271001-1006) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1006 | James Clark (C6271001-1006) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1008 | Orlando Puente (C6271001-1008) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1008 | Orlando Puente (C6271001-1008) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1015 | Alejandro DeLaCruz (C3671058-1015) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1015 | Alejandro DeLaCruz (C3671058-1015) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1017 | Patrick Dennis (C3671058-1017) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1017 | Patrick Dennis (C3671058-1017) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1019 | Jose Cardona (C6271001-1019) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1019 | Jose Cardona (C6271001-1019) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1024 | Joseph Surber (C3671058-1024) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1024 | Joseph Surber (C3671058-1024) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1025 | Sridhar Guduri (C6271001-1025) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1025 | Sridhar Guduri (C6271001-1025) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1027 | Barton Williams (C6271001-1027) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1027 | Barton Williams (C6271001-1027) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1028 | Stephan Sharp (C6271001-1028) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1028 | Stephan Sharp (C6271001-1028) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1032 | Timothy Jennings (C6271001-1032) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1032 | Timothy Jennings (C6271001-1032) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1033 | Stacey Layle (C6271001-1033) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1033 | Stacey Layle (C6271001-1033) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1035 | Christopher Romero (C6271001-1035) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1035 | Christopher Romero (C6271001-1035) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1037 | David DeAtkine (C3671058-1037) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1037 | David DeAtkine (C3671058-1037) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1040 | Daniel Brune (C3671058-1040) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1040 | Daniel Brune (C3671058-1040) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1043 | Harry Studdard (C3671058-1043) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1043 | Harry Studdard (C3671058-1043) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1055 | Sridhar Guduri (C3671058-1055) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1055 | Sridhar Guduri (C3671058-1055) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1056 | Lisa Usdan (C3671058-1056) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1056 | Lisa Usdan (C3671058-1056) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1061 | William Towner (C3671058-1061) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1061 | William Towner (C3671058-1061) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1062 | Timothy Jennings (C3671058-1062) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | 1062 | Timothy Jennings (C3671058-1062) | UNITED STATES | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | (Empty) | PFIZER | (Empty) | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | (Empty) | PFIZER | (Empty) | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | (Empty) | TRULAB INC | (Empty) | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-182467 | Approved - In CAPA | QE-182467 | Approved - In CAPA | 2025-05-30 | (Empty) | (Empty) | TRULAB INC | (Empty) | This is a resubmission of QE-182295 in light of additional information received pointing to systemic issues regarding site use of the TruLab app. See impact summary. Use of the TruLab app in studies C3671058 and C6271001 has resulted in a great deal more data re: biospecimen collection than the previous paper-based process. Study team members downloaded this sample collection data from the TruLab Sponsor Dashboard and, on their own analysis, discovered discrepancies around the times when initial blood draw was logged and the times for aliquoting of those samples post-clotting and centrifugation when compared to instructions provided for sample processing. Many site users logged samples in the app where the blood collection to aliquot time was less than 45 minutes or greater than 2 hours, time frames outside of acceptable sample processing steps as directed in the lab manual.This issue occurred the first time on 04 April 2025 for C3671058. | C3671058 | C3671058 | GCP_Major_May-2025_C3671058; C6271001;C4851001: Sample Data Collection_Multiple Sites; Pfizer; TruLab_USA | C367 | Major | SQE | 2025-08-22 | 2025-11-21 | N | 2025-08-22 | 2025-11-21 17:21 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS09 - Vendor Management | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-187977 | Closed | QE-187977 | Closed | 2025-07-01 | (Empty) | 1025 | Sarah Freeman (C6271001-1025) | UNITED STATES | Departing Study Coordinator (last day 02Jul2025) raised the following concerns to the SCP and Site Monitor during the onsite visit which occurred 26Jun2025: Site Management requesting blinded site staff to perform unblinded study tasks, Site Management requesting site staff to not process subject payments, indications that Site Network may be experiencing significant financial challenges. | C3671058 | C3671058 | GCP_Critical_Jul-2025_C6271001, C3671058: Potential Allegation, PI Oversight_Guduri, Sridhar, Freeman, Sarah_USA PRIVILEDGED AND CONFIDENTIAL | C367 | Critical | SQE | 2025-09-30 | 2025-10-10 | N | 2025-09-30 | 2025-10-10 | (Empty) | 2025-11-25 | (Empty) | (Empty) | 2025-11-25 | (Empty) | DATA INTEGRITY | Potential allegation of Falsification or misconduct | Potential allegation of Scientific fraud, falsification or misconduct | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-187977 | Closed | QE-187977 | Closed | 2025-07-01 | (Empty) | 1025 | Sarah Freeman (C6271001-1025) | UNITED STATES | Departing Study Coordinator (last day 02Jul2025) raised the following concerns to the SCP and Site Monitor during the onsite visit which occurred 26Jun2025: Site Management requesting blinded site staff to perform unblinded study tasks, Site Management requesting site staff to not process subject payments, indications that Site Network may be experiencing significant financial challenges. | C3671058 | C3671058 | GCP_Critical_Jul-2025_C6271001, C3671058: Potential Allegation, PI Oversight_Guduri, Sridhar, Freeman, Sarah_USA PRIVILEDGED AND CONFIDENTIAL | C367 | Critical | SQE | 2025-09-30 | 2025-10-10 | N | 2025-09-30 | 2025-10-10 | (Empty) | 2025-11-25 | (Empty) | (Empty) | 2025-11-25 | (Empty) | NOT APPLICABLE | Potential allegation of Falsification or misconduct | Potential allegation of Scientific fraud, falsification or misconduct | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-187977 | Closed | QE-187977 | Closed | 2025-07-01 | (Empty) | 1025 | Sarah Freeman (C6271001-1025) | UNITED STATES | Departing Study Coordinator (last day 02Jul2025) raised the following concerns to the SCP and Site Monitor during the onsite visit which occurred 26Jun2025: Site Management requesting blinded site staff to perform unblinded study tasks, Site Management requesting site staff to not process subject payments, indications that Site Network may be experiencing significant financial challenges. | C3671058 | C3671058 | GCP_Critical_Jul-2025_C6271001, C3671058: Potential Allegation, PI Oversight_Guduri, Sridhar, Freeman, Sarah_USA PRIVILEDGED AND CONFIDENTIAL | C367 | Critical | SQE | 2025-09-30 | 2025-10-10 | N | 2025-09-30 | 2025-10-10 | (Empty) | 2025-11-25 | (Empty) | (Empty) | 2025-11-25 | (Empty) | NOT APPLICABLE | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-187977 | Closed | QE-187977 | Closed | 2025-07-01 | (Empty) | 1025 | Sridhar Guduri (C6271001-1025) | UNITED STATES | Departing Study Coordinator (last day 02Jul2025) raised the following concerns to the SCP and Site Monitor during the onsite visit which occurred 26Jun2025: Site Management requesting blinded site staff to perform unblinded study tasks, Site Management requesting site staff to not process subject payments, indications that Site Network may be experiencing significant financial challenges. | C3671058 | C3671058 | GCP_Critical_Jul-2025_C6271001, C3671058: Potential Allegation, PI Oversight_Guduri, Sridhar, Freeman, Sarah_USA PRIVILEDGED AND CONFIDENTIAL | C367 | Critical | SQE | 2025-09-30 | 2025-10-10 | N | 2025-09-30 | 2025-10-10 | (Empty) | 2025-11-25 | (Empty) | (Empty) | 2025-11-25 | (Empty) | DATA INTEGRITY | Potential allegation of Falsification or misconduct | Potential allegation of Scientific fraud, falsification or misconduct | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-187977 | Closed | QE-187977 | Closed | 2025-07-01 | (Empty) | 1025 | Sridhar Guduri (C6271001-1025) | UNITED STATES | Departing Study Coordinator (last day 02Jul2025) raised the following concerns to the SCP and Site Monitor during the onsite visit which occurred 26Jun2025: Site Management requesting blinded site staff to perform unblinded study tasks, Site Management requesting site staff to not process subject payments, indications that Site Network may be experiencing significant financial challenges. | C3671058 | C3671058 | GCP_Critical_Jul-2025_C6271001, C3671058: Potential Allegation, PI Oversight_Guduri, Sridhar, Freeman, Sarah_USA PRIVILEDGED AND CONFIDENTIAL | C367 | Critical | SQE | 2025-09-30 | 2025-10-10 | N | 2025-09-30 | 2025-10-10 | (Empty) | 2025-11-25 | (Empty) | (Empty) | 2025-11-25 | (Empty) | NOT APPLICABLE | Potential allegation of Falsification or misconduct | Potential allegation of Scientific fraud, falsification or misconduct | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-187977 | Closed | QE-187977 | Closed | 2025-07-01 | (Empty) | 1025 | Sridhar Guduri (C6271001-1025) | UNITED STATES | Departing Study Coordinator (last day 02Jul2025) raised the following concerns to the SCP and Site Monitor during the onsite visit which occurred 26Jun2025: Site Management requesting blinded site staff to perform unblinded study tasks, Site Management requesting site staff to not process subject payments, indications that Site Network may be experiencing significant financial challenges. | C3671058 | C3671058 | GCP_Critical_Jul-2025_C6271001, C3671058: Potential Allegation, PI Oversight_Guduri, Sridhar, Freeman, Sarah_USA PRIVILEDGED AND CONFIDENTIAL | C367 | Critical | SQE | 2025-09-30 | 2025-10-10 | N | 2025-09-30 | 2025-10-10 | (Empty) | 2025-11-25 | (Empty) | (Empty) | 2025-11-25 | (Empty) | NOT APPLICABLE | Quality Oversight | Inadequate Principal Investigator quality oversight | COMPLETED | Vaccines | PHASE III | MAINTAIN | Abrysvo RSV Adult | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines