## Standard_Quality_Dashboard - SQ
Case ID | Case Status | Observation ID | Obs Status | Submission Date | Issue Audit Report (Actual) | Center Number | principal investigator | Country | Description | Study ID | Protocol ID | Title Short Description | Drug Program Code | Rating | Event Type | Case CAPA Approved Due Date | Case CAPA Approved On | CAPA Plan In Place Timely | Obs CAPA Approved Due Date | Obs CAPA Approved On | Obs Target Completion Date | Obs Actual Completion Date | Case CAPA Closure Timely | Case Target Completion Date | Case Actual Completion Date | Obs CAPA Closure Timely | Selected Business Process | Taxonomy Level 1 | Taxonomy Level 2 | Study Status | Business Category | Study Phase | Study Priority | Asset | Dev China | Dev Japan | Rapid Model | Business Category
QE-175099 | Approved - In CAPA | QE-175099 | Approved - In CAPA | 2025-04-15 | (Empty) | (Empty) | PFIZER | (Empty) | SAE Quality Metrics are not reporting in Flex for C5341020, C5351004 and C5361003 studies. Oversight of patient safety is a currently a key concern for these acquisition studies, particularly from the Nigerian regulatory authority (NAFDAC) | C3671059 | C3671059 | GCP_Major_Apr-2025_Multiple Protocols: CMCD: Quality Risk Management (Safety)_Pfizer_Global | C367 | Major | SQE | 2025-08-15 | 2026-03-16 | N | 2025-08-15 | 2026-03-16 20:58 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT27 - Clinical Trial Registry | Quality Oversight | Quality Management System issue | ONGOING | Vaccines | PHASE III | MAINTAIN | RSV Maternal | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-175099 | Approved - In CAPA | QE-175099 | Approved - In CAPA | 2025-04-15 | (Empty) | (Empty) | PFIZER | (Empty) | SAE Quality Metrics are not reporting in Flex for C5341020, C5351004 and C5361003 studies. Oversight of patient safety is a currently a key concern for these acquisition studies, particularly from the Nigerian regulatory authority (NAFDAC) | C3671059 | C3671059 | GCP_Major_Apr-2025_Multiple Protocols: CMCD: Quality Risk Management (Safety)_Pfizer_Global | C367 | Major | SQE | 2025-08-15 | 2026-03-16 | N | 2025-08-15 | 2026-03-16 20:58 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS06 - Quality Risk Management for Clinical Development | Quality Procedures | Requirement/process not met | ONGOING | Vaccines | PHASE III | MAINTAIN | RSV Maternal | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-194440 | Closed | QE-194440 | Closed | 2025-08-06 | (Empty) | 1002 | Jeffrey Baker (C4931010-1002) | UNITED STATES | On 10JUL2025, the Idaho Medical Board posted a Stipulation on Investigator Jeffrey Boyd Baker's (CCTR ID 182771) medical license based on the 2022 Idaho court case Mortensen v. Baker summarized below: A 27-year-old female presented with symptoms including IBS-C, migraines, depression, and cold sores.Dr. Baker attributed her gastrointestinal issues primarily to silicone breast implants (SBIs), recommending treatments such as near-daily rectal ozone insufflation, high intake of prebiotics (inulin, fructooligosaccharides), and fermentable foods (e.g., sauerkraut, kimchi).Concerns Raised:The patient’s symptoms worsened under this regimen.Dr. Baker did not consider alternative causes or refer the patient to a gastroenterologist.He encouraged breast implant removal without imaging to assess implant integrity.Dr. Baker diagnosed the patient with an autoimmune disease based solely on a single ANA test (1:80 nucleolar pattern) without further testing or clinical correlation.Violation:The Idaho Medical Board found that Dr. Baker failed to meet the community standard of care by focusing narrowly on SBIs without adequate differential diagnosis, recommending an invasive surgery without appropriate diagnostics, and diagnosing an autoimmune disease without sufficient evidence.Required Actions: As part of the disciplinary agreement, Dr. Baker must complete Board-approved educational courses within 90 daysOn 05 Aug 2025, the Investigator Status and Use sub-committee of the GCP-Quality Oversight Committee recommended a QE by opened to ensure Study Teams currently using the Investigator were aware of the stipulation and could consider any other potential mitigations. | C3671059 | C3671059 | GCP_Major_Aug-2025_Multiple Studies: Investigator Availability Status_Baker, Jeffrey_USA | C367 | Major | SQE | 2025-09-21 | 2025-08-27 | Y | 2025-09-21 | 2025-08-27 12:36 | (Empty) | 2025-08-27 | (Empty) | (Empty) | 2025-08-27 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Training & Qualifications | Personnel inadequately trained to perform their assigned job function | ONGOING | Vaccines | PHASE III | MAINTAIN | RSV Maternal | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-194440 | Closed | QE-194440 | Closed | 2025-08-06 | (Empty) | 1005 | Jeffrey Baker (C4931010-1005) | UNITED STATES | On 10JUL2025, the Idaho Medical Board posted a Stipulation on Investigator Jeffrey Boyd Baker's (CCTR ID 182771) medical license based on the 2022 Idaho court case Mortensen v. Baker summarized below: A 27-year-old female presented with symptoms including IBS-C, migraines, depression, and cold sores.Dr. Baker attributed her gastrointestinal issues primarily to silicone breast implants (SBIs), recommending treatments such as near-daily rectal ozone insufflation, high intake of prebiotics (inulin, fructooligosaccharides), and fermentable foods (e.g., sauerkraut, kimchi).Concerns Raised:The patient’s symptoms worsened under this regimen.Dr. Baker did not consider alternative causes or refer the patient to a gastroenterologist.He encouraged breast implant removal without imaging to assess implant integrity.Dr. Baker diagnosed the patient with an autoimmune disease based solely on a single ANA test (1:80 nucleolar pattern) without further testing or clinical correlation.Violation:The Idaho Medical Board found that Dr. Baker failed to meet the community standard of care by focusing narrowly on SBIs without adequate differential diagnosis, recommending an invasive surgery without appropriate diagnostics, and diagnosing an autoimmune disease without sufficient evidence.Required Actions: As part of the disciplinary agreement, Dr. Baker must complete Board-approved educational courses within 90 daysOn 05 Aug 2025, the Investigator Status and Use sub-committee of the GCP-Quality Oversight Committee recommended a QE by opened to ensure Study Teams currently using the Investigator were aware of the stipulation and could consider any other potential mitigations. | C3671059 | C3671059 | GCP_Major_Aug-2025_Multiple Studies: Investigator Availability Status_Baker, Jeffrey_USA | C367 | Major | SQE | 2025-09-21 | 2025-08-27 | Y | 2025-09-21 | 2025-08-27 12:36 | (Empty) | 2025-08-27 | (Empty) | (Empty) | 2025-08-27 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Training & Qualifications | Personnel inadequately trained to perform their assigned job function | ONGOING | Vaccines | PHASE III | MAINTAIN | RSV Maternal | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-194440 | Closed | QE-194440 | Closed | 2025-08-06 | (Empty) | 1011 | Jeffrey Baker (C3671059-1011) | UNITED STATES | On 10JUL2025, the Idaho Medical Board posted a Stipulation on Investigator Jeffrey Boyd Baker's (CCTR ID 182771) medical license based on the 2022 Idaho court case Mortensen v. Baker summarized below: A 27-year-old female presented with symptoms including IBS-C, migraines, depression, and cold sores.Dr. Baker attributed her gastrointestinal issues primarily to silicone breast implants (SBIs), recommending treatments such as near-daily rectal ozone insufflation, high intake of prebiotics (inulin, fructooligosaccharides), and fermentable foods (e.g., sauerkraut, kimchi).Concerns Raised:The patient’s symptoms worsened under this regimen.Dr. Baker did not consider alternative causes or refer the patient to a gastroenterologist.He encouraged breast implant removal without imaging to assess implant integrity.Dr. Baker diagnosed the patient with an autoimmune disease based solely on a single ANA test (1:80 nucleolar pattern) without further testing or clinical correlation.Violation:The Idaho Medical Board found that Dr. Baker failed to meet the community standard of care by focusing narrowly on SBIs without adequate differential diagnosis, recommending an invasive surgery without appropriate diagnostics, and diagnosing an autoimmune disease without sufficient evidence.Required Actions: As part of the disciplinary agreement, Dr. Baker must complete Board-approved educational courses within 90 daysOn 05 Aug 2025, the Investigator Status and Use sub-committee of the GCP-Quality Oversight Committee recommended a QE by opened to ensure Study Teams currently using the Investigator were aware of the stipulation and could consider any other potential mitigations. | C3671059 | C3671059 | GCP_Major_Aug-2025_Multiple Studies: Investigator Availability Status_Baker, Jeffrey_USA | C367 | Major | SQE | 2025-09-21 | 2025-08-27 | Y | 2025-09-21 | 2025-08-27 12:36 | (Empty) | 2025-08-27 | (Empty) | (Empty) | 2025-08-27 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Training & Qualifications | Personnel inadequately trained to perform their assigned job function | ONGOING | Vaccines | PHASE III | MAINTAIN | RSV Maternal | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-194440 | Closed | QE-194440 | Closed | 2025-08-06 | (Empty) | 1017 | Jeffrey Baker (C1091009-1017) | UNITED STATES | On 10JUL2025, the Idaho Medical Board posted a Stipulation on Investigator Jeffrey Boyd Baker's (CCTR ID 182771) medical license based on the 2022 Idaho court case Mortensen v. Baker summarized below: A 27-year-old female presented with symptoms including IBS-C, migraines, depression, and cold sores.Dr. Baker attributed her gastrointestinal issues primarily to silicone breast implants (SBIs), recommending treatments such as near-daily rectal ozone insufflation, high intake of prebiotics (inulin, fructooligosaccharides), and fermentable foods (e.g., sauerkraut, kimchi).Concerns Raised:The patient’s symptoms worsened under this regimen.Dr. Baker did not consider alternative causes or refer the patient to a gastroenterologist.He encouraged breast implant removal without imaging to assess implant integrity.Dr. Baker diagnosed the patient with an autoimmune disease based solely on a single ANA test (1:80 nucleolar pattern) without further testing or clinical correlation.Violation:The Idaho Medical Board found that Dr. Baker failed to meet the community standard of care by focusing narrowly on SBIs without adequate differential diagnosis, recommending an invasive surgery without appropriate diagnostics, and diagnosing an autoimmune disease without sufficient evidence.Required Actions: As part of the disciplinary agreement, Dr. Baker must complete Board-approved educational courses within 90 daysOn 05 Aug 2025, the Investigator Status and Use sub-committee of the GCP-Quality Oversight Committee recommended a QE by opened to ensure Study Teams currently using the Investigator were aware of the stipulation and could consider any other potential mitigations. | C3671059 | C3671059 | GCP_Major_Aug-2025_Multiple Studies: Investigator Availability Status_Baker, Jeffrey_USA | C367 | Major | SQE | 2025-09-21 | 2025-08-27 | Y | 2025-09-21 | 2025-08-27 12:36 | (Empty) | 2025-08-27 | (Empty) | (Empty) | 2025-08-27 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Training & Qualifications | Personnel inadequately trained to perform their assigned job function | ONGOING | Vaccines | PHASE III | MAINTAIN | RSV Maternal | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-194440 | Closed | QE-194440 | Closed | 2025-08-06 | (Empty) | 1021 | Jeffrey Baker (C4931002-1021) | UNITED STATES | On 10JUL2025, the Idaho Medical Board posted a Stipulation on Investigator Jeffrey Boyd Baker's (CCTR ID 182771) medical license based on the 2022 Idaho court case Mortensen v. Baker summarized below: A 27-year-old female presented with symptoms including IBS-C, migraines, depression, and cold sores.Dr. Baker attributed her gastrointestinal issues primarily to silicone breast implants (SBIs), recommending treatments such as near-daily rectal ozone insufflation, high intake of prebiotics (inulin, fructooligosaccharides), and fermentable foods (e.g., sauerkraut, kimchi).Concerns Raised:The patient’s symptoms worsened under this regimen.Dr. Baker did not consider alternative causes or refer the patient to a gastroenterologist.He encouraged breast implant removal without imaging to assess implant integrity.Dr. Baker diagnosed the patient with an autoimmune disease based solely on a single ANA test (1:80 nucleolar pattern) without further testing or clinical correlation.Violation:The Idaho Medical Board found that Dr. Baker failed to meet the community standard of care by focusing narrowly on SBIs without adequate differential diagnosis, recommending an invasive surgery without appropriate diagnostics, and diagnosing an autoimmune disease without sufficient evidence.Required Actions: As part of the disciplinary agreement, Dr. Baker must complete Board-approved educational courses within 90 daysOn 05 Aug 2025, the Investigator Status and Use sub-committee of the GCP-Quality Oversight Committee recommended a QE by opened to ensure Study Teams currently using the Investigator were aware of the stipulation and could consider any other potential mitigations. | C3671059 | C3671059 | GCP_Major_Aug-2025_Multiple Studies: Investigator Availability Status_Baker, Jeffrey_USA | C367 | Major | SQE | 2025-09-21 | 2025-08-27 | Y | 2025-09-21 | 2025-08-27 12:36 | (Empty) | 2025-08-27 | (Empty) | (Empty) | 2025-08-27 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Training & Qualifications | Personnel inadequately trained to perform their assigned job function | ONGOING | Vaccines | PHASE III | MAINTAIN | RSV Maternal | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-194440 | Closed | QE-194440 | Closed | 2025-08-06 | (Empty) | 1048 | Jeffrey Baker (C4601012-1048) | UNITED STATES | On 10JUL2025, the Idaho Medical Board posted a Stipulation on Investigator Jeffrey Boyd Baker's (CCTR ID 182771) medical license based on the 2022 Idaho court case Mortensen v. Baker summarized below: A 27-year-old female presented with symptoms including IBS-C, migraines, depression, and cold sores.Dr. Baker attributed her gastrointestinal issues primarily to silicone breast implants (SBIs), recommending treatments such as near-daily rectal ozone insufflation, high intake of prebiotics (inulin, fructooligosaccharides), and fermentable foods (e.g., sauerkraut, kimchi).Concerns Raised:The patient’s symptoms worsened under this regimen.Dr. Baker did not consider alternative causes or refer the patient to a gastroenterologist.He encouraged breast implant removal without imaging to assess implant integrity.Dr. Baker diagnosed the patient with an autoimmune disease based solely on a single ANA test (1:80 nucleolar pattern) without further testing or clinical correlation.Violation:The Idaho Medical Board found that Dr. Baker failed to meet the community standard of care by focusing narrowly on SBIs without adequate differential diagnosis, recommending an invasive surgery without appropriate diagnostics, and diagnosing an autoimmune disease without sufficient evidence.Required Actions: As part of the disciplinary agreement, Dr. Baker must complete Board-approved educational courses within 90 daysOn 05 Aug 2025, the Investigator Status and Use sub-committee of the GCP-Quality Oversight Committee recommended a QE by opened to ensure Study Teams currently using the Investigator were aware of the stipulation and could consider any other potential mitigations. | C3671059 | C3671059 | GCP_Major_Aug-2025_Multiple Studies: Investigator Availability Status_Baker, Jeffrey_USA | C367 | Major | SQE | 2025-09-21 | 2025-08-27 | Y | 2025-09-21 | 2025-08-27 12:36 | (Empty) | 2025-08-27 | (Empty) | (Empty) | 2025-08-27 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Training & Qualifications | Personnel inadequately trained to perform their assigned job function | ONGOING | Vaccines | PHASE III | MAINTAIN | RSV Maternal | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-194440 | Closed | QE-194440 | Closed | 2025-08-06 | (Empty) | 1082 | Jeffrey Baker (C3671044-1082) | (Empty) | On 10JUL2025, the Idaho Medical Board posted a Stipulation on Investigator Jeffrey Boyd Baker's (CCTR ID 182771) medical license based on the 2022 Idaho court case Mortensen v. Baker summarized below: A 27-year-old female presented with symptoms including IBS-C, migraines, depression, and cold sores.Dr. Baker attributed her gastrointestinal issues primarily to silicone breast implants (SBIs), recommending treatments such as near-daily rectal ozone insufflation, high intake of prebiotics (inulin, fructooligosaccharides), and fermentable foods (e.g., sauerkraut, kimchi).Concerns Raised:The patient’s symptoms worsened under this regimen.Dr. Baker did not consider alternative causes or refer the patient to a gastroenterologist.He encouraged breast implant removal without imaging to assess implant integrity.Dr. Baker diagnosed the patient with an autoimmune disease based solely on a single ANA test (1:80 nucleolar pattern) without further testing or clinical correlation.Violation:The Idaho Medical Board found that Dr. Baker failed to meet the community standard of care by focusing narrowly on SBIs without adequate differential diagnosis, recommending an invasive surgery without appropriate diagnostics, and diagnosing an autoimmune disease without sufficient evidence.Required Actions: As part of the disciplinary agreement, Dr. Baker must complete Board-approved educational courses within 90 daysOn 05 Aug 2025, the Investigator Status and Use sub-committee of the GCP-Quality Oversight Committee recommended a QE by opened to ensure Study Teams currently using the Investigator were aware of the stipulation and could consider any other potential mitigations. | C3671059 | C3671059 | GCP_Major_Aug-2025_Multiple Studies: Investigator Availability Status_Baker, Jeffrey_USA | C367 | Major | SQE | 2025-09-21 | 2025-08-27 | Y | 2025-09-21 | 2025-08-27 12:36 | (Empty) | 2025-08-27 | (Empty) | (Empty) | 2025-08-27 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Training & Qualifications | Personnel inadequately trained to perform their assigned job function | ONGOING | Vaccines | PHASE III | MAINTAIN | RSV Maternal | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-194440 | Closed | QE-194440 | Closed | 2025-08-06 | (Empty) | 1429 | Jeffrey Baker (C6271002-1429) | (Empty) | On 10JUL2025, the Idaho Medical Board posted a Stipulation on Investigator Jeffrey Boyd Baker's (CCTR ID 182771) medical license based on the 2022 Idaho court case Mortensen v. Baker summarized below: A 27-year-old female presented with symptoms including IBS-C, migraines, depression, and cold sores.Dr. Baker attributed her gastrointestinal issues primarily to silicone breast implants (SBIs), recommending treatments such as near-daily rectal ozone insufflation, high intake of prebiotics (inulin, fructooligosaccharides), and fermentable foods (e.g., sauerkraut, kimchi).Concerns Raised:The patient’s symptoms worsened under this regimen.Dr. Baker did not consider alternative causes or refer the patient to a gastroenterologist.He encouraged breast implant removal without imaging to assess implant integrity.Dr. Baker diagnosed the patient with an autoimmune disease based solely on a single ANA test (1:80 nucleolar pattern) without further testing or clinical correlation.Violation:The Idaho Medical Board found that Dr. Baker failed to meet the community standard of care by focusing narrowly on SBIs without adequate differential diagnosis, recommending an invasive surgery without appropriate diagnostics, and diagnosing an autoimmune disease without sufficient evidence.Required Actions: As part of the disciplinary agreement, Dr. Baker must complete Board-approved educational courses within 90 daysOn 05 Aug 2025, the Investigator Status and Use sub-committee of the GCP-Quality Oversight Committee recommended a QE by opened to ensure Study Teams currently using the Investigator were aware of the stipulation and could consider any other potential mitigations. | C3671059 | C3671059 | GCP_Major_Aug-2025_Multiple Studies: Investigator Availability Status_Baker, Jeffrey_USA | C367 | Major | SQE | 2025-09-21 | 2025-08-27 | Y | 2025-09-21 | 2025-08-27 12:36 | (Empty) | 2025-08-27 | (Empty) | (Empty) | 2025-08-27 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Training & Qualifications | Personnel inadequately trained to perform their assigned job function | ONGOING | Vaccines | PHASE III | MAINTAIN | RSV Maternal | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-227739 | In Investigation | QE-227739 | In Investigation | 2026-02-11 | (Empty) | (Empty) | PFIZER | (Empty) | C1091009 and C3671059 are two maternal Immunization studies that were recently migrated from Clinical Database InForm to Red Cap Cloud (RCC), and began using SAE+ to capture and transfer SAEs to Pfizer Safety. Pfizer safety notified the clinical team this week that they were missing AE relatedness for SAEs occurring to Infants in the SAE XML file (safety case). Safety had to send urgent queries to sites to confirm Relatedness for these AEs so that a proper assessment for SUSAR reporting could be completed. This is because causality determination entered in the AE log CRF by the site is not incorporated into the XML files sent to safety. This is an SAE+ internal flow issue as information entered by sites in the AE log is not flowing downstream. Without the derived causality assessment included in the XML, the Pfizer safety team defaults to consider the event RELATED which triggers downstream SUSAR reporting activities to meet regulatory reporting requirements. | C3671059 | C3671059 | GCP_Major_Feb-2026_C1091009; C3671059: SAE+; Data Flow_Pfizer_USA; TWN | C367 | Major | SQE | 2026-03-29 | (Empty) | (Empty) | 2026-03-29 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | AEM01 - Adverse Event Monitoring | IT Systems | Inadequate IT system (eg. planning, definitions, design, development, testing, validation, support) per regulatory requirements | ONGOING | Vaccines | PHASE III | MAINTAIN | RSV Maternal | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines