## Standard_Quality_Dashboard - Au
AMS Audit PR ID | AMS Observation PR ID | Target Completion Date | Actual Completion Date | TCD Due/Overdue Days | TCD Status | Observation Closed On | Observation Rating | Observation Phase | Investigator Full Name | Country | Unique Site Number | Type Of Entity | Issue Of Audit Report Actual | Issue Audit Closure Rpt Act | Observation Description | Response (Trackwise Only) | Actions Taken | CAPA Action Description | CAPA Action Created by | Responsibility | Responsible Contact | Audit Coordinator | Observation Status | Audit Status | Level 1 | Level 2 | Selected Business Process | Responsible Party Value | Rapid Model | Business Category | Site Care Partner | Cluster | Area ID | Area Name
AIA-009630 | QE-230536 | [5 empty] | Minor |  | Jose Cardona, Jose Cardona | UNITED STATES | C4591076_1002 | GCP Site Audit | 2026-03-03 |  | For 1 of 10 participant files reviewed, the investigator site failed to adhere to the protocol requirements regarding documentation of concomitant medications [Pfizer Protocol C4591076 (Amendment 1: 26 Aug 2025); ICH E6 (R3) 2.5.2]. The C4591076 Final Protocol (31 May 2025) required that all concomitant medications taken by participants aged 18 through 64 years be recorded on the case report form. For participant 10021007 (age 59), Tylenol taken for a headache from 12 Jul 2025 to 15 Jul 2025 was not documented in the electronic case report form for concomitant medication. Protocol Amendment 1, which removed this requirement, became effective on 26 Aug 2025 and was not applicable during the period in which the medication was taken. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Ann Frances; Kathy Hendricks | Issued | Pending Finding Closure | Protocol Deviations | Failure to follow protocol | CT02 - Clinical Protocols | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Vaccines | Amanda Feliciano Morales | GSSO | 84 | AMERICAS
AIA-009630 | QE-230541 | [5 empty] | Minor |  | Jose Cardona, Jose Cardona | UNITED STATES | C4591076_1002 | GCP Site Audit | 2026-03-03 |  | Investigational Product (IP) record keeping activities were inadequate as per the protocol and Investigational Product Manual [Pfizer Protocol C4591076 (Amendment 1: 26 Aug 2025) and Pfizer Protocol C4591076 Investigational Product Manual (version 2.0: 10 Sep 2025)]. A transcription error was identified between the Drug Shipment &amp; Proof of Receipt (1877624, received 01 Jul 2025) and the Investigational Product Accountability Log; the Proof of Receipt documented container number 5526686, while the Investigational Product Accountability Log documented 5226686. Note: The Impala Interactive Response Technology printout and the site's Blinded Vaccination Administration Record both documented container number 5526686. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Ann Frances; Kathy Hendricks | Issued | Pending Finding Closure | Medicinal Product | Inadequate accountability/record keeping | CT13-GSOP - Investigational Product | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Vaccines | Amanda Feliciano Morales | GSSO | 84 | AMERICAS
AIA-009630 | QE-230546 | [5 empty] | Minor |  | Jose Cardona, Jose Cardona | UNITED STATES | C4591076_1002 | GCP Site Audit | 2026-03-03 |  | Monitoring activities were inadequate with regards to issue detection and/or documentation [C4591076 Study Monitoring Plan (Version 2: dated 19 Sep 2025)]. Monitoring activities failed to identify the following issues noted: a. &nbsp;The investigator site did not adhere to the protocol (finding QE-230536).&nbsp; b. &nbsp;For 5 of 10 participant records reviewed, source documents were not accurate, complete or legible in accordance with the ALCOACCEA criteria. (finding QE-230538). c. &nbsp;For 2 of 10 participant records reviewed, discrepancies between the source data and the electronic Case Report Forms were identified (finding QE-230539). d. &nbsp;One Investigational Product (IP) accountability record was not completed as required (finding QE-230541). | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Ann Frances; Kathy Hendricks | In Response | Pending Finding Closure | Site Management and Monitoring | Failure to detect/document | INV04 - Investigational Site Management and Monitoring | PFIZER | MODEL 1 - INSOURCED | Vaccines | Amanda Feliciano Morales | GSSO | 84 | AMERICAS
AIA-009630 | QE-230538 | [5 empty] | Minor |  | Jose Cardona, Jose Cardona | UNITED STATES | C4591076_1002 | GCP Site Audit | 2026-03-03 |  | 5 of 10 participant records reviewed, source documentation practices were not in accordance with ALCOACCEA (Attributable, Legible, Contemporaneous, Original, Accurate, and Complete, Consistent, Enduring and Available) criteria [Pfizer Protocol C4591076 (Amendment 1: 26 Aug 2025); ICH E6 (R3) 2.12.2]. a. For Participant 10021013's Adverse Event (AE) #2, Urinary Tract Infection, documentation on the AE worksheet was incomplete, as the day of site awareness of the AE was recorded but the time of awareness was missing. b. For Visit 202, the Principal Investigator/Sub-Investigator did not document confirmation of concomitant medication review by checking either 'Yes' or 'No' or by initialing and dating the assessment for the following participants: &nbsp; &nbsp; 1. &nbsp;Participant 10021029 (Visit 202 occurred 04 Nov 2025) &nbsp; &nbsp; 2. &nbsp;Participant 10021051 (Visit 202 occurred 07 Nov 2025) &nbsp; &nbsp; 3. &nbsp;Participant 10021079 (Visit 202 occurred 19 Nov 2025) &nbsp; &nbsp; 4. &nbsp;Participant 10021080 (Visit 202 occurred 18 Nov 2025) c. &nbsp;Additionally, an inconsistency was observed between the Delegation of Authority Log and the Site Master Signature Log, whereby a Study Coordinator (who consented participants) was recorded on the delegation record but was absent from the corresponding signature log. This deficiency compromises the site’s ability to demonstrate attributable, complete, and accurate documentation of personnel authorization. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Ann Frances; Kathy Hendricks | Issued | Pending Finding Closure | Data Collection and Management | Inadequate source data/documentation | NOT APPLICABLE; NOT APPLICABLE | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Vaccines | Amanda Feliciano Morales | GSSO | 84 | AMERICAS
AIA-009630 | QE-230539 | [5 empty] | Minor |  | Jose Cardona, Jose Cardona | UNITED STATES | C4591076_1002 | GCP Site Audit | 2026-03-03 |  | For 2 of 10 participants’ records reviewed, a discrepancy was noted between the Case Report Form (CRF) and the source documentation [C4591076 CRF Completion Requirements Version 4, 05 Dec 2025; ICH GCP E6 (R3) Section 2.12.5]. a. For Participant 10021007, the source documentation recorded an Intrauterine Device Implant (Copper-T) implanted in 2000, which was not entered in the electronic Case Report Form (eCRF). b. For Participant 10021007, the source documentation recorded allergies to dust and chemicals (including chlorine), which were not entered in the eCRF. c. For Participant 10021080, the source documentation recorded a diagnosis of Gastroesophageal Reflux Disease (GERD) with an onset date of unknown/unknown/2024, which was not entered in the eCRF. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Ann Frances; Kathy Hendricks | Issued | Pending Finding Closure | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | NOT APPLICABLE; NOT APPLICABLE | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Vaccines | Amanda Feliciano Morales | GSSO | 84 | AMERICAS
AIA-008070 | QE-217255 | 2026-03-02 | 2026-01-08 |  | Completed On Time |  | Minor |  | Kevin Cannon, Kevin Cannon | UNITED STATES | C4591076_1004 | GCP Site Audit | 2025-12-11 |  | For 7 of 16 participants records reviewed, discrepancies were identified between the source data in the Electronic Health Record (EHR) and the information recorded in the electronic case report form (e- CRF).[Ref:&nbsp; C4591076 Protocol Amendment 1, 26 Aug 2025; Data Management Plan – Case Report Form (CRF) Completion Requirements 3.0, 29 Sep 2025] a. For participant 10041005, the electronic Case Report Form V2W2 FUP for the visit on 22 Jul 2025 recorded the vaccine injection body side as “left,” while the CRIO electronic health record source data stated “Right.” b. For participant 10041015, the electronic Case Report Form V2W2 FUP for the visit on 21 Jul 2025 recorded the vaccine injection body side as “Left,” while the CRIO electronic health record source data stated “Right.” c. For participant 10041024, the electronic Case Report Form V2W2 FUP for the visit on 22 Jul 2025 recorded the vaccine injection body side as “Left,” while the CRIO electronic health record source data stated “Right.” d. For participant 10041041, the electronic Case Report Form V202MTH1 for the visit on 06 Nov 2025 recorded the vaccine injection body side as “Left,” while the CRIO electronic health record source data stated “Right.” e. For participant 10041056, the electronic Case Report Form V201D1VX&nbsp; VACINTRT&nbsp; for the visit on 22 Jul 2025 recorded the vaccine injection body side as “Right,” while the CRIO electronic health record source data stated “Left.” f. For participants 10041007 and 10041018, the electronic Case Report Form did not include the medical history of “Ex-smoker,” which was recorded in the CRIO electronic health record for these participants.&nbsp; The site explained that the “Ex-smoker” history was the underlying medical condition supporting eligibility for study entry and that there was no field in the electronic Case Report Form to record this information. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | SCP documented issue description and completion of corrective action in Siebel (CTMS Issue IDs: 1-AJGFO14, 1-AJGFO4A, 1-AJGFO4Z, 1-AJGFO86, 1-AJGFO53, 1-AJGFO44, 1-AJGFO18). | Site staff to correct the data entered into the electronic Case Report Forms (eCRFs) to ensure the data is consistent with source documentation for the following participants: 10041005, 10041007, 10041015, 10041018, 10041024, 10041041, 10041056. Clinical Research Associate (CRA) confirmed site staff corrections and will document completion in the Issues and Actions Log.Responsible Role: Site Staff, Clinical Research Associate | Ann Frances |  | - | Ann Frances; Michael Wilson | Closed | Closed | Data Collection and Management | Inadequate source data/documentation | DMB07 - CRF and Database Design | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Vaccines | Michael Wilson | GSSO | 84 | AMERICAS
AIA-008070 | QE-217254 | 2026-03-02 | 2025-12-09 |  | Completed On Time |  | Minor |  | Kevin Cannon, Kevin Cannon | UNITED STATES | C4591076_1004 | GCP Site Audit | 2025-12-11 |  | The Electronic Case Report Form (e-CRF) Completion Requirements were not consistently followed due to the site’s misunderstanding of some of the instructions and/or where in e-CRF to enter the source data information. [Ref: Data Management Plan - Case Report Form (CRF) Completion Requirements 3.0, 29Sep2025] 1.The electronic data capture (EDC) e-CRF COVID ILL -COVID TEST form was incorrectly completed for 4 of 13 participants (with a COVID Illness form populated) that were reviewed. The e-CRF completion requirements noted that this form should only be populated when local COVID testing was done. This form was instead populated for these 4 participants even though their electronic health (EHR) records stated that the COVID testing was done using the sponsor supplied nasal swabs that were submitted to the central lab. The 4 impacted participants records were 10041009, 10041015, 10041027, and 10041040. 2.Participant 10041054 had a COVID Illness e-CRF form completed for a Remote Audit Video visit instead of an Unplanned Visit. The details of this visit were not COVID Illness related. 3.The electronic data capture (EDC) e-CRF TRIGGER FORM-COHORT SELECTION was incorrectly populated for 7 of 23 randomized cohort 1 participants even though the e-CRF Completion Requirements noted that that the “no” response to this e-CRF TRIGGER FORM-COHORT SELECTION was not applicable and should not be selected. All cohort 1 participants automatically have no response to the e-CRF TRIGGER FORM-COHORT SELECTION question. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Auditor and SCP discussed finding with site personnel. Site updated EDC as required. | See QE regarding eCRF issues. | Michael Wilson |  | - | Ann Frances; Michael Wilson | Closed | Closed | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | DMB07 - CRF and Database Design | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Vaccines | Michael Wilson | GSSO | 84 | AMERICAS
AIA-008070 | QE-217254 | 2026-03-02 | 2025-12-09 |  | Completed On Time |  | Minor |  | Kevin Cannon, Kevin Cannon | UNITED STATES | C4591076_1004 | GCP Site Audit | 2025-12-11 |  | The Electronic Case Report Form (e-CRF) Completion Requirements were not consistently followed due to the site’s misunderstanding of some of the instructions and/or where in e-CRF to enter the source data information. [Ref: Data Management Plan - Case Report Form (CRF) Completion Requirements 3.0, 29Sep2025] 1.The electronic data capture (EDC) e-CRF COVID ILL -COVID TEST form was incorrectly completed for 4 of 13 participants (with a COVID Illness form populated) that were reviewed. The e-CRF completion requirements noted that this form should only be populated when local COVID testing was done. This form was instead populated for these 4 participants even though their electronic health (EHR) records stated that the COVID testing was done using the sponsor supplied nasal swabs that were submitted to the central lab. The 4 impacted participants records were 10041009, 10041015, 10041027, and 10041040. 2.Participant 10041054 had a COVID Illness e-CRF form completed for a Remote Audit Video visit instead of an Unplanned Visit. The details of this visit were not COVID Illness related. 3.The electronic data capture (EDC) e-CRF TRIGGER FORM-COHORT SELECTION was incorrectly populated for 7 of 23 randomized cohort 1 participants even though the e-CRF Completion Requirements noted that that the “no” response to this e-CRF TRIGGER FORM-COHORT SELECTION was not applicable and should not be selected. All cohort 1 participants automatically have no response to the e-CRF TRIGGER FORM-COHORT SELECTION question. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | SCP documented issue description and completion of corrective action in Siebel (CTMS Issue IDs: 1-AJGFO07, 1-AJGFO79, 1-AJGFO7D, 1-AJGFO81, 1-AJGFO0C). | Site staff to follow the electronic Case Report Form (eCRF) Completion Requirements to correct the data entered in the eCRFs for the following participants: 10041009, 10041015, 10041027, 10041040, 10041054. Clinical Research Associate (CRA) confirmed site staff corrections and will document completion in the Issues and Actions Log.Responsible Role: Site Staff, Clinical Research Associate | Ann Frances |  | - | Ann Frances; Michael Wilson | Closed | Closed | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | DMB07 - CRF and Database Design | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Vaccines | Michael Wilson | GSSO | 84 | AMERICAS