## Standard_Quality_Dashboard - QE
Observation ID | Study ID | Targeted | PR ID | Site(s) | principal Investigator | EX Comp? | QE Threshold | Status | Observation Description (as submitted) | Awareness Date | Submission Date | Assessment Date | Title/Short Description | Business CAPA Plan Endorsed On | CAPA Plan in Place | Last Action Due Date | Investigation Summary and Conclusion | Effectiveness Check Required | Effectiveness Check Rationale | Investigation Completion Date | Closed On | PDAL Decision | Level 1 | Level 2 | Quality CAPA Plan Endorsed On | Quality Reviewer Approved On | Business Process | Submitter | Confirmed Serious Breach | Remediation Actions Taken (when QE was submitted) | CAPA Action Details | CAPA Action Owner | Root Cause Description | Root Cause Level 1 | Root Cause Level 2 | Root Cause Level 3 | Rapid Model | Business Category
QE-189230 | C4591076 | (Empty) | QE-189230 |  | PFIZER | N | Minor | Closed | Site was activated without PI having access to Inform account access. | 2025-07-07 | 2025-07-08 | 2025-07-08 19:16 | GCP_Minor_Jul-2025_C4591076: Site Activation_Pfizer_USA |  | NO |  |  | No |  |  | 2025-07-08 |  | Quality Procedures | Requirement/process not met |  |  | INV04-Investigational Site Management and Monitoring | Amanda Feliciano Morales |  | Backup SCP covering for the site identified that PI did not had access to InForm after the site email the backup SCP. The Backup SCP contacted Pfizer Account provisioning to ensure resolution of this matter. Later that day the site contacted the backup SCP via phone call to confirm site access and confirmed PI still did not had InForm access. Backup SCP informed Study Manager of the situation. At the time Site Selection Letter was already sent to the site. As soon as this was brought to the study team attention the SAP contacted the site and ask to hold enrollment until further noticed. SCP of the site contacted the site via phone call and got verbal confirmation that the PI was able to log in to his Inform account. Additionally, SIV Report wasn't finalized before the site was sent the Site Activation Letter. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-189975 | C4591076 | N | QE-189975 | 1004 | Kevin Cannon (C4591076-1004) | N | Major | Closed | C4591076 Site 1004, 19 of 23 enrolled patients didn’t meet Inclusion #4, receipt of Omicron KP.2 &gt;6 months prior to enrollment. Patients affected: 10041001, 10041002, 10041003, 10041005, 10041006, 10041007,10041008, 10041009, 10041010, 10041011, 10041012, 10041015, 10041018, 10041019, 10041020, 10041021, 10041022, 10041023, and 10041024 | 2025-07-11 | 2025-07-11 | 2025-07-14 13:43 | GCP_Major_Jul-2025_C4591076: Protocol Deviation: Inclusion/Exclusion Criteria_Cannon, Kevin_USA |  | YES |  | <p><span style="font-size: small;">Product Protocol Number:</span></p><p><span style="font-size: small;">C4591076</span></p><p><span style="font-size: small;"><br></span></p><p><span style="font-size: small;">Involved Party / Site Number (if applicable) / Country:</span></p><p><span style="font-size: small;">PI: Cannon, Kevin (Site Number:1004) / United States</span></p><p><span style="font-size: small;"><br></span></p><p><span style="font-size: small;">Protocol Title(s):</span></p><p><span style="font-size: small;">The C4591076 study is a Phase 3 Protocol to Investigate the Safety, Tolerability, and Immunogenicity of BNT162b2 RNA-Based Variant-Adapted Vaccine Candidate(s) Against SARS-CoV-2 in Adults, Including Those at Higher Risk of Severe COVID-19.</span></p><p><span style="font-size: small;"><br></span></p><p><span style="font-size: small;">Description of Issue(s):</span></p><p><span style="font-size: small;">On 11-Jul-2025, the Pfizer Site Care Partner (SCP) reported that 19 of the 23 enrolled participants at site 1004 in the C4591076 study did not meet the Inclusion Criteria #4 as having received a COVID-19 vaccine containing Omicron KP.2 greater than 6-months (&gt;175 days) prior to enrollment into the study.&nbsp;</span></p><p><span style="font-size: small;"><br></span></p><p><span style="font-size: small;">Participants affected included:10041001, 10041002, 10041003, 10041005, 10041006, 10041007, 10041008, 10041009, 10041010, 10041011, 10041012, 10041015, 10041018, 10041019, 10041020, 10041021, 10041022, 10041023, and 10041024.</span></p><p><span style="font-size: small;"><br></span></p><p><span style="font-size: small;">All 19 participants remain active in the study and no Serious Adverse Events (SAEs) were reported because of this error.</span></p><p><br></p> | No | Study/Program/Activity ended and issue does not impact other studies/programs/activities | 2025-08-21 | 2026-01-09 |  | Protocol Deviations | Failure to comply with protocol inclusion/exclusion criteria |  | 2025-08-22 12:56 | CT40-Management of Protocol Deviations | Michael Wilson | FALSE | SCP escalated to DSMM and SMs upon awareness from site 1004. |  |  | The site staff misread the Informed Consent Document (ICD) and did not notice the inclusion criteria update in the C4591076 study during the 2-day enrollment period.&nbsp; | Human Performance | Omission Error | Know But Confused (Incorrectly Completed) - Physiological Factors/Stressors Controls Non-Optimal | MODEL 1 - INSOURCED | Vaccines
QE-191489 | C4591076 | N | QE-191489 | 1001, 1002, 1003, 1004, 1005 | Helen Stacey (C4591076-1005), James Peterson (C4591076-1003), Jose Cardona (C4591076-1002), Kevin Cannon (C4591076-1004), William Howitt (C4591076-1001) | N | Minor | Closed | Study C4591076: VerifiedClinicalTrials (VCT) vendor provided with scanner for verification fo subjects however the compliance of use of scanners were lower than other Vaccine studies 47%. Usual VCT compliance for studies with the same number of subjects is 55%-60%. 2 out of 5 had issues with Firewall and cybersecurity set-up. One site was able to set up correctly device but experienced same issue at the time of the enrollment preventing them to use scanner device. | 2025-07-18 | 2025-07-22 | 2025-07-22 15:38 | GCP_Minor_Jul-2025_C4591076: Participant Verification Process_Verified Clinical Trials; Multiple Sites_USA |  | NO |  |  | No |  |  | 2025-07-22 |  | Equipment, Facility and Sample/Specimens, Protocol Deviations | Failure to comply with protocol inclusion/exclusion criteria, Inadequate equipment/lab supply mgmt. |  |  | No Process Assigned | Luis Alfredo Rosales Rubio |  | Sites used Bypassing option provided by VCT for that cases and check the subject in this way.Enrollment completed so no other CAPAs needed. QE reported as issue ca n affect other Pfizer studies with the same vendor. |  |  | NA | Equipment/System/Facility | System/Application |  | MODEL 1 - INSOURCED | Vaccines
QE-191489 | C4591076 | (Empty) | QE-191489 |  | VERIFIED CLINICAL TRIALS | N | Minor | Closed | Study C4591076: VerifiedClinicalTrials (VCT) vendor provided with scanner for verification fo subjects however the compliance of use of scanners were lower than other Vaccine studies 47%. Usual VCT compliance for studies with the same number of subjects is 55%-60%. 2 out of 5 had issues with Firewall and cybersecurity set-up. One site was able to set up correctly device but experienced same issue at the time of the enrollment preventing them to use scanner device. | 2025-07-18 | 2025-07-22 | 2025-07-22 15:38 | GCP_Minor_Jul-2025_C4591076: Participant Verification Process_Verified Clinical Trials; Multiple Sites_USA |  | NO |  |  | No |  |  | 2025-07-22 |  | Equipment, Facility and Sample/Specimens, Protocol Deviations | Failure to comply with protocol inclusion/exclusion criteria, Inadequate equipment/lab supply mgmt. |  |  | No Process Assigned | Luis Alfredo Rosales Rubio |  | Sites used Bypassing option provided by VCT for that cases and check the subject in this way.Enrollment completed so no other CAPAs needed. QE reported as issue ca n affect other Pfizer studies with the same vendor. |  |  | NA | Equipment/System/Facility | System/Application |  | MODEL 1 - INSOURCED | Vaccines
QE-193467 | C4591076 | N | QE-193467 | 1002 | Jose Cardona (C4591076-1002) | N | Minor | Closed | On 17Jul2025 sSOM Nicolas Balling informed SCP that it was identified that site 1002 in C4591076 have been shipping nasal swabs in 1 mL UTM vials instead of 3 mL vials. While the swabs can still be analyzed, please note that for this study Fisher did not provide 1 mL UTM vials which therefore should not be used.The Lab Manual (fig.11) has been updated to removed misleading instructions to use 1 mL UTM vials for swab collection and this will be mentioned in the upcoming newsletter.SCP reach out to the site to clarify how they got to use 1mL UTM vials via email on 17jJul2025. The site confirms on the same date that they receive the UTM 3mL and that the 1mL was used inadvertently instead of the 3mL tubes and the incorrect box was set out for the screening of these subjects. | 2025-07-17 | 2025-07-31 | 2025-07-31 19:05 | GCP_Minor_Jul-2025_C4591076: Nasal Swabs_Cardona, Jose_USA |  | NO |  |  | No |  |  | 2025-07-31 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens | Amanda Feliciano Morales |  | The site was informed of this error and that they should be using the 3mL UTM vials as state per Lab Manual. It was also confirmed the site has the correct supplies on 3ml UTM vial onsite. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-195566 | C4591076 | (Empty) | QE-195566 |  | PFIZER | N | Minor | Closed | C4591076 is an open-label study for which a dataset was prepared on 12-Aug-2025 to support a Level 1 interim 14-Day Post Dose deliverable for analysis. This dataset included immunogenicity data. While immunogenicity data for this study is not considered sensitive by the study team, it is managed as a sensitive clinical data file for processing and loading purposes. According to DMB08-GSOP section 4.3, sensitive clinical data files should be shared only after confirmation of the release of randomization codes. However, for the dataset prepared on 12-Aug-2025, the immunogenicity data was shared with the SDSA analysis programmer team prior to the release of the randomization codes. | 2025-08-13 | 2025-08-13 | 2025-08-13 19:37 | GCP_Minor_Aug-2025_C4591076: Database Release (Randomization Codes)_Pfizer_USA |  | NO |  |  | No |  |  | 2025-08-13 |  | Quality Procedures | Requirement/process not met |  |  | DMB08-Study Data Set Review Release and Archive | Tifani Dawson |  | Team was advised to await confirmation of randomization code release to proceed further and the randomization release was subsequently confirmed on 13-Aug-2025. The team reviewed the appropriate steps to ensure that this will not occur again. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-195909 | C4591076 | (Empty) | QE-195909 |  | PFIZER | N | Minor | Closed | The LLOQ (lower limit of quantification) and LOD (limit of detection) supplemental parameter values were missing in the sensitive data transfers for the COV2_3G_LP81_NT50 assay results for C4591076 and C4591054. The assay results in both studies are to support the C4591076 – 14 day post dose safety and immunogenicity analysis. The LLOQ and LOD values are required for the analysis and defined as expected in the DTS. | 2025-08-12 | 2025-08-15 | 2025-08-15 14:57 | GCP_Minor_Aug-2025_C4591076; C4591054: Dataset Transfer and Release_Pfizer_Global |  | NO |  |  | No |  |  | 2025-08-15 |  | IT Systems | Inadequate Data Conversion / Data Migration / Data Extension / Report Configuration |  |  | DMB08-Study Data Set Review Release and Archive | Tifani Dawson |  | Vaccines Lab Data Management team informed of the issue late evening on 12-Aug-2025. DMB08-WI-GL03-RF04 impact assessment completed. |  |  | NA | Equipment/System/Facility | System/Application |  | MODEL 1 - INSOURCED | Vaccines
QE-198369 | C4591076 | N | QE-198369 | 1005 | Helen Stacey (C4591076-1005) | N | Minor | Closed | On 17 Jul 2025 sSOM informed SCP that it was identified that C4591076 Site 1005 had been shipping nasal swabs in 1 mL UTM vials instead of 3 mL vials. While the swabs can still be analyzed, please note that for this study Fisher did not provide 1 mL UTM vials which therefore should not be used. This also happened at Site 1002, which was reported as QE-193467. | 2025-07-17 | 2025-08-28 | 2025-08-29 15:22 | GCP_Minor_Aug-2025_C4591076: Sample Management: Nasal Swabs_Stacey, Helen_USA |  | NO |  |  | No |  |  | 2025-08-29 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | No Process Assigned | Nicolas Balling |  | The Lab Manual (fig.11) has been updated to removed misleading instructions to use 1 mL UTM vials for swab collection and this will be mentioned in the upcoming newsletter. The site was informed of this error and that they should be using the 3mL UTM vials as state per Lab Manual. It was also confirmed the site has the correct supplies on 3ml UTM vial onsite. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-199654 | C4591076 | (Empty) | QE-199654 |  | PFIZER | N | Minor | Closed | Thermofisher, the ancillary supply provider for clinical study C4591076, prepared nasal swab collection kits. Upon completion of this task on 24-Jun-2025, the Thermofisher Project Manager sent the Production Batch record/Certificate of QA Approval Document (EBR) to the Study Operations Manager (sSOM) in charge for review and signature. The EBR was signed by the sSOM on the same day. On 04-Sep-2025, the SWAT Study Manager informed the sSOM that according to Pfizer QA, study managers were not expected to sign EBRs since these documents contain quality-related contents. | 2025-09-04 | 2025-09-04 | 2025-09-05 16:05 | GCP_Minor_Sep-2025_C4591076: Study Responsibilities: Document Signature_Pfizer_USA |  | NO |  |  | No |  |  | 2025-09-05 |  | Quality Procedures | Requirement/process not met |  |  | CT48-Study Operational Management | Nicolas Balling |  | This event has been escalated to the Pfizer Director of Logistics and the Local &amp; Ancillary Sourcing Lead for guidance on remediation. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-207135 | C4591076 | N | QE-207135 | 1003, 1017, 1020 | David Wheeler (C4591076-1020), James Peterson (C4591076-1003), Susann Varano (C4591076-1017) | N | Minor | Closed | Study Management was informed by the Scientist at Clinical Immunology and Diagnostics (formerly Vaccines Research and Development) that they received nasal swabs vials, 14 in total, from several C4591076 cohort 2 sites that included the study participant ID on them which is considered Protected Health Information (PHI). A second email listed the sites: 1003, 1008, 1017, 1019, 1020, impacting 5 shipments, indicating that may provide additional sites. | 2025-10-14 | 2025-10-15 | 2025-10-15 21:16 | GCP_Minor_Oct-2025_C4591076: Participant Confidentiality / Data Privacy_Multiple Sites_USA |  | NO |  |  | No |  |  | 2025-10-15 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Susan Macera |  | CSOM was requested to have the CRAs follow up with the 5 sites to remind them not to include PHI on the nasal swab vials as per the guidance in the lab manual. A reminder will also be included in the next upcoming newsletter. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-207135 | C4591076 | Y | QE-207135 | 1008, 1019 | Matthew Davis (C4591076-1019), Shane Christensen (C4591076-1008) | N | Minor | Closed | Study Management was informed by the Scientist at Clinical Immunology and Diagnostics (formerly Vaccines Research and Development) that they received nasal swabs vials, 14 in total, from several C4591076 cohort 2 sites that included the study participant ID on them which is considered Protected Health Information (PHI). A second email listed the sites: 1003, 1008, 1017, 1019, 1020, impacting 5 shipments, indicating that may provide additional sites. | 2025-10-14 | 2025-10-15 | 2025-10-15 21:16 | GCP_Minor_Oct-2025_C4591076: Participant Confidentiality / Data Privacy_Multiple Sites_USA |  | NO |  |  | No |  |  | 2025-10-15 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Susan Macera |  | CSOM was requested to have the CRAs follow up with the 5 sites to remind them not to include PHI on the nasal swab vials as per the guidance in the lab manual. A reminder will also be included in the next upcoming newsletter. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-208013 | C4591076 | N | QE-208013 | 1004 | Kevin Cannon (C4591076-1004) | N | Major | Approved - In Effectiveness Check | For study C4591076 cohort 1, 2 participants, 10041020 and 10041024, samples for Visit 2/Week 2 follow up (18 in total) were processed under 40 minutes (i.e. min clot time of 30 mins and centrifuge for 10 to 15 minutes per the lab manual). The SCP when following up with site 1004 to clarify, the site noted the following: The CRC confirmed that samples were coagulated prior to centrifuging and processing. Clinical Immunology and Diagnostics confirmed that will test the samples, clinical was informed and a decision to keep the results will be made by Clinical. It was confirmed by Clinical these do not need to be recorded as protocol deviations. For cohort 2, as of 20Oct, there were additional samples identified under the 40 minute threshold, across 9 sites, 16 participants, 138 samples for the visit V201/Day 1 Vax. The CRAs have been requested to follow up with the sites and the team is awaiting clarification confirmation that these were under 40 mins. If there is lab/source documentation (i.e., a sample processing log) available documenting processing times (collection, aliquot etc.) for the protocol samples, the sites will be requested to submit a data change request to update the data as appropriate. For any confirmed as under 40 minutes, the CRAs will need to retrain sites and document the retraining. It was requested not to enter PDs from Asset DSM, as awaiting further guidance regarding the outcome of a QRT meeting. The team was requested today to submit this as a QE as understand there is a similar QE for other studies using TruLab (QE-182467) where the TruLab app was not used in real time. Details of the potential ppts and sites impacted as of 20Oct are attached. | 2025-10-20 | 2025-10-20 | 2025-10-21 11:32 | GCP_Major_Oct-2025_C4591076: Sample Data Collection_Pfizer; TruLab, Cannon, Kevin_USA |  | YES |  | <p>It was reported on 21 Oct 2025 that the sample processing data for nine sites on protocol C4591076 was not aligned with the lab manual requirements for sample processing times. &nbsp;The sample processing data is captured via the TruLab application at all sites for the protocol. &nbsp;The application is to be used in real time to capture timepoints associated with sample collection, processing and shipment. &nbsp;</p><p>&nbsp;</p><p>The TruLab Application is a mobile-based data capture application for biospecimens that eliminates the need to capture sample collection information in the Electronic Sample Tracking Case Report Form (CRF). &nbsp;Information related to the samples and sample tracking is available in data transfers from the TruLab vendor and via site-facing dashboards. &nbsp; The TruLab mobile devices were employed at sites for the impacted protocols and users were instructed to utilize the application as source data for participant sample collection and processing. &nbsp;</p><p>&nbsp;</p><p>The non-contemporaneous use of the TruLab Application by site users impacted the data integrity of the corresponding samples, as the data was not aligned with the protocol required sample processing procedures. Following the completion of the investigation, it was confirmed that 0.2% of samples at one site had no other source for sample processing data existed. All other reported sites confirmed an alternate source for sample data and therefore were not impacted.&nbsp;</p><p>&nbsp;</p><p>An historical review was conducted of Quality Events (QEs) in the eQMS database to identify QEs that meet the following search criteria:&nbsp;</p><ul><li>Keywords: Sample</li><li>Timeframe: 2 years; 01 Jun 2023 – 19 Nov 2025</li></ul><p>Each historical QE was reviewed along with the QE Details, Root Causes, and Corrective and Preventive Action(s). Through this review, it was concluded that the current QE (QE-208013) is not a repeat occurrence.</p> | Yes |  | 2025-11-24 |  |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  | 2025-11-25 14:23 | CT29-Management of Clinical Study BioSpecimens, QMS09-Vendor Engagement | Susan Macera | FALSE | For cohort 2, the CRAs are following up with the sites that are under 40 minutes to clarify regarding these samples. If there is lab/source documentation (i.e., a sample processing log) available documenting processing times (collection, aliquot etc.) for the protocol samples, the sites will be requested to submit a data change request to update the data as appropriate. For any confirmed as under 40 minutes, the CRAs will need to retrain sites and document the retraining. |  |  | Site lab personnel are not always remembering to use the TruLab Application in real time for all samples processed for C4591076. &nbsp;, Site lab personnel were aware of the lab manual requirements for sample processing (minimum 40 minutes from collection to aliquot), however chose to centrifuge samples for two participants prior to the required sample rest time as they appeared to be clotting faster than anticipated. &nbsp; | Human Performance | Decision Error, Learning Error | Consequences of Decision Was not Known/Understood - Impact of Deviations/Variance in Process/Task not Known, Lack of or Inadequate Training Provided or Not Trained on Latest Version | MODEL 1 - INSOURCED | Vaccines
QE-208013 | C4591076 | (Empty) | QE-208013 |  | PFIZER, TRULAB INC | N | Major | Approved - In Effectiveness Check | For study C4591076 cohort 1, 2 participants, 10041020 and 10041024, samples for Visit 2/Week 2 follow up (18 in total) were processed under 40 minutes (i.e. min clot time of 30 mins and centrifuge for 10 to 15 minutes per the lab manual). The SCP when following up with site 1004 to clarify, the site noted the following: The CRC confirmed that samples were coagulated prior to centrifuging and processing. Clinical Immunology and Diagnostics confirmed that will test the samples, clinical was informed and a decision to keep the results will be made by Clinical. It was confirmed by Clinical these do not need to be recorded as protocol deviations. For cohort 2, as of 20Oct, there were additional samples identified under the 40 minute threshold, across 9 sites, 16 participants, 138 samples for the visit V201/Day 1 Vax. The CRAs have been requested to follow up with the sites and the team is awaiting clarification confirmation that these were under 40 mins. If there is lab/source documentation (i.e., a sample processing log) available documenting processing times (collection, aliquot etc.) for the protocol samples, the sites will be requested to submit a data change request to update the data as appropriate. For any confirmed as under 40 minutes, the CRAs will need to retrain sites and document the retraining. It was requested not to enter PDs from Asset DSM, as awaiting further guidance regarding the outcome of a QRT meeting. The team was requested today to submit this as a QE as understand there is a similar QE for other studies using TruLab (QE-182467) where the TruLab app was not used in real time. Details of the potential ppts and sites impacted as of 20Oct are attached. | 2025-10-20 | 2025-10-20 | 2025-10-21 11:32 | GCP_Major_Oct-2025_C4591076: Sample Data Collection_Pfizer; TruLab, Cannon, Kevin_USA |  | YES |  | <p>It was reported on 21 Oct 2025 that the sample processing data for nine sites on protocol C4591076 was not aligned with the lab manual requirements for sample processing times. &nbsp;The sample processing data is captured via the TruLab application at all sites for the protocol. &nbsp;The application is to be used in real time to capture timepoints associated with sample collection, processing and shipment. &nbsp;</p><p>&nbsp;</p><p>The TruLab Application is a mobile-based data capture application for biospecimens that eliminates the need to capture sample collection information in the Electronic Sample Tracking Case Report Form (CRF). &nbsp;Information related to the samples and sample tracking is available in data transfers from the TruLab vendor and via site-facing dashboards. &nbsp; The TruLab mobile devices were employed at sites for the impacted protocols and users were instructed to utilize the application as source data for participant sample collection and processing. &nbsp;</p><p>&nbsp;</p><p>The non-contemporaneous use of the TruLab Application by site users impacted the data integrity of the corresponding samples, as the data was not aligned with the protocol required sample processing procedures. Following the completion of the investigation, it was confirmed that 0.2% of samples at one site had no other source for sample processing data existed. All other reported sites confirmed an alternate source for sample data and therefore were not impacted.&nbsp;</p><p>&nbsp;</p><p>An historical review was conducted of Quality Events (QEs) in the eQMS database to identify QEs that meet the following search criteria:&nbsp;</p><ul><li>Keywords: Sample</li><li>Timeframe: 2 years; 01 Jun 2023 – 19 Nov 2025</li></ul><p>Each historical QE was reviewed along with the QE Details, Root Causes, and Corrective and Preventive Action(s). Through this review, it was concluded that the current QE (QE-208013) is not a repeat occurrence.</p> | Yes |  | 2025-11-24 |  |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  | 2025-11-25 14:23 | CT29-Management of Clinical Study BioSpecimens, QMS09-Vendor Engagement | Susan Macera | FALSE | For cohort 2, the CRAs are following up with the sites that are under 40 minutes to clarify regarding these samples. If there is lab/source documentation (i.e., a sample processing log) available documenting processing times (collection, aliquot etc.) for the protocol samples, the sites will be requested to submit a data change request to update the data as appropriate. For any confirmed as under 40 minutes, the CRAs will need to retrain sites and document the retraining. |  |  | Site lab personnel are not always remembering to use the TruLab Application in real time for all samples processed for C4591076. &nbsp;, Site lab personnel were aware of the lab manual requirements for sample processing (minimum 40 minutes from collection to aliquot), however chose to centrifuge samples for two participants prior to the required sample rest time as they appeared to be clotting faster than anticipated. &nbsp; | Human Performance | Decision Error, Learning Error | Consequences of Decision Was not Known/Understood - Impact of Deviations/Variance in Process/Task not Known, Lack of or Inadequate Training Provided or Not Trained on Latest Version | MODEL 1 - INSOURCED | Vaccines
QE-208504 | C4591076 | N | QE-208504 | 1004, 1018 | David Diemert (C4591076-1018), Kevin Cannon (C4591076-1004) | N | Minor | Closed | Study Management was informed by the Scientist at Clinical Immunology and Diagnostics (formerly Vaccines Research and Development/VRD) that they received additional nasal swabs vials from C4591076 cohort 2 sites that included the study participant ID on them which is considered Protected Health Information (PHI). Clinical Immunology and Diagnostics confirmed that the lab is redacting the participant ID. The following sites were impacted: 1004, 1012 and 1018. A previous, quality event, QE-207135, assessed as minor was submitted for nasal swabs at sites 1003, 1008, 1017, 1019 and 1020, for the same issue. Including the 5 sites from QE-207135, and these additional 3 sites this appears to apply to 189 nasal swabs as of 21Oct (please see attached). Two additional issues were also discovered – 4 nasal swabs without barcodes and 1 nasal swab with 2 barcodes. These will be submitted as separate QEs. | 2025-10-21 | 2025-10-22 | 2025-10-23 18:55 | GCP_Minor_Oct-2025_C4591076 : Participant Confidentiality_Multiple Sites_USA |  | NO |  |  | No |  |  | 2025-10-23 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Susan Macera |  | CSOM requested the CRAs follow up with these sites to remind them not to include PHI on the nasal swab vials as per the guidance in the lab manual. These will be reported as protocol deviations and the IRB will also be notified. A reminder was included in the study newsletter. The study team is also including reminders in the daily enrollment updates being sent to the sites. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-208504 | C4591076 | Y | QE-208504 | 1012 | David Fitz-Patrick (C4591076-1012) | N | Minor | Closed | Study Management was informed by the Scientist at Clinical Immunology and Diagnostics (formerly Vaccines Research and Development/VRD) that they received additional nasal swabs vials from C4591076 cohort 2 sites that included the study participant ID on them which is considered Protected Health Information (PHI). Clinical Immunology and Diagnostics confirmed that the lab is redacting the participant ID. The following sites were impacted: 1004, 1012 and 1018. A previous, quality event, QE-207135, assessed as minor was submitted for nasal swabs at sites 1003, 1008, 1017, 1019 and 1020, for the same issue. Including the 5 sites from QE-207135, and these additional 3 sites this appears to apply to 189 nasal swabs as of 21Oct (please see attached). Two additional issues were also discovered – 4 nasal swabs without barcodes and 1 nasal swab with 2 barcodes. These will be submitted as separate QEs. | 2025-10-21 | 2025-10-22 | 2025-10-23 18:55 | GCP_Minor_Oct-2025_C4591076 : Participant Confidentiality_Multiple Sites_USA |  | NO |  |  | No |  |  | 2025-10-23 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Susan Macera |  | CSOM requested the CRAs follow up with these sites to remind them not to include PHI on the nasal swab vials as per the guidance in the lab manual. These will be reported as protocol deviations and the IRB will also be notified. A reminder was included in the study newsletter. The study team is also including reminders in the daily enrollment updates being sent to the sites. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-209303 | C4591076 | N | QE-209303 | 1018 | David Diemert (C4591076-1018) | N | Minor | Closed | For the C4591076 clinical trial, Site 1018/Diemert sent 4 Nasal Swabs to TruLabs (central lab vendor) with no barcode. | 2025-10-17 | 2025-10-27 | 2025-10-27 18:24 | GCP_Minor_Oct-2025_C4591076: Nasal Swabs_Diemert, David_USA |  | NO |  |  | No |  |  | 2025-10-27 |  | Protocol Deviations | Failure to follow protocol |  |  | CT40-Management of Protocol Deviations | Deidra Wells |  | The site was informed of the issue on 21Oct2025 when CRA was asked to reach out to the site to ascertain more information as to why vials were shipped without the required barcode. The PI was asked to generate a NTF detailing what led to the missing clinical barcodes and to also confirm site has sufficient supplies available. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-209912 | C4591076 | N | QE-209912 | 1004, 1011, 1020 | Antoinette Pragalos (C4591076-1011), David Wheeler (C4591076-1020), Kevin Cannon (C4591076-1004) | N | Minor | Closed | Study Management was informed by the Scientist at Clinical Immunology and Diagnostics (formerly Vaccines Research and Development/VRD) that they received additional nasal swabs vials from C4591076 cohort 2 sites that included the study participant ID on them which is considered Protected Health Information (PHI). Clinical Immunology and Diagnostics confirmed that the lab is redacting the participant ID. The following sites were impacted: 1004, 1007, 1011, 1019 and 1020. Please see attached list of additional samples impacted dated 29Oct2025. Previous, quality events, QE-201735 &amp; QE-208504, assessed as minor was submitted for nasal swabs with PHI/subject ID at sites 1003, 1004, 1008, 1012, 1017, 1018, 1019 and 1020, for the same issue. For the previous samples that arrived with PHI/subject ID, it was confirmed by the lab that samples can still be analyzed. | 2025-10-24 | 2025-10-29 | 2025-10-30 13:34 | GCP_Minor_Oct-2025_C4591076: Participant Confidentiality_Multiple Sites_USA |  | NO |  |  | No |  |  | 2025-10-30 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Susan Macera |  | CSOM will request the CRAs follow up with any impacted sites to remind the sites not to include PHI/participant ID on the nasal swab vials as per the guidance in the lab manual. The IRB will also be notified. A reminder was included in the study newsletter released 22Oct2025. The study team also included reminders in the daily enrollment updates sent to the sites. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-209912 | C4591076 | Y | QE-209912 | 1007, 1019 | Daniel Finn (C4591076-1007), Matthew Davis (C4591076-1019) | N | Minor | Closed | Study Management was informed by the Scientist at Clinical Immunology and Diagnostics (formerly Vaccines Research and Development/VRD) that they received additional nasal swabs vials from C4591076 cohort 2 sites that included the study participant ID on them which is considered Protected Health Information (PHI). Clinical Immunology and Diagnostics confirmed that the lab is redacting the participant ID. The following sites were impacted: 1004, 1007, 1011, 1019 and 1020. Please see attached list of additional samples impacted dated 29Oct2025. Previous, quality events, QE-201735 &amp; QE-208504, assessed as minor was submitted for nasal swabs with PHI/subject ID at sites 1003, 1004, 1008, 1012, 1017, 1018, 1019 and 1020, for the same issue. For the previous samples that arrived with PHI/subject ID, it was confirmed by the lab that samples can still be analyzed. | 2025-10-24 | 2025-10-29 | 2025-10-30 13:34 | GCP_Minor_Oct-2025_C4591076: Participant Confidentiality_Multiple Sites_USA |  | NO |  |  | No |  |  | 2025-10-30 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Susan Macera |  | CSOM will request the CRAs follow up with any impacted sites to remind the sites not to include PHI/participant ID on the nasal swab vials as per the guidance in the lab manual. The IRB will also be notified. A reminder was included in the study newsletter released 22Oct2025. The study team also included reminders in the daily enrollment updates sent to the sites. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-210878 | C4591076 | Y | QE-210878 | 1012 | David Fitz-Patrick (C4591076-1012) | N | Minor | Closed | Site 1012 submitted a swab sample labeled with direct subject identifiers on the tube. This constitutes a breach of the Lab Manual regarding the handling of Protected Health Information (PHI). This is the third documented occurrence of this issue from Site 1012. The presence of PHI on specimen samples delays testing and processing at the lab. | 2025-10-29 | 2025-11-04 | 2025-11-04 16:46 | GCP_Minor_Nov-2025_C4591076: Participant Confidentiality_Fitz-Patrick, David_USA |  | NO |  |  | No |  |  | 2025-11-04 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Fadela Hamadi |  | The site was reminded that no PHI should be included on any specimen samples. This instruction is clearly outlined in the Lab Manual. The CRA followed up with the site to reinforce this requirement. Retraining of site personnel was requested, and the date of retraining will be documented for records. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-216983 | C4591076 | (Empty) | QE-216983 |  | PFIZER | N | Minor | Closed | An internal email was inadvertently sent by CRA with details containing Protected Health Information (PHI), specifically DOB, which was then forwarded internally to the study team by the cSOM. This constitutes a potential privacy breach under Pfizer standards. | 2025-12-04 | 2025-12-05 | 2025-12-05 21:28 | GCP_Minor_Dec-2025_C4591076: Participant Confidentiality; Data Privacy_Pfizer_USA |  | NO |  |  | No |  |  | 2025-12-05 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Fadela Hamadi |  | GSM promptly identified the inclusion of PHI in the email body and immediately removed the sensitive information from the email thread. Clear instructions were provided to the CRA on next steps, including initiating a QE and reporting the incident per Pfizer compliance requirements. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-218856 | C4591076 | N | QE-218856 | 1004 | Kevin Cannon (C4591076-1004) | N | Minor | Closed | During internal site review, it was identified that a patient’s full name was entered into the Pfizer PSSA reporting tool instead of the subject’s unique study ID when responding to a query related to a reported SAE. The error occurred due to manual data entry by a former CRC during query resolution.The patient’s name was visible in the portal from 01Aug2025 until 17Nov2025 and has since been removed. A site staff member did a review in the system and confirmed no other patients have been impacted. The incident involved one subject only and this is an open label study. | 2025-11-20 | 2025-12-15 | 2025-12-16 18:30 | GCP_Minor_Dec-2025_C4591076: Participant Confidentiality_Cannon, Kevin_USA |  | NO |  |  | No |  |  | 2025-12-16 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Katherine Hoopes |  | Upon discovery of subject identifiers site staff removed the name from the PSSA tool and confirmed that no other subjects were impacted. Site reported this to the monitor on 20Nov2025 and monitor escalated to cSOM and reported this incident as a protocol deviation. Monitor was informed to submit QE on 15Dec2025. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-222457 | C4591076 | N | QE-222457 | 1009, 1022 | Yanely Pineiro Puebla (C4591076-1009), Yanely Pineiro Puebla (C4591081-1022) | N | Minor | Closed | A subject was erroneously enrolled in C4591076 (SSID 10091179) instead of C4591081 (SSID 10221179, site 1022, PI Pineiro Puebla) in Trial Manager/Signant Health for e-diary (vaccination, COVID Illness) reporting. | 2026-01-08 | 2026-01-12 | 2026-01-12 18:31 | GCP_Minor_Dec-2025_C4591076, C4591081: Trial Manager Participant Enrollment_Pineiro Puebla, Yanely_USA |  | NO |  |  | No |  |  | 2026-01-12 |  | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry |  |  | No Process Assigned | Elliot DeHaan |  | An email notification from Signant Health was received and investigated by the study team. It was confirmed in an email on Thursday January 8 that the subject had been intended to be enrolled in C4591081. An additional meeting on Monday January 12 confirmed these details and it was agreed that this met QE reporting criteria. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-224035 | C4591076 | (Empty) | QE-224035 |  | PAREXEL INTERNATIONAL | N | Minor | Closed | .5pt; background-image: initial; background-position: initial; background-size: initial; background-repeat: initial; background-attachment: initial; background-origin: initial; background-clip: initial;'CRA employment was terminated based on concerns related to quality of work and overall performance. .0pt"CRA was advised of termination on 16JAN26, last day of employment planned for 23JAN26. CRA departed with one day notice, instead of 7 day notice previously agreed upon. CRA did not complete monitoring visit report for two visits and did not address open PDs or issues prior to her exit. | 2026-01-20 | 2026-01-21 | 2026-01-21 16:55 | GCP_Minor_Jan-2026_C4591076, C5091017: CMCD: Monitoring Responsibilities: Employment_Parexel_USA |  | NO |  |  | No |  |  | 2026-01-21 |  | Site Management and Monitoring | Failure to detect/document |  |  | INV04-Investigational Site Management and Monitoring | Shawn Szalay |  | CRA was removed from Pfizer partnership with Parexel. |  |  | NA | Personnel | Lack of or Inadequate Oversight |  | MODEL 1 - INSOURCED | Vaccines
QE-229748 | C4591076 | (Empty) | QE-229748 |  | PFIZER | N | Minor | Closed | During assessment of the need for a protocol amendment, it was identified that Protocol Administrative Change Letters (PACLs) had previously been issued for studies C4591082 and C4591076 to clarify a primary immunogenicity objective. At the time of submission, the PACLs were assessed and classified as non‑substantial and were endorsed by Regulatory. Subsequent re-review against the REG03‑GSOP‑RF05 SOP identified that the change may have met criteria for a substantial amendment, as it related to a primary study objective. While RF05 Table 1 lists changes to primary objectives as substantial, the update to the primary objective was considered a minor clarification (non-substantial) rather than a change. Per RF05, the table is intended as general guidance only, providing examples typically considered to be substantial or non-substantial, and allowing for sponsor case‑by‑case determination, based on the assessment conducted at the time.At the time of the PACL, the team evaluated if the change in wording of the primary objective would impact any aspect of the analysis of the primary objective. After confirming no change to the intended analysis, no change to the scientific intent of the objective, and that the rewording was cosmetic, the proposed change was reviewed with Regulatory and deemed non‑substantial.The clarification was implemented in response to CBER feedback received on 26‑Sep‑25 requesting clarification of the term “superiority” used in the objectives and statistical analysis sections. The feedback indicated that the terminology could be misinterpreted as implying a between‑intervention comparison, whereas the intended assessment was a within‑group, threshold‑based immunogenicity evaluation. | 2026-02-18 | 2026-02-23 | 2026-02-23 19:27 | GCP_Minor_Feb-2026_C4591076, C4591082: CMCD: Protocol Administrative Change Letter (PACL)_Pfizer_Global |  | NO |  |  | No |  |  | 2026-02-23 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | CT02-Protocol Development for Interventional Studies | Matthew Wiestaw Gawel |  | To ensure alignment with the REG03‑GSOP‑RF05 SOP and to remove subjectivity in the interpretation of guidance related to primary study objectives, the changes previously implemented via PACLs were conservatively re-assessed as substantial. In addition, it was recognized that failure to amend the protocols prior to final analysis could lead to confusion between the last approved protocol version and the CSR reporting the results.Therefore, the team agreed that initiating protocol amendments would address both downstream study consistency in study design and analysis and would continue to honour the intent and spirit of REG03-GSOP-RF05.Protocol amendments have accordingly been initiated for studies C4591082 and C4591076 to formally incorporate the clarifications. The amendments will be finalized prior to any immunogenicity reporting events.The interpretation of the SOP was also escalated to the CT02 BPO for further discussion with relevant BPO representatives and SMEs regarding whether additional clarifications within the SOP are warranted. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines