## Standard_Quality_Dashboard - SQ
Case ID | Case Status | Observation ID | Obs Status | Submission Date | Issue Audit Report (Actual) | Center Number | principal investigator | Country | Description | Study ID | Protocol ID | Title Short Description | Drug Program Code | Rating | Event Type | Case CAPA Approved Due Date | Case CAPA Approved On | CAPA Plan In Place Timely | Obs CAPA Approved Due Date | Obs CAPA Approved On | Obs Target Completion Date | Obs Actual Completion Date | Case CAPA Closure Timely | Case Target Completion Date | Case Actual Completion Date | Obs CAPA Closure Timely | Selected Business Process | Taxonomy Level 1 | Taxonomy Level 2 | Study Status | Business Category | Study Phase | Study Priority | Asset | Dev China | Dev Japan | Rapid Model | Business Category
AIA-008070 | Closed | QE-217254 | Closed | (Empty) | 2025-12-11 | 1004 | (Empty) | UNITED STATES | The Electronic Case Report Form (e-CRF) Completion Requirements were not consistently followed due to the site’s misunderstanding of some of the instructions and/or where in e-CRF to enter the source data information. [Ref: Data Management Plan - Case Report Form (CRF) Completion Requirements 3.0, 29Sep2025] 1.The electronic data capture (EDC) e-CRF COVID ILL -COVID TEST form was incorrectly completed for 4 of 13 participants (with a COVID Illness form populated) that were reviewed. The e-CRF completion requirements noted that this form should only be populated when local COVID testing was done. This form was instead populated for these 4 participants even though their electronic health (EHR) records stated that the COVID testing was done using the sponsor supplied nasal swabs that were submitted to the central lab. The 4 impacted participants records were 10041009, 10041015, 10041027, and 10041040. 2.Participant 10041054 had a COVID Illness e-CRF form completed for a Remote Audit Video visit instead of an Unplanned Visit. The details of this visit were not COVID Illness related. 3.The electronic data capture (EDC) e-CRF TRIGGER FORM-COHORT SELECTION was incorrectly populated for 7 of 23 randomized cohort 1 participants even though the e-CRF Completion Requirements noted that that the “no” response to this e-CRF TRIGGER FORM-COHORT SELECTION was not applicable and should not be selected. All cohort 1 participants automatically have no response to the e-CRF TRIGGER FORM-COHORT SELECTION question. | C4591076 | C4591076 | A Routine Investigator Site Audit of Study C4591076 Site 1004, Dr. Kevin D. Cannon, Wilmington, NC, USA | (Empty) | Minor | AUDIT | 2026-01-22 | (Empty) | N | (Empty) | (Empty) | 2026-03-02 | 2025-12-09 | Y | 2026-03-02 | 2026-01-08 | Y | DMB07 - CRF and Database Design | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-008070 | Closed | QE-217255 | Closed | (Empty) | 2025-12-11 | 1004 | (Empty) | UNITED STATES | For 7 of 16 participants records reviewed, discrepancies were identified between the source data in the Electronic Health Record (EHR) and the information recorded in the electronic case report form (e- CRF).[Ref:&nbsp; C4591076 Protocol Amendment 1, 26 Aug 2025; Data Management Plan – Case Report Form (CRF) Completion Requirements 3.0, 29 Sep 2025] a. For participant 10041005, the electronic Case Report Form V2W2 FUP for the visit on 22 Jul 2025 recorded the vaccine injection body side as “left,” while the CRIO electronic health record source data stated “Right.” b. For participant 10041015, the electronic Case Report Form V2W2 FUP for the visit on 21 Jul 2025 recorded the vaccine injection body side as “Left,” while the CRIO electronic health record source data stated “Right.” c. For participant 10041024, the electronic Case Report Form V2W2 FUP for the visit on 22 Jul 2025 recorded the vaccine injection body side as “Left,” while the CRIO electronic health record source data stated “Right.” d. For participant 10041041, the electronic Case Report Form V202MTH1 for the visit on 06 Nov 2025 recorded the vaccine injection body side as “Left,” while the CRIO electronic health record source data stated “Right.” e. For participant 10041056, the electronic Case Report Form V201D1VX&nbsp; VACINTRT&nbsp; for the visit on 22 Jul 2025 recorded the vaccine injection body side as “Right,” while the CRIO electronic health record source data stated “Left.” f. For participants 10041007 and 10041018, the electronic Case Report Form did not include the medical history of “Ex-smoker,” which was recorded in the CRIO electronic health record for these participants.&nbsp; The site explained that the “Ex-smoker” history was the underlying medical condition supporting eligibility for study entry and that there was no field in the electronic Case Report Form to record this information. | C4591076 | C4591076 | A Routine Investigator Site Audit of Study C4591076 Site 1004, Dr. Kevin D. Cannon, Wilmington, NC, USA | (Empty) | Minor | AUDIT | 2026-01-22 | (Empty) | N | (Empty) | (Empty) | 2026-03-02 | 2026-01-08 | Y | 2026-03-02 | 2026-01-08 | Y | DMB07 - CRF and Database Design | Data Collection and Management | Inadequate source data/documentation | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009630 | Pending Finding Closure | QE-230536 | In Response Approval | (Empty) | 2026-03-03 | 1002 | (Empty) | UNITED STATES | For 1 of 10 participant files reviewed, the investigator site failed to adhere to the protocol requirements regarding documentation of concomitant medications [Pfizer Protocol C4591076 (Amendment 1: 26 Aug 2025); ICH E6 (R3) 2.5.2]. The C4591076 Final Protocol (31 May 2025) required that all concomitant medications taken by participants aged 18 through 64 years be recorded on the case report form. For participant 10021007 (age 59), Tylenol taken for a headache from 12 Jul 2025 to 15 Jul 2025 was not documented in the electronic case report form for concomitant medication. Protocol Amendment 1, which removed this requirement, became effective on 26 Aug 2025 and was not applicable during the period in which the medication was taken. | C4591076 | C4591076 | Investigator Site Audit of Study C4591076, Site 1002, Dr. Jose Cardona, Hialeah, FL, USA | (Empty) | Minor | AUDIT | 2026-04-14 | (Empty) | (Empty) | (Empty) | (Empty) | 2026-05-20 | (Empty) | (Empty) | 2026-05-20 | (Empty) | (Empty) | CT02 - Clinical Protocols | Protocol Deviations | Failure to follow protocol | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009630 | Pending Finding Closure | QE-230538 | In Response Approval | (Empty) | 2026-03-03 | 1002 | (Empty) | UNITED STATES | 5 of 10 participant records reviewed, source documentation practices were not in accordance with ALCOACCEA (Attributable, Legible, Contemporaneous, Original, Accurate, and Complete, Consistent, Enduring and Available) criteria [Pfizer Protocol C4591076 (Amendment 1: 26 Aug 2025); ICH E6 (R3) 2.12.2]. a. For Participant 10021013's Adverse Event (AE) #2, Urinary Tract Infection, documentation on the AE worksheet was incomplete, as the day of site awareness of the AE was recorded but the time of awareness was missing. b. For Visit 202, the Principal Investigator/Sub-Investigator did not document confirmation of concomitant medication review by checking either 'Yes' or 'No' or by initialing and dating the assessment for the following participants: &nbsp; &nbsp; 1. &nbsp;Participant 10021029 (Visit 202 occurred 04 Nov 2025) &nbsp; &nbsp; 2. &nbsp;Participant 10021051 (Visit 202 occurred 07 Nov 2025) &nbsp; &nbsp; 3. &nbsp;Participant 10021079 (Visit 202 occurred 19 Nov 2025) &nbsp; &nbsp; 4. &nbsp;Participant 10021080 (Visit 202 occurred 18 Nov 2025) c. &nbsp;Additionally, an inconsistency was observed between the Delegation of Authority Log and the Site Master Signature Log, whereby a Study Coordinator (who consented participants) was recorded on the delegation record but was absent from the corresponding signature log. This deficiency compromises the site’s ability to demonstrate attributable, complete, and accurate documentation of personnel authorization. | C4591076 | C4591076 | Investigator Site Audit of Study C4591076, Site 1002, Dr. Jose Cardona, Hialeah, FL, USA | (Empty) | Minor | AUDIT | 2026-04-14 | (Empty) | (Empty) | (Empty) | (Empty) | 2026-03-05 | (Empty) | (Empty) | 2026-05-20 | (Empty) | N | NOT APPLICABLE; NOT APPLICABLE | Data Collection and Management | Inadequate source data/documentation | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009630 | Pending Finding Closure | QE-230539 | In Response Approval | (Empty) | 2026-03-03 | 1002 | (Empty) | UNITED STATES | For 2 of 10 participants’ records reviewed, a discrepancy was noted between the Case Report Form (CRF) and the source documentation [C4591076 CRF Completion Requirements Version 4, 05 Dec 2025; ICH GCP E6 (R3) Section 2.12.5]. a. For Participant 10021007, the source documentation recorded an Intrauterine Device Implant (Copper-T) implanted in 2000, which was not entered in the electronic Case Report Form (eCRF). b. For Participant 10021007, the source documentation recorded allergies to dust and chemicals (including chlorine), which were not entered in the eCRF. c. For Participant 10021080, the source documentation recorded a diagnosis of Gastroesophageal Reflux Disease (GERD) with an onset date of unknown/unknown/2024, which was not entered in the eCRF. | C4591076 | C4591076 | Investigator Site Audit of Study C4591076, Site 1002, Dr. Jose Cardona, Hialeah, FL, USA | (Empty) | Minor | AUDIT | 2026-04-14 | (Empty) | (Empty) | (Empty) | (Empty) | 2026-05-20 | (Empty) | (Empty) | 2026-05-20 | (Empty) | (Empty) | NOT APPLICABLE; NOT APPLICABLE | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009630 | Pending Finding Closure | QE-230541 | In Response Approval | (Empty) | 2026-03-03 | 1002 | (Empty) | UNITED STATES | Investigational Product (IP) record keeping activities were inadequate as per the protocol and Investigational Product Manual [Pfizer Protocol C4591076 (Amendment 1: 26 Aug 2025) and Pfizer Protocol C4591076 Investigational Product Manual (version 2.0: 10 Sep 2025)]. A transcription error was identified between the Drug Shipment &amp; Proof of Receipt (1877624, received 01 Jul 2025) and the Investigational Product Accountability Log; the Proof of Receipt documented container number 5526686, while the Investigational Product Accountability Log documented 5226686. Note: The Impala Interactive Response Technology printout and the site's Blinded Vaccination Administration Record both documented container number 5526686. | C4591076 | C4591076 | Investigator Site Audit of Study C4591076, Site 1002, Dr. Jose Cardona, Hialeah, FL, USA | (Empty) | Minor | AUDIT | 2026-04-14 | (Empty) | (Empty) | (Empty) | (Empty) | 2026-05-20 | (Empty) | (Empty) | 2026-05-20 | (Empty) | (Empty) | CT13-GSOP - Investigational Product | Medicinal Product | Inadequate accountability/record keeping | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009630 | Pending Finding Closure | QE-230546 | In Response Approval | (Empty) | 2026-03-03 | 1002 | (Empty) | UNITED STATES | Monitoring activities were inadequate with regards to issue detection and/or documentation [C4591076 Study Monitoring Plan (Version 2: dated 19 Sep 2025)]. Monitoring activities failed to identify the following issues noted: a. &nbsp;The investigator site did not adhere to the protocol (finding QE-230536).&nbsp; b. &nbsp;For 5 of 10 participant records reviewed, source documents were not accurate, complete or legible in accordance with the ALCOACCEA criteria. (finding QE-230538). c. &nbsp;For 2 of 10 participant records reviewed, discrepancies between the source data and the electronic Case Report Forms were identified (finding QE-230539). d. &nbsp;One Investigational Product (IP) accountability record was not completed as required (finding QE-230541). | C4591076 | C4591076 | Investigator Site Audit of Study C4591076, Site 1002, Dr. Jose Cardona, Hialeah, FL, USA | (Empty) | Minor | AUDIT | 2026-04-14 | (Empty) | (Empty) | (Empty) | (Empty) | 2026-04-14 | (Empty) | (Empty) | 2026-05-20 | (Empty) | (Empty) | INV04 - Investigational Site Management and Monitoring | Site Management and Monitoring | Failure to detect/document | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-189975 | Closed | QE-189975 | Closed | 2025-07-11 | (Empty) | 1004 | Kevin Cannon (C4591076-1004) | UNITED STATES | C4591076 Site 1004, 19 of 23 enrolled patients didn’t meet Inclusion #4, receipt of Omicron KP.2 &gt;6 months prior to enrollment. Patients affected: 10041001, 10041002, 10041003, 10041005, 10041006, 10041007,10041008, 10041009, 10041010, 10041011, 10041012, 10041015, 10041018, 10041019, 10041020, 10041021, 10041022, 10041023, and 10041024 | C4591076 | C4591076 | GCP_Major_Jul-2025_C4591076: Protocol Deviation: Inclusion/Exclusion Criteria_Cannon, Kevin_USA | C459 | Major | SQE | 2025-08-28 | 2025-08-22 | Y | 2025-08-28 | 2025-08-22 12:56 | (Empty) | 2026-01-09 | (Empty) | (Empty) | 2026-01-09 | (Empty) | CT40 - Protocol Deviations | Protocol Deviations | Failure to comply with protocol inclusion/exclusion criteria | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-208013 | Approved - In Effectiveness Check | QE-208013 | Approved - In Effectiveness Check | 2025-10-20 | (Empty) | 1004 | Kevin Cannon (C4591076-1004) | UNITED STATES | For study C4591076 cohort 1, 2 participants, 10041020 and 10041024, samples for Visit 2/Week 2 follow up (18 in total) were processed under 40 minutes (i.e. min clot time of 30 mins and centrifuge for 10 to 15 minutes per the lab manual). The SCP when following up with site 1004 to clarify, the site noted the following: The CRC confirmed that samples were coagulated prior to centrifuging and processing. Clinical Immunology and Diagnostics confirmed that will test the samples, clinical was informed and a decision to keep the results will be made by Clinical. It was confirmed by Clinical these do not need to be recorded as protocol deviations. For cohort 2, as of 20Oct, there were additional samples identified under the 40 minute threshold, across 9 sites, 16 participants, 138 samples for the visit V201/Day 1 Vax. The CRAs have been requested to follow up with the sites and the team is awaiting clarification confirmation that these were under 40 mins. If there is lab/source documentation (i.e., a sample processing log) available documenting processing times (collection, aliquot etc.) for the protocol samples, the sites will be requested to submit a data change request to update the data as appropriate. For any confirmed as under 40 minutes, the CRAs will need to retrain sites and document the retraining. It was requested not to enter PDs from Asset DSM, as awaiting further guidance regarding the outcome of a QRT meeting. The team was requested today to submit this as a QE as understand there is a similar QE for other studies using TruLab (QE-182467) where the TruLab app was not used in real time. Details of the potential ppts and sites impacted as of 20Oct are attached. | C4591076 | C4591076 | GCP_Major_Oct-2025_C4591076: Sample Data Collection_Pfizer; TruLab, Cannon, Kevin_USA | C459 | Major | SQE | 2025-12-05 | 2025-11-25 | Y | 2025-12-05 | 2025-11-25 14:23 | (Empty) | 2026-03-19 | (Empty) | (Empty) | 2026-03-19 | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-208013 | Approved - In Effectiveness Check | QE-208013 | Approved - In Effectiveness Check | 2025-10-20 | (Empty) | 1004 | Kevin Cannon (C4591076-1004) | UNITED STATES | For study C4591076 cohort 1, 2 participants, 10041020 and 10041024, samples for Visit 2/Week 2 follow up (18 in total) were processed under 40 minutes (i.e. min clot time of 30 mins and centrifuge for 10 to 15 minutes per the lab manual). The SCP when following up with site 1004 to clarify, the site noted the following: The CRC confirmed that samples were coagulated prior to centrifuging and processing. Clinical Immunology and Diagnostics confirmed that will test the samples, clinical was informed and a decision to keep the results will be made by Clinical. It was confirmed by Clinical these do not need to be recorded as protocol deviations. For cohort 2, as of 20Oct, there were additional samples identified under the 40 minute threshold, across 9 sites, 16 participants, 138 samples for the visit V201/Day 1 Vax. The CRAs have been requested to follow up with the sites and the team is awaiting clarification confirmation that these were under 40 mins. If there is lab/source documentation (i.e., a sample processing log) available documenting processing times (collection, aliquot etc.) for the protocol samples, the sites will be requested to submit a data change request to update the data as appropriate. For any confirmed as under 40 minutes, the CRAs will need to retrain sites and document the retraining. It was requested not to enter PDs from Asset DSM, as awaiting further guidance regarding the outcome of a QRT meeting. The team was requested today to submit this as a QE as understand there is a similar QE for other studies using TruLab (QE-182467) where the TruLab app was not used in real time. Details of the potential ppts and sites impacted as of 20Oct are attached. | C4591076 | C4591076 | GCP_Major_Oct-2025_C4591076: Sample Data Collection_Pfizer; TruLab, Cannon, Kevin_USA | C459 | Major | SQE | 2025-12-05 | 2025-11-25 | Y | 2025-12-05 | 2025-11-25 14:23 | (Empty) | 2026-03-19 | (Empty) | (Empty) | 2026-03-19 | (Empty) | QMS09 - Vendor Management | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-208013 | Approved - In Effectiveness Check | QE-208013 | Approved - In Effectiveness Check | 2025-10-20 | (Empty) | (Empty) | PFIZER | (Empty) | For study C4591076 cohort 1, 2 participants, 10041020 and 10041024, samples for Visit 2/Week 2 follow up (18 in total) were processed under 40 minutes (i.e. min clot time of 30 mins and centrifuge for 10 to 15 minutes per the lab manual). The SCP when following up with site 1004 to clarify, the site noted the following: The CRC confirmed that samples were coagulated prior to centrifuging and processing. Clinical Immunology and Diagnostics confirmed that will test the samples, clinical was informed and a decision to keep the results will be made by Clinical. It was confirmed by Clinical these do not need to be recorded as protocol deviations. For cohort 2, as of 20Oct, there were additional samples identified under the 40 minute threshold, across 9 sites, 16 participants, 138 samples for the visit V201/Day 1 Vax. The CRAs have been requested to follow up with the sites and the team is awaiting clarification confirmation that these were under 40 mins. If there is lab/source documentation (i.e., a sample processing log) available documenting processing times (collection, aliquot etc.) for the protocol samples, the sites will be requested to submit a data change request to update the data as appropriate. For any confirmed as under 40 minutes, the CRAs will need to retrain sites and document the retraining. It was requested not to enter PDs from Asset DSM, as awaiting further guidance regarding the outcome of a QRT meeting. The team was requested today to submit this as a QE as understand there is a similar QE for other studies using TruLab (QE-182467) where the TruLab app was not used in real time. Details of the potential ppts and sites impacted as of 20Oct are attached. | C4591076 | C4591076 | GCP_Major_Oct-2025_C4591076: Sample Data Collection_Pfizer; TruLab, Cannon, Kevin_USA | C459 | Major | SQE | 2025-12-05 | 2025-11-25 | Y | 2025-12-05 | 2025-11-25 14:23 | (Empty) | 2026-03-19 | (Empty) | (Empty) | 2026-03-19 | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-208013 | Approved - In Effectiveness Check | QE-208013 | Approved - In Effectiveness Check | 2025-10-20 | (Empty) | (Empty) | PFIZER | (Empty) | For study C4591076 cohort 1, 2 participants, 10041020 and 10041024, samples for Visit 2/Week 2 follow up (18 in total) were processed under 40 minutes (i.e. min clot time of 30 mins and centrifuge for 10 to 15 minutes per the lab manual). The SCP when following up with site 1004 to clarify, the site noted the following: The CRC confirmed that samples were coagulated prior to centrifuging and processing. Clinical Immunology and Diagnostics confirmed that will test the samples, clinical was informed and a decision to keep the results will be made by Clinical. It was confirmed by Clinical these do not need to be recorded as protocol deviations. For cohort 2, as of 20Oct, there were additional samples identified under the 40 minute threshold, across 9 sites, 16 participants, 138 samples for the visit V201/Day 1 Vax. The CRAs have been requested to follow up with the sites and the team is awaiting clarification confirmation that these were under 40 mins. If there is lab/source documentation (i.e., a sample processing log) available documenting processing times (collection, aliquot etc.) for the protocol samples, the sites will be requested to submit a data change request to update the data as appropriate. For any confirmed as under 40 minutes, the CRAs will need to retrain sites and document the retraining. It was requested not to enter PDs from Asset DSM, as awaiting further guidance regarding the outcome of a QRT meeting. The team was requested today to submit this as a QE as understand there is a similar QE for other studies using TruLab (QE-182467) where the TruLab app was not used in real time. Details of the potential ppts and sites impacted as of 20Oct are attached. | C4591076 | C4591076 | GCP_Major_Oct-2025_C4591076: Sample Data Collection_Pfizer; TruLab, Cannon, Kevin_USA | C459 | Major | SQE | 2025-12-05 | 2025-11-25 | Y | 2025-12-05 | 2025-11-25 14:23 | (Empty) | 2026-03-19 | (Empty) | (Empty) | 2026-03-19 | (Empty) | QMS09 - Vendor Management | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-208013 | Approved - In Effectiveness Check | QE-208013 | Approved - In Effectiveness Check | 2025-10-20 | (Empty) | (Empty) | TRULAB INC | (Empty) | For study C4591076 cohort 1, 2 participants, 10041020 and 10041024, samples for Visit 2/Week 2 follow up (18 in total) were processed under 40 minutes (i.e. min clot time of 30 mins and centrifuge for 10 to 15 minutes per the lab manual). The SCP when following up with site 1004 to clarify, the site noted the following: The CRC confirmed that samples were coagulated prior to centrifuging and processing. Clinical Immunology and Diagnostics confirmed that will test the samples, clinical was informed and a decision to keep the results will be made by Clinical. It was confirmed by Clinical these do not need to be recorded as protocol deviations. For cohort 2, as of 20Oct, there were additional samples identified under the 40 minute threshold, across 9 sites, 16 participants, 138 samples for the visit V201/Day 1 Vax. The CRAs have been requested to follow up with the sites and the team is awaiting clarification confirmation that these were under 40 mins. If there is lab/source documentation (i.e., a sample processing log) available documenting processing times (collection, aliquot etc.) for the protocol samples, the sites will be requested to submit a data change request to update the data as appropriate. For any confirmed as under 40 minutes, the CRAs will need to retrain sites and document the retraining. It was requested not to enter PDs from Asset DSM, as awaiting further guidance regarding the outcome of a QRT meeting. The team was requested today to submit this as a QE as understand there is a similar QE for other studies using TruLab (QE-182467) where the TruLab app was not used in real time. Details of the potential ppts and sites impacted as of 20Oct are attached. | C4591076 | C4591076 | GCP_Major_Oct-2025_C4591076: Sample Data Collection_Pfizer; TruLab, Cannon, Kevin_USA | C459 | Major | SQE | 2025-12-05 | 2025-11-25 | Y | 2025-12-05 | 2025-11-25 14:23 | (Empty) | 2026-03-19 | (Empty) | (Empty) | 2026-03-19 | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-208013 | Approved - In Effectiveness Check | QE-208013 | Approved - In Effectiveness Check | 2025-10-20 | (Empty) | (Empty) | TRULAB INC | (Empty) | For study C4591076 cohort 1, 2 participants, 10041020 and 10041024, samples for Visit 2/Week 2 follow up (18 in total) were processed under 40 minutes (i.e. min clot time of 30 mins and centrifuge for 10 to 15 minutes per the lab manual). The SCP when following up with site 1004 to clarify, the site noted the following: The CRC confirmed that samples were coagulated prior to centrifuging and processing. Clinical Immunology and Diagnostics confirmed that will test the samples, clinical was informed and a decision to keep the results will be made by Clinical. It was confirmed by Clinical these do not need to be recorded as protocol deviations. For cohort 2, as of 20Oct, there were additional samples identified under the 40 minute threshold, across 9 sites, 16 participants, 138 samples for the visit V201/Day 1 Vax. The CRAs have been requested to follow up with the sites and the team is awaiting clarification confirmation that these were under 40 mins. If there is lab/source documentation (i.e., a sample processing log) available documenting processing times (collection, aliquot etc.) for the protocol samples, the sites will be requested to submit a data change request to update the data as appropriate. For any confirmed as under 40 minutes, the CRAs will need to retrain sites and document the retraining. It was requested not to enter PDs from Asset DSM, as awaiting further guidance regarding the outcome of a QRT meeting. The team was requested today to submit this as a QE as understand there is a similar QE for other studies using TruLab (QE-182467) where the TruLab app was not used in real time. Details of the potential ppts and sites impacted as of 20Oct are attached. | C4591076 | C4591076 | GCP_Major_Oct-2025_C4591076: Sample Data Collection_Pfizer; TruLab, Cannon, Kevin_USA | C459 | Major | SQE | 2025-12-05 | 2025-11-25 | Y | 2025-12-05 | 2025-11-25 14:23 | (Empty) | 2026-03-19 | (Empty) | (Empty) | 2026-03-19 | (Empty) | QMS09 - Vendor Management | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-208013 | Approved - In Effectiveness Check | QE-208013 | Approved - In Effectiveness Check | 2025-10-20 | (Empty) | (Empty) | (Empty) | (Empty) | For study C4591076 cohort 1, 2 participants, 10041020 and 10041024, samples for Visit 2/Week 2 follow up (18 in total) were processed under 40 minutes (i.e. min clot time of 30 mins and centrifuge for 10 to 15 minutes per the lab manual). The SCP when following up with site 1004 to clarify, the site noted the following: The CRC confirmed that samples were coagulated prior to centrifuging and processing. Clinical Immunology and Diagnostics confirmed that will test the samples, clinical was informed and a decision to keep the results will be made by Clinical. It was confirmed by Clinical these do not need to be recorded as protocol deviations. For cohort 2, as of 20Oct, there were additional samples identified under the 40 minute threshold, across 9 sites, 16 participants, 138 samples for the visit V201/Day 1 Vax. The CRAs have been requested to follow up with the sites and the team is awaiting clarification confirmation that these were under 40 mins. If there is lab/source documentation (i.e., a sample processing log) available documenting processing times (collection, aliquot etc.) for the protocol samples, the sites will be requested to submit a data change request to update the data as appropriate. For any confirmed as under 40 minutes, the CRAs will need to retrain sites and document the retraining. It was requested not to enter PDs from Asset DSM, as awaiting further guidance regarding the outcome of a QRT meeting. The team was requested today to submit this as a QE as understand there is a similar QE for other studies using TruLab (QE-182467) where the TruLab app was not used in real time. Details of the potential ppts and sites impacted as of 20Oct are attached. | C4591076 | C4591076 | GCP_Major_Oct-2025_C4591076: Sample Data Collection_Pfizer; TruLab, Cannon, Kevin_USA | C459 | Major | SQE | 2025-12-05 | 2025-11-25 | Y | 2025-12-05 | 2025-11-25 14:23 | (Empty) | 2026-03-19 | (Empty) | (Empty) | 2026-03-19 | (Empty) | CT29 - Management of BioSpecimens | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-208013 | Approved - In Effectiveness Check | QE-208013 | Approved - In Effectiveness Check | 2025-10-20 | (Empty) | (Empty) | (Empty) | (Empty) | For study C4591076 cohort 1, 2 participants, 10041020 and 10041024, samples for Visit 2/Week 2 follow up (18 in total) were processed under 40 minutes (i.e. min clot time of 30 mins and centrifuge for 10 to 15 minutes per the lab manual). The SCP when following up with site 1004 to clarify, the site noted the following: The CRC confirmed that samples were coagulated prior to centrifuging and processing. Clinical Immunology and Diagnostics confirmed that will test the samples, clinical was informed and a decision to keep the results will be made by Clinical. It was confirmed by Clinical these do not need to be recorded as protocol deviations. For cohort 2, as of 20Oct, there were additional samples identified under the 40 minute threshold, across 9 sites, 16 participants, 138 samples for the visit V201/Day 1 Vax. The CRAs have been requested to follow up with the sites and the team is awaiting clarification confirmation that these were under 40 mins. If there is lab/source documentation (i.e., a sample processing log) available documenting processing times (collection, aliquot etc.) for the protocol samples, the sites will be requested to submit a data change request to update the data as appropriate. For any confirmed as under 40 minutes, the CRAs will need to retrain sites and document the retraining. It was requested not to enter PDs from Asset DSM, as awaiting further guidance regarding the outcome of a QRT meeting. The team was requested today to submit this as a QE as understand there is a similar QE for other studies using TruLab (QE-182467) where the TruLab app was not used in real time. Details of the potential ppts and sites impacted as of 20Oct are attached. | C4591076 | C4591076 | GCP_Major_Oct-2025_C4591076: Sample Data Collection_Pfizer; TruLab, Cannon, Kevin_USA | C459 | Major | SQE | 2025-12-05 | 2025-11-25 | Y | 2025-12-05 | 2025-11-25 14:23 | (Empty) | 2026-03-19 | (Empty) | (Empty) | 2026-03-19 | (Empty) | QMS09 - Vendor Management | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines