## Standard_Quality_Dashboard - QE
Observation ID | Study ID | Targeted | PR ID | Site(s) | principal Investigator | EX Comp? | QE Threshold | Status | Observation Description (as submitted) | Awareness Date | Submission Date | Assessment Date | Title/Short Description | Business CAPA Plan Endorsed On | CAPA Plan in Place | Last Action Due Date | Investigation Summary and Conclusion | Effectiveness Check Required | Effectiveness Check Rationale | Investigation Completion Date | Closed On | PDAL Decision | Level 1 | Level 2 | Quality CAPA Plan Endorsed On | Quality Reviewer Approved On | Business Process | Submitter | Confirmed Serious Breach | Remediation Actions Taken (when QE was submitted) | CAPA Action Details | CAPA Action Owner | Root Cause Description | Root Cause Level 1 | Root Cause Level 2 | Root Cause Level 3 | Rapid Model | Business Category
QE-219164 | C4591081 | (Empty) | QE-219164 |  | PFIZER | N | Minor | Closed | This event corresponds to the following exception request: DMB07-GSOP Exception C4591081 (22-Dec-2025 – 07-Jan-2026) QE-218319 v.1.0. Pfizer received a late regulatory request to collect Medically Attended Adverse Events (MAAE). In our response letter to this request, we informed CBER that the "study is advancing rapidly towards the start of enrollment" and that "late adjustments in the protocol and database cannot be made prior to the initiation of enrollment, and submission/review/approval by the IRB prior to implementation is required for a protocol amendment." Moreover, we outlined the following to CBER, "Pfizer/BioNTech intend to start the study but incorporate these changes after an amendment." Therefore, in alignment with what we communicated to CBER, the study team drafted a protocol amendment (PA1) dated 21Nov25 and submitted it to the Central IRB and CBER for approval. Approval was granted by early December, just prior to the planned FSFV on 10Dec25, and the database will be updated to include the MAAE CRF on 26Dec. This QE is being submitted then due to the noncompliance with DMB07-GSOP 11.0, Section 3.2.2, which requires CRF data acquisition and validation procedures to be deployed by First Subject First Visit. Also related to this situation, is the fact that PA1 is available to sites in the Central IRB portal and a handful of sites have referenced protocol amendment 1 on their site documentation. The study team will be providing instruction to the sites regarding the collection of MAAEs in source for the two weeks between FSFV on 10Dec and the CRF going live on 26Dec. Neither subject safety or data integrity have been compromised. These MAAEs would have been reported under the original protocol as AEs; under PA1 they will now be classified and collected as MAAEs. | 2025-12-15 | 2025-12-16 | 2025-12-17 19:54 | GCP_Minor_Dec-2025_C4591081: CMCD: Database Activation_Pfizer_USA |  | NO |  |  | No |  |  | 2025-12-17 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | DMB07-Study Data Set Design and Setup | Emily Graham |  | Team filed an exception and corresponding QE. The team will be providing instructions to sites this week regarding the collection of MAAEs. |  |  | NA | Human Performance | Decision Error |  | MODEL 1 - INSOURCED | Vaccines
QE-220497 | C4591081 | N | QE-220497 | 1007, 1022, 1058, 1157, 1173 | Charles Harper (C4591081-1157), James Peterson (C4591081-1058), Ryan Casey (C4591081-1173), Salma Saiger (C4591081-1007), Yanely Pineiro Puebla (C4591081-1022) | N | Minor | Closed | .0pt;"Study C4591081..0pt;"The following sites have received Protocol Amendment 1 IRB approval and began implementing it, even though (1) Pfizer-approved PA material was not yet made aware and (2) sites did not receive an official Sponsor approval to implement PA1..0pt;" .0pt;"(1)As per CT33-GSOP-RF01, "Pfizer Clinical Approved Protocol Training Materials and additional Pfizer Clinical approved Study Training Materials must be used" if self training or site training process were to be considered an equivalent. For the following sites, sites have implemented Protocol Amendment 1 without Pfizer Clinical approved training material. Sites indicated they have self-trained and are able to provide training logs..0pt;" .0pt;"(2)As per Pfizer process, a Protocol Amendment Notification Letter is sent out to notify sites when documents/approvals are in place for site to go ahead with implementation of Protocol Amendment 1. This was not sent out to the sites listed below prior to them implementing Protocol Amendment 1. The reason for implementation was noted that either they followed IRB guidance for PA1 implementation or follow site SOPs..0pt;".0pt;"Sites involved: 1007, 1022, 1058, 1141, 1146, 1157, 1173..0pt;"More related information can be found in the following QE that refers to reason for PA1 (request from CBER) and timing of its approval by IRB: Relevant QE: QE-218319 v.1.0 | 2025-12-19 | 2025-12-23 | 2025-12-23 19:55 | GCP_Minor_Dec-2025_C4591081: Protocol Implementation; Study Training_Multiple Sites_USA |  | NO |  |  | No |  |  | 2025-12-23 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | CT33-Study Training | Irina Mosesova |  | 1. As a corrective action, SCPs were requested to reach out to sites that received IRB approval and implemented it without Pfizer authorization to enrol participants on source documents under original protocol.2. As a corrective action, SCPs/CRAs will collect training logs for self-training and review for accuracy and acceptability. Sites will also be requested to document PA1 training in Firecrest, once training is made available for sites. 3. As a preventative action, SCPs will be requested to remind involved sites to wait for PA Notification Letter prior to implementing upcoming amendments |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-220497 | C4591081 | Y | QE-220497 | 1141, 1146 | David Fitz-Patrick (C4591081-1146), Shane Christensen (C4591081-1141) | N | Minor | Closed | .0pt;"Study C4591081..0pt;"The following sites have received Protocol Amendment 1 IRB approval and began implementing it, even though (1) Pfizer-approved PA material was not yet made aware and (2) sites did not receive an official Sponsor approval to implement PA1..0pt;" .0pt;"(1)As per CT33-GSOP-RF01, "Pfizer Clinical Approved Protocol Training Materials and additional Pfizer Clinical approved Study Training Materials must be used" if self training or site training process were to be considered an equivalent. For the following sites, sites have implemented Protocol Amendment 1 without Pfizer Clinical approved training material. Sites indicated they have self-trained and are able to provide training logs..0pt;" .0pt;"(2)As per Pfizer process, a Protocol Amendment Notification Letter is sent out to notify sites when documents/approvals are in place for site to go ahead with implementation of Protocol Amendment 1. This was not sent out to the sites listed below prior to them implementing Protocol Amendment 1. The reason for implementation was noted that either they followed IRB guidance for PA1 implementation or follow site SOPs..0pt;".0pt;"Sites involved: 1007, 1022, 1058, 1141, 1146, 1157, 1173..0pt;"More related information can be found in the following QE that refers to reason for PA1 (request from CBER) and timing of its approval by IRB: Relevant QE: QE-218319 v.1.0 | 2025-12-19 | 2025-12-23 | 2025-12-23 19:55 | GCP_Minor_Dec-2025_C4591081: Protocol Implementation; Study Training_Multiple Sites_USA |  | NO |  |  | No |  |  | 2025-12-23 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | CT33-Study Training | Irina Mosesova |  | 1. As a corrective action, SCPs were requested to reach out to sites that received IRB approval and implemented it without Pfizer authorization to enrol participants on source documents under original protocol.2. As a corrective action, SCPs/CRAs will collect training logs for self-training and review for accuracy and acceptability. Sites will also be requested to document PA1 training in Firecrest, once training is made available for sites. 3. As a preventative action, SCPs will be requested to remind involved sites to wait for PA Notification Letter prior to implementing upcoming amendments |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-221478 | C4591081 | (Empty) | QE-221478 |  | PFIZER | N | Minor | Closed | C4591081 - Site 1078: Site activated prior to completing PA 1 training in Firecrest. SCP notified site to not enroll any patients until PA 1 training is completed in FC. Site agreed and is completing training ASAP. | 2026-01-06 | 2026-01-06 | 2026-01-06 22:15 | GCP_Minor_Jan-2026_C4591081: Site Activation_Pfizer_USA |  | NO |  |  | No |  |  | 2026-01-06 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Kelsey Babinski |  | SCP notified site to not enroll any patients until PA 1 training is completed in FC. Site agreed and is completing training ASAP. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-222013 | C4591081 | (Empty) | QE-222013 |  | PFIZER | N | Minor | Closed | C4591081/Site 1061 site activated on 06JAN2026 prior to completion of Protocol Amendment 1 training. | 2026-01-06 | 2026-01-08 | 2026-01-09 15:32 | GCP_Minor_Jan-2026_C4591081: Site Activation_Pfizer_USA |  | NO |  |  | No |  |  | 2026-01-09 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Marquia Hayes |  | Site Care Partner contacted PI and staff via email on 07JAN2026, advising that C4591081 PA1 training dated 21NOV2025 is required to be completed in Firecrest for: PI, at least one minimum (1) Sub-I, at least one (1) Study Coordinator and at least two Unblinded Pharmacist(s) or designee(s); in which is the minimum requirement for Site Activation per Site Activations Checklist, before enrollment and study activities (screen/enroll patients) can be conducted. PI and minimum site staff for Site Activations completed C4591081 PA1 dated 21NOV2025 within Firecrest on 07JAN2026. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-222028 | C4591081 | (Empty) | QE-222028 |  | PFIZER | N | Minor | Closed | For trial C4591081: The Site Initiation Visit (SIV) was conducted for these sites (1001 and 1164) prior to receipt of IRB and IIP approval. The visit was conducted due to limited site availability, as the sites communicated at the end of December 2025 that January 2026 scheduling would be extremely challenging. The sites are part of the same organization/company and both PIs support each other as Sub-I's, which contributed to aligning schedules for both SIVs. The assigned monitor attended and supported the SIV presentation. At the time of the visit, it was anticipated that IRB approval would be granted later the same day; however, approval was not received as expected. | 2026-01-06 | 2026-01-09 | 2026-01-09 19:12 | GCP_Minor_Jan-2026_C4591081: Site Initiation Visit_Pfizer_USA |  | NO |  |  | No |  |  | 2026-01-09 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Armando Delanoy |  | -The site was reminded that no study-related activities may occur until all required approvals are in place. -The Site Care Partner has reviewed the and completed retraining on the applicable Pfizer policy and procedural requirements for conducting SIVs, including requirements related to IRB and IIP approval. -Site access and system readiness are being actively followed up to ensure full compliance once approvals are received. -Outstanding items will be tracked and addressed promptly in collaboration with Site Activation Partners. Preventive Actions: -SIVs will not be conducted prior to IRB and IIP approval unless explicitt prior approval is obtained and documented. -Internal confirmation and documented approval will be secured before proceeding with visits under exceptional circumstances. This event will be referenced in the associated trip reports. |  |  | NA | Human Performance | Decision Error |  | MODEL 1 - INSOURCED | Vaccines
QE-222137 | C4591081 | N | QE-222137 | 1005, 1008, 1025, 1166 | Orlando Puente (C4591081-1025), Orlando Puente (C6271001-1008), Orlando Puente (C6481001-1005), Ramon Leon (C4591081-1166) | N | Critical | Closed | We became aware of a published article, noting instances of sites (some participating in Pfizer studies) using "fake data".science.org/content/article/alzheimer-s-drug-developers-accuse-clinical-trial-sites-faking-data"Alzheimer’s drug developers accuse clinical trial sites of faking data Science AAAS | 2026-01-08 | 2026-01-09 | 2026-01-09 17:45 | GCP_Critical_Jan-2026_Multiple Protocols: Potential Allegation_Leon, Ramon; Puente, Orlando_USA |  | YES |  | <p>On 08 Jan 2026, Pfizer became aware of an article published in Science on 07 Jan 2026 reporting allegations of unreliable or falsified data generated by several U.S. clinical trial sites, primarily in South Florida. The article described issues raised through litigation involving T3D Therapeutics in 2023, whose Phase 2 Alzheimer’s trial (T3D 959) allegedly included data irregularities from five trial sites.&nbsp;</p><p><br></p><p>According to the article, anomalies included placebo group cognitive improvement inconsistent with Alzheimer’s progression, enrollment of participants who did not have Alzheimer’s disease, reused blood samples, duplicated biological data, and records showing drug administration despite absent drug levels in blood tests. Independent data analysts identified similar suspicious patterns across multiple Alzheimer’s trials conducted at the same sites, indicating potential systemic concerns.</p><p><br></p><p>The sites referenced in the article include IMIC Medical Research, CCM Clinical Research Group, Miami Dade Medical Research Institute, Premier Clinical Research Institute, and Health Care Family Rehabilitation, who are for profit research entities with extensive involvement in Alzheimer’s trials (59 trials involving 46 investigational drugs).&nbsp;</p><p><br></p><p>T3D alleged that these sites manipulated data and enrolled ineligible participants to increase revenue. Both the sites and the Clinical Research Organization, (CRO), Clinilabs, denied the allegations, attributing the issues to trial design weaknesses and misrepresentations by T3D.</p><p><br></p><p>The issue was identified through the Science publication and underlying litigation and data analyses. The potential impact included risks to clinical data integrity, trial validity, regulatory reliability, and potential relevance to other sponsors’ trials that may have utilized the same sites.</p><p><br></p><p>Pfizer currently has ongoing clinical studies at the Miami Dade Medical Research Institute site, (PI Puente) C4591081 and C6271001.</p><p><br></p><p>A Due Diligence investigation was conducted.</p><p><br></p><p>On 26-30 Jan 2026 a review of Central Monitoring Reports was conducted for both active studies to assess data integrity.</p><p>• &nbsp; &nbsp;C6271001: No signal or trends were identified. Zero adverse events (AEs) &nbsp;were reported across 118 healthy participants. &nbsp;The site is using the vendor Verified Clinical Trials (VCT) to address previous issues with multiple enrollers in the region.</p><p>• &nbsp; &nbsp;C4591081: No signals were identified in the first Central Monitoring review of data.</p><p><br></p><p>On 02-05 Feb 2026 a non-routine audit was completed at the Miami Dade Research location for the C6271001 and the C4591081 studies. The Regulatory Quality Assurance (RQA) Audit Team confirmed there were no concerns with either study regarding the data integrity.&nbsp;</p><p><br></p><p>The RQA team also confirmed that Dr. Americo Padilla, who was mentioned in the Science article, was not part of the site staff in either study. Dr. Padilla was a Principal Investigator in the Pfizer C4951009 Study for pediatric migraine. Pfizer RQA performed a non-routine audit for the C4951009 study and identified issues with the ICD process at the site. Dr. Padilla left the site in Mar 2023 following the RQA audit and the site was subsequently terminated for Good Clinical Practice non-compliance on 31 Oct 2023.</p><p><br></p><p>A Due Diligence Investigation was conducted therefore no root cause was identified and a repeat occurrence review to identify prior QEs with the same or similar cause was not conducted.</p><p><br></p> | No | Quality Event only required due diligence investigation | 2026-02-24 | 2026-02-27 |  | Potential allegation of Falsification or misconduct | Potential allegation of Scientific fraud, falsification or misconduct |  | 2026-02-24 21:00 | No Process Assigned | Lauren Litzinger | FALSE | Assessment of how to best report for follow-upAssessment of specific sites compared to Pfizer history:There are 2 sites that are participating in Pfizer studies, in Vaccines: IMIC Medical Research – Vaccines – C4591081 – SCP: Ivette FarmerMiami Dade Medical Research Institute, LLC – Vaccines C4591081 – SCP: Mala Suppiah C6271001 – SCP: Mala Suppiah C6481001 – SCP: Mala Suppiah |  |  | Due Diligence | Due Diligence | N/A | N/A | MODEL 1 - INSOURCED | Vaccines
QE-222180 | C4591081 | (Empty) | QE-222180 |  | NPHASE INC (REDCAP CLOUD), PFIZER | N | Major | In Investigation | We are raising this event to please request that the minor assessment for QE-219754 be reconsidered. To again summarize the what occured, a legitimate query was raised in the C4601019 study by our medical monitor. However in RCC this query changed to a different user name and role (LabTech). That different user is a real person at Pfizer, but they never requested access to C4601019 and they are not on our Site User Report. This user does not have access to the C4601019 study in RCC, as confirmed by the RCC Admin team's review of the study's audit logs. Further, the Lab Tech role does NOT have access to issue a query in RCC. As a result, the RCC system does not clearly link back to user who issued the query, which we believe violates FDA guidance per CFR 21 Part 11, likely with guidance from EMA and other regulators similarly breached. When this QE was initally submitted, there were 3 such known issues across 2 RCC studies. There are now 9 known issues across 6 RCC studies. | 2025-12-16 | 2026-01-09 | 2026-01-12 20:17 | GCP_Major_Jan-2026_System/Enterprise Level_System Access Controls Redcap Cloud (RCC): Broader Issue_Pfizer; NPHASE INC (REDCAP CLOUD)_Global |  | NO | [7 empty] | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) |  |  | CP403 | Katherine Paternel |  | Raised as a critical finding for RCC white glove as of 17 Dec2025 - CAS00002285. Raised the topic to Pfizer and RCC SMEs for immediate action. | [6 empty] | MODEL 1 - INSOURCED | Vaccines
QE-222457 | C4591081 | N | QE-222457 | 1009, 1022 | Yanely Pineiro Puebla (C4591076-1009), Yanely Pineiro Puebla (C4591081-1022) | N | Minor | Closed | A subject was erroneously enrolled in C4591076 (SSID 10091179) instead of C4591081 (SSID 10221179, site 1022, PI Pineiro Puebla) in Trial Manager/Signant Health for e-diary (vaccination, COVID Illness) reporting. | 2026-01-08 | 2026-01-12 | 2026-01-12 18:31 | GCP_Minor_Dec-2025_C4591076, C4591081: Trial Manager Participant Enrollment_Pineiro Puebla, Yanely_USA |  | NO |  |  | No |  |  | 2026-01-12 |  | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry |  |  | No Process Assigned | Elliot DeHaan |  | An email notification from Signant Health was received and investigated by the study team. It was confirmed in an email on Thursday January 8 that the subject had been intended to be enrolled in C4591081. An additional meeting on Monday January 12 confirmed these details and it was agreed that this met QE reporting criteria. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-222465 | C4591081 | (Empty) | QE-222465 |  | PFIZER | N | Minor | Closed | Incorrect RCC access granted for Study C4591081, Site 1049 for 1 user | 2025-12-22 | 2026-01-12 | 2026-01-12 19:39 | GCP_Minor_Jan-2026_C4591081: System Access Controls_Pfizer_USA |  | NO |  |  | No |  |  | 2026-01-12 |  | IT Systems | Inadequate system access or account management |  |  | CP403 | Steven Levis |  | The incorrect access was identified and rectified. The Investigator Signature role was correctly granted to Larkin Wadsworth in the RCC system for Study C4591081 – Site 1049 on 04th January 2026. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-223418 | C4591081 | (Empty) | QE-223418 |  | PFIZER | N | Minor | Closed | On 14 Jan 2026, Pfizer Due Diligence notified the GCP-QOC Investigator Status and Use sub-committee facilitators that duplicate IDs with different Investigator Status were located for Investigator Marshall Nash: CTMS ID Person IDs 33919 (UPAR) and 6176843 (Available). Due Diligence confirmed the two individuals were the same person and that the two ids should be merged.Upon further investigation, Person ID 33919 was created on 27 Mar 2014 and associated with an address in Decatur, GA. This ID was made UPAR on 25 Aug 2016 for QE PFT098228/PR1829596 due to ongoing concerns about Investigator Nash’s refusal to allow the CRA and auditor on site to review B1481022 and B1481038 participant data representing potential risks to participant safety. The QE Summary confirmed the Investigator would remain UPAR after the close of the QE. No evidence was found in the Investigator Status History report or the records of the GCP-QOC Investigator Status and Use sub-committee SharePoint showing that Marshall Nash was ever returned, or considered for return, to Available. Person ID 6176843 was created on 05 Sep 2023 and associated with an address in FL. This ID was subsequently added as a Sub-Investigator with C4591081 Site 1161 and C4781004 Site 1123. Per the Site View report, C4591081 Site 1161 was selected in Oct 2025 and has not yet begun enrolling. C4781004 Site 1123 was selected in May 2022 and had LSLV in 2023. As the Investigator was UPAR at the time they were added to the C4591081 and C4781004 studies, those Study Teams should have requested RF14 exceptions to use Investigator Nash. In addition to the situation described above, I found duplicate IDs for three investigators in 2025 during the course of normal business (in other words, not while conducting activities intended to find duplicates): 281077 and 6296913 for Fei Xu333720 and 6137450 for Victor Casildo Bohorquez Lopez433718 and 6134641 for Chau Yee NgIn all three instances, the addresses were nearly identical (see attached) such that it is not understood by the QE submitter what controls exist to flag potential duplicates, for example during a mastery process. It is not known by the submitter how the IDs above were created or if whether there is any relation to the issue described in QE-115342.This QE is being submitted to make the C4591081 Study Team aware of the Investigator’s Status and give them the opportunity to document their compliance with INV02-GSOP-RF14 and to request an investigation of the investigator mastery process for potential gaps. | 2026-01-15 | 2026-01-16 | 2026-01-20 17:45 | GCP_Minor_Jan-2026_C4591081, C4781004: Investigator Person ID; Investigator Exception Process_Pfizer_Global |  | NO |  |  | No |  |  | 2026-01-20 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Joshua Jones |  | Due Diligence submitted UIMS ticket to merge duplicate IDs for Investigator Nash on 15 Jan 2026 (completed 16 Jan 2026). |  |  | NA | Personnel | Inadequate Information for Determination |  | MODEL 1 - INSOURCED | Vaccines
QE-223424 | C4591081 | N | QE-223424 | 1007 | Salma Saiger (C4591081-1007) | N | Minor | Closed | Site 1007 utilized PA1 without site IRB approval for PA 1. Study level PA 1 was approved; however, it was not approved for site use. PA 1 approved to site on 05 Jan 2026 by Central IRB.During the enrollment site was approved with initial protocol IRB approved for enrollment. PA1 did not include any updates to participant safety and did not result in ICD updates. | 2026-01-16 | 2026-01-20 | 2026-01-20 18:20 | GCP_Minor_Jan-2026_C4591081: IRB Approval: PA1_Saiger, Salma_USA |  | NO |  |  | No |  |  | 2026-01-20 |  | Compliance Requirements - Country Specific Requirements | Failure to follow country-specific requirements |  |  | CT02-Protocol Development for Interventional Studies | Mala Suppiah |  | Site was retrained and site verbalized understanding. Contact report was created. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-223623 | C4591081 | (Empty) | QE-223623 |  | PFIZER | N | Minor | Closed | Site Activation Letter was provided to C4591081-USA-1072 prior to receiving the Protocol Signature Page for Protocol Amendment 1. The site had been IIP approved under FAP, but was required to be activated under Protocol Amendment 1. All other required documents for activation were received prior to the Site Activation Letter being provided to site. The document was received before EOD January 8th, 2026 and a corrected Site Activation notification was provided to the site. | 2026-01-08 | 2026-01-19 | 2026-01-20 20:26 | GCP_Minor_Jan-2026_C4591081: CMCD: Site Activation_Pfizer_USA |  | NO |  |  | No |  |  | 2026-01-20 |  | Site Management and Monitoring | Failure to follow study specific monitoring plan/ requirements |  |  | INV04-Investigational Site Management and Monitoring | Morgan Dussault |  | Site Activation Partner noted the Protocol Signature Page was not received at 10:04 MST, after Site Activation Letter had been sent at 09:59 MST. Phone call made to Erin Novotny at site level at 10:05 MST on January 8th, 2026 to alert them to hold site activation activities and to expedite the receipt of the Protocol Signature Page. Email sent to site at 12:22 MST on January 8th, 2026 to provide written confirmation to disregard the Site Activation Letter until the missing document was provided. Pending document received and revised/confirmed Site Activation Letter and notification emailed to site at 15:35 MST on January 8th, 2026. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-224105 | C4591081 | N | QE-224105 | 1003 | Aaron Weinberg (C4591081-1003) | N | Minor | Closed | During review of documents filed in the Clinical.ly eISF for C4591081 Site 1003, the unblinded CRA noted that unblinded Investigational Product (IP) documentation appeared to be correctly categorized as unblinded and restricted from blinded study team. However, it was identified that the site "Recruiter" role may have had visibility to the unblinded IP documentation folder based on system role permissions. For confirmation, the unblinded CRA requested confirmation from the site regarding which site role was associated with the "Recruiter" permission level and whether that role had access to unblinded IP documentation. The site subsequently indicated that recruiters were not intended to have access to the unblinded IP documentation folder and that the observed access may have resulted from a clerical or system configuration error. Given the potential risk to study blinding and access control integrity, the site initiated an internal review and escalated the matter to Clinical.ly to assess and confirm appropriate role-based access permissions within the eISF. | 2026-01-14 | 2026-01-21 | 2026-01-22 16:12 | GCP_Minor_Jan-2026_C4591081: Potential Unblinding: System Access Controls_Weinberg, Aaron_USA |  | NO |  |  | No |  |  | 2026-01-21 |  | IT Systems | Inadequate system access or account management |  |  | DMB06-Randomization Schedule Data Blinding and Break Blind | Elizabeth Miller |  | Upon identification of the potential access concern, the site initiated an internal review of eISF access permissions associated with the "Recruiter" role. The issue was escalated internally and to Clinical.ly for assessment and confirmation of appropriate role-based access configuration. The site accessed the Clinical.ly eISF system and removed the ability for the "Recruiter" role to view unblinded IP documentation. The unblinded CRA confirmed that access permission to view unblinded documents have been removed from the Recruiter role within the Clinical.ly eISF. The site provided signed recruiter attestations for personnel assigned the Recruiter role in the eISF, confirming that they did not access, view, download, or otherwise interact with any unblinded IP documentation while assigned that role. Unblinded CRA to follow-up with site during next on-site unblinded monitoring visit, scheduled for 22-Jan-2026. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-224108 | C4591081 | N | QE-224108 | 1165 | Vasundhara Cheekati (C4591081-1165) | N | Minor | Closed | Study C4591081, PI Vasundhara Cheekati, Site 1165, was activated without Trulab access granted, and sent samples without entering the information into the Trulab system. | 2026-01-20 | 2026-01-21 | 2026-01-21 22:14 | GCP_Minor_Jan-2026_C4591081: CMCD: Site Activation, Trulab Access, and Biospecimen Sample Management_Cheekati, Vasundhara; Pfizer_USA |  | NO |  |  | No |  |  | 2026-01-21 |  | Equipment, Facility and Sample/Specimens, Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan), Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens, INV02-Investigational Site Selection, Preparation, and Initiation | FaMitah Buchanan |  | Site enrollment has been placed on hold and IMPALA has been updated to ensure they cannot enroll subject. Enrollment will not resume until site access is provided, the study assigned devices are confirmed and the site is retrained. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-224108 | C4591081 | (Empty) | QE-224108 |  | PFIZER | N | Minor | Closed | Study C4591081, PI Vasundhara Cheekati, Site 1165, was activated without Trulab access granted, and sent samples without entering the information into the Trulab system. | 2026-01-20 | 2026-01-21 | 2026-01-21 22:14 | GCP_Minor_Jan-2026_C4591081: CMCD: Site Activation, Trulab Access, and Biospecimen Sample Management_Cheekati, Vasundhara; Pfizer_USA |  | NO |  |  | No |  |  | 2026-01-21 |  | Equipment, Facility and Sample/Specimens, Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan), Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens, INV02-Investigational Site Selection, Preparation, and Initiation | FaMitah Buchanan |  | Site enrollment has been placed on hold and IMPALA has been updated to ensure they cannot enroll subject. Enrollment will not resume until site access is provided, the study assigned devices are confirmed and the site is retrained. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-224119 | C4591081 | N | QE-224119 | 1003 | Aaron Weinberg (C4591081-1003) | N | Minor | Closed | During remote review by unblinded CRA of site documentation practices related to the IP Accountability Log (IPAL) for C4591081 Site 1003, it was identified that the site maintains the IPAL using a Microsoft Word document as the controlled source file. Per site explanation provided via email, updates to the IPAL are made within the Microsoft Word document and subsequently re-uploaded to the Clinical.ly eISF as needed. Archived versions within the eISF represent prior iterations of the document. This practice raised a concern regarding potential non-alignment with Sponsor expectations for source control, versioning, and audit trail integrity. While archived versions are retained in the eISF, it is unclear whether the Microsoft Word source document includes sufficient controls (e.g., restricted access, change tracking, user attribution) to fully support ALCOA+ principles. At the time of submission, this practice has not yet been fully verified. The unblinded CRA is scheduled to conduct an on-site visit to further assess the IPAL maintenance process and confirm whether adequate controls (e.g., document access restrictions, tracked changes, version history, user entry) are in place. | 2026-01-14 | 2026-01-21 | 2026-01-22 15:25 | GCP_Minor_Jan-2026_C4591081: Investigational Product Accountability Log (IPAL)_Weinberg, Aaron_USA |  | NO |  |  | No |  |  | 2026-01-22 |  | Data Collection and Management | Inadequate source data/documentation |  |  | IP13-Investigational Medicinal Product | Elizabeth Miller |  | Unblinded CRA requested clarification from the site regarding IPAL maintenance, source control, and versioning practices. Unblinded CRA has received some clarification on site process, but more information is needed to better determine whether or not the process is adequate. On-site review scheduled to further assess the situation and to discuss with unblinded site staff. |  |  | NA | Human Performance | Inconsistency Error |  | MODEL 1 - INSOURCED | Vaccines
QE-224302 | C4591081 | (Empty) | QE-224302 |  | PFIZER | N | Major | Closed | Potential or known unintentional unblinding of study data. On 12-Jan2026- the Unblinded CRA emailed 2 Unblinded site SCs (site 1066) regarding the IPAL and included a screenshot of IP Prep Worksheet for 1 subject that contained unblinded IP information. The PI was copied on the email and should not have received this email. On 18Jan2026 the PI emailed the Unblinded SC stating that he received this email and confirmed that he did not review the contents of the email. On 19Jan2026 the unblinded SC alerted the unblinded CRA by email that the PI (blinded PI) was copied on an email that contains unblinding information. PI immediately noticed the recipients of the email were unblinded and sent the unblinded SC a note that he deleted the email. PI confirmed he did not read any of the contents, so he was not unblinded to the subject's treatment assignment. On 20Jan2026, the SCP notified the Unblinded CRA that this should be submitted as a QE and copied 2 Blinded cSOMs. The Blinded cSOMs should not have been copied on this email. | 2026-01-20 | 2026-01-22 | 2026-01-22 21:33 | GCP_Major_Jan-2026_C4591081: Unblinding: Blinded Email Communication_Pfizer_USA |  | YES |  | <p>On 12 Jan 2026 the Clinical Research Associate (CRA) for site 1066 sent information to the unblinded Study Coordinator (SC) regarding corrections needed within an Investigational Product Accountability Log (IPAL) at the site, this email contained an image showing dosing information for a single participant (10661021). The CRA inadvertently copied the Principal investigator at the site, who is blinded. The principal investigator at the site noted who the email was addressed to, did not open the email, and deleted it to prevent any unintentional unblinding.</p><p>&nbsp;</p><p>On 21 Jan 2026 the Pfizer Site Care Partner (SCP) requested to the CRA that a quality event (QE) be submitted for the unblinding near miss. The SCP copied two blinded country Study Operations Managers (cSOM) on the request which included the unblinding image. Both cSOMs opened the email prior to noticing the unblinding nature of the email. This potentially unblinded the cSOMs copied on the request.</p><p>&nbsp;</p><p>A historical review of Quality Events (QEs) in the electronic Quality Management System (eQMS) database was conducted for the period 22 Jan 2024– 10 Feb 2026, using the keyword “C4591081” and “Unblinding.” No historical QEs were identified as previous occurrences. Based on this review, the current QE (QE-224302) is not considered a repeat occurrence.</p> | No | Other | 2026-02-12 | 2026-02-13 |  | Data Collection and Management | Incorrect assignment/randomization and/or maintenance of the study blind |  | 2026-02-13 22:12 | DMB06-Randomization Schedule Data Blinding and Break Blind | Carolyn Wood | FALSE | PI notified his unblinded SC that he deleted the email and did not read the contents. The unblinded SC notified the CRA that the PI was copied on an email containing subject unblinded information. Additionally, the SCP copied 2 Blinded cSOMs on an email to the unblinded CRA to submit a QE - and the email chain still contained unblinded information. The cSOM notified the SCP that they should not have been copied on the email containing unblinded information. on 22Jan2026- the 2 cSOMs confirmed that the email had been deleted from their Outlook. |  |  | The study was not following established processes with regards to forwarding information from unblinded colleagues, nor was there a unified convention within the study for email subject lines to warn of potential unblinding information contained within. | Method/Procedure | Procedure/Form/Plan | Inadequate/Inaccurate/Confusing (Document Standard Lacking/Incorrect Standard Content) | MODEL 1 - INSOURCED | Vaccines
QE-224326 | C4591081 | N | QE-224326 | 1061 | Alpa Patel (C4591081-1061) | N | Minor | Closed | Study C4591081, Site 1061 enrolled 7 patients (1001, 1002, 1003, 1004, 1005, 1006, 1007) without properly utilizing the TruLab application in real time for their lab specimen collection and processing. | 2026-01-16 | 2026-01-22 | 2026-01-23 18:11 | GCP_Minor_Jan-2026_C4591081: Sample Data Collection: TruLabs App_Patel, Alpa_USA |  | NO |  |  | No |  |  | 2026-01-23 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens | Jessica Watts |  | Site was contacted by CRA on 16Jan2026 at time of awareness in order to schedule a retraining on the protocol and best practices when it comes to TruLab. The site agreed to a training, and it was scheduled for 22Jan2026. The CRA confirmed access for staff performing TruLab duties in the sponsor dashboard and with the staff via training meeting. A site contact report was created following the retraining and a protocol deviation for each subject impacted was added to CTMS. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-224343 | C4591081 | (Empty) | QE-224343 |  | PFIZER | N | Minor | Closed | On 19-Jan, HCL agent Lyubomir Petrov granted the SNBB access instead of the requested TPB one for the user Avery Woodard to study C4591081 site 1063. This incorrect access was corrected as soon as confirmed on 22Jan2026. | 2026-01-22 | 2026-01-22 | 2026-01-23 02:30 | GCP_Minor_Jan-2026_C4591081: Third Party Blind Access_Pfizer_USA |  | NO |  |  | No |  |  | 2026-01-22 |  | IT Systems | Inadequate system access or account management |  |  | CP403 | Nadine Bailey |  | Correction of the ticket: TPB access provided for user Avery Woodard and SNBBB removed. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-224485 | C4591081 | (Empty) | QE-224485 |  | PFIZER | N | Minor | Closed | For study C4591081 site 1045, when providing Impala access, the following errors occured by vendor HCL Tech:Kyler Madeira was provided Site No break Bllind (SNBB) instead of Third- Party Blind (TPB) to Impala 2.0Rachael Kahnwas provided with Third- Party Blind (TPB) instead of Site No Break Bllind (SNBB) to Impala 2.0Please see attachment with description of SNBB and TPB roles for Impala 2.0. | 2026-01-22 | 2026-01-26 | 2026-01-26 20:37 | GCP_Minor_Jan-2026_C4591081: Impala System Access Controls_Pfizer_USA |  | NO |  |  | No |  |  | 2026-01-26 |  | IT Systems | Inadequate system access or account management |  |  | CP403 | Nadine Bailey |  | Accesses were immediately corrected. an Both team members have been addressed through one-on-one meetings, during which they were reminded of the importance of consulting the knowledge articles. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-224549 | C4591081 | (Empty) | QE-224549 |  | PFIZER | N | Minor | Closed | C4591081 - site 1098 C4591081 Site 1098 was activated but did not meet the Site Activation Checklist requirements. The Signant Health Trial Manager portion of the Site Activation Checklist reads "Access to be confirmed by user successfully logging into Trial Manager. Site staff must log into Trial Manager and select “Add a new participant.” Staff must then select the “Participant Language” drop down menu and confirm that all relevant languages are available for selection." Site Care Partner confirmed with the PI during the SIV that he was able to log into Signant Health Trial Manager; however, site staff did not login to Signant Health Trial Manager and select "add a new participant" and confirm that English was available. The Signant Health User Access Reports show that all blinded staff have access to Signant Health Trial Manager -- however, on 01/22/26 when staff attempted to log into Signant Health Trial Manager they were unable to login. The Sub-Investigator was able to log into Signant Health Trial Manager on 01/23/26 and finish registering the patient in Signant Health Trial Manager. Site will need to create a DCF in Signant Health Trial Manager and correct the date of enrollment/start date for diary entry. | 2026-01-23 | 2026-01-26 | 2026-01-26 19:01 | GCP_Minor_Jan-2026_C4591081: Site Activation_Pfizer_USA |  | NO |  |  | No |  |  | 2026-01-26 |  | IT Systems | Inadequate system access or account management |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Stacey Gibson |  | SCP has submitted a support ticket so access to Signant Health Trial Manager will populate on the MyPfizer Studies link and staff can access through their Exostar. Sub-I has logged into Signant Health Trial Manager successfully and site staff have finished setting up patient 10981001's diary. Site will create a DCR to update the date of enrollment. |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Vaccines
QE-224796 | C4591081 | N | QE-224796 | 1013, 1041, 1050, 1068, 1079, 1086, 1089, 1090, 1139, 1193 | Al Robaina (C4591081-1090), Alexander White (C4591081-1079), Brandon Alleman (C4591081-1050), J. Overcash (C4591081-1193), Jerry Punch (C4591081-1139), JUDITH KIRSTEIN (C4591081-1086), Lazaro Garcia (C4591081-1068), Lisa Holloway (C4591081-1013), Robert Lockwood (C4591081-1041), Scott English (C4591081-1089) | N | Minor | Closed | QE for Study C4591081 &amp; sites :1013, 1050, 1068, 1079, 1089, 1090, 1139, 1193, 1041, 1062, 1086. PHI including patient health information (PHI) as defined by VRD’s lab manual, on the vials sent to VRD. | 2026-01-26 | 2026-01-28 | 2026-01-29 17:58 | GCP_Minor_Jan-2026_C4591081: Participant Confidentiality_Multiple Sites_USA |  | NO |  |  | No |  |  | 2026-01-29 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Jamia Bazemore |  | All CRAs have been informed of this but just to be sure: all these sites will need to be retrained to remind them of the VRD requirements for not adding any information. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-224796 | C4591081 | Y | QE-224796 | 1062 | John Rubino (C4591081-1062) | N | Minor | Closed | QE for Study C4591081 &amp; sites :1013, 1050, 1068, 1079, 1089, 1090, 1139, 1193, 1041, 1062, 1086. PHI including patient health information (PHI) as defined by VRD’s lab manual, on the vials sent to VRD. | 2026-01-26 | 2026-01-28 | 2026-01-29 17:58 | GCP_Minor_Jan-2026_C4591081: Participant Confidentiality_Multiple Sites_USA |  | NO |  |  | No |  |  | 2026-01-29 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Jamia Bazemore |  | All CRAs have been informed of this but just to be sure: all these sites will need to be retrained to remind them of the VRD requirements for not adding any information. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-225031 | C4591081 | (Empty) | QE-225031 |  | PFIZER | N | Minor | Closed | .6667px; background-color: rgb(218, 242, 208);'incorrect access was granted, PI received “investigator with signature only” but we need “investigator with data entry and signature only”. Correct training completed. | 2026-01-20 | 2026-01-27 | 2026-01-27 21:37 | GCP_Minor_Jan-2026_C4591081: System Access Controls_Pfizer_USA |  | NO |  |  | No |  |  | 2026-01-27 |  | IT Systems | Inadequate system access or account management |  |  | DMB07-Study Data Set Design and Setup | Steven Levis |  | The incorrect access was identified and rectified. The Investigator Signature role w/DE was correctly granted in the RCC system for Study C4591081 – Site 1046 on 27th January 2026. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-225259 | C4591081 | (Empty) | QE-225259 |  | PFIZER | N | Minor | Closed | TrueLab was not on site or site staff did not have the proper access prior to site activation. -1064- Training completed, access granted but never updated pin to gain access to live portal.-1059- -1068 - Training completed, access granted but never updated pin to gain access to live portal. -1138- Training completed, access granted but never updated pin to gain access to live portal. The Provisioning Spread Sheet needed to be updated to send pin to site to update to gain access to live portal. | 2026-01-22 | 2026-01-30 | 2026-01-30 16:36 | GCP_Minor_Jan-2026_C4591081: Site Activation: System Access_Pfizer_USA |  | NO |  |  | No |  |  | 2026-01-30 |  | Quality Procedures | Business process not addressed |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Donald DeSousa |  | Retraining was provided for the entire Site Care Partner team to review how to confirm that TrueLab access pin has been changed and updated to reflect live access to the portal. This training was provided on 28-Jan-2026 by C. Ryan/ A. Dollard/ |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-225397 | C4591081 | (Empty) | QE-225397 |  | PFIZER | N | Minor | Closed | Site confirmed access to Signant eDiary portal at SIV however SCP did not verify on access tracker. Access was not provided at time of activation. | 2026-01-29 | 2026-01-29 | 2026-01-29 17:23 | GCP_Minor_Jan-2026_C4591081: Site Activation: System Access_Pfizer_USA |  | NO |  |  | No |  |  | 2026-01-29 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Sharon Donahue |  | Site was instructed not to enroll subjects until access is provided. No subjects were screened or enrolled. |  |  | NA | Personnel | Lack of or Inadequate Oversight |  | MODEL 1 - INSOURCED | Vaccines
QE-225698 | C4591081 | (Empty) | QE-225698 |  | SIGNANT HEALTH GLOBAL SOLUTIONS LIMITED | N | Minor | Closed | Study C4591081 encountered an issue from Signant Health during data transfers. It was brought to DMs attention by the study team that subject number was not being transferred in the data files we were receiving. DM then discovered there were multiple subject IDs that were not reflecting in the data transfer when compared to the TrialMax data (Signant application). | 2026-01-29 | 2026-02-02 | 2026-02-03 19:43 | GCP_Minor_Feb-2026_C4591081: Data Transfer_Signant Health_USA |  | NO |  |  | No |  |  | 2026-02-03 |  | Data Collection and Management | Data management error |  |  | No Process Assigned | Hiren Patel |  | Signant created a new export that is set to update daily, and the ADT will always use the latest version of this export. From now on this problem will not happen again. |  |  | NA | Equipment/System/Facility | System/Application |  | MODEL 1 - INSOURCED | Vaccines
QE-225991 | C4591081 | N | QE-225991 | 1127 | Mary Bailey (C4591081-1127) | N | Minor | Closed | Patient health information (subject ID) was documented on the nasal swab samples that arrived at VRD for site 1127 study C4591081 | 2026-02-02 | 2026-02-02 | 2026-02-03 18:34 | GCP_Minor_Feb-2026_C4591081: Participant Confidentiality / Data Privacy_Mary Bailey_USA |  | NO |  |  | No | Minor/Unrated Quality Event |  | 2026-02-03 |  | Data Privacy | Data privacy/confidentiality |  |  | REG09-Protecting the Privacy of Personal Information | Titi Akinyosoye |  | CRA retrained site staff on ensuring that the only identifier allowed on vials are barcode labels. |  |  | N/A | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-225991 | C4591081 | (Empty) | QE-225991 |  | PFIZER | N | Minor | Closed | Patient health information (subject ID) was documented on the nasal swab samples that arrived at VRD for site 1127 study C4591081 | 2026-02-02 | 2026-02-02 | 2026-02-03 18:34 | GCP_Minor_Feb-2026_C4591081: Participant Confidentiality / Data Privacy_Mary Bailey_USA |  | NO |  |  | No | Minor/Unrated Quality Event |  | 2026-02-03 |  | Data Privacy | Data privacy/confidentiality |  |  | REG09-Protecting the Privacy of Personal Information | Titi Akinyosoye |  | CRA retrained site staff on ensuring that the only identifier allowed on vials are barcode labels. |  |  | N/A | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-226016 | C4591081 | (Empty) | QE-226016 |  | PFIZER | N | Minor | Closed | Site # 1105 (Dr. Romero) was activated on the C4591081 study without transferring the electronic Investigator Site File (eISF) to the site. | 2026-01-26 | 2026-02-03 | 2026-02-03 19:18 | GCP_Minor_Feb-2026_C4591081: Site Oversite Data Management_Pfizer_USA |  | NO |  |  | No | Minor/Unrated Quality Event |  | 2026-02-03 |  | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Eric Flores |  | The SCP submitted the eISF transfer request on 26 Jan 2026. On same day, the SCP was re‑trained on site activation requirements and informed that SCPs are to request eISF transfer requests through the MyTrial Assist Portal. The Clinical Trial Assistant transferred the eISF to the site on 30 Jan 2026, and the SCP confirmed receipt with the site on the same day. |  |  | N/A | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Vaccines
QE-226294 | C4591081 | (Empty) | QE-226294 |  | PFIZER | N | Minor | Closed | On January 15th a release to the Data Integrity and Validation Application (DIVA) resulted in an issue with the signed versions of the Data Integrity Plan (DIP) not providing an accurate document history or validation modifications for signed versions of the DIP, which were then posted with these inaccuracies to the pTMF. 32 studies were impacted by this error. This also impacted the standard library DIP, with the inaccuracies documented in a signed version of the library DIP which was subsequently posted to Gnosis. | 2026-02-03 | 2026-02-03 | 2026-02-04 18:45 | GCP_Minor_Feb-2026_Multiple Protocols: Data Integrity Plan_Pfizer_Global |  | NO |  |  | No |  |  | 2026-02-04 |  | Data Collection and Management | Data management error |  |  | CT01-Trial Master Files | Jennifer Maloney |  | Upon realizing the issue DIVA support was engaged to identify the root cause and to fix the issue so additional studies would not be impacted. The DIVA support team is working through a remediation for the studies that are currently impacted. |  |  | NA | Equipment/System/Facility | System/Application |  | MODEL 1 - INSOURCED | Vaccines
QE-226523 | C4591081 | N | QE-226523 | 1003, 1031, 1041, 1050, 1061, 1075, 1094, 1193 | Aaron Weinberg (C4591081-1003), Alpa Patel (C4591081-1061), Brandon Alleman (C4591081-1050), Clint Flanagan (C4591081-1075), J. Overcash (C4591081-1193), Jorge Caso (C4591081-1094), Jose Bordon (C4591081-1031), Robert Lockwood (C4591081-1041) | N | Minor | Closed | On study C4591081, multiple sites have included Subject ID#s on vials shipped to VRD. This is in deviation to VRD lab manual. Although this was discussed during IM, some sites included Subject ID on the vials. The sites involved are: 1050 .375in;font-family:Calibri;font-size:11.0pt"1003 .375in;font-family:Calibri;font-size:11.0pt"1031 .375in;font-family:Calibri;font-size:11.0pt"1075 .375in;font-family:Calibri;font-size:11.0pt"1193 .375in;font-family:Calibri;font-size:11.0pt"1061 .375in;font-family:Calibri;font-size:11.0pt"1094 .375in;font-family:Calibri;font-size:11.0pt"1041 | 2026-01-23 | 2026-02-04 | 2026-02-05 17:23 | GCP_Minor_Feb-2026_C4591081: Participant Confidentiality_Mulitple Sites_USA |  | NO |  |  | No |  |  | 2026-02-05 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Irina Mosesova |  | CRAs for all sites were contacted with request to re-train the sites. In addition, a news blast was sent on 30Jan2026 to all sites to remind them of this VRD lab manual requirement.In addition to above, 2 Trulab re-trainings are scheduled with sites (Feb 10 and Feb 12) to ensure there is another way to remind sites of this requirement. |  |  | NA | Human Performance | Decision Error |  | MODEL 1 - INSOURCED | Vaccines
QE-226977 | C4591081 | (Empty) | QE-226977 |  | PFIZER | N | Minor | Closed | granted TPB access to an incorrect user for IMPALA 2.0 | 2026-02-06 | 2026-02-06 | 2026-02-06 21:02 | GCP_Minor_Feb-2026_C4591081: Impala System Access Controls: Third Party Blind_Pfizer_USA |  | NO |  |  | No |  |  | 2026-02-06 |  | IT Systems | Inadequate system access or account management |  |  | CP403 | Steven Levis |  | Third Party Blind access for study C4591081, site 1137 was granted to Anum Chowdary. This access has now been removed from Anum Chowdary’s account, and the same access has been granted to Jessica Armstrong. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-227332 | C4591081 | N | QE-227332 | 1188 | Sarah Smiley (C4591081-1188) | N | Minor | Closed | Site 1188 of Study C4771002 has sent a self swab sample with subject name (PHI) on it to the VRD, subject involved is 11881007 and site stated that the subject inadvertently wrote their own name on the sample but site staff failed to catch it. | 2026-02-05 | 2026-02-11 | 2026-02-11 16:27 | GCP_Minor_Feb-2026_C4591081: Participant Confidentiality_Smiley, Sarah_USA |  | NO |  |  | No |  |  | 2026-02-11 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Yiyi Torgerson |  | CRA has contacted site regarding this incident and retrained the site, site confirmed understanding and will ensure no PHI on any samples being sent to lab. PD has been recorded in Veeva by CRA and site has recorded PD in source. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-227483 | C4591081 | (Empty) | QE-227483 |  | PFIZER | N | Minor | Closed | A request was submitted by SCPr on behalf of the end users, D F and L K , to provide access to the Impala 2 application. During provisioning, an incorrect role was initially granted in Impala 2 | 2026-02-09 | 2026-02-10 | 2026-02-10 21:09 | GCP_Minor_Feb-2026_C4591081: Impala System Access Controls: Third Party Blind_Pfizer_USA |  | NO |  |  | No |  |  | 2026-02-10 |  | IT Systems | Inadequate system access or account management |  |  | DMB07-Study Data Set Design and Setup | Steven Levis |  | Correct access has been modifiedFeedback was shared with the responsible agent, and the non‑conformance has been logged. |  |  | NA | Human Performance | Inconsistency Error |  | MODEL 1 - INSOURCED | Vaccines
QE-227545 | C4591081 | N | QE-227545 | 1094 | Jorge Caso (C4591081-1094) | N | Major | In Investigation | Study C4591081 Site 1094:An issue related to the IPAL document was raised containing unblinded information of subject within Veeva Site Vault. This resulted an automatic email notification containing the unblinded information of a subject being sent to 4 blinded site staff. The unblinded site staff supervises inboxes of the 4 blinded staff and was able to delete the email notification for two blinded site staff before they could view it, but the other two blinded staff viewed the email before the deletion, which resulted an unblinding event. | 2026-02-10 | 2026-02-11 | 2026-02-11 18:56 | GCP_Major_Feb-2026_C4591081: Unblinding: Site Email_Caso, Jorge_USA |  | NO | [7 empty] | Data Collection and Management | Incorrect assignment/randomization and/or maintenance of the study blind |  |  | DMB06-Randomization Schedule Data Blinding and Break Blind | Steven Yang |  | Once it was notified by the site, CRA deleted the raised issue immediately and escalated the event to Site Care Partner, and unblinded study manager, and the Clinical Pharmacy Liaison. The unblinded study manager will notify the GSM regarding the issue. The unblinded site staff immediately deleted the emails, therefore only 2 blinded site staff out of 4 read the email notification. | [6 empty] | MODEL 1 - INSOURCED | Vaccines
QE-227932 | C4591081 | N | QE-227932 | 1013 | Lisa Holloway (C4591081-1013) | N | Minor | Closed | The site 1013 wrote the subject ID number on the nasal swab vial along with the barcode for specimen sent to the Central lab. | 2026-01-21 | 2026-02-12 | 2026-02-12 20:26 | GCP_Minor_Feb-2026_C4591081: Participant Confidentiality_Holloway, Lisa_USA |  | NO |  |  | No |  |  | 2026-02-12 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Cathryn Lloyd |  | The site was retrained by the Monitor on the Lab Manual and the proper process for labelling specimens. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-227935 | C4591081 | N | QE-227935 | 1031 | Jose Bordon (C4591081-1031) | N | Minor | Closed | A routine monitoring visit (My first visit since SIV) was conducted at Dr. Bordon's site 1031. During the visit, the CRA identified compliance concerns, including data entry errors, missing documentation, inaccuracies in source records, and lacking documentation practices across multiple subjects. These findings raise concerns regarding subject eligibility, informed consent integrity, and data reliability. Key Findings:1.Subject Eligibility and Screening issuesMultiple subjects were identified as potentially ineligible based on protocol requirements:Subject 10311001 (This subject should have been classified as a screen failure due to exclusion criterion 5.2.8 (BMI≥30)Subject 10311003- Date of birth listed as 20-JAN-2013 making the subject 13 years old and ineligible for the study. Subject also reported to be on amlodipine, however no supporting medical history or documentation from the PI stating his approval. No concomitant medications listed.2.Informed Consent Process Deficiencies:Several deficiencies were noted related to the informed consent process and documentation:Subject 10311002 - Vaccination Consent Template (VCT) signed and dated 15-JAN-2026 while the main ICF was signed 16-JAN-2026, indicating consent sequencing issues.Vaccination history question marked as YES for vaccination within the last 3 months. Site confirmed vaccination occurred 11-OCT-2025 exactly 3 months and 5days.Subject 10311007Question "Was the subject given adequate time to review the ICF?" Marked as NOSubject 10311007,10311008 and 10311010:No ICF for CRA to reviewNo randomization prints out from IRT availableNo VCT available for review 3. Randomization Discrepancies:Discrepancies were identified between source documentation and the IRT systems:Subject 10311013 and 10311014- Randomization number documented in source did not match the IRT print out., 4. Incomplete or unsigned Source Documentation. Subject 10311015- Physical examination was performed however:The data was not documented in source; the assessment was not signed by the PI or delegated sub-I 5. Post-Vaccination Observation DocumentationAcross all subjects reviewed, there was no documentation confirming that subjects were observed for 30 minutes post-vaccination as required by the protocol. CRA requested the site to walk through their subject screening and recruitment processCRC stated that subjects are recruited through Website outreachPhone outreachFlyersCommunity eventsSponsor referrals (Pfizer)He also stated that they pre-screen subjects over the phone prior to bringing them in for a screening visit.When asked about obtaining consent to access and review medical records, CRC stated this is often difficult as some subjects might be homeless as a result, medical histories are frequently self-reported by subjects and documented by site staff without external verification. Site Discussion and Corrective Actions.A discussion was held with the PI and site staff on Feb 9th, 2026, at 10.a.m to review the findings. During this discussion via Zoom1.CRA emphasized the seriousness of the documentation and compliance gaps2. CRA recommended additional protocol and GCP training for site staff.3. PI acknowledged the issues and agreed that additional training is necessary | 2026-02-06 | 2026-03-04 | 2026-03-05 17:48 | GCP_Minor_Mar-2026_C4591081: PI Oversight_Bordon, Jose_USA |  | NO |  |  | No |  |  | 2026-03-05 |  | Quality Oversight | Inadequate Principal Investigator quality oversight |  |  | CT40-Management of Protocol Deviations | Titi Akinyosoye |  | CRA retrained the site immediately.Immediate corrective actions, including retraining and process review, are necessary to mitigate ongoing risks to data integrity and subject safety. Also, CRA escalated this to the study team who met and decided that a recruitment hold is necessary for this site. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-227966 | C4591081 | N | QE-227966 | 1098 | Saad Alvi (C4591081-1098) | N | Minor | Closed | Deepa Lime submitting on behalf of CRA, Mahmoud A - Study C4591081, Subject X at site 1098 (keeping the subject number unidentified as per the study team's request): On 10-FEB-2026, while site staff were preparing remote access for remote monitoring, they inadvertently uploaded IP-related unblinding information that was accessible to the blinded CRA during his blinded remote monitoring activities.Actions taken:The issue was immediately escalated to site staff and the study teamAs per the study team's directive, the CRA terminated further activities during the blinded monitoring visit pending next steps from the study team. The CRA and SCP connected with site staff via phone and asked them to review all files to ensure no unblinded documents were uploaded or accessible by the blinded CRA for any upcoming site visits. | 2026-02-10 | 2026-02-12 | 2026-02-13 18:43 | GCP_Minor_Feb-2026_C4591081: Unblinding: IP Documentation_Alvi, Saad_USA |  | NO |  |  | No |  |  | 2026-02-13 |  | Data Collection and Management | Incorrect assignment/randomization and/or maintenance of the study blind |  |  | DMB06-Randomization Schedule Data Blinding and Break Blind | Deepa Lim |  | Actions taken:The issue was immediately escalated to site staff and the study teamAs per the study team's directive, the CRA terminated further activities during the blinded monitoring visit pending next steps from the study team. The CRA and SCP connected with site staff via phone and asked them to review all files to ensure no unblinded documents were uploaded or accessible by the blinded CRA for any upcoming site visits. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-227975 | C4591081 | (Empty) | QE-227975 |  | PFIZER | N | Minor | Closed | INV02-GSOP-RF20 was not followed: For study C4591081 Site 1102 SIV was conducted without study team authorization on 06FEB2026 prior to IIP approval.For study C4591081 Site 1102 SIV was conducted on 09FEB2026 prior to IRB and IIP approval. SIV was also conducted without study team authorization. | 2026-02-10 | 2026-02-12 | 2026-02-13 22:02 | GCP_Minor_Feb-2026_C4591081: Site Initiation Visit_Pfizer_USA |  | NO |  |  | No |  |  | 2026-02-13 |  | Site Management and Monitoring | Failure to follow study specific monitoring plan/ requirements |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Aleksandr Shraga |  | SCP requested an exemption from the study team to conduct Follow Up/Part 2 SIV for site 1102 now that IRB approval has been received. IIP approval is anticipated week of Feb 16th.For site 1102: SCP will conduct FollowUp / part 2 of the SIV and update SIV report to include 1) rationale for SIV prior to IIP approval using standard language, 2) review receipt of IRB approval &amp; IRB approved ICD, 3) explain to the site that the eISF is forthcoming and will discuss pending site activation items and tentative timeline to activate the site.For site 1204 SCP requested a post SIV exemption from the study team and will update SIV report to include rationale for conducting SIV prior to IIP approval using standard language |  |  | NA | Human Performance | Decision Error |  | MODEL 1 - INSOURCED | Vaccines
QE-228165 | C4591081 | N | QE-228165 | 1090, 1139, 1142, 1196 | Al Robaina (C4591081-1090), Jerry Punch (C4591081-1139), Lisa Blair (C4591081-1142), Michael Zimmerman (C4591081-1196) | N | Minor | Closed | The following sites have shipped samples to VRD adding subject ID to the vials, which is not as per VRD lab manual. 1090 - AWB: 620X38590255 - subject ID (last 4 digits), awareness date 5feb, training completed on 05feb1139 - AWB: 620X38555970, 620X38228193, 620X38228193, 620X38228193 - subject id on the tube - awareness date 09feb - training confirmation requested1142 - AWB: 620X38750358 - subject id, initial and time - awareness date 13feb - training confirmation requested1196 - AWB: 620X38750557 - subject id - awareness date 13feb - training confirmation requested | 2026-02-05 | 2026-02-13 | 2026-02-13 19:31 | GCP_Minor_Feb-2026_C4591081: Participant Confidentiality _Multiple Sites_ USA |  | NO |  |  | No | Minor/Unrated Quality Event |  | 2026-02-13 |  | Data Privacy | Data privacy/confidentiality |  |  | CT29-Management of Clinical Study BioSpecimens | Irina Mosesova |  | On the SITE level: VRD informs Pfizer team and CRAs for mentioned sites contact site staff and remind them of the proper process confirming they understand not to add any additional information on the tube as per lab manual. On the STUDY level, as a preventative measure - two trulab re-training sessions were held this week for all sites. |  |  | N/A | Method/Procedure | Procedure/Form/Plan |  | MODEL 1 - INSOURCED | Vaccines
QE-228251 | C4591081 | N | QE-228251 | 1073 | Carlos Fierro (C4591081-1073) | N | Minor | Closed | Subject x for site 1073 in the C4591081 study had their data unintentionally unblinded by the sites unblinded pharmacist. | 2026-02-13 | 2026-02-13 | 2026-02-13 22:01 | GCP_Minor_Feb-2026_C4591081: Blinding Plan: IP Documentation_Casey, Ryan_USA |  | NO |  |  | No |  |  | 2026-02-13 |  | Data Collection and Management | Incorrect assignment/randomization and/or maintenance of the study blind |  |  | DMB06-Randomization Schedule Data Blinding and Break Blind | Justin Racine |  | CRIO is used as the primary source for administration data, but the site also records dosing time and other relevant information on the paper dose prep documents. The site has been taking those documents with them to record right after documenting in CRIO. Going forward the site will no longer take any potentially unblinding documents with them to our adjacent administration room to prevent this from happening accidentally again. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-228267 | C4591081 | (Empty) | QE-228267 |  | PFIZER | N | Minor | Closed | INV02-GSOP-RF20 was not followed: For study C4771002 Sites 1046 and 1183. SIV was conducted without IRB approval. 1046 SIV was conducted on 27Jan2026 and IRB approval occurred 09Feb2026. 1183 SIV was conducted on 11Feb2026 and site does not have IRB approval yet. For study C4591081 Site 1102 SIV was conducted on 09FEB2026 prior to IRB and IIP approval. SIV was also conducted without study team authorization. Note, study team did authorize to proceed with SIV prior to IIP approval. | 2026-02-13 | 2026-02-13 | 2026-02-13 22:33 | GCP_Minor_Feb-2026_C4771002, C4591081: CMCD: Site Initiation Visit (SIV)_Pfizer_USA |  | NO |  |  | No |  |  | 2026-02-13 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Erin Palm |  | Confirmed neither site has been activated yet.Reeducated SCP on minimum requirements for SIV. Followed up on status of IRB for Site 1183. Communicated with study team.Site Care Partner to review IRB approvals and ICDs during e-ISF reconciliation prior to activation. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-229532 | C4591081 | (Empty) | QE-229532 |  | SCOUT CLINICAL | N | Minor | Closed | Participant 10631022 used Scout (a Pfizer-provided vendor) for a Lyft ride to and from their site visit. Following the visit, the driver took the participant to a location that was not their home address. | 2026-02-20 | 2026-02-20 | 2026-02-23 15:35 | GCP_Minor_Feb-2026_C4591081: Participant Transportation_Scout Clinical_USA |  | NO |  |  | No |  |  | 2026-02-23 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | No Process Assigned | Caitlin Balascio |  | The participant worked with the site during the ride to ensure the Lyft driver was paid for taking her to the correct location. Scout completed payment to the driver and filed a formal report with Lyft. Additionally, Scout disabled the autofill setting to prevent this from occurring in the future. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-229538 | C4591081 | (Empty) | QE-229538 |  | PFIZER | N | Minor | Closed | C4591081 - Site 1197 - Dr ConwaySite activated prior to eISF transfer completed. | 2026-02-19 | 2026-02-20 | 2026-02-24 17:04 | GCP_Minor_Feb-2026_C4591081: CMCD: Site Activation_Pfizer_USA |  | NO |  |  | No |  |  | 2026-02-24 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Michaela Grey |  | SCP contacted site to hold on screening and enrollment activities until eISF is transferred and site confirms receipt. SCP and cSOMs monitoring CTA Task ticket TSK-0000375274. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-229863 | C4591081 | (Empty) | QE-229863 |  | PFIZER | N | Minor | Closed | I am submitted this on behalf of SCP, Kim Dunklin. For C4591081, Site 1028/McGill. Since having two TPBs is part of the SAC, and this site was activated with only one. | 2026-02-19 | 2026-02-23 | 2026-02-24 16:55 | GCP_Minor_Feb-2026_C4591081: Site Activation_Pfizer_USA |  | NO |  |  | No |  |  | 2026-02-24 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Lauren Broderick |  | Site has not screened or enrolled any patients to date. All staff have accesses in all systems today. SCP verified this in iview2. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-230079 | C4591081 | N | QE-230079 | 1080 | Rafael Nunez-Avila (C4591081-1080) | N | Minor | Closed | .0pt;"On 24 Feb 2026, it was identified that a Site 1080 (C4591081), immunogenicity and nasal swab samples were processed by unblinded study coordinators. The desired state is for these samples to be processed by appropriately delegated and trained blinded study personnel. | 2026-02-24 | 2026-02-24 | 2026-02-24 22:34 | GCP_Minor_Feb-2026_C4591081: Sample Processing Site Role Assignment_Nunez-Avila, Rafael_USA |  | NO |  |  | No |  |  | 2026-02-24 |  | Data Collection and Management | Incorrect assignment/randomization and/or maintenance of the study blind |  |  | DMB06-Randomization Schedule Data Blinding and Break Blind | Brianna Barnes |  | .0pt;"Sponsor guidance was provided on 24 Feb 2026 that immunogenicity and nasal swab processing are restricted to blinded study personnel. Access was removed from unblinded personnel. Access was granted to blinded personnel. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-230086 | C4591081 | N | QE-230086 | 1089 | Scott English (C4591081-1089) | N | Minor | Closed | .5pt'On 19 January 2026, Subject 10891006 at Site 1089 was randomized; however, due to an IRT system issue, the investigational product could not be dispensed. As the protocol required vaccination on the same day and the subject had already been randomized, the participant could not be re‑screened. The subject’s status was updated in Impala as Randomized, Not Dosed..5pt' .5pt'During the visit, protocol-required samples were collected. Based on instructions received at the time by Site Care Partner, the site discarded the samples and documented this action in TruLab. It was later identified that although the lab manual and study procedures outlined the required steps for biospecimen destruction, including completion of the CT29‑GSOP‑RF03 During the Study Biospecimen Destruction Request Form, DCF submission to TruLab, and receipt of formal approval, these resources were not referenced before the samples were discarded. | 2026-02-05 | 2026-02-24 | 2026-02-25 15:33 | GCP_Minor_Feb-2026_C4591081: Biospecimen Sample Management_English, Scott; Pfizer_USA |  | NO |  |  | No |  |  | 2026-02-25 |  | Equipment, Facility and Sample/Specimens, Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan), Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens | Nikita Patel |  | .5pt'Immediate Actions Taken: .5pt'Site updated subject status in Impala and TruLab to reflect .5pt'Randomized, Not Dosed.5pt' and .5pt'Samples Discarded,.5pt' respectively. .5pt'Sponsor was notified of the destruction of samples. .5pt'Corrective Actions: .5pt'The site has been re-trained on the correct procedure for sample destruction, including mandatory completion of CT29‑GSOP‑RF03, DCF submission to TruLab, and obtaining approval before discarding any samples. .5pt'The cSOM re-trained the Site Care Partner, who acknowledged understanding of the correct process and location of all relevant instruction. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-230086 | C4591081 | (Empty) | QE-230086 |  | PFIZER | N | Minor | Closed | .5pt'On 19 January 2026, Subject 10891006 at Site 1089 was randomized; however, due to an IRT system issue, the investigational product could not be dispensed. As the protocol required vaccination on the same day and the subject had already been randomized, the participant could not be re‑screened. The subject’s status was updated in Impala as Randomized, Not Dosed..5pt' .5pt'During the visit, protocol-required samples were collected. Based on instructions received at the time by Site Care Partner, the site discarded the samples and documented this action in TruLab. It was later identified that although the lab manual and study procedures outlined the required steps for biospecimen destruction, including completion of the CT29‑GSOP‑RF03 During the Study Biospecimen Destruction Request Form, DCF submission to TruLab, and receipt of formal approval, these resources were not referenced before the samples were discarded. | 2026-02-05 | 2026-02-24 | 2026-02-25 15:33 | GCP_Minor_Feb-2026_C4591081: Biospecimen Sample Management_English, Scott; Pfizer_USA |  | NO |  |  | No |  |  | 2026-02-25 |  | Equipment, Facility and Sample/Specimens, Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan), Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens | Nikita Patel |  | .5pt'Immediate Actions Taken: .5pt'Site updated subject status in Impala and TruLab to reflect .5pt'Randomized, Not Dosed.5pt' and .5pt'Samples Discarded,.5pt' respectively. .5pt'Sponsor was notified of the destruction of samples. .5pt'Corrective Actions: .5pt'The site has been re-trained on the correct procedure for sample destruction, including mandatory completion of CT29‑GSOP‑RF03, DCF submission to TruLab, and obtaining approval before discarding any samples. .5pt'The cSOM re-trained the Site Care Partner, who acknowledged understanding of the correct process and location of all relevant instruction. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-230229 | C4591081 | N | QE-230229 | 1114 | MIGUEL APONTE (C4591081-1114) | N | Minor | Closed | .0pt;color:black;"On 24 Feb 2026, it was identified that Site 1114 (C4591081), immunogenicity and nasal swab samples were processed by unblinded study coordinators. The desired state is for these samples to be processed by appropriately delegated and trained blinded study personnel. | 2026-02-24 | 2026-02-25 | 2026-02-25 16:29 | GCP_Minor_Feb-2026_C4591081: Potential Unblinding: Unblinded Staff Delegation of Duties_Aponte, Miguel_USA |  | NO |  |  | No |  |  | 2026-02-25 |  | Data Collection and Management | Incorrect assignment/randomization and/or maintenance of the study blind |  |  | DMB06-Randomization Schedule Data Blinding and Break Blind | Brianna Barnes |  | .0pt;color:black;"Sponsor guidance was provided on 24 Feb 2026 that immunogenicity and nasal swab processing are restricted to blinded study personnel. Access was removed from unblinded personnel. Access was granted to blinded personnel. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-230590 | C4591081 | N | QE-230590 | 1180 | Stanton Elzi (C4591081-1180) | N | Minor | Closed | During SIV, site staff confirmed VCT scanner was installed. However, on 25Feb26, SCP noticed the scanner was not successfully installed. When reached out to site, they responded were under impression that scanner had been properly installed, but during the 1st subject screening, they discovered the scanner was not functioning, so they used the approved alternative VCT method by using subject's driver license number to screen and activate the subject successfully in VCT system.Site was able to work with VCT team and successfully installed the scanner on 26Feb2026 and biometric scanned subject 1180-1010. | 2026-02-25 | 2026-02-26 | 2026-02-27 18:25 | GCP_Minor_Feb-2026_C4591081: Site Initiation Visit Equipement Issue_Elzi, Stanton_USA |  | NO |  |  | No | Minor/Unrated Quality Event |  | 2026-02-27 |  | Equipment, Facility and Sample/Specimens | Inadequate equipment/lab supply mgmt. |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Tri Tran |  | Site was able to work around with VCT team and successfully installed the scanner on 26Feb2026 and biometric scanned subject 1180-1010. Issue resolved. |  |  | N/A | Equipment/System/Facility | Equipment |  | MODEL 1 - INSOURCED | Vaccines
QE-230590 | C4591081 | (Empty) | QE-230590 |  | PFIZER, VERIFIED CLINICAL TRIALS | N | Minor | Closed | During SIV, site staff confirmed VCT scanner was installed. However, on 25Feb26, SCP noticed the scanner was not successfully installed. When reached out to site, they responded were under impression that scanner had been properly installed, but during the 1st subject screening, they discovered the scanner was not functioning, so they used the approved alternative VCT method by using subject's driver license number to screen and activate the subject successfully in VCT system.Site was able to work with VCT team and successfully installed the scanner on 26Feb2026 and biometric scanned subject 1180-1010. | 2026-02-25 | 2026-02-26 | 2026-02-27 18:25 | GCP_Minor_Feb-2026_C4591081: Site Initiation Visit Equipement Issue_Elzi, Stanton_USA |  | NO |  |  | No | Minor/Unrated Quality Event |  | 2026-02-27 |  | Equipment, Facility and Sample/Specimens | Inadequate equipment/lab supply mgmt. |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Tri Tran |  | Site was able to work around with VCT team and successfully installed the scanner on 26Feb2026 and biometric scanned subject 1180-1010. Issue resolved. |  |  | N/A | Equipment/System/Facility | Equipment |  | MODEL 1 - INSOURCED | Vaccines
QE-230604 | C4591081 | N | QE-230604 | 1074, 1139, 1175, 1193 | Almena Free (C4591081-1175), Faisal Amin (C4591081-1074), J. Overcash (C4591081-1193), Jerry Punch (C4591081-1139) | N | Minor | Closed | As per lab manual, sites are not to enter subject IDs on the vials. On several occasions sites entered subject ID on the tubes as part of their process to ensure the tubes are traced to appropriate participant and did not remove the subject ID prior to shipping to VRD. As this is not as per lab manual, this QE is being generated. Sites were retrained to remind them of the correct process as per lab manual.Site 1074, shipment AWB620X38814726, awareness date 16FEB, retrained 17FEBSite 1139, shipment AWB 620X38750348, awareness date 16FEB, retrained 17FEBSite 1183, shipment AWB 620X38556373 , awareness date 19FEB, CRA informed and pending confirmation of retraining site 1175, shipment AWB 620X38849425, awareness date 20FEB, CRA informed and pending confirmation of retraining | 2026-02-16 | 2026-02-27 | 2026-02-27 18:23 | GCP_Minor_Feb-2026_C4591081: Biospecimen Sample Management: Subject IDs on Vials_Multiple Sites_USA |  | NO |  |  | No |  |  | 2026-02-27 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens | Irina Mosesova |  | Sites were informed and retrained by CRA to remind them of the process as per lab manual. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-231153 | C4591081 | N | QE-231153 | 1079 | Alexander White (C4591081-1079) | N | Minor | Closed | Site 1079 sent aliquot samples to VRD, lab, with Patient Health Information (PHI) on vials. | 2026-01-16 | 2026-03-02 | 2026-03-02 19:26 | GCP_Minor_Mar-2026_C4591081: Participant Confidentiality / Data Privacy_White, Alexander_USA |  | NO |  |  | No |  |  | 2026-03-02 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Ryan Hedges |  | On 16Jan, CRA contacted site staff to retrain them on proper sample management. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-231216 | C4591081 | (Empty) | QE-231216 |  | PFIZER | N | Minor | Closed | Lindsey Marshall, the Site Coordinator for site 1088, incorrectly had access to site 1081 in Simplify.Due to this incorrect access, she submitted multiple access requests under site 1081, even though all staff members belonged to site 1088.All incorrect tickets were rejected, except for two (Impala and Signant), which had already been closed. Since Lindsey was granted access to these systems, the cSOM investigated whether she had accessed them—and she did: Impala (site 1081): 14 Jan 2026Signant: 08 Jan 2025 | 2026-02-17 | 2026-03-02 | 2026-03-02 22:00 | GCP_Minor_Mar-2026_C4591081: System Access Request Controls: Impala; Signant_Pfizer_USA |  | NO |  |  | No |  |  | 2026-03-02 |  | IT Systems | Inadequate system access or account management |  |  | CP404 | Mimi Renaldo |  | A ticket was opened with Simplify requesting: a. Removal of Lindsey’s incorrect access to site 1081 b. Removal of all access requests submitted under the wrong site c. Identification of the likely root causeAll incorrect tickets were rejected, except for two (Impala and Signant), which had already been closed. Access was revoked for ImpalaSignant access revocation is in progress |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-231511 | C4591081 | (Empty) | QE-231511 |  | PFIZER | N | Minor | Closed | On 18Feb2026, after the blinded cSOM was copied in one email from the Unblinded team sent to the SCPs requesting to send the UNB document for their review and approval, the blinded cSOM team became aware that 14 sites were activated without the Unblinded (UNB) source document being sent, reviewed, or approved by the UNB GSMs. The Site Activation Checklist (SAC) states: “If not already done, obtain the source document shared by unblinded site staff to the blinded site staff and send it to the Unblinded Pfizer team to ensure it does not contain unblinding information and includes a maintaining-the-blind statement.”However, sites 1009, 1043, 1053, 1073, 1076, 1085, 1088, 1097, 1126, 1134, 1164, 1169, 1214, and 1217 were activated without the UNB source document being provided to the UNB team. From these 14 sites, site 1043 was the first to be activated on 12 Jan 2026, and the most recent site was activated on 11 Feb 2026. | 2026-02-18 | 2026-03-04 | 2026-03-05 15:13 | GCP_Minor_Mar-2026_C4591081: CMCD: Site Activation_Pfizer_USA |  | NO |  |  | No |  |  | 2026-03-05 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Lizbeth Coria |  | 1. For sites pending activation:cSOMs instructed SCPs that prior to activation, they must provide proof of UNB approval of the source document, specifically by sending a screenshot of the approval.2. For sites already activated without approval:cSOMs requested that SCPs obtain the UNB GSM approval immediately for the missing UNB source documents. This activity has been completed. 3. Verification of potential unblinding:A review was conducted to assess whether any unblinding occurrences had taken place at the 14 affected sites. SCPs confirmed no unblinding events.4. On 23Feb2026, SCPs were reminded to review the contents of the SAC and make sure it is complete before sending to the SAP (Site Activation Partner). |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-231634 | C4591081 | (Empty) | QE-231634 |  | PFIZER | N | Minor | Closed | Site 1205/Maas was activated on C4591081 without the VCT fingerprint scanner activated. | 2026-02-25 | 2026-03-04 | 2026-03-04 22:04 | GCP_Minor_Mar-2026_C4591081: Site Activation_Pfizer_USA |  | NO |  |  | No |  |  | 2026-03-04 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Geraldine Quiogue |  | Scanner was activated properly on 26Feb2026. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-231691 | C4591081 | N | QE-231691 | 1207 | Heather Myers (C4591081-1207) | N | Minor | Closed | Site 1207 consented subject 12071001 with the VCT consent on 13-Feb-26. Prior to Site Activation and prior to V1. | 2026-03-02 | 2026-03-04 | 2026-03-04 20:38 | GCP_Minor_Mar-2026_C4591081: Informed Consent Process_Myers, Heather_USA |  | NO |  |  | No |  |  | 2026-03-04 |  | Informed Consent | Inadequate consent process at the investigator site |  |  | CT05-Informed Consent Document | Cathryn Lloyd |  | On 03-Mar-2026 the site was retrained on the correct flow of study related procedures. They were informed that all activities (including VCT consent) for screening and enrollment need to be performed on the same day (V1). |  |  | NA | Human Performance | Decision Error |  | MODEL 1 - INSOURCED | Vaccines
QE-232126 | C4591081 | N | QE-232126 | 1207 | Heather Myers (C4591081-1207) | N | Minor | Closed | Subject 12071003 signed the VCT consent (13-Jan-2026) prior to site activation (16-Feb-26) and prior to the Day 1 (V1 visit). | 2026-03-02 | 2026-03-06 | 2026-03-06 16:31 | GCP_Minor_Mar-2026_C4591081: Informed Consent Process_Myers, Heather_USA |  | NO |  |  | No |  |  | 2026-03-06 |  | Informed Consent | Inadequate consent process at the investigator site |  |  | CT05-Informed Consent Document | Cathryn Lloyd |  | The PI, Site Team, cSOM, GSM and SCP were notified. PD was documented in the source document and ISF. The site was informed of the appropriate timing for administration of the VCT consent. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-232131 | C4591081 | N | QE-232131 | 1207 | Heather Myers (C4591081-1207) | N | Minor | Closed | Subject 12071004 consented with the VCT consent on 31-Dec-2025, prior to GRAF approval, Day 1 (V1) visit, and Site activation. The VCT consent was IRB approved on 11-Nov-2025. | 2026-03-02 | 2026-03-06 | 2026-03-06 17:43 | GCP_Minor_Mar-2026_C4591081: Informed Consent Process_Myers, Heather_USA |  | NO |  |  | No |  |  | 2026-03-06 |  | Informed Consent | Inadequate consent process at the investigator site |  |  | CT05-Informed Consent Document | Cathryn Lloyd |  | 02-Mar-26 The PI and Site staff were notified, and they were informed on the appropriate timing of obtaining VCT consent. PD was documented in source documents and ISF.The VCT consent could not be logged into Veeva for the Subject ICF tracker because the date signed was prior to GRAF approval. The PI, Site Team, cSOM, GSM and SCP were notified. PD was documented in the CTMS. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-232132 | C4591081 | N | QE-232132 | 1207 | Heather Myers (C4591081-1207) | N | Minor | Closed | Subject 12071009 signed the VCT consent on 06-Jan-2026, prior to the GRAF approval, site activation (14-Feb-16), and prior to the Day 1 (V1) visit. | 2026-03-02 | 2026-03-06 | 2026-03-06 17:21 | GCP_Minor_Mar-2026_C4591081: Verified Clinical Trials (VCT) Consent Process_Myers, Heather_USA |  | NO |  |  | No |  |  | 2026-03-06 |  | Informed Consent | Inadequate consent process at the investigator site |  |  | CT05-Informed Consent Document | Cathryn Lloyd |  | 02-Mar-26 The PI and Site staff were notified, and they were informed on the appropriate timing of obtaining VCT consent. PD was documented in source documents and ISF.The VCT consent could not be logged into Veeva for the Subject ICF tracker because the date signed was prior to GRAF approval. The PI, Site Team, cSOM, GSM and SCP were notified. PD was documented in the CTMS. |  |  | NA | Human Performance | Inconsistency Error |  | MODEL 1 - INSOURCED | Vaccines
QE-232232 | C4591081 | N | QE-232232 | 1151 | Ana Elosegui (C4591081-1151) | N | Minor | Closed | C4591081 1151 had not fully completed the facility move process and enrolled patients (1 screen failure &amp; 1 enrolled) at the new facility. The updated regulatory documents had not been received; Spanish consent had not been GRAF, VCT consents had not been updated with new address, and IIP was not approved. | 2026-03-06 | 2026-03-06 | 2026-03-06 23:01 | GCP_Minor_Mar-2026_C4591081: Study Conduct Location_Elosegui, Ana_USA |  | NO |  |  | No |  |  | 2026-03-06 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Elizabeth Steck |  | 5March26: SCP notified CRA and completed a virtual tour of the site on 5March2026 and instructed the Site Manager that no patients should be seen at the new facility until the blinded CRA confirmed all steps were completed. 6March26 Unblinded Study Manager turned IMPALA off at the site level when the SCP informed the Unblinded Study Manager the site had enrolled patients at a facility that was not completely verified as acceptable. |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Vaccines
QE-232995 | C4591081 | N | QE-232995 | 1088 | Thomas Moriarity (C4591081-1088) | N | Minor | Closed | Nasal swab vial arrived at VRD with PHI (Subject ID) | 2026-03-11 | 2026-03-11 | 2026-03-11 17:26 | GCP_Minor_Mar-2026_C4591081: Participant Confidentiality / Data Privacy_Moriarity, Thomas_USA |  | NO |  |  | No |  |  | 2026-03-11 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Stephanie Gaskin |  | CRA contacted site and retrained site regarding not putting any PHI on swab, only barcode label can be used. 11 MAR 2026 CRA did email the site and call to set up a day and time regarding the incident with the Subject number being written on the vial. In the email, they were instructed to only use the barcode labels on specimen containers. It was requested to consider the email as training and to inform any staff processing specimens of the process and to file a copy of the email in their Regulatory documents as evidence of re-training. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-233522 | C4591081 | (Empty) | QE-233522 |  | PFIZER | N | Minor | Closed | During a routine review of system access for Study C4591081, it was identified that user Reagan Deal (User ID: dealr_8879) had active access assigned in Impala to Site 1001 despite not being affiliated with this site. The user is not listed in the site records in Veeva, and the site confirmed the individual has never been part of Site 1001. No access request for this assignment was found in Simplify. The issue has been escalated to the provisioning team for investigation and documented through this Quality Event. | 2026-03-13 | 2026-03-13 | 2026-03-13 20:19 | GCP_Minor_Mar-2026_C4591081: System Access Control_Pfizer_USA |  | NO |  |  | No | Minor/Unrated Quality Event |  | 2026-03-13 |  | Quality Oversight | Quality Management System issue |  |  | CP403 | Armando Delanoy |  | -Issue reported to the Pfizer Provisioning team for investigation. -Verification performed confirming the user is not part of site 1001. -Quality event opened to document and track the issue. -Access status is being reviewed to ensure any incorrect access is removed if still active. |  |  | N/A | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-233544 | C4591081 | (Empty) | QE-233544 |  | PFIZER | N | Minor | Closed | A New Account Access request was submitted by Allison Shields on behalf of Dimitry Divevich to provision access to Impala 2.0. During processing, access was inadvertently granted to Site 1082 instead of the requested Site 1104. The discrepancy was identified after the end user contacted the service desk, following which the correct access was provisioned. | 2026-03-10 | 2026-03-13 | 2026-03-13 20:32 | GCP_Minor_Mar-2026_C4591081: System Access Control_Pfizer_USA |  | NO |  |  | No | Minor/Unrated Quality Event |  | 2026-03-13 |  | Quality Oversight | Quality Management System issue |  |  | CP403 | Steven Levis |  | Reshma received a call from SCP Yemissi Sanni on behalf of the end user, reporting the incorrect site assignment.The issue was reviewed, and access was corrected during the call. The user was successfully granted access to Site 1104. |  |  | N/A | Human Performance | Decision Error |  | MODEL 1 - INSOURCED | Vaccines
QE-233573 | C4591081 | N | QE-233573 | 1098 | Saad Alvi (C4591081-1098) | N | Minor | Closed | It has been identified that Subject 10981106 at Site 1098 has had identifying information incorrectly entered into the Prior COVID Vaccine field within the eCRF. This entry violates data confidentiality guidelines and may lead to a potential breach in subject anonymity, which is a critical requirement as per Good Clinical Practice (GCP) and the study protocol. | 2026-03-13 | 2026-03-13 | 2026-03-13 20:38 | GCP_Minor_Mar-2026_C4591081: Participant Confidentiality / Data Privacy_Alvi, Saad_USA |  | NO |  |  | No |  |  | 2026-03-13 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Mahmoud Algharabli |  | Review and Correction:Site 1098 must immediately correct the entry in the Prior COVID Vaccine field for Subject 10981106, ensuring that only relevant vaccine information is entered and no identifying information remains.Update the record to remove any personal identifying information and retain only the vaccine details as per the study protocol.Subject Record Review:Site staff must review other subject records to ensure there are no similar issues regarding the entry of identifying information in incorrect fields. A detailed audit of records should be conducted to verify compliance with privacy and data protection guidelines. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-233620 | C4591081 | N | QE-233620 | 1016, 1027, 1043, 1047, 1074, 1139 | Barton Williams (C4591081-1043), Faisal Amin (C4591081-1074), Jason Haffizulla (C4591081-1027), Jerry Punch (C4591081-1139), Robert Springer (C4591081-1016), Scott Striplin (C4591081-1047) | N | Minor | Closed | As per lab manual, sites are not to enter subject IDs on the vials. On several occasions sites entered subject ID on the tubes as part of their process to ensure the tubes are traced to appropriate participant and did not remove the subject ID prior to shipping to VRD. As this is not as per lab manual, this QE is being generated. CRAs are continuously working with sites to ensure this doesn't happen in the future. List of sites involved with sample information available to the QE author:Site 1016. AWB 620X38937528, sample CFJ905, written Subject ID on the vial;Site 1139, nasal swab sample CFMK95; written subject ID on the vial;Site 1047, samples CJ4T0F and CJ4SZ4, written last four digits of Subject ID on the vialSite 1027, shipment 620X38937606, samples samples CFLP6C, CFLP6B, CFLP61, CFLP64 and CFLP6D; subject ID written on vialSite 1043, AWB 620X38555734, Subject ID on samples CFJ28V, CFJ28Y, and CFJ29Site 1074 AWB 620X38849697 Subject ID on the vial | 2026-02-26 | 2026-03-14 | 2026-03-16 17:10 | GCP_Minor_Mar-2026_C4591081: Biospecimen Sample Management_Multiple Sites_USA |  | NO |  |  | No |  |  | 2026-03-16 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens | Irina Mosesova |  | Site notified, CRA retrains the sites and confirms site's understanding of the process. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-233827 | C4591081 | (Empty) | QE-233827 |  | PFIZER | N | Minor | Closed | During a cross-check of Impala users for Study C4591081, it was identified that user diazy_3410 had access associated with an incorrect site. The user had active access to Site 1166, while the correct site was Site 1017. A review confirmed that no access request was documented in Simplify for the incorrect site assignment. The provisioning team confirmed that the access to Site 1166 was identified without a supporting request and has since been removed. A valid request has now been submitted to provision the correct access for site 1017. | 2026-03-16 | 2026-03-16 | 2026-03-17 18:06 | GCP_Minor_Mar-2026_C4591081: System Access Controls: Impala_Pfizer_USA |  | NO |  |  | No |  |  | 2026-03-17 |  | IT Systems | Inadequate system access or account management |  |  | CP403 | Armando Delanoy |  | -Incorrect Impala access to Site 1166 was revoked by the provisioning team. -Access review performed following the Impala cross-check. -A valid access request has been submitted for site 1017. -Quality Event opened to document the issue. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-233853 | C4591081 | (Empty) | QE-233853 |  | PFIZER | N | Minor | Closed | C4591081 - Site 1081: Site user requested access to Impala for incorrect site number - Impala access was granted for a site user who does not work at the site. User ID: marshalll_7048. Site user works at site 1088 and accidentally made the request for 1081. SCP requested access be revoked 16Mar2026 | 2026-03-16 | 2026-03-16 | 2026-03-17 20:45 | GCP_Minor_Mar-2026_C4591081: System Access Controls: Impala_Pfizer_USA |  | NO |  |  | No |  |  | 2026-03-17 |  | IT Systems | Inadequate system access or account management |  |  | CP403 | Kelsey Babinski |  | SCP requested access be revoked 16Mar2026 |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-233872 | C4591081 | N | QE-233872 | 1025 | Orlando Puente (C4591081-1025) | N | Minor | Closed | There was an issue identified with Final-Spanish Consent Form [S1-0] (English Approved 12-02-2025) [IRB approved at Site Level 11-Dec-2025]. This issue was noted in US for Final-Spanish Consent Form [S1-0] (English Approved 12-02-2025), Approved by WCG IRB.Checkmarks on Table 1 - Overview of Study Assessments and Tests (pg. 7, 8) and Table 2 - Potential COVID-19 Illness Visit Procedures (pg. 12) were not visible on printed copies of ICFs. | 2026-01-31 | 2026-03-16 | 2026-03-17 18:40 | GCP_Minor_Mar-2026_C4591081: Informed Consent Document_WCG IRB;Puente, Orlando_USA |  | NO |  |  | No |  |  | 2026-03-17 |  | Informed Consent | Inadequate consent document content |  |  | CT05-Informed Consent Document | Hillary Minch |  | Site was provided instructions/guidance on how to print Final-Spanish Consent Form [S1-0] (English Approved 12-02-2025), to ensure hidden text was visible:Ensure formatting displays hidden text:Select File &gt; Options &gt; DisplaySelect Hidden TextWhen printing:Select Page Setup &gt; Print OptionsSelect DisplaySelect Hidden Text Site completed above actions and confirmed checkmarks were visible on print out. Site was requested to notify IRB. Site was requested to reconsent all affected subjects at their next visit. To date (16-Mar-2026), Site confirmed one subject was reconsented on corrected Final-Spanish Consent Form [S1-0] (English Approved 12-02-2025).Upon review of Informed Consent Tracking log, a total of 121 Subjects were identified as completing the Final-Spanish Consent Form [S1-0] (English Approved 12-02-2025). Site Monitor will complete review of affected subjects and complete investigation, and record Protocol Deviations as appropriate. |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Vaccines
QE-233872 | C4591081 | (Empty) | QE-233872 |  | WCG IRB | N | Minor | Closed | There was an issue identified with Final-Spanish Consent Form [S1-0] (English Approved 12-02-2025) [IRB approved at Site Level 11-Dec-2025]. This issue was noted in US for Final-Spanish Consent Form [S1-0] (English Approved 12-02-2025), Approved by WCG IRB.Checkmarks on Table 1 - Overview of Study Assessments and Tests (pg. 7, 8) and Table 2 - Potential COVID-19 Illness Visit Procedures (pg. 12) were not visible on printed copies of ICFs. | 2026-01-31 | 2026-03-16 | 2026-03-17 18:40 | GCP_Minor_Mar-2026_C4591081: Informed Consent Document_WCG IRB;Puente, Orlando_USA |  | NO |  |  | No |  |  | 2026-03-17 |  | Informed Consent | Inadequate consent document content |  |  | CT05-Informed Consent Document | Hillary Minch |  | Site was provided instructions/guidance on how to print Final-Spanish Consent Form [S1-0] (English Approved 12-02-2025), to ensure hidden text was visible:Ensure formatting displays hidden text:Select File &gt; Options &gt; DisplaySelect Hidden TextWhen printing:Select Page Setup &gt; Print OptionsSelect DisplaySelect Hidden Text Site completed above actions and confirmed checkmarks were visible on print out. Site was requested to notify IRB. Site was requested to reconsent all affected subjects at their next visit. To date (16-Mar-2026), Site confirmed one subject was reconsented on corrected Final-Spanish Consent Form [S1-0] (English Approved 12-02-2025).Upon review of Informed Consent Tracking log, a total of 121 Subjects were identified as completing the Final-Spanish Consent Form [S1-0] (English Approved 12-02-2025). Site Monitor will complete review of affected subjects and complete investigation, and record Protocol Deviations as appropriate. |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Vaccines
QE-234381 | C4591081 | (Empty) | QE-234381 |  | HCL TECHNOLOGIES, PFIZER | N | Major | In Investigation | Incorrect Access Provisioning: The HCL agent inadvertently granted access to Study C4591081 – Site 1010 instead of the requested Site 1071. Incorrect access was identified and corrected. | 2026-03-12 | 2026-03-18 | 2026-03-19 21:06 | GCP_Major_Mar-2026_C4591081: Trend: System Access Controls: Impala_Pfizer; HCL Technologies_Global |  | NO | [7 empty] | IT Systems | Inadequate system access or account management |  |  | CP403 | Nadine Bailey |  | Incorrect access was identified and corrected.Access was granted to the appropriate Study C4591081 – Site 1071 as per the original request.Feedback was shared with the responsible agent, and the non‑conformance has been logged. | [6 empty] | MODEL 1 - INSOURCED | Vaccines