## Standard_Quality_Dashboard - SQ
Case ID | Case Status | Observation ID | Obs Status | Submission Date | Issue Audit Report (Actual) | Center Number | principal investigator | Country | Description | Study ID | Protocol ID | Title Short Description | Drug Program Code | Rating | Event Type | Case CAPA Approved Due Date | Case CAPA Approved On | CAPA Plan In Place Timely | Obs CAPA Approved Due Date | Obs CAPA Approved On | Obs Target Completion Date | Obs Actual Completion Date | Case CAPA Closure Timely | Case Target Completion Date | Case Actual Completion Date | Obs CAPA Closure Timely | Selected Business Process | Taxonomy Level 1 | Taxonomy Level 2 | Study Status | Business Category | Study Phase | Study Priority | Asset | Dev China | Dev Japan | Rapid Model | Business Category
AIA-009677 | Pending Finding Closure | QE-227670 | Issued | (Empty) | 2026-02-18 | 1025 | (Empty) | UNITED STATES | For 2 of 12 participant records reviewed, discrepancies between the source data and the electronic Case Report Forms (eCRFs) were identified [Pfizer C4591081 CRF Completion Requirements (Version 2: 30 Dec 2025)]. 1. For Participant 10251001 the protocol version date was reported as 25 Sep 2025 in the eCRF; however, the site's Informed Consent Form Process &amp; Review worksheet had 11 Nov 2025 recorded.&nbsp; Note: Protocol Amendment 1 had not yet been approved by the Institutional Review Board, and the participant had consented under the C4591081 Protocol dated 25 Sep 2025. &nbsp; 2. For Participant 10251001 the derived date of birth (DOB) in the eCRF had the year 1970; however, the site's Demographics worksheet had the year of birth recorded as 2025. 3. Participant 10251116 was consented under the C4591081 Protocol dated 25 Sep 2025; however, 21 Nov 2025, the date of C4591081 Protocol Amendment 1, had been entered in the eCRF. | C4591081 | C4591081 | An Investigator Site Audit of Study C4591081, Site 1025, Dr. Orlando Puente, Miami, FL, USA | (Empty) | Minor | AUDIT | 2026-04-01 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | DMB07 - CRF and Database Design | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009677 | Pending Finding Closure | QE-227672 | Issued | (Empty) | 2026-02-18 | 1025 | (Empty) | UNITED STATES | For 12 of 12 participant records reviewed, source data (paper and/or electronic) did not consistently meet ALCOACCEA (Attributable, Legible, Contemporaneous, Original, Accurate, Complete, Consistent, Enduring, and Available) criteria [ICH E6(R3) 2.12.2. 9.4]. 1.&nbsp;For Participant 10251001 Racial Designation on the site Demographics worksheet was left blank (e.g. the 'N/A' checkbox was not checked). 2. The Informed Consent Document for Participant 10251091 was misfiled in VEEVA SiteVault under Participant 10251099. 3. For Participants 10251099, 10251104 &amp; 10251134, exclusion criteria #7 regarding individuals who are pregnant or breastfeeding was marked No; however, the participants were male and Not Applicable (NA) was available to select. 4. For Participant 10251110 the following were missing from the Subject Binder and Veeva SiteVault: Body Mass Index (BMI) calculation printout; copies of the C4591081 Covid-19 Illness Memory Aid,&nbsp; C4591081 Covid 19 Vaccine Participant Card and Study Site contact numbers/Information card as evidence of how the calculation was performed and that the cards were provided to the participant. Note: The National Institute of Health website BMI calculator was used; however, the printout did not have this information. It was suggested the site document the calculator used for all study participants for clarity. 5. For Participants 10251110, 10251134 the Authorization for Release of Patient Information was incomplete. The participants had signed the bottom of the form but none of the checkboxes at the top of the form were checked and these checkboxes defined what was authorized for release (e.g. the disclosure of all protected information for the review and evaluation in connection with a legal claim; all physician, occupation and rehabilitation requests or all pharmacy prescription records, etc.). 6. The Visit 1 Medical History form was not consistently completed and endorsed by the Investigator as required. This form was divided into sections (endocrine/metabolic, social history, etc.) and if an entry (relevant condition) was present, the Investigator would sign/initial in the appropriate column; however, for Participant 10251035, the entry Hyperthyroidism was not initialed or dated. Also, for 11 of 12 participants in the audit sample, social history entries for smoking, alcohol and drug use (e.g. never smoked, etc.) were not signed/initialed by the investigator. The 11 Participants were 10251001, 10251017, 10251035, 10251036, 10251040, 10251056, 10251067, 10251091, 10251099, 10251104, 10251110. 7. The site Vitals worksheet at Visit 1 listed temperature but no unit was present. Note: The worksheet also included height and weight which had associated units of centimeters (cm) and kilograms (kg) listed.&nbsp; 8. The site worksheet titled Visit 1 (Screening) version 01 Dec 2025 did not have a date field on page 1 of 23 where site staff were attesting to various screening procedures having been completed. Note: The remaining pages had signatures and dates per section (e.g. inclusion/exclusion, medical history, etc.) 9. The site worksheet titled Visit 2 (1 week) version 05 Nov 2025 did not have a date field on page 1 of 8 where site staff were attesting to various visit procedures having been completed. Note: The remaining pages had signatures and dates per section (e.g. Clinical assessment, Review of eDiary, etc.). 10. The site worksheet titled Visit 3 (1 Month Follow-Up) version 28 Oct 2025 did not have a date field on page 1 of 8 where site staff were attesting to various visit procedures having been completed. Note: The remaining pages had signatures and dates per section (e.g. Clinical assessment, Review of eDiary, etc.). | C4591081 | C4591081 | An Investigator Site Audit of Study C4591081, Site 1025, Dr. Orlando Puente, Miami, FL, USA | (Empty) | Major | AUDIT | 2026-04-01 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | NOT APPLICABLE; NOT APPLICABLE | Data Collection and Management | Inadequate source data/documentation | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009677 | Pending Finding Closure | QE-227673 | In Response | (Empty) | 2026-02-18 | 1025 | (Empty) | UNITED STATES | Eight documents in the Pfizer Trial Master File (PTMF) were missing [Pfizer SOP CT01-GSOP Trial Master Files (Version 8.0: 03 Oct 2022); ICH GCP E6 (R3) Section 2.12.2; 2.12.5]. 1. Site Informed Consent Document (Main) dated 16 Oct 2025, IRB approved 02Dec2025, Translation IRB approved 11 Dec 2025. 2. Site Informed Consent Document (Optional Procedure) dated 16 Oct 2025, IRB approved 02Dec2025, Translation IRB approved 11 Dec 2025. 3. Case Report Form (CRF) Completion Requirements Version 2, dated 30 Dec 2025 4. C4591081 Study Laboratory Manual versions: 1.2 dated 07 Dec 2025; 1.3 dated 16 Dec 2025; 1.5 dated 07 Jan 2026 5. Verified Clinical Trials (VCT) Research Subject Database Personal Information Authorization, Pfizer Template Version 01 dated 28 Jun 2024, IRB Approved at the Protocol Level 11 Nov 2025 Note: The Spanish language version was filed. 6. Exposure During Pregnancy (EDP) Partner Form | C4591081 | C4591081 | An Investigator Site Audit of Study C4591081, Site 1025, Dr. Orlando Puente, Miami, FL, USA | (Empty) | Minor | AUDIT | 2026-04-01 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT01 - Trial Master Files | Document Management | Missing document | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009677 | Pending Finding Closure | QE-227674 | In Response | (Empty) | 2026-02-18 | 1025 | (Empty) | UNITED STATES | Monitoring activities were inadequate with regards to issue detection and/or documentation [Pfizer C4591081 Study Monitoring Plan (Version 1.1: 05 Dec 2025)]. 1. Per the Site Monitoring Plan, the first participant randomized at the site had to be Source Data Verified (SDV); however, Participant 10251001 was not included in the SDV sample, and this was not escalated as an issue. 2. The Informed Consent Document (ICD) Log had the following deficiencies: a. For the Spanish language ICDs the date of 'IRB/IEC Approval' was listed as 12 Dec 2025; however, the correct date was 11 Dec 2025. b. Participant 10251091 was not listed on the Informed Consent Tracking log. c. Participant 10251101 was listed as ICD verified on 05 Jan 2026; however, this was the only participant verified on this date and there was no corresponding Monitoring Visit on that date.&nbsp; 3. The Subject Code List was not provided to the site. 4. Qualification and training records did not demonstrate that 2 of 20 site staff were adequately trained to complete their delegated duties (audit finding QE-227679). 5. For 2 of 12 participant records reviewed, discrepancies between the source data and the electronic Case Report Forms were identified (audit finding QE-227670). 6. For 12 of 12 participant records reviewed source data (paper and/or electronic) did not consistently meet ALCOACCEA (Attributable, Legible, Contemporaneous, Original, Accurate, Complete, Consistent, Enduring, and Available) criteria (audit finding QE-227672). 7. Eight documents in the Pfizer Trial Master File were missing (audit finding QE-227673). 8. Eight essential documents in the Investigator Site File were inaccurate, incomplete or missing (audit finding QE-227676). 9. For 5 of 20 site staff, electronic system accounts were not adequately managed (audit finding QE-227678). | C4591081 | C4591081 | An Investigator Site Audit of Study C4591081, Site 1025, Dr. Orlando Puente, Miami, FL, USA | (Empty) | Major | AUDIT | 2026-04-01 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV04 - Investigational Site Management and Monitoring | Site Management and Monitoring | Failure to detect/document | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009677 | Pending Finding Closure | QE-227676 | Issued | (Empty) | 2026-02-18 | 1025 | (Empty) | UNITED STATES | Eight essential documents in the Investigator Site File (ISF) were inaccurate, incomplete or missing [ICH E6 (R3) C.2.5 and C.2.6]. Inaccurate documents: 1. The site Spanish language Main Informed Consent Form approved by the Institutional Review Board on 11 Dec 2025 was incomplete; Table 1 and Table 2 were missing the check marks depicting the activities to be performed at each visit for the participant.&nbsp; 2. The Source Document Locator (SDL) had source 'Location' listed as both ISF (paper) and Veeva eISF eBinder; however, the site original documents were paper which were later scanned and uploaded into Veeva SiteVault for sponsor remote access. Note: The SDL method of sponsor access was listed as Veeva eISF Binder. Incomplete document: 3. The Screening and Enrollment Log was missing Participant 10251004. Missing documents: 4. Site selection letter dated 07 Oct 2025. 5. Site Initiation Visit Follow Up Letter dated 11 Dec 2025 5. The Subject Code List was not available. Note: The site's Clinical Trial Management System contained the required information. &nbsp; 7. The current Mayo Clinic Hazardous Goods Transportation Training Certificate for the blinded coordinator on row 12 of the Signature Sheet and Delegation of Duties Log. 8. Exposure During Pregnancy (EDP) Partner Form | C4591081 | C4591081 | An Investigator Site Audit of Study C4591081, Site 1025, Dr. Orlando Puente, Miami, FL, USA | (Empty) | Minor | AUDIT | 2026-04-01 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | NOT APPLICABLE; NOT APPLICABLE | Document Management | Missing document | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009677 | Pending Finding Closure | QE-227678 | Issued | (Empty) | 2026-02-18 | 1025 | (Empty) | UNITED STATES | For 5 of 20 site staff, electronic system accounts were not adequately managed [ICH E6 (R3) 4.3.8 (b)]. 1. The blinded Sub-Investigator (SI) on row 11 of the Signature Sheet and Delegation of Duties Log (SSDDL) was trained in RedCap Cloud (RCC), the clinical trial database, and was delegated to sign eCRFs; however, this SI did not have access to RCC at the time of the audit. 2. The blinded SI on row 16 of the SSDDL was trained in RedCap Cloud and had access; however, this SI had not been delegated either data entry or eCRF signature duties. 3. The blinded SIs on rows 15 and 20 of the SSDDL were delegated to eDiary oversight and review in TrialMax; however, neither had access to TrialMax at the time of the audit. 4. A Coordinator who had completed training in Firecrest but wasn't listed in the SSDDL remained active in Firecrest at the time of the audit. Note: Site staff confirmed this individual had not joined the study,&nbsp; | C4591081 | C4591081 | An Investigator Site Audit of Study C4591081, Site 1025, Dr. Orlando Puente, Miami, FL, USA | (Empty) | Minor | AUDIT | 2026-04-01 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CP406 - Electronic Identity & Access Management | IT Systems | Inadequate system access or account management | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009677 | Pending Finding Closure | QE-227679 | Issued | (Empty) | 2026-02-18 | 1025 | (Empty) | UNITED STATES | Qualification and training records did not demonstrate that 2 of 20 site staff were adequately trained to complete their delegated duties [ICH E6 (R3) 2.1.1, 2.1.2, 2.3.2]. 1. The Blinded Coordinator on row 3 of the Signature Sheet and Delegation of Duties Log (SSDDL), was assigned to (1) recruit subjects, (2) conduct informed consent, conduct/review (4a) medical history, (4c) concomitant medications, (4d) vital signs and (4e) electrocardiograms (ECGs), (18) observe participants for 30 minutes post dose and (20c) eDiary data oversight and follow up on severe reactions; however, the Curriculum Vitae (CV) on file did not include any medical training and prior clinical trial experience was administrative. Also, High School attendance was listed from 2000-2004; however, the receipt of a diploma was not specified.&nbsp; 2. The Blinded Coordinator on row 13 of the SSDDL, was assigned to (1) recruit subjects (task entered twice) and (20c) eDiary data oversight and follow up on severe reactions; however, the CV on file did not demonstrate any medical training. Prior clinical trial experience was administrative and although a High School diploma was specified, the year it was conferred was missing. Note: The blinded coordinator, on row 17 of the SSDDL, was missing education information in the CV on file, but this did not indicate inadequate training for the assigned duty (1- recruit subjects) as her previous experience supported this task. | C4591081 | C4591081 | An Investigator Site Audit of Study C4591081, Site 1025, Dr. Orlando Puente, Miami, FL, USA | (Empty) | Minor | AUDIT | 2026-04-01 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | QMS07 - Colleague Training | Training & Qualifications | Job description, qualification/education or CV does not meet requirements to perform the assigned job function | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009678 | Pending Finding Closure | QE-228205 | Issued | (Empty) | 2026-02-19 | 1160 | (Empty) | UNITED STATES | For 9 of 15 participant records reviewed, discrepancies between the source data and the electronic Case Report Forms (eCRFs) were identified [Pfizer C4591081 CRF Completion Requirements (Version 2: 30Dec 2025)] 1. A total hysterectomy performed in 2018 was documented in the Surgery or Procedure source worksheet (page 8 of 37); however, this information was not entered in the eCRF at the time of the audit. Furthermore, the indication for the hysterectomy was not specified in the source worksheet for Participant 11601046. 2. Although 'uterine fibroids' with a start date of 2008 and an end date of 2010 were documented in the eCRF, neither uterine fibroids nor these corresponding dates were documented in the source worksheet for Participant 11601060. 3. A hysterectomy performed in 2016 and the indication for the hysterectomy - uterine fibroids were documented in the Surgery or Procedure source worksheet (page 8 of 37); however, this information was not entered in the eCRF at the time of the audit for Participant 11601108. Furthermore, a query response regarding post-menopausal state was inaccurate, the response stated “subject was contacted today and confirmed they have had an FSH drawn in the past. They confirmed their postmenopausal state.”&nbsp; 4. Substance use was documented in source records as ‘never’ for both Tabacco and Alcohol; however, it was documented in the CRF as “Reason Intentionally Blank: Not Applicable” for Participant 11601108. 5. The derived date of birth (DOB) in the eCRF had the year 1970; however, the site's Verified Clinical Trials (VCT) Research Subject Database Personal Information Authorization, had the year of birth recorded as 1969 (Participant 11601172). 6. The COVID19 Vaccine history worksheet (page 12 of 37) had two vaccinations documented for Participant 11601001, 13Jul2023 and 16Sep2024; however, this information was not entered in the eCRF at the time of the audit. 7. The COVID19 Vaccine history worksheet (page 12 of 37) had a dose unit different than the unit entered in the eCRF, as follows:&nbsp; &nbsp;a) Source records for Participant 11601024 had dose unit 0.1 for vaccination dates 14May2021 and 07Jun2021; yet dose unit 0.5 was entered in the eCRF. &nbsp;b)&nbsp; Source records for Participant 11601077 had dose unit 0.5 for vaccination dates 20Apr2021 and 22Nov2021; yet dose unit 0.1 was entered in the eCRF. 8. The study protocol required 3 blood pressure (BP) measurements (3 consecutive BP readings be recorded at intervals of at least 1 minute apart) to be documented in the source records and the average of the 3 BP readings to be recorded on the CRF; however, site was entering all 3 consecutive BP readings, instead of the average of the 3 BP readings (e.g., Participants 11601051, 11601099, 11601172) | C4591081 | C4591081 | Investigator Site Audit of Study C4591081, Site 1160, Dr. Frank Alvarez, Hialeah, Florida, USA | (Empty) | Minor | AUDIT | 2026-04-02 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | DMB07 - CRF and Database Design | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009678 | Pending Finding Closure | QE-228208 | Issued | (Empty) | 2026-02-19 | 1160 | (Empty) | UNITED STATES | For 4 of 15 participant records reviewed, source data were not consistently available, accurate, contemporaneous, attributable or complete [C4591081 Protocol Amendment 1, 21 Nov 2025, ICH E6 (R3) 2.12.2]. 1. Medical History ‘Total Hysterectomy’ was documented in the source worksheet, but the corresponding medical history indication was left blank (Participants 11601046, 11601060). &nbsp; 3. A question in the “Potential COVID-19 Illness visit” source worksheet (page 6 of 17) related to the reactogenicity eDiary was answered yes; however, site 1160 did not participate in the reactogenicity study subset (Participants 11601051, 11601172).&nbsp; 4. Protocol-specified Adverse Events of Special Interests (AESIs), such as post menstrual disturbances, were to be collected from the time the participant provides informed consent through end of study completion (protocol section 8.4.1); however, the site's worksheet for Visit 1 did not include a section for capturing this information. Notably, the Visit 3 source worksheets did contain a dedicated section for documenting any post-menstrual disturbances.&nbsp; 5. Source records for study participants enrolled after 18Dec2025 – the date the PI acknowledged Protocol Amendment 1, dated 21 Nov 2025 - included a copy of the Schedule of Activities (SoA) from the original version of the Protocol, dated 25 Sep 2025. Furthermore, the source worksheet used to document the Informed Consent process (page 2 of 2) and the Randomization/Eligibility source worksheet (page 27 of 37) referenced the original protocol version dated 25Sep2025 instead of the protocol amendment version dated 21Nov2025. | C4591081 | C4591081 | Investigator Site Audit of Study C4591081, Site 1160, Dr. Frank Alvarez, Hialeah, Florida, USA | (Empty) | Minor | AUDIT | 2026-04-02 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | NOT APPLICABLE; NOT APPLICABLE | Data Collection and Management | Inadequate source data/documentation | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009678 | Pending Finding Closure | QE-228212 | Issued | (Empty) | 2026-02-19 | 1160 | (Empty) | UNITED STATES | Documentation related to Investigational Product (IP) accountability, destruction, and storage was inadequate [Pfizer C4591081 Investigational Product Manual (Version 1.0: 05 Nov 2025)]. 1. There was no available documentation regarding the destruction of the Investigational Product (IP). The unblinded Pharmacist Technician stated that one box had been sent out for destruction in January; however, records confirming that the site was authorized to destroy IP onsite could not be located. According to the IP Manual (page 26), if product must be sent out for destruction, the unblinded pharmacist or technician is required to contact the Sponsor's unblinded primary point of contact, and no product should be sent for destruction without prior authorization from that contact. At the time of the audit, neither communication nor authorization from the unblinded primary point of contact was available for review. 2. The preparation records did not have the IP carton tear-off label attached, as instructed in the IP Manual, to support reconciliation/accountability activities (IP Manual, section 9, page 26 of 49). 3. Based on correspondence reviewed by the Auditor during the pharmacy visit, it was noted that, on January 23, 2026, the pharmacy technician at site 1160 informed Almac of a temperature excursion involving an IP shipment (quantity: 89) that had been inadvertently delivered to the incorrect site. As a result, temperature conditions for the period of January 16 to January 21, 2026, could not be verified. On January 26, 2026, the Almac Temperature Services Coordinator acknowledged receipt of the report and provided details regarding the forms submitted concerning the incident. The quarantined IP was stored in a box alongside other study IP; however, the box was neither labeled as ‘Quarantine IP’ nor otherwise marked to indicate that the product should not be used or dispensed. | C4591081 | C4591081 | Investigator Site Audit of Study C4591081, Site 1160, Dr. Frank Alvarez, Hialeah, Florida, USA | (Empty) | Major | AUDIT | 2026-04-02 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT13-GSOP - Investigational Product | Medicinal Product | Inadequate packaging, label, drug instructions | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009678 | Pending Finding Closure | QE-228213 | Issued | (Empty) | 2026-02-19 | 1160 | (Empty) | UNITED STATES | Electronic system user access was not adequately managed [ICH E6 (R3) 2.12.10(b)]. Discrepancies were identified between site personnel status and user access across study systems. Specifically, a Sub‑Investigator (SI) who departed the site on 05 Jan 2026 remained active in multiple electronic systems at the time of the audit (28 Jan 2026): 1. &nbsp; &nbsp;The SI was listed as inactive in Veeva Vault, however retained active Break‑Blind access in the Interactive Response Technology (IRT). 2. &nbsp; &nbsp;The same SI also maintained active user access to other study systems, including Trial Manager and REDCap Cloud (RCC), after departing the site. | C4591081 | C4591081 | Investigator Site Audit of Study C4591081, Site 1160, Dr. Frank Alvarez, Hialeah, Florida, USA | (Empty) | Minor | AUDIT | 2026-04-02 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CP406 - Electronic Identity & Access Management | IT Systems | Inadequate system access or account management | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009678 | Pending Finding Closure | QE-228215 | Issued | (Empty) | 2026-02-19 | 1160 | (Empty) | UNITED STATES | Monitoring activities were inadequate with regards to issue detection and/or documentation [Pfizer C4591081 Study Monitoring Plan (Version 1.1: 05 Dec 2025)]. 1. Monitoring oversight activities were insufficient to ensure that the study was appropriately executed. At the time of the audit, monitoring consisted of three (3) remote reviews, despite the high enrollment at the site (240 screened/218 entered) and being the only Pfizer study under the Principal Investigator. The site did not receive onsite visits from the assigned blinded/unblinded Monitors or Site Care Partners (FSFV occurred on 11Dec2025). Additionally, key documents were missing from the Trial Master File, including the Feasibility Questionnaire, Site Initiation Visit confirmation letter, and the Site Qualification Form, indicating that these activities were either not conducted or not properly documented (Audit finding QE-229107).&nbsp; 2. At the time of the audit, unblinded monitoring consisted of one (1) remote review conducted on 05-06 January 2026 (1.5 days). At this time, there were 140 participants enrolled/vaccinated. The unblinded monitoring report indicated (check box marked: yes) that site had returned and/or destroyed IP according to instructions and documented appropriately; however, documentation for IP destroyed off-site was not available. Additionally, comments related to the Pharmacy and the IP, such as the review of the Investigator Product Accountability Logs (IPALs) were not recorded in the report. As stated in the SMP, “Unblinded CRA was to review IPAL and dose preparation records for completion of what was dispensed, and what needs to be returned/destroyed.” IPALs were in paper format and filed at the Pharmacy. 3. The Screening and Enrollment Log documented a nine-digit Subject ID for participants listed on pages 23 and 24, rather than the required eight-digit Subject ID. Specifically, an extra digit "1" was inserted between the four-digit site number and the four-digit Participant ID. For example, participants were identified as 116011223–116011240.&nbsp; 4. The Monitoring Visit report for the virtual review conducted on January 15-16, 2026, noted that the ‘CRA retrained site staff to ensure Marken Airway Bill is scanned rather than the sample box barcode”. However, this training was not recorded in the training log, even though the report stated that training was provided at the site. Furthermore, at the time of the audit, when the sample management process was reviewed with the laboratory technician, it was observed that both the airway bill and the sample box barcode needed to be scanned. 5. The blinded Study Coordinator added to the Signature Sheet and Delegations of Duties Log on 16Jan2026 was listed in Veeva; yet she was not listed in Sponsor Operational Data Review (ODR) Site View report.&nbsp; 6. Lack of protocol adherence by the Principal Investigator and site staff was not identified (Audit finding QE-229065) 7. Discrepancies between the source data and the electronic Case Report Forms (eCRFs) were not identified (Audit finding QE-228205). 8. Participant records reviewed (paper and/or electronic source data) did not consistently meet Attributable, Contemporaneous, Accurate, Complete, Consistent, and Available criteria (Audit finding QE-228208). 9. Electronic system accounts were not adequately managed (Audit finding QE-228213). 10. Documentation related to Investigational Product (IP) accountability, destruction, and storage was inadequate (Audit finding QE-228212). 10. Temperature logs were not maintained as required by the Laboratory Manual (Audit finding QE-229114) | C4591081 | C4591081 | Investigator Site Audit of Study C4591081, Site 1160, Dr. Frank Alvarez, Hialeah, Florida, USA | (Empty) | Major | AUDIT | 2026-04-02 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV04 - Investigational Site Management and Monitoring | Site Management and Monitoring | Failure to detect/document | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009678 | Pending Finding Closure | QE-229065 | Issued | (Empty) | 2026-02-19 | 1160 | (Empty) | UNITED STATES | The Principal Investigator (PI) and site staff did not consistently adhere to the protocol requirements regarding Medical History. The following deficiencies were noted (C4591081 Protocol Amendment 1, 21 Nov 2025) 1. Medical history data was incomplete, follicle-stimulating hormone (FSH) records were not available in the source records for post-menopausal individuals. According to protocol section 10.4.3., “FSH level of postmenopausal range must also be used to confirm a postmenopausal state in individuals under 60 years old…”. At the time of the audit 8 of 11 women in the audit sample were under 60 years old and for 4 out of the 8 FSH records were not available/reviewed prior study vaccination. The same situation applied for all women in the study who were under 60 years old and who did not have surgical intervention and FSH records were not available. Additionally, queries sent to the site stated, “PD needs to be recorded for all those if subject is under 60yr Female where FSH levels were not reviewed before vax and no hysterectomy etc. history is present and still marked as women of not child bearing potential”, at the time of the audit protocol deviations (PDs) were not submitted as instructed by the study team (e.g., Participants 11601001, 11601099, 11601110, 11601172). The PI and site staff were proactively retrieving FSH records from LabCorp for all the female participants under 60 years old who did not have any medical history (e.g., permanent sterilization methods) documented in their source records. 2. Protocol-specified Adverse Events of Special Interests (AESIs), such as post menstrual disturbances, were to be collected from the time the participant provides informed consent through end of study completion (protocol section 8.4.1); however, source data was not present for Visit 1 for the participants selected in the audit sample. Note: Visit 3 source worksheets had a section to collect data related to post-menstrual disturbances. | C4591081 | C4591081 | Investigator Site Audit of Study C4591081, Site 1160, Dr. Frank Alvarez, Hialeah, Florida, USA | (Empty) | Major | AUDIT | 2026-04-02 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT40 - Protocol Deviations | Protocol Deviations | Failure to follow protocol | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009678 | Pending Finding Closure | QE-229107 | Issued | (Empty) | 2026-02-19 | 1160 | (Empty) | UNITED STATES | Essential documents related to Monitoring activities were missing in the Trial Master File [Pfizer SOP CT01-GSOP Trial Master Files (Version 8.0: 03 Oct 2022); ICH GCP E6 (R3) Section 2.12.2; 2.12.5]. The following documents were missing from the Trial Master File indicating that these activities were either not conducted or not properly documented. 1. Site Feasibility Documentation (Site Level)&nbsp; 2. Site Initiation Visit Confirmation 3. Site Qualification Form | C4591081 | C4591081 | Investigator Site Audit of Study C4591081, Site 1160, Dr. Frank Alvarez, Hialeah, Florida, USA | (Empty) | Minor | AUDIT | 2026-04-02 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT01 - Trial Master Files | Document Management | Missing document | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
AIA-009678 | Pending Finding Closure | QE-229114 | Issued | (Empty) | 2026-02-19 | 1160 | (Empty) | UNITED STATES | Study-specific temperature logs were not maintained as required by the Sponsor (C4591081 Study Laboratory Manual Version 1.5 Final 07Jan2026). 1. The laboratory manual required continuous monitoring, including the highest/lowest temperature of any non-working periods (e.g., weekends and holidays); however, the laboratory temperature logs reviewed had three readings documented on Monday- one each for Saturday, Sunday and Monday- all recorded with Monday’s date, time and temperature. Additionally, the site’s process for temperature documentation was inconsistently followed by site staff working at the laboratory.&nbsp; Note: The site Director indicated that continuous temperature records could be made available upon request for inspection readiness purposes. 2. The temperature logs did not have study identifiers (e.g., study protocol number, site ID number).&nbsp; 3. Corrections were made in the temperature logs that lacked signatures and dates.&nbsp; | C4591081 | C4591081 | Investigator Site Audit of Study C4591081, Site 1160, Dr. Frank Alvarez, Hialeah, Florida, USA | (Empty) | Minor | AUDIT | 2026-04-02 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | NOT APPLICABLE; NOT APPLICABLE | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-222137 | Closed | QE-222137 | Closed | 2026-01-09 | (Empty) | 1005 | Orlando Puente (C6481001-1005) | UNITED STATES | We became aware of a published article, noting instances of sites (some participating in Pfizer studies) using "fake data".science.org/content/article/alzheimer-s-drug-developers-accuse-clinical-trial-sites-faking-data"Alzheimer’s drug developers accuse clinical trial sites of faking data Science AAAS | C4591081 | C4591081 | GCP_Critical_Jan-2026_Multiple Protocols: Potential Allegation_Leon, Ramon; Puente, Orlando_USA | C459 | Critical | SQE | 2026-02-23 | 2026-02-24 | N | 2026-02-23 | 2026-02-24 | (Empty) | 2026-02-27 | (Empty) | (Empty) | 2026-02-27 | (Empty) | NOT APPLICABLE | Potential allegation of Falsification or misconduct | Potential allegation of Scientific fraud, falsification or misconduct | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-222137 | Closed | QE-222137 | Closed | 2026-01-09 | (Empty) | 1008 | Orlando Puente (C6271001-1008) | UNITED STATES | We became aware of a published article, noting instances of sites (some participating in Pfizer studies) using "fake data".science.org/content/article/alzheimer-s-drug-developers-accuse-clinical-trial-sites-faking-data"Alzheimer’s drug developers accuse clinical trial sites of faking data Science AAAS | C4591081 | C4591081 | GCP_Critical_Jan-2026_Multiple Protocols: Potential Allegation_Leon, Ramon; Puente, Orlando_USA | C459 | Critical | SQE | 2026-02-23 | 2026-02-24 | N | 2026-02-23 | 2026-02-24 | (Empty) | 2026-02-27 | (Empty) | (Empty) | 2026-02-27 | (Empty) | NOT APPLICABLE | Potential allegation of Falsification or misconduct | Potential allegation of Scientific fraud, falsification or misconduct | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-222137 | Closed | QE-222137 | Closed | 2026-01-09 | (Empty) | 1025 | Orlando Puente (C4591081-1025) | UNITED STATES | We became aware of a published article, noting instances of sites (some participating in Pfizer studies) using "fake data".science.org/content/article/alzheimer-s-drug-developers-accuse-clinical-trial-sites-faking-data"Alzheimer’s drug developers accuse clinical trial sites of faking data Science AAAS | C4591081 | C4591081 | GCP_Critical_Jan-2026_Multiple Protocols: Potential Allegation_Leon, Ramon; Puente, Orlando_USA | C459 | Critical | SQE | 2026-02-23 | 2026-02-24 | N | 2026-02-23 | 2026-02-24 | (Empty) | 2026-02-27 | (Empty) | (Empty) | 2026-02-27 | (Empty) | NOT APPLICABLE | Potential allegation of Falsification or misconduct | Potential allegation of Scientific fraud, falsification or misconduct | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-222137 | Closed | QE-222137 | Closed | 2026-01-09 | (Empty) | 1166 | Ramon Leon (C4591081-1166) | UNITED STATES | We became aware of a published article, noting instances of sites (some participating in Pfizer studies) using "fake data".science.org/content/article/alzheimer-s-drug-developers-accuse-clinical-trial-sites-faking-data"Alzheimer’s drug developers accuse clinical trial sites of faking data Science AAAS | C4591081 | C4591081 | GCP_Critical_Jan-2026_Multiple Protocols: Potential Allegation_Leon, Ramon; Puente, Orlando_USA | C459 | Critical | SQE | 2026-02-23 | 2026-02-24 | N | 2026-02-23 | 2026-02-24 | (Empty) | 2026-02-27 | (Empty) | (Empty) | 2026-02-27 | (Empty) | NOT APPLICABLE | Potential allegation of Falsification or misconduct | Potential allegation of Scientific fraud, falsification or misconduct | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-222180 | In Investigation | QE-222180 | In Investigation | 2026-01-09 | (Empty) | (Empty) | NPHASE INC (REDCAP CLOUD) | (Empty) | We are raising this event to please request that the minor assessment for QE-219754 be reconsidered. To again summarize the what occured, a legitimate query was raised in the C4601019 study by our medical monitor. However in RCC this query changed to a different user name and role (LabTech). That different user is a real person at Pfizer, but they never requested access to C4601019 and they are not on our Site User Report. This user does not have access to the C4601019 study in RCC, as confirmed by the RCC Admin team's review of the study's audit logs. Further, the Lab Tech role does NOT have access to issue a query in RCC. As a result, the RCC system does not clearly link back to user who issued the query, which we believe violates FDA guidance per CFR 21 Part 11, likely with guidance from EMA and other regulators similarly breached. When this QE was initally submitted, there were 3 such known issues across 2 RCC studies. There are now 9 known issues across 6 RCC studies. | C4591081 | C4591081 | GCP_Major_Jan-2026_System/Enterprise Level_System Access Controls Redcap Cloud (RCC): Broader Issue_Pfizer; NPHASE INC (REDCAP CLOUD)_Global | C459 | Major | SQE | 2026-02-26 | (Empty) | N | 2026-02-26 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CP403 - Acceptable Use of Information | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-222180 | In Investigation | QE-222180 | In Investigation | 2026-01-09 | (Empty) | (Empty) | PFIZER | (Empty) | We are raising this event to please request that the minor assessment for QE-219754 be reconsidered. To again summarize the what occured, a legitimate query was raised in the C4601019 study by our medical monitor. However in RCC this query changed to a different user name and role (LabTech). That different user is a real person at Pfizer, but they never requested access to C4601019 and they are not on our Site User Report. This user does not have access to the C4601019 study in RCC, as confirmed by the RCC Admin team's review of the study's audit logs. Further, the Lab Tech role does NOT have access to issue a query in RCC. As a result, the RCC system does not clearly link back to user who issued the query, which we believe violates FDA guidance per CFR 21 Part 11, likely with guidance from EMA and other regulators similarly breached. When this QE was initally submitted, there were 3 such known issues across 2 RCC studies. There are now 9 known issues across 6 RCC studies. | C4591081 | C4591081 | GCP_Major_Jan-2026_System/Enterprise Level_System Access Controls Redcap Cloud (RCC): Broader Issue_Pfizer; NPHASE INC (REDCAP CLOUD)_Global | C459 | Major | SQE | 2026-02-26 | (Empty) | N | 2026-02-26 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CP403 - Acceptable Use of Information | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-224302 | Closed | QE-224302 | Closed | 2026-01-22 | (Empty) | (Empty) | PFIZER | (Empty) | Potential or known unintentional unblinding of study data. On 12-Jan2026- the Unblinded CRA emailed 2 Unblinded site SCs (site 1066) regarding the IPAL and included a screenshot of IP Prep Worksheet for 1 subject that contained unblinded IP information. The PI was copied on the email and should not have received this email. On 18Jan2026 the PI emailed the Unblinded SC stating that he received this email and confirmed that he did not review the contents of the email. On 19Jan2026 the unblinded SC alerted the unblinded CRA by email that the PI (blinded PI) was copied on an email that contains unblinding information. PI immediately noticed the recipients of the email were unblinded and sent the unblinded SC a note that he deleted the email. PI confirmed he did not read any of the contents, so he was not unblinded to the subject's treatment assignment. On 20Jan2026, the SCP notified the Unblinded CRA that this should be submitted as a QE and copied 2 Blinded cSOMs. The Blinded cSOMs should not have been copied on this email. | C4591081 | C4591081 | GCP_Major_Jan-2026_C4591081: Unblinding: Blinded Email Communication_Pfizer_USA | C459 | Major | SQE | 2026-03-08 | 2026-02-13 | Y | 2026-03-08 | 2026-02-13 22:12 | (Empty) | 2026-02-13 | (Empty) | (Empty) | 2026-02-13 | (Empty) | DMB06 - Study Subject Randomization Schedule | Data Collection and Management | Incorrect assignment/randomization and/or maintenance of the study blind | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-227545 | In Investigation | QE-227545 | In Investigation | 2026-02-11 | (Empty) | 1094 | Jorge Caso (C4591081-1094) | UNITED STATES | Study C4591081 Site 1094:An issue related to the IPAL document was raised containing unblinded information of subject within Veeva Site Vault. This resulted an automatic email notification containing the unblinded information of a subject being sent to 4 blinded site staff. The unblinded site staff supervises inboxes of the 4 blinded staff and was able to delete the email notification for two blinded site staff before they could view it, but the other two blinded staff viewed the email before the deletion, which resulted an unblinding event. | C4591081 | C4591081 | GCP_Major_Feb-2026_C4591081: Unblinding: Site Email_Caso, Jorge_USA | C459 | Major | SQE | 2026-03-28 | (Empty) | (Empty) | 2026-03-28 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | DMB06 - Study Subject Randomization Schedule | Data Collection and Management | Incorrect assignment/randomization and/or maintenance of the study blind | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-234381 | In Investigation | QE-234381 | In Investigation | 2026-03-18 | (Empty) | (Empty) | HCL TECHNOLOGIES | (Empty) | Incorrect Access Provisioning: The HCL agent inadvertently granted access to Study C4591081 – Site 1010 instead of the requested Site 1071. Incorrect access was identified and corrected. | C4591081 | C4591081 | GCP_Major_Mar-2026_C4591081: Trend: System Access Controls: Impala_Pfizer; HCL Technologies_Global | C459 | Major | SQE | 2026-05-03 | (Empty) | (Empty) | 2026-05-03 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CP403 - Acceptable Use of Information | IT Systems | Inadequate system access or account management | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-234381 | In Investigation | QE-234381 | In Investigation | 2026-03-18 | (Empty) | (Empty) | PFIZER | (Empty) | Incorrect Access Provisioning: The HCL agent inadvertently granted access to Study C4591081 – Site 1010 instead of the requested Site 1071. Incorrect access was identified and corrected. | C4591081 | C4591081 | GCP_Major_Mar-2026_C4591081: Trend: System Access Controls: Impala_Pfizer; HCL Technologies_Global | C459 | Major | SQE | 2026-05-03 | (Empty) | (Empty) | 2026-05-03 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CP403 - Acceptable Use of Information | IT Systems | Inadequate system access or account management | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-234891 | In Investigation | QE-234891 | In Investigation | 2026-03-20 | (Empty) | 1074 | Faisal Amin (C4591081-1074) | UNITED STATES | This Quality Event is being initiated due to multiple emerging concerns related to data integrity, protocol compliance, and PI oversight at the site. Although the site’s Pre-Trial Assessment (PTA) indicates several years of experience conducting vaccine studies, this is the first known instance of the site enrolling subjects in a Pfizer-sponsored clinical trial.A series of quality issues have since been identified that collectively raise concerns about the reliability of the data generated at this site and the adequacy of oversight practices:1. eDiary Compliance ConcernsRecent review of eDiary metrics reveals highly unusual patterns, including:Exceptionally high overall noncompliance rates when compared to other sites.Egregious over-reporting of symptoms across multiple subjects. These patterns are inconsistent with typical site performance and may indicate inaccurate or coached reporting.2. Data Timeliness and ResponsivenessThe site has repeatedly failed to respond to data queries and to enter required data, despite multiple follow-up requests. This ongoing lack of responsiveness impacts data timeliness and raises broader concerns regarding site engagement and adherence to study expectations.3. Data Quality and Subject Symptom ReportingDuring a call held by Clinicians with the site on 19Mar2026, staff disclosed that they believe several subjects may not be accurately representing their symptoms. This acknowledgement directly calls into question the accuracy and validity of subject-reported data.4. PI Oversight IssuesThe site’s Principal Investigator (PI) was explicitly requested to attend the call referenced above; however, the PI did not participate. Instead, the CEO/Site Director joined the call and took the lead in responding to clinical questions. While the PI did attend the SIV and IM, monitoring documentation to date does not reflect PI attendance or involvement in subsequent monitoring visits (see slides). This raises concerns regarding insufficient PI oversight of key study activities. | C4591081 | C4591081 | GCP_Major_Mar-2026_C4591081: Data Integrity; PI Oversight_Amin, Faisel_USA | C459 | Major | SQE | 2026-05-07 | (Empty) | (Empty) | 2026-05-07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | DMB08 - Study Data Set Collection, Review and Release | Data Collection and Management | Inadequate source data/documentation | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines
QE-234891 | In Investigation | QE-234891 | In Investigation | 2026-03-20 | (Empty) | 1074 | Faisal Amin (C4591081-1074) | UNITED STATES | This Quality Event is being initiated due to multiple emerging concerns related to data integrity, protocol compliance, and PI oversight at the site. Although the site’s Pre-Trial Assessment (PTA) indicates several years of experience conducting vaccine studies, this is the first known instance of the site enrolling subjects in a Pfizer-sponsored clinical trial.A series of quality issues have since been identified that collectively raise concerns about the reliability of the data generated at this site and the adequacy of oversight practices:1. eDiary Compliance ConcernsRecent review of eDiary metrics reveals highly unusual patterns, including:Exceptionally high overall noncompliance rates when compared to other sites.Egregious over-reporting of symptoms across multiple subjects. These patterns are inconsistent with typical site performance and may indicate inaccurate or coached reporting.2. Data Timeliness and ResponsivenessThe site has repeatedly failed to respond to data queries and to enter required data, despite multiple follow-up requests. This ongoing lack of responsiveness impacts data timeliness and raises broader concerns regarding site engagement and adherence to study expectations.3. Data Quality and Subject Symptom ReportingDuring a call held by Clinicians with the site on 19Mar2026, staff disclosed that they believe several subjects may not be accurately representing their symptoms. This acknowledgement directly calls into question the accuracy and validity of subject-reported data.4. PI Oversight IssuesThe site’s Principal Investigator (PI) was explicitly requested to attend the call referenced above; however, the PI did not participate. Instead, the CEO/Site Director joined the call and took the lead in responding to clinical questions. While the PI did attend the SIV and IM, monitoring documentation to date does not reflect PI attendance or involvement in subsequent monitoring visits (see slides). This raises concerns regarding insufficient PI oversight of key study activities. | C4591081 | C4591081 | GCP_Major_Mar-2026_C4591081: Data Integrity; PI Oversight_Amin, Faisel_USA | C459 | Major | SQE | 2026-05-07 | (Empty) | (Empty) | 2026-05-07 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | NOT APPLICABLE | Quality Oversight | Inadequate Principal Investigator quality oversight | ONGOING | Vaccines | PHASE III | MAINTAIN | Comirnaty | (Empty) | (Empty) | MODEL 1 - INSOURCED | Vaccines