## Standard_Quality_Dashboard - QE
Observation ID | Study ID | Targeted | PR ID | Site(s) | principal Investigator | EX Comp? | QE Threshold | Status | Observation Description (as submitted) | Awareness Date | Submission Date | Assessment Date | Title/Short Description | Business CAPA Plan Endorsed On | CAPA Plan in Place | Last Action Due Date | Investigation Summary and Conclusion | Effectiveness Check Required | Effectiveness Check Rationale | Investigation Completion Date | Closed On | PDAL Decision | Level 1 | Level 2 | Quality CAPA Plan Endorsed On | Quality Reviewer Approved On | Business Process | Submitter | Confirmed Serious Breach | Remediation Actions Taken (when QE was submitted) | CAPA Action Details | CAPA Action Owner | Root Cause Description | Root Cause Level 1 | Root Cause Level 2 | Root Cause Level 3 | Rapid Model | Business Category
QE-200197 | C4591082 | (Empty) | QE-200197 |  | PFIZER | N | Major | Approved - In CAPA | The PRS Prediction tool (Protocol Risk Score) is a machine learning algorithm run against 31 data points (primarily Registry) pulled from the GPDIP database to provide a PRS for study team and RQA set up and planning. It was recently noted that the tool has been generating final PRS scores for users based upon incomplete and/or stale data. The PRS scores are used by:.25in;"Study Management for development of the SDV/SDR percentage in the Study Monitoring Plan per INV02-INV04-GSOP-RF04 and INV04-GSOP-RF17. Data Management for SDV requirements during the EDC database build as per DMB07-GSOP-RF27.Study teams for contract and budgeting purposes at the endorsed study outline time pointRegulatory Quality Assurance for their audit strategy development The PRS is provided automatically twice during a study; an ‘at risk’ PRS score is provided at Study Outline, and Final PRS is provided at Study FAP (within 24-48hrs of those dates being received in GPDIP). A review of data shows:that 43/60 studies receiving a Final PRS since the prediction tool was implemented had at least 4 of the 31 required fields missing.Some studies had more than 15 missing data points at the time their PRS was calculated.All 60 studies were missing the same 3 data points – which were retired several years ago from the Registry. The replacement field is not used in the calculation..25in;" Lastly, study teams submitting updates to the Registry have noticed that their updates are not reflected in revised PRS scores. This led to the discovery that data from 2 GPDIP databases are not flowing to the PRS Prediction Tool. – so the tool is using stale data to make calculations. 17 studies have had Final PRS calculated with stale data. 2 support tickets were submitted by Pan Liu, which remained open last week. It might be as much as a month ago that the stale data were identified. It does not appear that RQA nor any study teams are aware of the stale data issue, or the potential impact of using a PRS generated from incomplete data.The start date would be the launch date of the PRS Prediction Tool (Confirm with Tarin McTague or Sheri Kuss). The awareness date would be 8Sep2025, when AQLs met with Ivan Walrath and Tarin McTague to discuss and confirm concerns. | 2025-09-08 | 2025-09-08 | 2025-09-09 15:30 | GCP_Major_Sep-2025_Multiple Protocols: PRS Prediction tool (Protocol Risk Score)_Pfizer_Global |  | YES |  | <p style="margin-left: 0in;"><span style="font-size: small;">On 08 September 2025, a Pfizer Asset Quality Lead (AQL) identified stale data impacting the Protocol Risk Score (PRS) Tool. Updated data from upstream systems had not flowed into the PRS Tool since 01 May 2025, meaning calculations performed by the tool during this period were based on outdated information.</span></p><p style="margin-left: 0in;"><span style="font-size: small;">&nbsp;</span></p><p style="margin-left: 0in;"><span style="font-size: small;">The PRS Tool is a machine learning algorithm that calculates a study-level risk score using 31 data points entered by study teams into various source systems. These data points are aggregated by the PRS Tool and processed through the algorithm to generate an overall risk classification (i.e., low, medium, or high). This score informs study teams of the study’s risk profile and supports decisions on risk mitigation activities such as monitoring plans, Source Document Review (SDR), and Source Data Verification (SDV).</span></p><p style="margin-left: 0in;"><span style="font-size: small;">&nbsp;</span></p><p style="margin-left: 0in;"><span style="font-size: small;">The PRS Tool automatically calculates scores at two key time points:</span></p><ul type="disc"><li style="margin-left: 0.5in; font-size: small;">Post-Study Outline: Provides an initial risk score based on limited early data.</li><li style="margin-left: 0.5in; font-size: small;">Post-Final Approved Protocol (FAP): Generates a comprehensive risk score using a more complete dataset.</li></ul><p style="margin-left: 0.3in;"><span style="font-size: small;">&nbsp;</span></p><p style="margin-left: 0in;"><span style="font-size: small;">Additionally, study teams may request ad hoc PRS scores at any time.</span></p><p style="margin-left: 0in;"><span style="font-size: small;">&nbsp;</span></p><p style="margin-left: 0in;"><span style="font-size: small;">Data flow to the PRS Tool was restored on 15 September 2025. During the outage period, PRS scores were calculated for 16 studies at the FAP time point.</span></p><p style="margin-left: 0in;"><span style="font-size: small;">&nbsp;</span></p><p style="margin-left: 0in;"><span style="font-size: small;">A historical review of Quality Events (QEs) in the electronic Quality Management System (eQMS) database was conducted for the period 08 September 2023 – 18 December 2025, using the keywords “Protocol Risk Score Tool” and “PRS Score Tool.” No historical QEs were identified. Based on this review, the current QE (QE-208430) is not considered a repeat occurrence.</span></p> | No | CAPA Plan included error proofing that will prevent reoccurrence | 2026-01-06 |  |  | IT Systems | Inadequate IT system (eg. planning, definitions, design, development, testing, validation, support) per regulatory requirements |  | 2026-01-07 18:19 | QMS06-Risk Management for Clinical Development | Walter Sauer | FALSE | 4Aug2025 AQL JS noted gaps in data set for B7981118 upon completion of ad hoc update. AQL JS downloaded full data set from PRS Prediction Tool to perform personal review of data. Consulted over the next week or so with AQLs HW and MG. 18Aug2025 AQL MG Requested meeting with technical and process SMEs/BPOs - scheduled for 10Sep 2025. 28Aug2025 AQL JS and HW met with Registry team to review processes and data requirements. 8 Sep 2025 AQL JS presented investigation results to QMS06 BPO and Head, Risk Quality and Operations. Agreement that QE submission was warranted even without full impact assessment and/or BPO identification |  |  | A lack of awareness of the relationship between CT27 "Clinical Trial Registry" data entry and PRS tool automated score within study teams can cause updated data to be missing from the Clinical Trial Registry during PRS automated score calculation., An update associated with the Siebel CTMS to Veeva transition caused a value within Siebel CTMS to become unrecognized by GPDIP and prevented updated data from flowing into GPDIP. The PRS tool was then pulling stale data from GPDIP. | Equipment/System/Facility | System/Application | Failure or Malfunction, Signals Unavailable or Ineffective | MODEL 1 - INSOURCED | Vaccines
QE-210902 | C4591082 | (Empty) | QE-210902 |  | PFIZER | N | Minor | Closed | Protocol C4591082 is in start up phase and is in the process of activating sites currently in the US only. RedCAP Cloud (RCC) is the EDC database system that we are using. As several sites (1007, 1025 and 1055) were going through the Site Activation Checklist (SAC), it was verified that the Investigator and Site Staff had access to C4591082 in RCC. Once all required items on the SAC were confirmed, these 3 sites were activated. However, it was later discovered that even though the sites could log in to RCC successfully, the C4591082 study was not showing up in their view. A few of these sites had enrolled participants and had data waiting to be entered, but until resolved, this could not happen. | 2025-11-04 | 2025-11-04 | 2025-11-04 17:44 | GCP_Minor_Nov-2025_C4591082: CMCD: RedCAP Cloud (RCC) System View_Pfizer_USA |  | NO |  |  | No |  |  | 2025-11-04 |  | IT Systems | Inadequate system access or account management |  |  | CP403 | Meri Lee Tyler |  | Activation for additional sites was put on pause until this could be resolved. A Help Desk ticket was opened and Data Management was also made aware. |  |  | NA | Equipment/System/Facility | System/Application |  | MODEL 1 - INSOURCED | Vaccines
QE-212399 | C4591082 | (Empty) | QE-212399 |  | PFIZER | N | Minor | Closed | data from EDC (RCC) not populating to ODR reports, causing issues on monitoring and potential Protocol Deviation managements | 2025-11-06 | 2025-11-12 | 2025-11-13 23:46 | GCP_Minor_Nov-2025_C4591082: REDCap Cloud Data Integration; Monitoring Responsibilities_Pfizer_USA |  | NO |  |  | No |  |  | 2025-11-13 |  | Site Management and Monitoring | Failure to follow study specific monitoring plan/ requirements |  |  | INV04-Investigational Site Management and Monitoring | Gholamreza Khalili |  | CTMS ticket (.4px; background-color: rgb(239, 239, 239);'INC01033539) raised on 6 November, then based on CTMS team recommendation another ticket (.4px; background-color: rgb(239, 239, 239);'RITM0072262 &amp; .4px; background-color: rgb(239, 239, 239);'INC01040359) raised to Spotfire. issues are currently escalated through DM ()team and also CSTL and is under investigation. Risk based monitoring is affected as CRA's cannot get SDR/SDV reports in their MOBOT reports. Meanwhile CRAs asked to perform their onsite monitoring visits, and manually entering site's first subject for SDR. CMCD query raised on 11 Nov for site monitoring guidance waiting feedback. |  |  | NA | Equipment/System/Facility | System/Application |  | MODEL 1 - INSOURCED | Vaccines
QE-212932 | C4591082 | (Empty) | QE-212932 |  | NPHASE INC (REDCAP CLOUD), PFIZER | N | Minor | Closed | C4591082 Study: The Site user has access to all sites but should only have access to 1004, 1055 | 2025-11-14 | 2025-11-14 | 2025-11-14 20:31 | GCP_Minor_Nov-2025_C4591082: System Access Controls_NPhase Inc; Pfizer_USA |  | NO |  |  | No |  |  | 2025-11-14 |  | IT Systems, Quality Procedures | Business process not addressed, Inadequate system access or account management |  |  | INV02-Investigational Site Selection, Preparation, and Initiation, QMS09-Vendor Engagement | Ajitha Akurati |  | 1. Access Revoke request sent to support team. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-214738 | C4591082 | (Empty) | QE-214738 |  | PFIZER | N | Major | In Investigation | There is an error in the Modified Schwartz CrCl Equation used to estimate GFR for children age 2 years to &lt;12 year in C3601008 Protocol Section 10.6.2.2. The proportionality constant (K) for males &lt;12 years of age is listed as 0.70, whereas it should be 0.55 for both males and females. This results in eGFR being overestimated by 21% for males 2-12 years of age.CrCl normalized to BSA (mL/min/1.73 m2) = (K × Ht)/SCrHeight (Ht) in centimeters; SCr in mg/dL.K (proportionality constant): Female child &lt;12 years: K=0.55, Male child &lt;12 years: K=0.70This error was present in the 2014 FDA Draff Pediatric Clin Pharm Guidance document until removed in 2022, and it was in the CT02 Pediatric Library and CT02 Kidney Safety Library which was how it was introduced into the protocol. Dosing for ATM-AVI the C3601008 is based on weight and CrCl with a dose reduction for CrCL &lt;50 and &lt;30 and exclusion for CrCl &lt;15. C3601008 has completed enrollment of participants 2-12 and all 12 male subjects age 2-12 had eCrCl &gt;100 mL/min/1.73m2 using K=0.7, so a 21% reduction in eCrCl using K=0.55 would not have changed the dose. At least 2 other ongoing pediatric studies, C5301023 and C4671026 are also using the incorrect K=0.7 proportionality constant to calculate eCrCL for males &lt;12 years of age, and there may be others among ongoing pediatric studies.. | 2025-11-24 | 2025-11-24 | 2025-11-25 17:34 | GCP_Major_Nov-2025_Multiple Protocols: Modified Schwartz CrCl Equation; Potential Medication Error_Pfizer_Global |  | NO | [7 empty] | Quality Oversight/Documentation | Inadequate quality documentation |  |  | CT02-Protocol Development for Interventional Studies | Richard England |  | none | [6 empty] | MODEL 1 - INSOURCED | Vaccines
QE-218532 | C4591082 | (Empty) | QE-218532 |  | PFIZER | N | Minor | Closed | On the C4591082 study the PIPD list was inadvertently endorsed by a contractor Clinical Data Reviewer following the endorsement notification (27-Oct-2025), prior to FSFV (30-Oct-2025). It was identified when completing the Clinical QC of documentation in PTMF that the PIPD list had not uploaded from CORD to PTMF. A ticket was submitted and it was flagged that the endorser did not have PTMF access. When reviewing the Clinical endorser, it was identified that it was a contractor Clinical Data Reviewer who endorsed the form and not a Clinician/Clinical Scientist as specified in CT40-GSOP. The same PIPD list was endorsed again on 12-Dec-2025 by the appropriate Clinical Scientist and Statistician roles. No changes were required to the PIPD list, which had already been reviewed by all members of the study Clinical team before 27-Oct-2025. No formal analysis had taken place. A QE has been entered due to the potential impact of not having a suitably endorsed PIPD list at FSFV. | 2025-12-12 | 2025-12-12 | 2025-12-12 22:09 | GCP_Minor_Dec-2025_C4591082: CMCD: PIPD Endorsement_Global |  | NO |  |  | No |  |  | 2025-12-12 |  | Quality Procedures | Business process not addressed |  |  | CT40-Management of Protocol Deviations | Matthew Wiestaw Gawel |  | The same PIPD list was endorsed again on 12-Dec-2025 by the study Clinical Scientist and Statistician. The Clinical team and contractor were retrained on the CT40 SOP requirements (12-Dec-2025). |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-221532 | C4591082 | N | QE-221532 | 1002 | Tatyana Miroshnikova (C4591082-1002) | N | Minor | Closed | A quality event was identified related to laboratory documentation and shipment procedures affecting multiples subjects (10021001, 10021002, 10021003, and 10021004). The TruLab application was used only for nasal swab documentation and was not used for blood/aliquots collected at the site. Additionally, blood collection times and processing times were not documented in either the Trulab application or source records. Laboratoyr samples were shipped using a previous Pfizer shipping method rather than the procedures outlined in the current study laboratory manual. | 2025-12-22 | 2026-01-06 | 2026-01-07 18:17 | GCP_Minor_Jan-2026_C4591082: Biospecimen Management_Miroshnikova, Tatyana_USA |  | NO |  |  | No |  |  | 2026-01-07 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | No Process Assigned | Toi Dickson |  | As an immediate action, the site was placed on hold until an adequate level of reassurance regarding the site's understanding and implementation of study-specific laboratory procedures could be demonstrated. The site completed targeted retraining on protocol requirements, Trulab application usage, source documentation recommendations, the current laboratory manual and current shipping requirements (23DEC2025). Legacy Pfizer shipping procedures were discontinued. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-221708 | C4591082 | N | QE-221708 | 1002 | Tatyana Miroshnikova (C4591082-1002) | N | Minor | Closed | at site 1002 for study C4591082, 2 different users were provided access to the TruLab applicable to process and track samples.However, during a routine monitoring visit, the CRA discovered that the lab techinician was using in some instances the TruLab device logged in with the SC account. Altough it was confirmed that now password sharing occurred, attributability of the data entry was in question. | 2026-01-05 | 2026-01-07 | 2026-01-07 19:05 | GCP_Minor_Jan-2026_C4591082: System Access Controls_Miroshnikova, Tatyana_USA |  | NO |  |  | No |  |  | 2026-01-07 |  | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) |  |  | CP403 | Marco Mazza |  | site retraining |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-222180 | C4591082 | (Empty) | QE-222180 |  | NPHASE INC (REDCAP CLOUD), PFIZER | N | Major | In Investigation | We are raising this event to please request that the minor assessment for QE-219754 be reconsidered. To again summarize the what occured, a legitimate query was raised in the C4601019 study by our medical monitor. However in RCC this query changed to a different user name and role (LabTech). That different user is a real person at Pfizer, but they never requested access to C4601019 and they are not on our Site User Report. This user does not have access to the C4601019 study in RCC, as confirmed by the RCC Admin team's review of the study's audit logs. Further, the Lab Tech role does NOT have access to issue a query in RCC. As a result, the RCC system does not clearly link back to user who issued the query, which we believe violates FDA guidance per CFR 21 Part 11, likely with guidance from EMA and other regulators similarly breached. When this QE was initally submitted, there were 3 such known issues across 2 RCC studies. There are now 9 known issues across 6 RCC studies. | 2025-12-16 | 2026-01-09 | 2026-01-12 20:17 | GCP_Major_Jan-2026_System/Enterprise Level_System Access Controls Redcap Cloud (RCC): Broader Issue_Pfizer; NPHASE INC (REDCAP CLOUD)_Global |  | NO | [7 empty] | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) |  |  | CP403 | Katherine Paternel |  | Raised as a critical finding for RCC white glove as of 17 Dec2025 - CAS00002285. Raised the topic to Pfizer and RCC SMEs for immediate action. | [6 empty] | MODEL 1 - INSOURCED | Vaccines
QE-222470 | C4591082 | N | QE-222470 | 1016 | Leonel Reyes, Jr. (C4591082-1016) | N | Minor | Closed | VRD received shipment 620X38109391 from site 1016 on C4591082 study with PHI information on two of the Nasal swab tubes. site staff wrote the project-specific participant ID on the tubes' labels.Samples impacted are: CFGLDFCFGLDG | 2026-01-08 | 2026-01-12 | 2026-01-12 18:50 | GCP_Minor_Jan-2026_C4591082: Participant Confidentiality / Data Privacy_Reyes Jr, Leonel_USA |  | NO |  |  | No |  |  | 2026-01-12 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Marco Mazza |  | site retraining. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-225067 | C4591082 | N | QE-225067 | 1005 | Grant Paulsen (C4591082-1005) | N | Minor | Closed | Participant 1005-1006 had a telehealth illness visit on 13JAN2026 where the LAR collected the nasal swab and called courier Marken for pickup on 14JAN2026. On 16JAN2026 site personnel, not having received the sample from Marken, reached out to the LAR and she stated they never came to pick up the swab (she confirmed that she received an email for the requested pickup). LAR clainmed she had a very busy week and completely forgot to follow up with them. on 20JAN2026 - site reached out to LAR to confirm if Marken picked up the swab, she stated they picked up at 10AM (Tuesday 20JAN). Upon further investigation, Marken was able to locate a sample shipped under 620X38354783 belonging to protocol C4591081 subject 1005-1006 which was collected from the patient’s home on 20-Jan-2026. Our team did receive an alert from the C4591081 team that their site in Mentor had received samples from a patient that wasn’t active yet. We believe that due to the protocol proximity in numbers, it could have cause an unfortunate misrouting of samples. | 2026-01-26 | 2026-01-27 | 2026-01-28 15:26 | GCP_Minor_Jan-2026_C4591082: Biospecimen Sample Management_Paulson, Grant_USA |  | NO |  |  | No |  |  | 2026-01-28 |  | Equipment, Facility and Sample/Specimens | Inadequate equipment/lab supply mgmt. |  |  | CT29-Management of Clinical Study BioSpecimens | Marco Mazza |  | sample was tracked and it was determined was tracked to a different site in error. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Vaccines
QE-226294 | C4591082 | (Empty) | QE-226294 |  | PFIZER | N | Minor | Closed | On January 15th a release to the Data Integrity and Validation Application (DIVA) resulted in an issue with the signed versions of the Data Integrity Plan (DIP) not providing an accurate document history or validation modifications for signed versions of the DIP, which were then posted with these inaccuracies to the pTMF. 32 studies were impacted by this error. This also impacted the standard library DIP, with the inaccuracies documented in a signed version of the library DIP which was subsequently posted to Gnosis. | 2026-02-03 | 2026-02-03 | 2026-02-04 18:45 | GCP_Minor_Feb-2026_Multiple Protocols: Data Integrity Plan_Pfizer_Global |  | NO |  |  | No |  |  | 2026-02-04 |  | Data Collection and Management | Data management error |  |  | CT01-Trial Master Files | Jennifer Maloney |  | Upon realizing the issue DIVA support was engaged to identify the root cause and to fix the issue so additional studies would not be impacted. The DIVA support team is working through a remediation for the studies that are currently impacted. |  |  | NA | Equipment/System/Facility | System/Application |  | MODEL 1 - INSOURCED | Vaccines
QE-228569 | C4591082 | N | QE-228569 | 1007, 1013, 1033 | Ana Roig Cantisano (C4591082-1013), Jose Cardona (C4591082-1007), Lilia Roque Guerrero (C4591082-1033) | N | Major | Approved - In CAPA | C4591082: Based on potential duplicate participation report (5 Dec 25 &amp; 12Jan26) provided by central monitoring team, 4 participant ID pairs have been confirmed to be duplicates (eg there are 8 participant IDs for only 4 unique participants (List below). CRA confirmed the below by reviewing the consents, same participant, first middle and last name and the parent (mother’s) name was the same. CRA also verified DOB with subject identification log since it's not captured in IRT or RCC. 1st Pair10071007101310132nd Pair10071006101310123rd Pair10071031103310014th Pair1007100310131006 | 2026-02-13 | 2026-02-16 | 2026-02-17 18:09 | GCP_Major_Feb-2026_C4591082: CMCD: Multiple Enrollment_Multiple Sites_USA |  | YES |  | <p>In Feb 2026, the C4591082 Central Monitoring Team identified three potential duplicate participant enrollment pairs within Study C4591082 following review of Potential Duplicate Participant (PDP) analyses generated in Dec 2025 and Jan 2026, based on predefined detection criteria.</p><p><br></p><p>A fourth duplicate participant pair was identified by the Clinical Research Associate (CRA) during follow up review, as this pair did not meet the PDP matching thresholds due to differences in recorded participant weight between sites.</p><p><br></p><p>The four pairs of participants were enrolled across three investigational sites in Florida, all within a driving distance of approximately 20 miles from each other: Site 1007 (Hialeah), Site 1013 (Miami), and Site 1033 (Miami). Enrollment and dosing for the affected participants occurred between 03 Nov 2025 and 08 Jan 2026, as detailed below:</p><p><br></p><ol><li>Participant 10071003 was enrolled and dosed at Site 1007 on 03 Nov 2025, and participant 10131006 was enrolled and dosed at Site 1013 on 19 Nov 2025.</li><li>Participant 10071006 was enrolled and dosed at Site 1007 on 04 Nov 2025, and participant 10131012 was enrolled and dosed at Site 1013 on 26 Nov 2025.</li><li>Participant 10071007 was enrolled and dosed at Site 1007 on 04 Nov 2025, and participant 10131013 was enrolled and dosed at Site 1013 on 26 November 2025.</li><li>Participant 10331001 was enrolled and dosed at Site 1033 on 14 Nov 2025, and participant 10071031 was enrolled and dosed at Site 1007 on 08 Jan 2026.</li></ol><p><br></p><p>Source data verification performed by the CRA on 17 Feb 2026 confirmed that, for all four participants, both enrollments corresponded to the same individual. Confirmation was based on identical participant names, matching parent (mother’s) names, and matching dates of birth documented at the respective sites. All confirmed duplicate enrollments involved participants who were enrolled and dosed at more than one site within the same study after being independently presented for screening by their legal representatives.</p><p><br></p><p>The issue represented a protocol non‑compliance involving multiple enrollment of the same individuals within study C4591082, which posed a risk to study integrity, including the reliability of enrollment controls and participant identification processes across sites.</p><p><br></p><p>An historical review was conducted of Quality Events (QEs) in Veeva, Pfizer’s electronic quality management system, to identify QEs that meet the following search criteria:</p><ul><li>Keywords: Multiple Enrollment, Multiple Enroller, Duplicate Enrollment, or Duplicate Enroller</li><li>Timeframe: 2 years &lt;17 Feb 2024 – 17 Feb 2026&gt;</li></ul><p><br></p><p>No additional QEs were identified. Through this review, it was concluded that the current QE (QE-228569) is not a repeat occurrence.</p> | No | Study/Program/Activity ended and issue does not impact other studies/programs/activities | 2026-03-20 |  |  | Protocol Deviations | Failure to comply with protocol inclusion/exclusion criteria |  | 2026-03-20 21:10 | DMB07-Study Data Set Design and Setup | Vishal Patel | FALSE | CRA has verified the potential duplicate participants reports and confirmed that 4 pairs of subjects enrolled were duplicate from 3 sites after verifying the source data. Clinical and Biostat team have been informed as per DMB07- DMB08- INV02-INV04- GSOP (IDENTIFICATION AND MANAGEMENT OF MULTIPLE ENROLLER PARTICIPANTS IN CLINICAL TRIALS). |  |  | The multiple enrollments resulted from study‑level risk‑based control design, whereby duplicate enrollment was managed through retrospective, threshold‑based centralized monitoring rather than preventive screening controls. Verified Clinical Trials (VCT) was not utilized as it is out of scope for pediatric studies (per Pfizer policy) and due to the overall study-level risk assessment being assessed as low, and patient reimbursement could not serve as a detection control due to non‑standardized reimbursement models across sites. As a result, duplicate enrollment was identified only after enrollment and dosing through centralized monitoring and study team review. | Method/Procedure | Procedure/Form/Plan | Document Doesn't Exist/Lack of Access or Availability (Signals to Use Standard or Use of Standard) | MODEL 1 - INSOURCED | Vaccines
QE-229022 | C4591082 | (Empty) | QE-229022 |  | MARKEN LTD | N | Minor | Closed | VRD lab received samples in a different AWB (620X38101667), and not the AWB that was created for the initial shipment (620X38101923).upon further investigation from the Marken team, it was determined that all movements of samples were captured accurately while in transit. Marken also confirmed that the shipment’s chain of custody was never compromised, as all milestones were correctly captured under job 620X38101923. While the shipment was tendered using the label for 620X38101667, which had been cancelled, all transportation events were properly recorded. Marken also verified that shipment 620X38101667 was not entered into TruLab on the day of collection; the shipment entered in the TruLab app was 620X38101923.Upon arrival at the Marken NYC facility, the shipment was found to be missing a HAWB. The team then printed the label for 620X38101667 and requested it to be uncancelled. As this was an internal operational error with no impact to the samples, it was escalated directly to Marken Vendor Management team. Marken local partner has agreed to ensure that alerts are reviewed and actioned appropriately moving forward. Additionally, Marken addressed the error related to un-cancelling a previously cancelled shipment with the Marken NYC team. | 2026-02-09 | 2026-02-18 | 2026-02-18 20:00 | GCP_Minor_Feb-2026_C4591082: Biospecimen Sample Management: Shipment_Marken_USA |  | NO |  |  | No |  |  | 2026-02-18 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens | Marco Mazza |  | issue escalated internally at Marken. |  |  | NA | Equipment/System/Facility | System/Application |  | MODEL 1 - INSOURCED | Vaccines
QE-229748 | C4591082 | (Empty) | QE-229748 |  | PFIZER | N | Minor | Closed | During assessment of the need for a protocol amendment, it was identified that Protocol Administrative Change Letters (PACLs) had previously been issued for studies C4591082 and C4591076 to clarify a primary immunogenicity objective. At the time of submission, the PACLs were assessed and classified as non‑substantial and were endorsed by Regulatory. Subsequent re-review against the REG03‑GSOP‑RF05 SOP identified that the change may have met criteria for a substantial amendment, as it related to a primary study objective. While RF05 Table 1 lists changes to primary objectives as substantial, the update to the primary objective was considered a minor clarification (non-substantial) rather than a change. Per RF05, the table is intended as general guidance only, providing examples typically considered to be substantial or non-substantial, and allowing for sponsor case‑by‑case determination, based on the assessment conducted at the time.At the time of the PACL, the team evaluated if the change in wording of the primary objective would impact any aspect of the analysis of the primary objective. After confirming no change to the intended analysis, no change to the scientific intent of the objective, and that the rewording was cosmetic, the proposed change was reviewed with Regulatory and deemed non‑substantial.The clarification was implemented in response to CBER feedback received on 26‑Sep‑25 requesting clarification of the term “superiority” used in the objectives and statistical analysis sections. The feedback indicated that the terminology could be misinterpreted as implying a between‑intervention comparison, whereas the intended assessment was a within‑group, threshold‑based immunogenicity evaluation. | 2026-02-18 | 2026-02-23 | 2026-02-23 19:27 | GCP_Minor_Feb-2026_C4591076, C4591082: CMCD: Protocol Administrative Change Letter (PACL)_Pfizer_Global |  | NO |  |  | No |  |  | 2026-02-23 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | CT02-Protocol Development for Interventional Studies | Matthew Wiestaw Gawel |  | To ensure alignment with the REG03‑GSOP‑RF05 SOP and to remove subjectivity in the interpretation of guidance related to primary study objectives, the changes previously implemented via PACLs were conservatively re-assessed as substantial. In addition, it was recognized that failure to amend the protocols prior to final analysis could lead to confusion between the last approved protocol version and the CSR reporting the results.Therefore, the team agreed that initiating protocol amendments would address both downstream study consistency in study design and analysis and would continue to honour the intent and spirit of REG03-GSOP-RF05.Protocol amendments have accordingly been initiated for studies C4591082 and C4591076 to formally incorporate the clarifications. The amendments will be finalized prior to any immunogenicity reporting events.The interpretation of the SOP was also escalated to the CT02 BPO for further discussion with relevant BPO representatives and SMEs regarding whether additional clarifications within the SOP are warranted. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-232753 | C4591082 | Y | QE-232753 | 1004 | Shane Christensen (C4591082-1004) | N | Minor | Closed | VRD received a sample shipment from site 1004 containing Nasal Swab sample labeled with PHI (participant name). This is impacting subject 10041012, covid illness swab sample collected on 27Feb26 with barcode GB35906. | 2026-03-06 | 2026-03-10 | 2026-03-10 18:36 | GCP_Minor_Mar-2026_C4591082: Participant Confidentiality / Data Privacy_Christensen, Shane_USA |  | NO |  |  | No |  |  | 2026-03-10 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Marco Mazza |  | Site retraining. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Vaccines
QE-233431 | C4591082 | (Empty) | QE-233431 |  | PFIZER | N | Minor | Closed | Global reference table to derive mapped variables was not available in standards template for Clinical Model SM_FAVSD068 (a table in RCC SRDM to receive the eDiary vendor data) during the initial deployment for this study. This was included as part of a database post-production change (PPC) but study team decided to remove it from the scope of PPC due to possible delay in database deployment and impact to the upcoming L1 deliverable. However, standards team already incorporated the global reftable in development stage of this study and the builder missed to reset the development model before the UAT deployment resulted in this global reftable added to UAT and Production instances for SM_FAVSD068 without a formal UAT. The production database Clinical Model SM_FAVSD068 has been reviewed by the Clinical Data Scientist and confirmed that no issues with the data flow and global reftable mapped variables are populating the data as expected. | 2026-03-13 | 2026-03-13 | 2026-03-13 19:33 | GCP_Minor_Mar-2026_C4591082: CMCD: Database Quality Check_Pfizer_Global |  | NO |  |  | No |  |  | 2026-03-13 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | DMB07-Study Data Set Design and Setup | Jayasri Sivaprasad |  | The quality of the study conduct is not impacted, and no impact to the eDiary vendor data in production study. The dataflow from eDiary vendor is working as expected and the newly added global reftable mapped variables are populating the data as expected. UAT team has been contacted to perform a testing retrospectively to ensure all components of the User Acceptance testing are completed as soon as possible. |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Vaccines