## Standard_Quality_Dashboard - Au
AMS Audit PR ID | AMS Observation PR ID | Target Completion Date | Actual Completion Date | TCD Due/Overdue Days | TCD Status | Observation Closed On | Observation Rating | Observation Phase | Investigator Full Name | Country | Unique Site Number | Type Of Entity | Issue Of Audit Report Actual | Issue Audit Closure Rpt Act | Observation Description | Response (Trackwise Only) | Actions Taken | CAPA Action Description | CAPA Action Created by | Responsibility | Responsible Contact | Audit Coordinator | Observation Status | Audit Status | Level 1 | Level 2 | Selected Business Process | Responsible Party Value | Rapid Model | Business Category | Site Care Partner | Cluster | Area ID | Area Name
AIA-005598 | QE-160013 | 2025-03-21 | 2025-03-21 |  | Completed On Time |  | Minor |  | Hilton, John | CANADA | C4891006_1004 | GCP Site Audit | 2025-01-23 |  | For 3 of 3 patients reviewed, source documents were not in accordance with the ALCOACCEA criteria (Accurate, Legible, Contemporaneous, Original, Attributable, Complete, Consistent, Enduring, &amp; Available) (Pfizer Protocol C4891006, Amendment 3, dated 17 Jul 2023). 1. The following issues were identified with respect to incomplete source documentation: a. Patient 10041001: The source records included a Medical History note by the Study Coordinator (SC) dated 18 Apr 2023; however, the note did not contain a patient or study identifier. b. Patient 10041003: Two Breast Cancer/Medical History source notes were filed in the patient's chart; however, neither note contained a study or patient identifier and one note had not been signed or dated by the SC.&nbsp; c. Patient 10041006: The source records included a Medical History note which was not signed or dated by the individual completing the note and did not contain a patient or study identifier. 2. The following issue was identified with respect to consistency of data:&nbsp; Patient 10041003: The 'Tumour Assessment Form-RECIST 1.1' indicated the date of imaging for the Baseline measurements as 18 Nov 2023; however, the Computerized Tomography report indicated the procedure was conducted on 08 Nov 2023. 3. The following issue was identified with respect to attributability of data:&nbsp; Patient 10041006: The Pharmacology Work Sheet (Cycle 1/Day 1) 07 Mar 2024 entry was initialed by the Pharmacology Nurse; however, the initials did not match the initials noted on the Signature Sheet and Delegation of Duties Log. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | With regards to finding "3", the Quality Assurance Specialist responded the following:It should be noted that the note in EMR (EPIC) for the visit done on 07Mar2024 for pt#10041006 clearly says that the blood work was done by LT. The note is entered by SC, who is the lab technician who did the rest of the assessments for that visit and who put both her initials and LTs initials on the worksheet. SC is currently on maternity leave; but I will make sure to re-send this reminder to her when she returns in the fall of 2025.In addition, the attached email has been sent to the Pharmacology lead to have a better process implemented to capture dosing being taken by patient on PK sample days. | a. Patient 10041001: The source records included a Medical History note by the Study Coordinator (SC) dated 18 Apr 2023; however, the note did not contain a patient or study identifier.During the meeting held on 14Feb2025, the Primary Study Coordinator (SC) and Data Manager clarified the source records mentioned in item a. is a working document and for such reason, there were no patient identifiers. During the monitoring visit completed on 27Jan2025, Clinical Research Associate (CRA) confirmed that the Data Manager added patient number 10041001 on the medical history sheet and signed with late entry on 16Jan2025. During the monitoring visit on 27Jan2025 and again during the meeting held on 14Feb2025, the coordinators were trained on Good Document Practices (GDPs) and ALCOA+ (Accurate, Legible, Contemporaneous, Original, Attributable) Principles by CRA and Clinical Trial Manager (CTM).b. Patient 10041003: Two Breast Cancer/Medical History source notes were filed in the patient's chart; however, neither note contained a study or patient identifier and one note had not been signed or dated by the SC.During the monitoring visit on 27Jan2025, the CRA verified that the Data Manager entered patient number 10041003 on the medical history sheet and signed with late entry on 16Jan2025.The Primary Study Coordinator signed the other note with late entry date on 17Jan2025. Site clarified that source mentioned in item b. was a working document, therefore, not clearly identified. Site has been re-trained in GDP and ALCOA+ principles as mentioned above.c. Patient 10041006: The source records included a Medical History note which was not signed or dated by the individual completing the note and did not contain a patient or study identifier.The CRA verified on 27Jan2025 that the Data Manager, entered patient number 10041006 on the medical history sheet and signed with late entry on 16Jan2025. Site clarified that source mentioned in item c. was a working document, therefore, not clearly identified. Site has been re-trained in GDP and ALCOA+ principles as mentioned above.2. The following issue was identified with respect to consistency of data: Patient 10041003: The 'Tumour Assessment Form-RECIST 1.1' indicated the date of imaging for the Baseline measurements as 18 Nov 2023; however, the Computerized Tomography report indicated the procedure was conducted on 08 Nov 2023.The CRA verified on 27Jan2025 that the Primary Study Coordinator corrected the Tumor sheet to 08Nov2023 with initials and date on 17Jan2025. During the Interim Monitoring Visit (IMV), coordinators were trained on Good Document Practices (GDPs) and ALCOA+ Principles by CRA.3. The following issue was identified with respect to attributability of data: Patient 10041006: The Pharmacology Work Sheet (Cycle 1/Day 1) 07 Mar 2024 entry was initialed by the Pharmacology Nurse; however, the initials did not match the initials noted on the Signature Sheet and Delegation of Duties Log.This issue was discussed with the study team on the meeting held on 14Feb2025 where the SC informed that the pharmacology nurse collected the PK samples, but the initials might have been entered by another pharmacology staff. The SC was requested to follow up with the pharmacology team and make a Note to File to clarify this issue and explain the different initials on the Pharmacology sheet. During the meeting held on 14Feb2025, site has been trained on Good Document Practices (GDPs) and ALCOA+ Principles by CRA and CTM.Responsible Role: Primary Study Coordinator | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | Data Collection and Management | Inadequate source data/documentation | NOT APPLICABLE; NOT APPLICABLE | SITE PERSONNEL | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-005598 | QE-160012 | 2025-03-21 | 2025-04-02 |  | Complete Late |  | Minor |  | Hilton, John | CANADA | C4891006_1004 | GCP Site Audit | 2025-01-23 |  | Protocol non‑compliance was identified for 1 of 3 patients reviewed (Pfizer Protocol C4891006, Amendment 3, dated 17 Jul 2023). Patient 10041006: The Cycle 1/Day 1 (07 Mar 2024) pre-dose Pharmacokinetic (PK) samples were collected at 09:38, but the time of dosing of Vepdegestrant (ARV-471) and Abemaciclib was not indicated on the Pharmacology Work Sheet. The dosing diary indicated that the patient self administered both study drugs at 14:30, after 'arriving home at 2:PM'. As per the protocol, on ARV-471 and Abemaciclib PK sampling days, the study drug doses should be taken in the clinic under the supervision of the study site personnel and pre-dose samples were to be collected within 2 hours prior to dosing. There was no additional source note to explain why the study drugs were not administered in the clinic within the required timelines.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Primary Monitor reviewed the Protocol Deviation log while on site on 02Apr2025 and did find the following deviation filed: Patient 10041006 took IP dose greater than 2 hours after pre-dose sample collection on C1D1 (07Mar2024) due to patient non compliance. This was a one time occurrence. This deviation was signed by QI on 02April2025 who checked it as Not reportable to the IRB.Siebel CTMS has been updated as well. Issue fully resolved. | The Clinical Research Associate (CRA) and Clinical Team Manager (CTM) held a meeting with Primary Study Coordinator, Data Manager and Regulatory Coordinator on 14Feb2025 and site confirmed the protocol deviation for C1D1 PKs samples obtained greater than 2 hours from the first dosing will be captured as a protocol deviation and reported to IRB if meet reporting criteria. Site was asked to provide the submission letter to CRA, and CRA will update Protocol Deviation Log in Siebel CTMS once documentation has been received.With regards the first dosing being taken without supervision of site personnel, site clarified the typical process for C1D1 is to obtain pre dose PK/other samples, and then subject is instructed to go to the pharmacy for IP dispensing. There is no clear documentation in the source the reason for first dosing been taken at home. During the meeting, site has been re-trained to comply with protocol requirements with regards IP administration. This is the only occurrence from 6 enrolled patients, in addition, additional D1 of cycles from subject 10041006 were compliant with this requirement. Responsible Role: Primary Study Coordinator, Clinical Research Associate | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | Protocol Deviations | Failure to follow protocol | CT40 - Protocol Deviations | PRINCIPAL INVESTIGATOR | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-005598 | QE-160016 | 2025-02-28 | 2025-02-28 |  | Completed On Time |  | Minor |  | Hilton, John | CANADA | C4891006_1004 | GCP Site Audit | 2025-01-23 |  | For 1 of 3 patients reviewed, there was a delay in the reporting of safety evaluations and safety evaluations were inconsistent with electronic Case Report Forms (eCRF) (Pfizer Protocol C4891006, Amendment 3, dated 17 Jul 2023). Patient 10041001: a. The Emergency Department record dated 01 Mar 2024 noted the patient fell and reported a sore right foot as a result. Neither the fall or the pain in the right foot had been reported as adverse events (AE) in the source records or entered in the eCRF. A serious adverse event (SAE) of Transient Ischemic Attack (TIA) was reported to the sponsor on 01 Mar 2024 (same date as awareness of the SAE) and the fall occurred as a result of the TIA. b. The source records for the AEs of Nausea (29-30 Oct 2023) and Vomiting (30 Oct 2023) indicated that both AEs were related to 'URTI'; however, Unknown was entered in the electronic case report form (eCRF). c. The SAE report dated 01 Mar 2024 indicated the event (TIA) was considered serious due to hospitalized/prolongation of hospitalization; however, the patient was seen in the Emergency Department only and discharged the same day without admission to the hospital. The Principal Investigator confirmed that the event would be considered serious as it was an important medical event. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | As per comments under Description field, all corrections have been done. | Patient 10041001:a. The Emergency Department record dated 01 Mar 2024 noted the patient fell and reported a sore right foot as a result. Neither the fall or the pain in the right foot had been reported as adverse events (AE) in the source records or entered in the eCRF. A serious adverse event (SAE) of Transient Ischemic Attack (TIA) was reported to the sponsor on 01 Mar 2024 (same date as awareness of the SAE) and the fall occurred as a result of the TIA. During the meeting held on 14Feb2025, Primary Study Coordinator (SC) confirmed that she had entered non serious Fall adverse event (AE ) (start 29Feb2024- Stop 29Feb2024) on AE log with late entry on 17Jan2025. EDC has been updated and verified by CRA. As per site response on 28Feb2025, for the sore right foot, site was not able to obtain relevant dates from patient given how long ago this was, therefore, this is not being considered reportable.b. The source records for the AEs of Nausea (29-30 Oct 2023) and Vomiting (30 Oct 2023) indicated that both AEs were related to 'URTI'; however, Unknown was entered in the electronic case report form (eCRF).The Clinical Research Associate (CRA) verified that electronic Case Report Form (eCRF) was corrected by the Data Manager on 27Jan2025.c. The SAE report dated 01 Mar 2024 indicated the event (TIA) was considered serious due to hospitalized/prolongation of hospitalization; however, the patient was seen in the Emergency Department only and discharged the same day without admission to the hospital. The Principal Investigator confirmed that the event would be considered serious as it was an important medical event.The CRA and Clinical Trial Manager (CTM) had a discussion on 14Feb2025, and the Primary Study Coordinator confirmed that she will discuss this SAE with Principal Investigator and inform the CRA and CTM of the outcome. The Data Manager updated the seriousness criteria of SAE as being medically important event per PI discretion, this has been updated in eCRF. Follow up SAE form submitted thru PSSA (Pfizer SAE Submission Assistant) application on 14Feb2025, to update seriousness criteria from Hospitalization to Important Medical Event. | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | AE reporting to Sponsor | Incomplete AE reporting | AEM01 - Adverse Event Monitoring | PRINCIPAL INVESTIGATOR | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-005598 | QE-160015 | 2025-03-21 | 2025-03-21 |  | Completed On Time |  | Minor |  | Hilton, John | CANADA | C4891006_1004 | GCP Site Audit | 2025-01-23 |  | Twenty-nine essential documents were missing in the Investigator Site File or were not personally dated by the individual signing the document (ISF) [ICH GCP E6 (R2) 4.9.4]. 1. The following documents could not be located in the ISF: a. The Investigator Protocol Acceptance Form for the final approved protocol (version dated 14 Jun 2022) was filed in the ISF and signed by the Principal Investigator (PI) and was dated 'Sept. 14, 2022' by another individual. The version filed in the Pfizer Trial Master File was signed and dated by the PI on 18 Oct 2022. The 18 Oct 2022 version of the form was not filed in the ISF. b. The Monitoring Visit Follow-up Letter dated 12 Oct 2023 for the virtual visit conducted on 21 Sep 2023. 2. The following documents were signed by the Investigators; however, the date of signature had been populated by another individual, so it was unclear if the documents were signed on the date indicated. For example: a. Personal Data Consent Forms: Nine of 11 forms were dated 14 Sep 2022 by someone other than the Investigator signing the document. b. The Arvinas Privacy Notice for Staff Members of the Trial Site: 19 Sep 2022 had been populated on the form for the Principal Investigator; 14 Sep 2022 was populated for seven Sub-Investigators. c. Financial Disclosure Forms: Ten of 13 forms were electronically dated 20 Jul 2022 and not personally dated by the Investigators who had signed the form. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | With regards to finding "2", please find attached the email sent to Regulatory team by Quality Assurance Specialist on 27Jan2025, with purpose of re-training the team on the essential documents not personally dated by the individual signing the document. | a. The Investigator Protocol Acceptance Form for the final approved protocol (version dated 14 Jun 2022) was filed in the ISF and signed by the Principal Investigator (PI) and was dated 'Sept. 14, 2022' by another individual. The version filed in the Pfizer Trial Master File was signed and dated by the PI on 18 Oct 2022. The 18 Oct 2022 version of the form was not filed in the ISF.During the Monitoring visit on 27Jan2025, Clinical Research Associate (CRA) confirmed Protocol Acceptance Form dated 18Oct2022 has been filed in Investigator Site File (ISF).b. The Monitoring Visit Follow-up Letter dated 12 Oct 2023 for the virtual visit conducted on 21 Sep 2023.Follow up letter has been sent to site on 26-Feb-2025 with instructions to file them in ISF. 2. The following documents were signed by the Investigators; however, the date of signature had been populated by another individual, so it was unclear if the documents were signed on the date indicated.During the meeting held on 14Feb2025, regulatory coordinator clarified the regulatory team has been re-trained on signature process for essential documents. Site was asked to produce a Note to File or share the email distributed internally with instructions. | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | Document Management | Missing document | CT01 - Trial Master Files | SITE PERSONNEL | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-005598 | QE-160014 | 2025-02-28 | 2025-02-28 |  | Completed On Time |  | Minor |  | Hilton, John | CANADA | C4891006_1004 | GCP Site Audit | 2025-01-23 |  | For 2 of 3 patients reviewed, electronic Case Report Form (eCRF) data was inconsistent with source documentation [ICH GCP E6 (R2) 4.9.1; 4.9.2]. 1. Patient 10041001: a. The Breast Cancer History source record indicated the patient received Arimidex from 'Sept 2005 to 4 Aug 2011'; however, the eCRF indicated a start date of 'Aug 2005'. b. The Medical History source record indicated the patient had a 'TIA' with a start date of '2006' and no end date noted. The eCRF indicated an end date of UNK/UNK/2006. 2. Patient 10041006: The Concomitant Medication Log indicated a start date of 22 Apr 2024 for Reactine (Cetirizine noted in eCRF), but 20 Apr 2024 had been entered in the eCRF. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Corrections have been completed as per comments in Description field. | 1. Patient 10041001:a. The Breast Cancer History source record indicated the patient received Arimidex from 'Sept 2005 to 4 Aug 2011'; however, the eCRF indicated a start date of 'Aug 2005'. The Clinical Research Associate (CRA) reviewed the entry in electronic Case Report Form (eCRF) and queried site to update the end date of Arimidex. It was corrected by the Data Manager and was verified by the CRA on 27Jan2025, during the Monitoring Visit. b. The Medical History source record indicated the patient had a 'TIA' with a start date of '2006' and no end date noted. The eCRF indicated an end date of UNK/UNK/2006.The CRA verified on 27Jan2025 that the Data Manager had updated the baseline sheet with end date 2006, late entry made on 16Jan2025.2. Patient 10041006: The Concomitant Medication Log indicated a start date of 22 Apr 2024 for Reactine (Cetirizine noted in eCRF), but 20 Apr 2024 had been entered in the eCRF.The CRA verified on 27Jan2025 that the data manager had corrected the start date 22Apr2024 in eCRF. | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | DMB03-GSOP - Data Management | SITE PERSONNEL | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-002720 | QE-108828 | 2024-05-24 | 2024-05-27 |  | Complete Late |  | Minor |  | Ma, Cynthia | UNITED STATES | C4891006_1006 | GCP Site Audit | 2024-04-12 |  | System User Account Management associated with the Electronic Data Capture (EDC) system, InForm, was not managed appropriately [ICH GCP E6 (R2) 5.5.3] 1. One site staff member was not assigned to perform CRF Completion duties; however, this individual had an active InForm account.&nbsp; a. Clinic Coordinator | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | CAPA: corrective and preventive actions- Site produced a NTF to document the “Case Report Form” delegation was erroneously omitted from Ms. Halim’s original Delegation of Authority Log entry. Upon discovery of this error, her original DOA entry was lined through, and a new entry was added. - A Note to File dated 22Apr2024 to document this corrective action has been collected.- Site was retrained to review the DOA log vs. delegated tasks and ensure required system access is available for site staff who are actively involved with the study. Re-training date 14May2024, during the regular Monitoring Visit.- In addition, the study monitors were reminded to reconcile the DOA against the tasks delegated and the respective trainings and systems access are granted. Date of training 17May2024, during the study Team call. | Finding 3: Description: System User Account Management associated with the Electronic Data Capture (EDC) system, InForm, was not managed appropriately [ICH GCP E6 (R2) 5.5.3]1. One site staff member was not assigned to perform CRF Completion duties; however, this individual had an active InForm account. a. Clinic Coordinator | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) | CP403 - Acceptable Use of Information | VENDOR / CONTRACTOR | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-002720 | QE-109183 | 2024-05-24 | 2024-05-27 |  | Complete Late |  | Minor |  | Ma, Cynthia | UNITED STATES | C4891006_1006 | GCP Site Audit | 2024-04-12 |  | Issues related to Principal Investigator (PI) oversight, training of site staff, and inaccuracies on the Site Delegation of Authority (DoA) Log were identified. [ICH GCP E6 (R2) 4.1.5, 4.2.4, 4.3.1] 1. It was found that three site staff members who were assigned to perform Case Report Form (CRF) completion duties lacked the necessary InForm training and active Inform accounts.&nbsp; 2. The Site DoA Log contained inaccuracies, with duties being delegated to staff members who did not have the appropriate training or system access. Specifically, 25 staff members were assigned Interactive Voice Response System (IVRS) activities but did not have an active IMPALA account. Additionally, three staff members were assigned CRF completion duties but did not have an active InForm account. 3. There was a lack of PI and/or Sub-Investigator oversight related to the assessment of Inclusion/Exclusion criteria. The forms related to these criteria were completed by two Study Coordinators, but there was no way to verify which Study Coordinator(s) completed these assessments due to a lack of attributability on the forms. This made it difficult to ensure that the assessments were adequately performed by a qualified medical professional.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Findings 4.1 and 4.2CAPA: corrective and preventive actions- Not applicable as this is in compliance with site process. Finding 4.3:CAPA: corrective and preventive actions- A NTF will be added to each chart to clarify who did which eligibility check in which color ink. - All future eligibility review done will clearly indicated who completed the review and QC Check.- In addition, the Study Monitors were reminded to review the source and ensure there is evidence that a qualified medical professional has reviewed the patient eligibility prior to enrollment. Ensure site has a robust process for eligibility review, and ensure the data is attributable. Date of training 17May2024 during the Study Team meeting. | Finding 4:Description: Issues related to Principal Investigator (PI) oversight, training of site staff, and inaccuracies on the Site Delegation of Authority (DoA) Log were identified. [ICH GCP E6 (R2) 4.1.5, 4.2.4, 4.3.1]1. It was found that three site staff members who were assigned to perform Case Report Form (CRF) completion duties lacked the necessary InForm training and active Inform accounts.2. The Site DoA Log contained inaccuracies, with duties being delegated to staff members who did not have the appropriate training or system access. Specifically, 25 staff members were assigned Interactive Voice Response System (IVRS) activities but did not have an active IMPALA account. Additionally, three staff members were assigned CRF completion duties but did not have an active InForm account.3. There was a lack of PI and/or Sub-Investigator oversight related to the assessment of Inclusion/Exclusion criteria.The forms related to these criteria were completed by two Study Coordinators, but there was no way to verify which Study Coordinator(s) completed these assessments due to a lack of attributability on the forms. This made it difficult to ensure that the assessments were adequately performed by a qualified medical professional. | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | Quality Oversight | Inadequate Principal Investigator quality oversight | NOT APPLICABLE; NOT APPLICABLE | PRINCIPAL INVESTIGATOR | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-002720 | QE-108827 | 2024-05-24 | 2024-05-27 |  | Complete Late |  | Minor |  | Ma, Cynthia | UNITED STATES | C4891006_1006 | GCP Site Audit | 2024-04-12 |  | For 2 of 3 participants, Protocol deviations were identified at the site [Pfizer Protocol C4891006 (Amendment 3: 17 Jul 2023)]&nbsp; 1. Participant 10061004 a. Cycle 3 Day 1 (19 Oct 2023): Blood Sample for Pharmacodynamics (PD) post-dose was not collected for this visit.&nbsp; b. Cycle 7 Day 1 (08 Feb 2024): Pharmacokinetics blood draws were not collected for this visit 2. Participant 10061005 a. End of Treatment (01 Feb 2024): Circulating tumor DNA (ctDNA) sample was not collected for this visit.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Findings 2.2.a:CAPA: corrective and preventive actions-Site was retrained to always review the lab kit inventory (both regular visit kits and non-visit specific kits) and ensure they have valid kits for samples per SOA. Site retraining documented through the monitoring visit report dated May 14, 2024-Site entered ctDNA collection dated 15Feb2024 in EDC -Protocol deviation for collecting ctDNA not according to SOA has been added in Siebel.-Study Monitors were retrained to always review and discuss with sites the lab kits inventory during the IMVs and/or Site Management calls. Re-training was done at the Study Team call held on 17May2024. | Finding 2:Description: For 2 of 3 participants, Protocol deviations were identified at the site [Pfizer Protocol C4891006 (Amendment 3: 17 Jul2023)]2. Participant 10061005a. End of Treatment (01 Feb 2024): Circulating tumor DNA (ctDNA) sample was not collected for this visit. | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | Protocol Deviations | Failure to follow protocol | CT40 - Protocol Deviations | SITE PERSONNEL | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-002720 | QE-108826 | 2024-05-24 | 2024-05-27 |  | Complete Late |  | Minor |  | Ma, Cynthia | UNITED STATES | C4891006_1006 | GCP Site Audit | 2024-04-12 |  | Source Documentation was not legible and incomplete for 1 of 3 Participants [Pfizer Protocol C4891006 (Amendment 3: 17 Jul 2023) and ICH GCP E6 (R2) 2.10, 4.9.0] 1. Participant 10061002: Source documentation found in the Participant's medical chart was difficult to read and not legible. For example, the site utilized Adverse Event (AE) forms where Coordinator(s) were documenting AEs, severity and start/stop dates; however, this information was at times illegible and difficult to read.&nbsp; 2. Participant 10061002: Source documentation related to five of the Participant's Dosing Diary was left incomplete by the site staff. Examples include missing signatures of site staff and no dispensation date recorded on the diaries by the site staff. The following diaries were found to be incomplete. a. Cycle 1 Diary (date range: 17 to 31 Mar 2023): No site signature and dispensation date from pages 02 to 14; Pages 13 and 14 were left blank/unanswered.&nbsp; b. Cycle 3 Diary (date range: 10 May to 07 Jun 2023): Site signature missing and Pages 11 and 12 were left blank/unanswered.&nbsp; c. Cycle 5 Diary (date range: 05 Jul to 02 Aug 2023): Pages 11 and 12 were left blank/unanswered. d. Cycle 6 Diary (date range: 09 Aug to 06 Sep 2023): Site signature missing and Pages 11 and 12 were left blank/unanswered. e. Cycle 7 Diary (date range: 06 Sep to 04 Oct 2023): Site signature missing and Pages 11 and 12 were left blank/unanswered. &nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Finding 1.1:CAPA: corrective and preventive actions-This issue was addressed during the course of the trial and the coordinators’ handwriting did improve. Coordinator has been reminded again about importance of writing clearly. A note to file documenting this retraining has been provided. Note to File date 13May2024.Study Monitors were also reminded to discuss with sites when source documentation is not legible or corrections are not done following GCP requirements. Retraining date 17May2024, during the Study Team meeting.Finding 1.2:CAPA: corrective and preventive actions- Site acknowledged items were missing from the diary. This discussed this with the auditor and the Note to File was made available to the auditor for review during the audit. - A note to file documenting retraining of SC to fill out all necessary fields in diaries has been obtained. Note to File date 28Feb2024.- In addition, once CRA noted the patient trend to not return diaries and/or IP bottles at the next study visit, an email has been sent to PI and site on 12Jul2023 reinforcing the importance to re-educate the patient to bring the diaries and IP bottles to ensure drug accountability and IP compliance review is done as per protocol. | 1. Participant 10061002: Source documentation found in the Participant's medical chart was difficult to read and not legible. For example, the site utilized Adverse Event (AE) forms where Coordinator(s) were documenting AEs, severity and start/stop dates; however, this information was at times illegible and difficult to read. 2. Participant 10061002: Source documentation related to five of the Participant's Dosing Diary was left incomplete by the site staff. Examples include missing signatures of site staff and no dispensation date recorded on the diaries by the site staff. The following diaries were found to be incomplete. a. Cycle 1 Diary (date range: 17 to 31 Mar 2023): No site signature and dispensation date from pages 02 to 14; Pages 13 and 14 were left blank/unanswered.b. Cycle 3 Diary (date range: 10 May to 07 Jun 2023): Site signature missing and Pages 11 and 12 were left blank/unanswered.c. Cycle 5 Diary (date range: 05 Jul to 02 Aug 2023): Pages 11 and 12 were left blank/unanswered.d. Cycle 6 Diary (date range: 09 Aug to 06 Sep 2023): Site signature missing and Pages 11 and 12 were left blank/unanswered.e. Cycle 7 Diary (date range: 06 Sep to 04 Oct 2023): Site signature missing and Pages 11 and 12 were left blank/unanswered. | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | Data Collection and Management | Inadequate source data/documentation | NOT APPLICABLE; NOT APPLICABLE | SITE PERSONNEL | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-002720 | QE-109188 | 2024-05-24 | 2024-05-27 |  | Complete Late |  | Minor |  | Ma, Cynthia | UNITED STATES | C4891006_1006 | GCP Site Audit | 2024-04-12 |  | Monitoring Activities were not completed per the Study Monitoring Plan and were insufficient to identify and/or address issues reported in other sections of this audit report [Pfizer Monitoring Plan C4891006 (Version 3: 19 Apr 2023) and Pfizer Protocol C4891006 (Amendment 3: 17 Jul 2023)]&nbsp; This included:&nbsp; 1. Failure to identify potential protocol deviations and maintaining the Protocol Deviation Log found in Pfizer Operational Data Reports (ODR) system (Observation: QE-108827) 2. Source data that were identified to be illegible and or incomplete (Observation: QE-108826) 3. Failure to ensure appropriate system management of InForm (Observation: QE-108828) 4. Failure to ensure qualified medical professionals provided documented oversight on the review of Inclusion/Exclusion Forms (Observation: QE-109183) | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Finding 5.1 Failure to identify potential protocol deviations and maintaining the Protocol Deviation Log found in Pfizer Operational Data Reports (ODR) system (Observation: QE-108827)CAPA: corrective and preventive actions-Protocol deviation for collecting ctDNA not according to SOA has been added in Siebel.-Study Monitors were retrained to always review and discuss with sites the lab kits inventory during the IMVs and/or Site Management calls. Re-training was done at the Study Team call held on 17May2024.Finding 5.2 Source data that were identified to be illegible and or incomplete (Observation: QE-108826)CAPA: corrective and preventive actionsStudy Monitors were also reminded to discuss with sites when source documentation is not legible, or corrections are not done following GCP requirements. Retraining date 17May2024, during the Study Team meeting.Finding 5.3 Failure to ensure appropriate system management of InForm (Observation: QE-108828)CAPA: corrective and preventive actions-The study monitors were reminded to reconcile the DOA against the tasks delegated and the respective trainings and systems access are granted. Date of training 17May2024, during the study Team call.Finding 5.4 Failure to ensure qualified medical professionals provided documented oversight on the review of Inclusion/Exclusion Forms (Observation: QE-109183)CAPA: corrective and preventive actions-All future eligibility review done will clearly indicated who completed the review and QC Check.-In addition, the Study Monitors were reminded to review the source and ensure there is evidence that a qualified medical professional has reviewed the patient eligibility prior to enrollment. Ensure site has a robust process for eligibility review, and ensure the data is attributable. Date of training 17May2024 during the Study Team meeting. | Finding 5 Description: Monitoring Activities were not completed per the Study Monitoring Plan and were insufficient to identify and/or address issues reported in other sections of this audit report [Pfizer Monitoring Plan C4891006 (Version 3: 19 Apr 2023) and Pfizer Protocol C4891006 (Amendment 3: 17 Jul 2023)]This included:1. Failure to identify potential protocol deviations and maintaining the Protocol Deviation Log found in Pfizer Operational Data Reports (ODR) system (Observation: QE-108827)2. Source data that were identified to be illegible and or incomplete (Observation: QE-108826)3. Failure to ensure appropriate system management of InForm (Observation: QE-108828)4. Failure to ensure qualified medical professionals provided documented oversight on the review ofInclusion/Exclusion Forms (Observation: QE-109183) | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | Site Management and Monitoring | Failure to detect/document | INV04 - Investigational Site Management and Monitoring | VENDOR / CONTRACTOR | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS