## Standard_Quality_Dashboard - SQ
Case ID | Case Status | Observation ID | Obs Status | Submission Date | Issue Audit Report (Actual) | Center Number | principal investigator | Country | Description | Study ID | Protocol ID | Title Short Description | Drug Program Code | Rating | Event Type | Case CAPA Approved Due Date | Case CAPA Approved On | CAPA Plan In Place Timely | Obs CAPA Approved Due Date | Obs CAPA Approved On | Obs Target Completion Date | Obs Actual Completion Date | Case CAPA Closure Timely | Case Target Completion Date | Case Actual Completion Date | Obs CAPA Closure Timely | Selected Business Process | Taxonomy Level 1 | Taxonomy Level 2 | Study Status | Business Category | Study Phase | Study Priority | Asset | Dev China | Dev Japan | Rapid Model | Business Category
AIA-002720 | Closed | QE-108826 | Closed | (Empty) | 2024-04-12 | 1006 | (Empty) | UNITED STATES | Source Documentation was not legible and incomplete for 1 of 3 Participants [Pfizer Protocol C4891006 (Amendment 3: 17 Jul 2023) and ICH GCP E6 (R2) 2.10, 4.9.0] 1. Participant 10061002: Source documentation found in the Participant's medical chart was difficult to read and not legible. For example, the site utilized Adverse Event (AE) forms where Coordinator(s) were documenting AEs, severity and start/stop dates; however, this information was at times illegible and difficult to read.&nbsp; 2. Participant 10061002: Source documentation related to five of the Participant's Dosing Diary was left incomplete by the site staff. Examples include missing signatures of site staff and no dispensation date recorded on the diaries by the site staff. The following diaries were found to be incomplete. a. Cycle 1 Diary (date range: 17 to 31 Mar 2023): No site signature and dispensation date from pages 02 to 14; Pages 13 and 14 were left blank/unanswered.&nbsp; b. Cycle 3 Diary (date range: 10 May to 07 Jun 2023): Site signature missing and Pages 11 and 12 were left blank/unanswered.&nbsp; c. Cycle 5 Diary (date range: 05 Jul to 02 Aug 2023): Pages 11 and 12 were left blank/unanswered. d. Cycle 6 Diary (date range: 09 Aug to 06 Sep 2023): Site signature missing and Pages 11 and 12 were left blank/unanswered. e. Cycle 7 Diary (date range: 06 Sep to 04 Oct 2023): Site signature missing and Pages 11 and 12 were left blank/unanswered. &nbsp; | C4891006 | C4891006 | A Routine Investigator Site Audit of Study C4891006, Site 1006, Dr. Cynthia Ma, St. Louis, Missouri, USA | (Empty) | Minor | AUDIT | 2024-05-24 | (Empty) | N | (Empty) | (Empty) | 2024-05-24 | 2024-05-27 | N | 2024-05-24 | 2024-05-27 | N | NOT APPLICABLE; NOT APPLICABLE | Data Collection and Management | Inadequate source data/documentation | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
AIA-002720 | Closed | QE-108827 | Closed | (Empty) | 2024-04-12 | 1006 | (Empty) | UNITED STATES | For 2 of 3 participants, Protocol deviations were identified at the site [Pfizer Protocol C4891006 (Amendment 3: 17 Jul 2023)]&nbsp; 1. Participant 10061004 a. Cycle 3 Day 1 (19 Oct 2023): Blood Sample for Pharmacodynamics (PD) post-dose was not collected for this visit.&nbsp; b. Cycle 7 Day 1 (08 Feb 2024): Pharmacokinetics blood draws were not collected for this visit 2. Participant 10061005 a. End of Treatment (01 Feb 2024): Circulating tumor DNA (ctDNA) sample was not collected for this visit.&nbsp; | C4891006 | C4891006 | A Routine Investigator Site Audit of Study C4891006, Site 1006, Dr. Cynthia Ma, St. Louis, Missouri, USA | (Empty) | Minor | AUDIT | 2024-05-24 | (Empty) | N | (Empty) | (Empty) | 2024-05-24 | 2024-05-27 | N | 2024-05-24 | 2024-05-27 | N | CT40 - Protocol Deviations | Protocol Deviations | Failure to follow protocol | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
AIA-002720 | Closed | QE-108828 | Closed | (Empty) | 2024-04-12 | 1006 | (Empty) | UNITED STATES | System User Account Management associated with the Electronic Data Capture (EDC) system, InForm, was not managed appropriately [ICH GCP E6 (R2) 5.5.3] 1. One site staff member was not assigned to perform CRF Completion duties; however, this individual had an active InForm account.&nbsp; a. Clinic Coordinator | C4891006 | C4891006 | A Routine Investigator Site Audit of Study C4891006, Site 1006, Dr. Cynthia Ma, St. Louis, Missouri, USA | (Empty) | Minor | AUDIT | 2024-05-24 | (Empty) | N | (Empty) | (Empty) | 2024-05-24 | 2024-05-27 | N | 2024-05-24 | 2024-05-27 | N | CP403 - Acceptable Use of Information | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
AIA-002720 | Closed | QE-109183 | Closed | (Empty) | 2024-04-12 | 1006 | (Empty) | UNITED STATES | Issues related to Principal Investigator (PI) oversight, training of site staff, and inaccuracies on the Site Delegation of Authority (DoA) Log were identified. [ICH GCP E6 (R2) 4.1.5, 4.2.4, 4.3.1] 1. It was found that three site staff members who were assigned to perform Case Report Form (CRF) completion duties lacked the necessary InForm training and active Inform accounts.&nbsp; 2. The Site DoA Log contained inaccuracies, with duties being delegated to staff members who did not have the appropriate training or system access. Specifically, 25 staff members were assigned Interactive Voice Response System (IVRS) activities but did not have an active IMPALA account. Additionally, three staff members were assigned CRF completion duties but did not have an active InForm account. 3. There was a lack of PI and/or Sub-Investigator oversight related to the assessment of Inclusion/Exclusion criteria. The forms related to these criteria were completed by two Study Coordinators, but there was no way to verify which Study Coordinator(s) completed these assessments due to a lack of attributability on the forms. This made it difficult to ensure that the assessments were adequately performed by a qualified medical professional.&nbsp; | C4891006 | C4891006 | A Routine Investigator Site Audit of Study C4891006, Site 1006, Dr. Cynthia Ma, St. Louis, Missouri, USA | (Empty) | Minor | AUDIT | 2024-05-24 | (Empty) | N | (Empty) | (Empty) | 2024-05-24 | 2024-05-27 | N | 2024-05-24 | 2024-05-27 | N | NOT APPLICABLE; NOT APPLICABLE | Quality Oversight | Inadequate Principal Investigator quality oversight | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
AIA-002720 | Closed | QE-109188 | Closed | (Empty) | 2024-04-12 | 1006 | (Empty) | UNITED STATES | Monitoring Activities were not completed per the Study Monitoring Plan and were insufficient to identify and/or address issues reported in other sections of this audit report [Pfizer Monitoring Plan C4891006 (Version 3: 19 Apr 2023) and Pfizer Protocol C4891006 (Amendment 3: 17 Jul 2023)]&nbsp; This included:&nbsp; 1. Failure to identify potential protocol deviations and maintaining the Protocol Deviation Log found in Pfizer Operational Data Reports (ODR) system (Observation: QE-108827) 2. Source data that were identified to be illegible and or incomplete (Observation: QE-108826) 3. Failure to ensure appropriate system management of InForm (Observation: QE-108828) 4. Failure to ensure qualified medical professionals provided documented oversight on the review of Inclusion/Exclusion Forms (Observation: QE-109183) | C4891006 | C4891006 | A Routine Investigator Site Audit of Study C4891006, Site 1006, Dr. Cynthia Ma, St. Louis, Missouri, USA | (Empty) | Minor | AUDIT | 2024-05-24 | (Empty) | N | (Empty) | (Empty) | 2024-05-24 | 2024-05-27 | N | 2024-05-24 | 2024-05-27 | N | INV04 - Investigational Site Management and Monitoring | Site Management and Monitoring | Failure to detect/document | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
AIA-005598 | Closed | QE-160012 | Closed | (Empty) | 2025-01-23 | 1004 | (Empty) | CANADA | Protocol non‑compliance was identified for 1 of 3 patients reviewed (Pfizer Protocol C4891006, Amendment 3, dated 17 Jul 2023). Patient 10041006: The Cycle 1/Day 1 (07 Mar 2024) pre-dose Pharmacokinetic (PK) samples were collected at 09:38, but the time of dosing of Vepdegestrant (ARV-471) and Abemaciclib was not indicated on the Pharmacology Work Sheet. The dosing diary indicated that the patient self administered both study drugs at 14:30, after 'arriving home at 2:PM'. As per the protocol, on ARV-471 and Abemaciclib PK sampling days, the study drug doses should be taken in the clinic under the supervision of the study site personnel and pre-dose samples were to be collected within 2 hours prior to dosing. There was no additional source note to explain why the study drugs were not administered in the clinic within the required timelines.&nbsp; | C4891006 | C4891006 | A Routine Investigator Site Audit of C4891006, Site 1004, Dr. John Hilton, Ottawa, Ontario, Canada | (Empty) | Minor | AUDIT | 2025-03-06 | (Empty) | N | (Empty) | (Empty) | 2025-03-21 | 2025-04-02 | N | 2025-03-21 | 2025-04-02 | N | CT40 - Protocol Deviations | Protocol Deviations | Failure to follow protocol | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
AIA-005598 | Closed | QE-160013 | Closed | (Empty) | 2025-01-23 | 1004 | (Empty) | CANADA | For 3 of 3 patients reviewed, source documents were not in accordance with the ALCOACCEA criteria (Accurate, Legible, Contemporaneous, Original, Attributable, Complete, Consistent, Enduring, &amp; Available) (Pfizer Protocol C4891006, Amendment 3, dated 17 Jul 2023). 1. The following issues were identified with respect to incomplete source documentation: a. Patient 10041001: The source records included a Medical History note by the Study Coordinator (SC) dated 18 Apr 2023; however, the note did not contain a patient or study identifier. b. Patient 10041003: Two Breast Cancer/Medical History source notes were filed in the patient's chart; however, neither note contained a study or patient identifier and one note had not been signed or dated by the SC.&nbsp; c. Patient 10041006: The source records included a Medical History note which was not signed or dated by the individual completing the note and did not contain a patient or study identifier. 2. The following issue was identified with respect to consistency of data:&nbsp; Patient 10041003: The 'Tumour Assessment Form-RECIST 1.1' indicated the date of imaging for the Baseline measurements as 18 Nov 2023; however, the Computerized Tomography report indicated the procedure was conducted on 08 Nov 2023. 3. The following issue was identified with respect to attributability of data:&nbsp; Patient 10041006: The Pharmacology Work Sheet (Cycle 1/Day 1) 07 Mar 2024 entry was initialed by the Pharmacology Nurse; however, the initials did not match the initials noted on the Signature Sheet and Delegation of Duties Log. | C4891006 | C4891006 | A Routine Investigator Site Audit of C4891006, Site 1004, Dr. John Hilton, Ottawa, Ontario, Canada | (Empty) | Minor | AUDIT | 2025-03-06 | (Empty) | N | (Empty) | (Empty) | 2025-03-21 | 2025-03-21 | N | 2025-03-21 | 2025-04-02 | Y | NOT APPLICABLE; NOT APPLICABLE | Data Collection and Management | Inadequate source data/documentation | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
AIA-005598 | Closed | QE-160014 | Closed | (Empty) | 2025-01-23 | 1004 | (Empty) | CANADA | For 2 of 3 patients reviewed, electronic Case Report Form (eCRF) data was inconsistent with source documentation [ICH GCP E6 (R2) 4.9.1; 4.9.2]. 1. Patient 10041001: a. The Breast Cancer History source record indicated the patient received Arimidex from 'Sept 2005 to 4 Aug 2011'; however, the eCRF indicated a start date of 'Aug 2005'. b. The Medical History source record indicated the patient had a 'TIA' with a start date of '2006' and no end date noted. The eCRF indicated an end date of UNK/UNK/2006. 2. Patient 10041006: The Concomitant Medication Log indicated a start date of 22 Apr 2024 for Reactine (Cetirizine noted in eCRF), but 20 Apr 2024 had been entered in the eCRF. | C4891006 | C4891006 | A Routine Investigator Site Audit of C4891006, Site 1004, Dr. John Hilton, Ottawa, Ontario, Canada | (Empty) | Minor | AUDIT | 2025-03-06 | (Empty) | N | (Empty) | (Empty) | 2025-02-28 | 2025-02-28 | N | 2025-03-21 | 2025-04-02 | Y | DMB03-GSOP - Data Management | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
AIA-005598 | Closed | QE-160015 | Closed | (Empty) | 2025-01-23 | 1004 | (Empty) | CANADA | Twenty-nine essential documents were missing in the Investigator Site File or were not personally dated by the individual signing the document (ISF) [ICH GCP E6 (R2) 4.9.4]. 1. The following documents could not be located in the ISF: a. The Investigator Protocol Acceptance Form for the final approved protocol (version dated 14 Jun 2022) was filed in the ISF and signed by the Principal Investigator (PI) and was dated 'Sept. 14, 2022' by another individual. The version filed in the Pfizer Trial Master File was signed and dated by the PI on 18 Oct 2022. The 18 Oct 2022 version of the form was not filed in the ISF. b. The Monitoring Visit Follow-up Letter dated 12 Oct 2023 for the virtual visit conducted on 21 Sep 2023. 2. The following documents were signed by the Investigators; however, the date of signature had been populated by another individual, so it was unclear if the documents were signed on the date indicated. For example: a. Personal Data Consent Forms: Nine of 11 forms were dated 14 Sep 2022 by someone other than the Investigator signing the document. b. The Arvinas Privacy Notice for Staff Members of the Trial Site: 19 Sep 2022 had been populated on the form for the Principal Investigator; 14 Sep 2022 was populated for seven Sub-Investigators. c. Financial Disclosure Forms: Ten of 13 forms were electronically dated 20 Jul 2022 and not personally dated by the Investigators who had signed the form. | C4891006 | C4891006 | A Routine Investigator Site Audit of C4891006, Site 1004, Dr. John Hilton, Ottawa, Ontario, Canada | (Empty) | Minor | AUDIT | 2025-03-06 | (Empty) | N | (Empty) | (Empty) | 2025-03-21 | 2025-03-21 | N | 2025-03-21 | 2025-04-02 | Y | CT01 - Trial Master Files | Document Management | Missing document | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
AIA-005598 | Closed | QE-160016 | Closed | (Empty) | 2025-01-23 | 1004 | (Empty) | CANADA | For 1 of 3 patients reviewed, there was a delay in the reporting of safety evaluations and safety evaluations were inconsistent with electronic Case Report Forms (eCRF) (Pfizer Protocol C4891006, Amendment 3, dated 17 Jul 2023). Patient 10041001: a. The Emergency Department record dated 01 Mar 2024 noted the patient fell and reported a sore right foot as a result. Neither the fall or the pain in the right foot had been reported as adverse events (AE) in the source records or entered in the eCRF. A serious adverse event (SAE) of Transient Ischemic Attack (TIA) was reported to the sponsor on 01 Mar 2024 (same date as awareness of the SAE) and the fall occurred as a result of the TIA. b. The source records for the AEs of Nausea (29-30 Oct 2023) and Vomiting (30 Oct 2023) indicated that both AEs were related to 'URTI'; however, Unknown was entered in the electronic case report form (eCRF). c. The SAE report dated 01 Mar 2024 indicated the event (TIA) was considered serious due to hospitalized/prolongation of hospitalization; however, the patient was seen in the Emergency Department only and discharged the same day without admission to the hospital. The Principal Investigator confirmed that the event would be considered serious as it was an important medical event. | C4891006 | C4891006 | A Routine Investigator Site Audit of C4891006, Site 1004, Dr. John Hilton, Ottawa, Ontario, Canada | (Empty) | Minor | AUDIT | 2025-03-06 | (Empty) | N | (Empty) | (Empty) | 2025-02-28 | 2025-02-28 | N | 2025-03-21 | 2025-04-02 | Y | AEM01 - Adverse Event Monitoring | AE reporting to Sponsor | Incomplete AE reporting | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-103298 | Closed | QE-103298 | Closed | 2024-03-11 | (Empty) | (Empty) | PFIZER | (Empty) | During site 1004's Pfizer C4891001 RQA audit, the Auditor noted there was no evidence that the investigator provided adequate investigational product (IP) instructions to the participants to protect the participants’ caregivers (other than the participants) from the hazardous IP (ARV-471). The C4891001 Global GSM noted the dosing diary and ICD do not contain language pertaining to the proper handling of the hazardous ARV-471 for the caretaker, as it is written in the current IP manual. | C4891006 | C4891006 | GCP_Major_Mar-2024_Multiple C489 Studies: Investigational Product (IP) Handling_Pfizer_Global | C489 | Major | SQE | 2024-07-08 | 2024-07-14 | N | 2024-07-08 | 2024-07-14 23:41 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | IP13 - Study Investigational Product Supplies | Medicinal Product | Inadequate handling, storage, availability | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1003 | Andrew Leavitt (C3731003-1003) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1003 | Andrew Leavitt (C3731003-1003) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1003 | Kieuhoa Vo (A5481092-1003) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1003 | Kieuhoa Vo (A5481092-1003) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1010 | Amy Chien (C4891006-1010) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1010 | Amy Chien (C4891006-1010) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1010 | Amy Chien (C4891023-1010) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1010 | Amy Chien (C4891023-1010) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1010 | Amy Chien (C4891026-1010) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1010 | Amy Chien (C4891026-1010) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1010 | Hope Rugo (A5481173-1010) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1010 | Hope Rugo (A5481173-1010) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1013 | Sofia Verstraete (A3921210-1013) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1013 | Sofia Verstraete (A3921210-1013) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1037 | Hope Rugo (C4551001-1037) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1037 | Hope Rugo (C4551001-1037) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1093 | Andrew Leavitt (C0371002-1093) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1093 | Andrew Leavitt (C0371002-1093) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1425 | Hope Rugo (C4391022-1425) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1425 | Hope Rugo (C4391022-1425) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | (Empty) | ICON PLC | (Empty) | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | (Empty) | ICON PLC | (Empty) | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | (Empty) | PFIZER | (Empty) | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | (Empty) | PFIZER | (Empty) | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | (Empty) | PPD, INC. | (Empty) | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | (Empty) | PPD, INC. | (Empty) | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | (Empty) | SYNEOS HEALTH LLC | (Empty) | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | (Empty) | SYNEOS HEALTH LLC | (Empty) | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891006 | C4891006 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-137900 | Closed | QE-137900 | Closed | 2024-09-13 | (Empty) | (Empty) | PFIZER | (Empty) | Spain and Italy were added to the protocol C4891006 in ARGUS system on 04Sept2024 whereas study was initiated in these countries much earlier (Q1 2024). As per Siebel information the First subject first visit (FSFV) for Spain on 21Feb2024 and FSFV for Italy on 14Jun2024. We would need to investigate the root cause for which both countries, Italy and Spain were not timely notified and added to study configuration in Argus. | C4891006 | C4891006 | SAF_Sep2024_Spain and Italy Added to Study C4891006 Configuration in Argus Later After Study Initiation_Spain_Italy | C489 | Major | SQE | 2024-10-31 | 2024-11-26 | N | 2024-10-31 | 2024-11-26 16:19 | (Empty) | 2025-02-28 | (Empty) | (Empty) | 2025-02-28 | (Empty) | AEM01 - Adverse Event Monitoring | Data Collection and Management | Data management error | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-170101 | Approved - In CAPA | QE-170101 | Approved - In CAPA | 2025-03-14 | (Empty) | 1010 | Amy Chien (C4891023-1010) | UNITED STATES | UCSF Medical Center in California, USA was audited on 11 to 12 Sep2024 for C4891023 study (site 1010) and the auditors were refused onsite access to the pharmacy and some relevant pharmacy records for the study. UCSF personnel stated that as per their SOPs monitors and auditors are not allowed access to the pharmacy. The expected CAPA action for this situation was for UCSF to at allow at least an above study onsite visit to the pharmacy C4891023, C4891026, and C489 1006 as all 3 of these studies have the same issue i.e. UCSF repeatedly denying sponsor monitor and auditors onsite access to the pharmacy. UCSF to date have not allowed onsite visit to their pharmacy hindering the sponsor’s efforts to comply sponsor oversight requirements. The current understanding is that the sponsor has never seen the pharmacy at this facility. UCSF keep providing pre-recorded video of the pharmacy. | C4891006 | C4891006 | GCP_Major_Mar-2025_C489: Failed CAPA: Pharmacy Access_Chien, Amy; University California, San Francisco_USA | C489 | Major | SQE | 2025-05-01 | 2025-07-08 | N | 2025-05-01 | 2025-07-08 14:17 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV04 - Investigational Site Management and Monitoring | Quality Oversight | Inadequate Principal Investigator quality oversight | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-173319 | Approved - In CAPA | QE-173319 | Approved - In CAPA | 2025-04-04 | (Empty) | 1006 | Andrew Davis (C4891024-1006) | UNITED STATES | Site is refusing to now complete Sponsor specific trainings like Suspected Serious Breach and general Safety Standalone trainings in Firecrest per new Site Policy/SOPs that were provided to Pfizer. Alerted the PPD CRO study team who escalated to Pfizer clinical management. | C4891006 | C4891006 | GCP_Major_Apr-2025_C4891006, C4891023, C4891024: Study Training_Multiple PIs (Washington University)_USA | C489 | Major | SQE | 2025-05-22 | 2025-05-23 | N | 2025-05-22 | 2025-05-23 18:35 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT33 - Study-Specific Training | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-173319 | Approved - In CAPA | QE-173319 | Approved - In CAPA | 2025-04-04 | (Empty) | 1006 | Cynthia Ma (C4891006-1006) | UNITED STATES | Site is refusing to now complete Sponsor specific trainings like Suspected Serious Breach and general Safety Standalone trainings in Firecrest per new Site Policy/SOPs that were provided to Pfizer. Alerted the PPD CRO study team who escalated to Pfizer clinical management. | C4891006 | C4891006 | GCP_Major_Apr-2025_C4891006, C4891023, C4891024: Study Training_Multiple PIs (Washington University)_USA | C489 | Major | SQE | 2025-05-22 | 2025-05-23 | N | 2025-05-22 | 2025-05-23 18:35 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT33 - Study-Specific Training | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-173319 | Approved - In CAPA | QE-173319 | Approved - In CAPA | 2025-04-04 | (Empty) | 1006 | Katherine Clifton (C4891023-1006) | UNITED STATES | Site is refusing to now complete Sponsor specific trainings like Suspected Serious Breach and general Safety Standalone trainings in Firecrest per new Site Policy/SOPs that were provided to Pfizer. Alerted the PPD CRO study team who escalated to Pfizer clinical management. | C4891006 | C4891006 | GCP_Major_Apr-2025_C4891006, C4891023, C4891024: Study Training_Multiple PIs (Washington University)_USA | C489 | Major | SQE | 2025-05-22 | 2025-05-23 | N | 2025-05-22 | 2025-05-23 18:35 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT33 - Study-Specific Training | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-173319 | Approved - In CAPA | QE-173319 | Approved - In CAPA | 2025-04-04 | (Empty) | (Empty) | (Empty) | (Empty) | Site is refusing to now complete Sponsor specific trainings like Suspected Serious Breach and general Safety Standalone trainings in Firecrest per new Site Policy/SOPs that were provided to Pfizer. Alerted the PPD CRO study team who escalated to Pfizer clinical management. | C4891006 | C4891006 | GCP_Major_Apr-2025_C4891006, C4891023, C4891024: Study Training_Multiple PIs (Washington University)_USA | C489 | Major | SQE | 2025-05-22 | 2025-05-23 | N | 2025-05-22 | 2025-05-23 18:35 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT33 - Study-Specific Training | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology