## Standard_Quality_Dashboard - Au
AMS Audit PR ID | AMS Observation PR ID | Target Completion Date | Actual Completion Date | TCD Due/Overdue Days | TCD Status | Observation Closed On | Observation Rating | Observation Phase | Investigator Full Name | Country | Unique Site Number | Type Of Entity | Issue Of Audit Report Actual | Issue Audit Closure Rpt Act | Observation Description | Response (Trackwise Only) | Actions Taken | CAPA Action Description | CAPA Action Created by | Responsibility | Responsible Contact | Audit Coordinator | Observation Status | Audit Status | Level 1 | Level 2 | Selected Business Process | Responsible Party Value | Rapid Model | Business Category | Site Care Partner | Cluster | Area ID | Area Name
AIA-005019 | QE-140673 | 2024-12-20 | 2024-12-16 |  | Completed On Time |  | Minor |  | Chien, Amy Jo | UNITED STATES | C4891023_1010 | GCP Site Audit | 2024-10-02 |  | For 3 of 3 participants records reviewed, there were discrepancies between the source data and the corresponding electronic case report form(e-CRF). [ICH E6(R2) 4.9.2] The following examples (not all inclusive) were observed: Participant 10102001: Adverse event (AE) log entries had stop dates that were not recorded in the e-CRF &nbsp;Headache (start date 21Nov2023) stop date of 23Apr2024 was missing from the e-CRF. Constipation (start date 21Nov2023) stop date of 23 Apr2024 was missing from the e-CRF. Nausea (start date 22Nov2023) stop date of 23 Apr2024 was missing from the e-CRF. Fatigue (start date 06Dec2023) stop date of 23 Apr2024 was missing from the e-CRF. Hot flashes (Grade 2 with start date 17Jan2024) were missing stop date 24Apr2024 Neutrophil Count Decreased (Grade 3 with start date 06Dec2023) stop date 15Dec2023 was missing from e-CRF. AE entry of fatigue with start date 24Apr2024 was recorded on AE log but not the e-CRF. &nbsp;&nbsp; Participant 10102002: AEs causality relatedness entered in the e-CRF was missing from the AE Log for: Hot Flashes (Grade 1) with start date 25Jan2024 Neck ache (Grade 1) with start date 14Feb2024 Wrist ache (Grade 1) with start date 14Feb2024 Participant 10102003: Adverse events information recorded in the e-CRF but missing from the AE Log: - -Pruritic Rash Right exterior upper arm (Grade 1) with start date 16Jul2024 and ongoing -Neutrophil count decreased (Grade 3) start date 06Aug2024 stop date 12Aug2024 AE dyspnea (grade 1) recorded on the AE Log with start date 27Mar2024 and stop date 11Jun2024 had the stop date omitted from the e-CRF entry. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | To address the findings of inconsistencies with investigator assessment of AE causality and documentation of AE stop dates, the site has added an AE log tracker to progress notes and patient source. Upon review, the AE log trackers for all patients adequately document PI review of AEs and any changes that are made, including the addition of stop dates. Such study participant's log was reconciled with the eCRF and discrepancies were raised via eCRF queries. The SC agreed to address queries in a timely manner. The site was also re-trained on the proper process for AE updates and documentation and site staff expressed understanding. All queries and issues were resolved on 16Dec2024. | Adverse Event entries will be reviewed between EMR and EDC at the next IMV scheduled on 11-12Dec2024, and reconciliation and/or updates will be made accordingly. Site to be re-trained on Adverse Event updates in both EDC and EMR (evidence of training to be provided, as part of Monitoring Visit report). | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | DMB03-GSOP - Data Management | VENDOR / CONTRACTOR | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-005019 | QE-140662 | 2024-12-20 | 2025-04-29 |  | Complete Late |  | Major |  | Chien, Amy Jo | UNITED STATES | C4891023_1010 | GCP Site Audit | 2024-10-02 |  | The quality of essential trial records was deficient. [ICH E6 (R2) 4.9.0] a) For 3 of 3 participants (10102001, 10102002, 10102003) records reviewed, the quality of the signed Health Insurance Portability and Accountability Act consent documents was deficient. The e-sign electronic signatures affixed to form to denote the study participants initials in a specific section of the document obscured the text of HIPAA consent document. This was discussed with the site, and they acknowledged that remediation would require an Information Technology (IT) solution by the University of California San Francisco (UCSF) not the C4891023 Site 1010 study team. b) It could not be determined when the adverse event (AE) Log adverse event entries stop dates were added to the log nor when the causality assessment was performed for each entry on the log. The site utilized e-Sign electronic signature on the AE Logs where electronic signatures with several different dates were affixed to the bottom of the document. The AE Logs were cumulative with each AE occupying a separate line on the log with its respective start stop date, seriousness, and relatedness to each study medication. c) The site inconsistently completed the causality assessment field on the AE Log. For example, participant 10102003 AE Log (Day -7 10Apr2024; C1D1 17Apr2024) was completed using Y for related and N for not related instead of using the pre-printed relatedness number key at the bottom of the AE Log. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | a) to be discussed with UCSF IT department if there a QC or review once the consent is uploaded to review if all pages/language is visible.Deadline: this issue will be followed with UCSF Manager until she provides the responses from UCSF IT department. An on site IMV scheduled at UCSF on 11-12Dec2024, when Study Monitor to have opportunity for further discussions.b-c) the AE log tracker will be reviewed by Monitor at next IMV, scheduled on 11-12Dec2024, and the quality of AE log and accuracy will be documented within the Monitoring Visit report.As per Monitoring Visit completed on 11Dec2024 at UCSF (site 1010), the CRA inquired on about the electronic signatures obscuring HIPAA consent text. Per the SC, the Site Manager remains in discussion with the site's IT team to resolve this issue. This issue will continue being followed up with site. Next IMV will be scheduled in Feb2025 per Study Monitoring Plan, therefore, CRA can verify the resolution of this issue. In addition, to address recent finding of inconsistencies with investigator assessment of AE causality and documentation of AE stop dates, the site has added an AE log tracker to progress notes and patient source. Upon review, the AE log trackers for all patients adequately document PI review of AEs and any changes that are made, including the addition of stop dates. Such study participant's log was reconciled with the eCRF and discrepancies were raised via eCRF queries. The SC agreed to address queries in a timely manner. The site was also re-trained on the proper process for AE updates and documentation and site staff expressed understanding.As per updates from Clinical Research manager obtained on 14Apr2025, they brought up the HIPAA formatting issue with the Cancer Center leadership and UCSF IRB Director. It is being proposed an update to the document. Site will provide additional information as soon as available. On 29Apr2025, site has been asked to provide a date they expect UCSF IRB Director will trigger and initiate the correction of HIPAA formatting issue. on 29Apr2025, UCSF Clinical Research Manager shared IRB has approved and posted the updated HIPAA form with adjusted spacing to allow room for the initials and text to not overlap. Attached the updated HIPAA pdf version as well as Research Manager's email. | a) The site is in the process of escalating this issue to the UCSF IT department and will provide updates to PPD and Pfizer when available. Per UCSF Manager Amy DeLuca, the site can’t modify how the 21 part 11 compliant stamp shows up on the page without a higher level change in the formatting so it is still being followed internally within UCSF.b-c) The site has created an AE log tracker post discussion with auditor that will be included in source clinic notes within the EMR. This tracker will be used to capture electronic signatures for each data change, including stop dates and causality assessments. The implementation of an AE log tracker should prevent further issues on documentation inconsistency on causality assessment. | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | Quality Oversight/Documentation | Inadequate quality documentation | INV04 - Investigational Site Management and Monitoring | PRINCIPAL INVESTIGATOR | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-005019 | QE-140651 | 2024-12-20 | 2025-11-19 |  | Complete Late |  | Major |  | Chien, Amy Jo | UNITED STATES | C4891023_1010 | GCP Site Audit | 2024-10-02 |  | Organization of trial records in the electronic investigator site file (e-ISF), Complion was inadequate to facilitate efficient and timely traceability of trial conduct activities impacting the Sponsor’s ability to effect required oversight of study conduct at the site. [INV04-GSOP-RF17, 6.0 Requirements for Source Document Review and Source Data Verification, 15Mar2024] Complion e-ISF had two sections, one for housing the regulatory study documents and the other where scanned source documents (not included in the EMR) were kept. The e-ISF did not have a consistent organized file structure by study visit type to allow easy and efficient review of these source records by study visit type. The site batched source study records (including but not limited to ECG tracings, AE logs, Nursing Flow Sheet used to record PK sample draw times and ECG times) from various visit types and dates in a single dated portable document format (pdf) record containing three hundred or more pages then upload this pdf to Complion. Further organization and labeling of the type of source records in a batched pdf was not always available resulting in the user of Complion having to engage in a time-consuming task of scrolling endlessly through pages and pages of records to check if a particular record type (e.g., AE Log for participant 10102002 with some 20 AEs entered in the electronic data capture that was embedded in a batched pdf record) was included in the pdf batch record. Please note during the auditors interaction with site study staff, they became aware that the site staff had an internal electronic file share area where study records were organized by study visit type (screening etc.,) from which records were generated in pdf batched records and uploaded to Complion. The site study staff informed the auditors that only the site staff have access to this internal electronic file share area, the site monitor/clinical research associate was never granted access to this internal electronic file share area. Additionally, the Site’s Study Coordinator supervisor stated that this batched pdf approach was used because it took a lot of time (approximately 5 minutes) for a pdf record to be uploaded to Complion, a burden for site coordinators. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | 1) Site agrees to upload the documentation into Complion prior to each Monitoring visit, including all source records from previous upload until the IMV date. In addition, site is currently verifying with Complion team to add bookmark view to monitors to make the source more organized for monitoring. This will be reviewed at next on site IMV, scheduled on 11-12Dec20242) No further corrective actions, since site clarified the purposes of internal electronic file shared area.As per Monitoring Visit completed on 11Dec2024 at UCSF (site 1010), the CRA inquired about the site adding bookmarks to Complion to ease navigation of source documents. Per the SC, the Site Manager remains in discussions with Complion. This issue will continue being followed up with site. Next IMV will be scheduled in Feb2025 per Study Monitoring Plan, therefore, CRA can verify the implementation of enhancements within Complion platform.Site Research Manager reached out to Complion support on 25Mar2025 for further updates, still pending response.Per Monitoring visit report dated 16Apr2025, CRA indicated that during the present IMV and as a work around for the missing bookmarks, the site provided screenshots of file bookmarks of recent source uploads. This work around has dramatically increased the efficiency of SDR/SDV for the CRA while the site is in discussion with the Complion IT team to provide the CRA access to source bookmarks. On 29Apr2025, site has been asked to provide a date they expect Complion support will provide the final response about ability to add bookmarkers to CRA view in Complion. As per her response, on 21Apr2025, Complion helpdesk confirmed they moved up the priority of the ticket request. 19Nov2025: Platform Complion has not been updated to add bookmarks, however, site has provided screenshots of file bookmarks at each IMV. In addition, site has consolidated all documents into a single upload for each IMV to improve file review efficiency for the CRA. Source Document Review is current and we can consider this CAPA as resolved. | 1) Per discussion held on 25Oct2024 with Amy DeLuca and site and PPD members, the site has asked Complion to add the same bookmark view to monitors and the site will provide an update to the PPD and Pfizer teams when available.2) Per discussion held on 25Oct2024 with Amy DeLuca and site and PPD members, it was clarified the SharePoint is used by study coordinators to store EMR records and other source documents for Subject study visits. Monitors cannot have access to the SharePoint as documents are editable. Rather, source documents are uploaded to the Complion system that maintain source in a read-only format for monitor review. It was confirmed the SharePoint (internal electronic file share area) is not considered source document, and all study records are uploaded into Complion / EMR. Source Document Locator does not require an update. | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | Data Collection and Management | Inadequate source data/documentation | INV04 - Investigational Site Management and Monitoring | VENDOR / CONTRACTOR | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-005019 | QE-140667 | 2024-12-20 | 2025-03-26 |  | Complete Late |  | Major |  | Chien, Amy Jo | UNITED STATES | C4891023_1010 | GCP Site Audit | 2024-10-02 |  | From the audit trail sample provided by the site for their Electronic Medical Record (EMR) Epic Hyperspace, it could not be determined if the e-Source Readiness Assessment responses for the EMR Audit Trail were accurate. [ICH E6(R2) 5.5.3 a.c] The audit trail record provided did not clearly demonstrate the exact data that was added and/or removed but only reference the titled section of the EMR accessed by the user. Additionally, it was unknown if and how the EMR’s audit trail functionality was protected from unauthorized deletion since an Information Technology (IT) subject matter expert (SME) for the site was not available during the audit to demonstrate the system or answer related questions. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | As per SC, the site is still in the process of escalating the issue related to the EMR audit trail record that did not clearly demonstrate the exact data that was added and/or removed to the UCSF IT department. Once an update is available, it will be shared with PPD and Pfizer. The site has been asked to describe the capabilities of the EMR audit trail including how audit trail functionality was protected from unauthorized deletion.Responses obtained from site on 26Mar2025: During the audit, auditor had requested a level of audit tracking that doesn’t exist in site system. Site reviewed this with the IT security group. For each field in EPIC there is an audit trail with the ability to review and see when the information was entered and who made changes etc., but this is not something that can be logged and printed for every single data point relating to our research patients. Site doesn’t have the capability of presenting a comprehensive audit trail summary of every data field. Clinical Research Manager from UCSF asked their IT security about this and they said this wasn’t possible. Auditor can get direct access to EMR via MDLinks and can review the fields and their audit trail as necessary but they can’t globally print a log. | The site is in the process of escalating this issue to the UCSF IT department and will provide updates to PPD and Pfizer on the capabilities of the audit trail including how audit trail functionality was protected from unauthorized deletion. The study coordinators further confirmed that the EMR audit trail is visible to monitors as part of EMR access during monitoring visits. The eSRA (eSource Readiness Assessment) states audit trail information is readable and readily available. An onsite IMV scheduled at UCSF on 11-12Dec2024, when Study Monitor to have opportunity for further discussions. | Sandra Banevicius |  | - | Sandra Banevicius | Approved - In CAPA | Closed | IT Systems | Inadequate IT system (eg. planning, definitions, design, development, testing, validation, support) per regulatory requirements | DMB03-GSOP - Data Management | PRINCIPAL INVESTIGATOR | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-005019 | QE-139112 | 2024-12-20 | 2024-12-11 |  | Completed On Time |  | Major |  | Chien, Amy Jo | UNITED STATES | C4891023_1010 | GCP Site Audit | 2024-10-02 |  | The Sponsor’s access to study source records at the investigator site to perform required oversight was not in accordance with the signed clinical trial agreement (CSA) impacting the sponsor’s ability to fulfill its obligation to perform required oversight of study conduct at the site. Additionally, this issue of the Investigator Site not granting sponsor representatives access to the pharmacy was not raised as an issue in a timely manner. [Clinical Study Agreement-Prism Research LLC dba Nucleus Network, 25Oct2022; ICH E6(R2) 4.9.7 and 5.1.2)] Sponsor representatives i.e., monitors/Clinical research associates (CRAs), Site Care Partner, and auditors were not granted access to the site’s pharmacy and IP dispensing verification records due to site policy of not granting access to the pharmacy. Additionally, virtual pre-trial assessment and Site Initiation visits (SIV) were conducted on the 14Jul2022 and 28Jul2023, respectively. Therefore, no Sponsor representatives were able to visualize the IP and IP storage facility at this investigator site since the study began there. The issue was raised as part of quality event QE-122798 when a newly assigned Site Care Partner noticed authorization for the site to use their investigational product accountability log (IPAL) was missing. The site used the electronic system Vestigo to manage IP accountability and house IP temperature monitoring records. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | PPD CRAs have been re-trained on 01Nov2024 to ensure a onsite IMV is performed at UCSF and IDS, including a virtual tour to the facility as permitted per IDS-SOP 11: Monitoring Policy at least within 12 months, as per Study Monitoring Plan.Onsite IMV being scheduled on 11-12Dec2024, with a virtual tour to the pharmacy and review of documents not made available thru Vestigo. Discussions to be held with pharmacy staff on ability to accommodate on site visits to pharmacy and provision of documents maintained at pharmacy and not available thru Vestigo, at least once per year. Deadline 20Dec2024 | Ongoing discussions are being held between site representative Lisa Janssen Carlson, Manager of Investigational Drug Services and the Pfizer Care Partners and PPD CRA in order to perform an above-study on site visit to the pharmacy, and perform the tour at the IDS (Investigational Drug Service) facility and have oversight of IP storage/handling and related documents that might not be made available remotely (via system Vestigo). If permitted by UCSF, the PPD CRA will complete a onsite IMV to the UCSF pharmacy and produce a Monitoring Visit Report to document the tour at IDS and IP handling. If possible, this onsite pharmacy visit will cover the 3 protocols being conducted at UCSF and managed by PPD – Arvinas program C4891006, C4891023, C4891026. In addition, PPD CRAs have been re-trained during the Study Team meeting held on 01Nov2024 to escalate as soon as possible site restrictions that would affect the Pfizer requirement to have a onsite visit (at all facilities, including pharmacy) within 12 months. Update: An onsite IMV has been scheduled with site on 11-12Dec2024, and the pharmacist agreed to provide the pharmacy binders for review during this onsite visit. They will also allow for a virtual tour of the pharmacy and IP review via Zoom video tool. After on site IMV is completed, the Monitoring Visit Report (MVR) will be produced covering studies C4891006, C4891023 and C4891026, with documentation on IP handling and oversight. | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | Site Management and Monitoring | Failure to escalate or resolve issue | INV02 - Investigational Site Selection, Preparation, and Initiation | PFIZER | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS