## Standard_Quality_Dashboard - QE
Observation ID | Study ID | Targeted | PR ID | Site(s) | principal Investigator | EX Comp? | QE Threshold | Status | Observation Description (as submitted) | Awareness Date | Submission Date | Assessment Date | Title/Short Description | Business CAPA Plan Endorsed On | CAPA Plan in Place | Last Action Due Date | Investigation Summary and Conclusion | Effectiveness Check Required | Effectiveness Check Rationale | Investigation Completion Date | Closed On | PDAL Decision | Level 1 | Level 2 | Quality CAPA Plan Endorsed On | Quality Reviewer Approved On | Business Process | Submitter | Confirmed Serious Breach | Remediation Actions Taken (when QE was submitted) | CAPA Action Details | CAPA Action Owner | Root Cause Description | Root Cause Level 1 | Root Cause Level 2 | Root Cause Level 3 | Rapid Model | Business Category
2216847 | C4891023 | N | 2216805 | 1014 | Layman, Rachel M | Y | Minor | Closed | Product Protocol Number: C4891006 C4891026 C4891023 C4891027 C4891024 C4891028 Involved Party / Country: Pfizer / United States Awareness Date: 16-Aug-2022 Quality Event Description: A Virtual Pre-Trial Assessment (PTA) was completed at MD Anderson (Houston, TX) by the local SRP on 16-Aug-2022. The SRP was not able to have a visual inspection of the patient treatment areas, biopsy areas, imaging areas or the four (4) satellite locations. What Should Have Happened: A visual assessment of the above-mentioned areas should have occurred. Why Did This Event Happen: On-site institutional restrictions still in place due to COVID. Immediate Actions Taken: Post PTA, the site was able to provide pictures of the patient treatment areas dated 26-Oct-2022, pictures of lab dated 26-Oct-2022, there was video present on the institution's website of their imaging facilities dated 10-Oct-2022. The MD Anderson website describes the site's surgical abilities but we are not able to see the biopsy areas. Confirmed the online videos and photos for the four (4) satellite locations are current as of 01-Nov-2022 per the below from the site. Site's response to Pfizer Inquiry: "The League City, Sugar Land, and West Houston information is current and correct. The Woodlands info is a video from the former location before the site moved in 2019. I am not aware of a more current video. However, the site would have the same concept/layout, etc as League City and West Houston locations. I also see they utilized Yelp to find photos of West Houston (which are of current facility). I located these photos on Yelp of The Woodlands and can confirm they are photos of the current facility." CMCD Information: Start Date: 04-Nov-2022 End Date: 31-Dec-2023 Reason for Start/End Date: To ensure it is in place for the life of study enrolment. CMCD Requirement Not Met: NV02-GSOP-RF15: Provision must be made for a visual review. The following are the acceptable methods for conducting the visual review: -On-site visit, [e.g., pre-trial assessment (PTA), site initiation visit (SIV), any visit for the study prior to site activation (preferred method)] -Video tour (guided or recorded), photos (photos are acceptable but not preferred); including all the items noted above*. Any recorded video tour or photos must have been prepared no longer than 12 months prior to the current assessment. The requirement for a visual review is not mandatory if an on-site visit, including visual review of facilities and equipment has been conducted within the last 12 months. -If a visual review has been performed in the last 12 months, but there are additional study specific facilities/equipment that have not been reviewed, a visual review of the study specific items is required. Instead of CMCD Requirement: Site selection and activation will be performed with a visual assessment of the facilities as confirmed by the site's provided pictures and email confirmations. Biopsy area: The MD Anderson website describes the surgical capabilities but does not provide imaging. We want to request an exception since we have previously never requested to visit these areas and will not get permission to view these areas due to patient privacy and sterile area requirements. Historical Review: Vendor / Key Word Search: There were no previous similar Quality Events identified for this Vendor on this protocol upon review of quality database. Assessment Comments: This quality event represents CMCD non-conformance. The CMCD that is referenced by the event reporter is: INV02-GSOP 5.0 Investigational Site Selection, Preparation, and Initiation 01-Jun-2022. For this CMCD QE, the past component occurred during the dates of 16-Aug-2022 to date of QE submission (04-Nov-2022), whereby start date represents the date of the virtual PTA. The submission indicates that a virtual PTA was completed at MD Anderson by the local SRP on 16-Aug-2022, but an assessment of the patient treatment areas (biopsy area, imaging area and 4 satellite locations) did not occur due to COVID-19 restrictions. It is noted that the site provided pictures of the areas dated 26-Oct-2022, and online videos and photos for the 4 satellite locations on the institution’s website are current as of 01-Nov-2022 as confirmed by the site. There is no indication in the submission of significant adverse impact to study participants or study data, due to this event. The event appears to be appropriate for the study team to continue to manage. As such, the event does not appear to materially or have a substantial likelihood to impact participant safety, rights, confidentiality, and well-being; data integrity and/or scientific rigor; compliance with regulatory requirements; license obligations; or trust in the clinical research enterprise per QMS01 criteria (Significant Quality Event). This quality event represents a nonconformity to applicable policy, procedure, protocol or Good Practices Quality Guidelines and Regulations (GxP). Therefore, this is a T1 Quality Event and the study team should continue to manage and document the Quality Event and the actions taken to address the issue. Please discuss as necessary with study Clinician, Clinical Scientist and/or CPM/CSTL, and if they consider this event to have potential or material (significant) adverse impact to any of the criteria noted above due to this event, or if the issue persists post-remediation, please resubmit providing detail on the impact. | 2022-08-16 | 2022-11-04 | 2022-11-04 | GCP_T1_Nov-2022_Multiple Protocols: CMCD: Pre-Trial Assessment (PTA) (Coronavirus Impact)_Pfizer_USA |  | NO |  | --- |  |  |  | 2022-11-04 20:36 |  | Quality Procedures | Requirement/process not met |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Michelle Mikhail |  | Post PTA the site was able to provide pictures of: the patient treatment areas dated 26Oct2022, pictures of lab dated 26Oct2022, there was video present on the institution's website of their imaging facilities dated 10Oct2022. The MD Anderson website describes the site's surgical abilities but we are not able to see the biopsy areas. Confirmed the online videos and photos for the four (4) satellite locations are current as of 01Nov2022 per the below from the site. Site's response to Pfizer Inquiry: "The League City, Sugar Land, and West Houston information is current and correct. The Woodlands info is a video from the former location before the site moved in 2019. I am not aware of a more current video. However, the site would have the same concept/layout, etc as League City and West Houston locations. I also see they utilized Yelp to find photos of West Houston (which are of current facility). I located these photos on Yelp of The Woodlands and can confirm they are photos of the current facility." Pfizer Inquiry: Hi Pamela, Just a few more questions about the satellite locations. Your responses are greatly appreciated. League City Location, There is a video posted on the MD Anderson website regarding the League city location. Since there is no date on this video, can you please confirm the video is still valid and has not changed? Sugarland Location, There is a video posted on the MD Anderson website regarding the Sugarland location. Since there is no date on this video, can you please confirm the video is still valid and has not changed? Woodlands Location, There is a video dated 03Jun2011 posted on YouTube regarding the Woodlands location. Since the date of this video is over a year, can you please confirm the video is still valid and has not changed? West Houston Location, We were able to retrieve the below photos dated 30May2019 from Yelp posted by MD Anderson. The date of these photos are over a year, can you please confirm these photos are still valid and have not changed? | [6 empty] | MODEL 0 - LEGACY | Oncology
2216847 | C4891023 | (Empty) | 2216805 |  |  | Y | Minor | Closed | Product Protocol Number: C4891006 C4891026 C4891023 C4891027 C4891024 C4891028 Involved Party / Country: Pfizer / United States Awareness Date: 16-Aug-2022 Quality Event Description: A Virtual Pre-Trial Assessment (PTA) was completed at MD Anderson (Houston, TX) by the local SRP on 16-Aug-2022. The SRP was not able to have a visual inspection of the patient treatment areas, biopsy areas, imaging areas or the four (4) satellite locations. What Should Have Happened: A visual assessment of the above-mentioned areas should have occurred. Why Did This Event Happen: On-site institutional restrictions still in place due to COVID. Immediate Actions Taken: Post PTA, the site was able to provide pictures of the patient treatment areas dated 26-Oct-2022, pictures of lab dated 26-Oct-2022, there was video present on the institution's website of their imaging facilities dated 10-Oct-2022. The MD Anderson website describes the site's surgical abilities but we are not able to see the biopsy areas. Confirmed the online videos and photos for the four (4) satellite locations are current as of 01-Nov-2022 per the below from the site. Site's response to Pfizer Inquiry: "The League City, Sugar Land, and West Houston information is current and correct. The Woodlands info is a video from the former location before the site moved in 2019. I am not aware of a more current video. However, the site would have the same concept/layout, etc as League City and West Houston locations. I also see they utilized Yelp to find photos of West Houston (which are of current facility). I located these photos on Yelp of The Woodlands and can confirm they are photos of the current facility." CMCD Information: Start Date: 04-Nov-2022 End Date: 31-Dec-2023 Reason for Start/End Date: To ensure it is in place for the life of study enrolment. CMCD Requirement Not Met: NV02-GSOP-RF15: Provision must be made for a visual review. The following are the acceptable methods for conducting the visual review: -On-site visit, [e.g., pre-trial assessment (PTA), site initiation visit (SIV), any visit for the study prior to site activation (preferred method)] -Video tour (guided or recorded), photos (photos are acceptable but not preferred); including all the items noted above*. Any recorded video tour or photos must have been prepared no longer than 12 months prior to the current assessment. The requirement for a visual review is not mandatory if an on-site visit, including visual review of facilities and equipment has been conducted within the last 12 months. -If a visual review has been performed in the last 12 months, but there are additional study specific facilities/equipment that have not been reviewed, a visual review of the study specific items is required. Instead of CMCD Requirement: Site selection and activation will be performed with a visual assessment of the facilities as confirmed by the site's provided pictures and email confirmations. Biopsy area: The MD Anderson website describes the surgical capabilities but does not provide imaging. We want to request an exception since we have previously never requested to visit these areas and will not get permission to view these areas due to patient privacy and sterile area requirements. Historical Review: Vendor / Key Word Search: There were no previous similar Quality Events identified for this Vendor on this protocol upon review of quality database. Assessment Comments: This quality event represents CMCD non-conformance. The CMCD that is referenced by the event reporter is: INV02-GSOP 5.0 Investigational Site Selection, Preparation, and Initiation 01-Jun-2022. For this CMCD QE, the past component occurred during the dates of 16-Aug-2022 to date of QE submission (04-Nov-2022), whereby start date represents the date of the virtual PTA. The submission indicates that a virtual PTA was completed at MD Anderson by the local SRP on 16-Aug-2022, but an assessment of the patient treatment areas (biopsy area, imaging area and 4 satellite locations) did not occur due to COVID-19 restrictions. It is noted that the site provided pictures of the areas dated 26-Oct-2022, and online videos and photos for the 4 satellite locations on the institution’s website are current as of 01-Nov-2022 as confirmed by the site. There is no indication in the submission of significant adverse impact to study participants or study data, due to this event. The event appears to be appropriate for the study team to continue to manage. As such, the event does not appear to materially or have a substantial likelihood to impact participant safety, rights, confidentiality, and well-being; data integrity and/or scientific rigor; compliance with regulatory requirements; license obligations; or trust in the clinical research enterprise per QMS01 criteria (Significant Quality Event). This quality event represents a nonconformity to applicable policy, procedure, protocol or Good Practices Quality Guidelines and Regulations (GxP). Therefore, this is a T1 Quality Event and the study team should continue to manage and document the Quality Event and the actions taken to address the issue. Please discuss as necessary with study Clinician, Clinical Scientist and/or CPM/CSTL, and if they consider this event to have potential or material (significant) adverse impact to any of the criteria noted above due to this event, or if the issue persists post-remediation, please resubmit providing detail on the impact. | 2022-08-16 | 2022-11-04 | 2022-11-04 | GCP_T1_Nov-2022_Multiple Protocols: CMCD: Pre-Trial Assessment (PTA) (Coronavirus Impact)_Pfizer_USA |  | NO |  | --- |  |  |  | 2022-11-04 20:36 |  | Quality Procedures | Requirement/process not met |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Michelle Mikhail |  | Post PTA the site was able to provide pictures of: the patient treatment areas dated 26Oct2022, pictures of lab dated 26Oct2022, there was video present on the institution's website of their imaging facilities dated 10Oct2022. The MD Anderson website describes the site's surgical abilities but we are not able to see the biopsy areas. Confirmed the online videos and photos for the four (4) satellite locations are current as of 01Nov2022 per the below from the site. Site's response to Pfizer Inquiry: "The League City, Sugar Land, and West Houston information is current and correct. The Woodlands info is a video from the former location before the site moved in 2019. I am not aware of a more current video. However, the site would have the same concept/layout, etc as League City and West Houston locations. I also see they utilized Yelp to find photos of West Houston (which are of current facility). I located these photos on Yelp of The Woodlands and can confirm they are photos of the current facility." Pfizer Inquiry: Hi Pamela, Just a few more questions about the satellite locations. Your responses are greatly appreciated. League City Location, There is a video posted on the MD Anderson website regarding the League city location. Since there is no date on this video, can you please confirm the video is still valid and has not changed? Sugarland Location, There is a video posted on the MD Anderson website regarding the Sugarland location. Since there is no date on this video, can you please confirm the video is still valid and has not changed? Woodlands Location, There is a video dated 03Jun2011 posted on YouTube regarding the Woodlands location. Since the date of this video is over a year, can you please confirm the video is still valid and has not changed? West Houston Location, We were able to retrieve the below photos dated 30May2019 from Yelp posted by MD Anderson. The date of these photos are over a year, can you please confirm these photos are still valid and have not changed? | [6 empty] | MODEL 0 - LEGACY | Oncology
2225629 | C4891023 | (Empty) | 2225604 |  |  | N | Minor | Closed | Product Protocol Number: C4891001, C4891006, C4891023 Involved Party / Country: Vendor: Leal Health / United States Awareness Date: 27-Apr-2023 Quality Event Description: A potential participant went to PfizerClinicalTrials.com Breast Cancer Landing page and completed an imbedded prescreener by a Pfizer Vendor, Leal Health. The potential participant followed the vendor process and printed out a form of clinical trials they matched to from the Vendor's system to discuss with her healthcare professional. After discussing further with a nurse, the potential participant and nurse engaged the vendor's platform and had a negative experience. The nurse reported to a Pfizer Field Medical Director that the experience that they had with the Vendor was unprofessional and did not appear legitimate. What Should Have Happened: The potential participant and the nurse should have had a positive experience with the Vendor, Leal Health. Why Did This Event Happen: The cause is unknown. The study team and Vendor Lead(s) are investigating the issue further with the Vendor. Immediate Actions Taken: The study team and Vendor Lead(s) met with the Vendor to discuss the feedback, review their process(es) and platform connected with the Pfizer Breast Cancer program, and requested for the Vendor to audit the landing pages the potential participant/nurse would have experiences as well as the discussions their patient navigator had since the campaign launched. The Vendor confirmed that they have been actively auditing their patient navigator supporting the program, and an issue like this has never been identified or reported. Historical Review: Protocol Search: There are no previous similar Quality Events identified for theseProtocols upon review of quality database. Vendor Search: There are no previous similar Quality Events identified for this Vendor upon review of quality database. Assessment Comments: The submission indicates that a potential participant and Nurse using the PfizerClinicalTrials.com Breast Cancer Landing page reported that the experience that they had with the Vendor was unprofessional and did not appear legitimate. Due to the potential for significant adverse impact to the participant’s experience, rights, well-being, and potential impact to Pfizer reputation, this will be a T2 Significant Quality Event. If it is identified during the course of the investigation that activity by the vendor is considered to represent misconduct, the Investigation Lead should consider whether the event should be raised to T3. Corporate Compliance are copied for awareness. | 2023-04-27 | 2023-04-28 | 2023-04-28 | GCP_T1_Apr-2023_C4891001,C4891006,C4891023: Vendor Responsibilities:Potential Participant Complaint_Leal Health_USA_DWG |  | NO | 2023-08-14 | --- |  |  |  | 2023-05-17 02:26 |  | Potential allegation of Falsification or misconduct | Potential allegation of Scientific fraud, falsification or misconduct |  |  | No Process Assigned | Dena Waldier |  | The study team and Vendor Lead(s) met with the Vendor to discuss the feedback, review their process(es) and platform connected with the Pfizer Breast Cancer program, and requested for the Vendor to audit the landing pages the potential participant/nurse would have experiences as well as the discussions their patient navigator had since the campaign launched. The Vendor confirmed that they have been actively auditing their patient navigator supporting the program, and an issue like this has never been identified or reported. | The SQE team to determine if all safety and efficacy data can be used for all study reports for C4891001, C4891023, and C4891006 based on the results of the SQE. | Krachon, Deana |  |  |  |  | MODEL 0 - LEGACY | Oncology
2225632 | C4891023 | (Empty) | 2225613 |  |  | N | Minor | Closed | Product Protocol Number: C4891001, C4891006, C4891023 Involved Party / Country: Vendor: Leal Health / United States Awareness Date: 28-Apr-2023 Quality Event Description: While investigating another quality event, it was discovered that a Vendor was not utilizing IRB approved content for a potential participant-facing email communication. What Should Have Happened: Vendor should have been utilizing IRB approved content for the potential participant-facing email communication. Why Did This Event Happen: This was an error by the Vendor. Immediate Actions Taken: Pfizer will be notifying the Vendor upon awareness to correct the email distribution to the IRB approved content immediately. CMCD Information: Start Date: 01-Mar-2023 End Date: 28-Apr-2023 Reason for Start/End Date: NA CMCD Requirement Not Met: INV03-GSOP 4.0 Study Participant Recruitment and Retention Planning 27-Oct-2022 - 3.2. All study participant-directed recruitment materials must be approved by institutional review board (IRB)/independent ethics committee (IEC). INV03-GSOP Online and Social Media Clinical Study Participant Recruitment Requirements - 3.1.2. IRB/EC approved study participant-directed recruitment material may not be altered, amended or appended (e.g., with the posting of comments or other online content) without further IRB/EC review and approval prior to online publication or use. Instead of CMCD Requirement: Vendor made an error and sent unapproved content to a potential participant. Vendor will be updating content to the IRB approved content moving forward. Historical Review: Vendor Search: There is 1 previous Quality Event identified for this Vendor upon review of quality database. PR 2225604_GCP_T2_Apr-2023_C4891001, C4891006, C4891023: Vendor Responsibilities: Potential Participant Complaint_Leal Health_USA (Ongoing: Inv Lead: D Krachon) Assessment Comments: This quality event represents CMCD non-conformance. The CMCDs that are referenced by the event reporter are: INV03-GSOP 4.0 Study Participant Recruitment and Retention Planning INV03-GSOP Online and Social Media Clinical Study Participant Recruitment Requirements 27-Oct-2022 The submission indicates that the Vendor did not use IRB approved content for a potential participant-facing email communication sent to 1 potential participant. It is noted that the Vendor will be updating content to the IRB approved content moving forward; the vendor is to correct the email distribution to use the IRB approved content immediately. The event appears to be limited to 1 participant and appears to be possible for the study team/vendor to remediate; there is no indication in the submission of significant adverse impact to study participants or study data, due to this event. The event appears to be appropriate for the monitor/study team to continue to manage. As such, the event does not appear to materially or have a substantial likelihood to impact participant safety, rights, confidentiality, and well-being; data integrity and/or scientific rigor; compliance with regulatory requirements; license obligations; or trust in the clinical research enterprise per QMS01 criteria (Significant Quality Event). This quality event represents a nonconformity to applicable policy, procedure, protocol or Good Practices Quality Guidelines and Regulations (GxP). Therefore, this is a T1 Quality Event and the monitor/study team should continue to manage and document the Quality Event and the actions taken to address the issue. Please discuss as necessary with study Clinician, Clinical Scientist and/or CPM/CSTL, and if they consider this event to have potential or material (significant) adverse impact to any of the criteria noted above due to this event, or if the issue persists post-remediation, please resubmit providing detail on the impact. | 2023-04-28 | 2023-04-28 | 2023-04-28 | GCP_T1_Apr-2023_C4891001, C4891006, C4891023: Vendor Responsibilities: Recruitment Material Approval_Leal Health_USA |  | NO |  | --- |  |  |  | 2023-04-28 19:47 |  | Quality Procedures | Failure to use adequate controls (e.g., Required Forms, templates) |  |  | INV03-Study Participant Recruitment and Retention Planning | Dena Waldier |  | Pfizer will be notifying the Vendor upon awareness to correct the email distribution to the IRB approved content immediately. | [6 empty] | MODEL 0 - LEGACY | Oncology
QE-079395 | C4891023 | N | QE-079395 | 1006 | Andrew Davis (C4891023-1006) | N | Minor | Closed | This is for study C4891023, site 1006, USA, I am submitting on behalf of Elizabeth Javor who is on the CIPT team, I am the SRP. Elizabeth Javor, from the Central ICD Review team, brough the following to the attention to the study team: There were some discrepancies between the master central IRB template and this site’s main consent (that is based off of that master central IRB template). Both the central IRB master main consent and the site’s version/edits of this consent are attached to this email.To orient you: She compared the site’s Main consent that was revised by Advarra on 23Aug2023, and based on the Advarra template from 06Apr2023 (This information is found in the footer of the site’s updated consent document: “Advarra IRB Approved Version 06 Apr 2023, Revised 23 Aug 2023”).Please address the below items (A and B) within your team and with the central IRB, as needed.A. In comparing the site’s version of their Main consent against Advarra’s Main consent template, it appears that the tables on pages 12-14 do not agree:1. The Advarra Main consent template for Phase 1b does not indicate tumor assessment imaging, but this assessment is indicated on the site’s Phase 1b table as occurring every 8 weeks from the date of both drugs first dose for the first year, etc.3. The Advarra Main consent template for Phase 2 lists a tumor assessment imaging row, but the site’s consent does not include that row on its Phase 2 table.4. The Advarra Main consent template for Phase 2 lists a bone scan row, but the site’s consent does not include that row on its Phase 2 table.The Advarra Main consent template for Phase 2 lists a “Note” section at the end, but the site’s consent does not include that row on its Phase 2 table.the Illinois Main consent version IRB approved 06Apr2023 Revised 23Aug2023, has the SoA errors (missing bone scan and tumor assessment), but the Missouri Main consent version IRB approved 06Apr2023 Revised 23Aug2023, does not have these errors.If the patient signed the Illinois Main consent IRB approved 06Apr2023 Revised 23Aug2023, and they were screened for Phase 2, then it needs to be determined if the patient had a bone scan or tumor assessment included in their screening. This Illinois consent did not include the bone scan and tumor assessment in the SoA for Phase 2, so you need to determine if the patient had those things done: if they were done, then it may be a Quality Event because these things were not in the SoA Illinois Main consent version IRB approved 06Apr2023 Revised 23Aug2023. However it has been confirmed by the study team that the screen failed patient did not signed his consent, instead the consent for Phase 1B.This was approved by the IRB on 06-Apr-2023. | 2023-09-18 | 2023-11-07 | 2023-11-07 18:54 | GCP_Minor_Nov-2023_C4891023: Informed Consent Process_Davis, Andrew; Advarra; Pfizer_USA |  | NO |  |  | No |  |  | 2023-11-07 |  | Informed Consent | Inadequate consent process at the investigator site |  |  | CT05-Informed Consent Document | Misha McCullough |  | The GRAF was completed without Pfizer approval, the ICD document was not considered Pfizer approved. Additionally, there was. |  |  | NA | Human Performance | Application Error |  | MODEL 0 - LEGACY | Oncology
QE-079395 | C4891023 | (Empty) | QE-079395 |  | ADVARRA INC, PFIZER | N | Minor | Closed | This is for study C4891023, site 1006, USA, I am submitting on behalf of Elizabeth Javor who is on the CIPT team, I am the SRP. Elizabeth Javor, from the Central ICD Review team, brough the following to the attention to the study team: There were some discrepancies between the master central IRB template and this site’s main consent (that is based off of that master central IRB template). Both the central IRB master main consent and the site’s version/edits of this consent are attached to this email.To orient you: She compared the site’s Main consent that was revised by Advarra on 23Aug2023, and based on the Advarra template from 06Apr2023 (This information is found in the footer of the site’s updated consent document: “Advarra IRB Approved Version 06 Apr 2023, Revised 23 Aug 2023”).Please address the below items (A and B) within your team and with the central IRB, as needed.A. In comparing the site’s version of their Main consent against Advarra’s Main consent template, it appears that the tables on pages 12-14 do not agree:1. The Advarra Main consent template for Phase 1b does not indicate tumor assessment imaging, but this assessment is indicated on the site’s Phase 1b table as occurring every 8 weeks from the date of both drugs first dose for the first year, etc.3. The Advarra Main consent template for Phase 2 lists a tumor assessment imaging row, but the site’s consent does not include that row on its Phase 2 table.4. The Advarra Main consent template for Phase 2 lists a bone scan row, but the site’s consent does not include that row on its Phase 2 table.The Advarra Main consent template for Phase 2 lists a “Note” section at the end, but the site’s consent does not include that row on its Phase 2 table.the Illinois Main consent version IRB approved 06Apr2023 Revised 23Aug2023, has the SoA errors (missing bone scan and tumor assessment), but the Missouri Main consent version IRB approved 06Apr2023 Revised 23Aug2023, does not have these errors.If the patient signed the Illinois Main consent IRB approved 06Apr2023 Revised 23Aug2023, and they were screened for Phase 2, then it needs to be determined if the patient had a bone scan or tumor assessment included in their screening. This Illinois consent did not include the bone scan and tumor assessment in the SoA for Phase 2, so you need to determine if the patient had those things done: if they were done, then it may be a Quality Event because these things were not in the SoA Illinois Main consent version IRB approved 06Apr2023 Revised 23Aug2023. However it has been confirmed by the study team that the screen failed patient did not signed his consent, instead the consent for Phase 1B.This was approved by the IRB on 06-Apr-2023. | 2023-09-18 | 2023-11-07 | 2023-11-07 18:54 | GCP_Minor_Nov-2023_C4891023: Informed Consent Process_Davis, Andrew; Advarra; Pfizer_USA |  | NO |  |  | No |  |  | 2023-11-07 |  | Informed Consent | Inadequate consent process at the investigator site |  |  | CT05-Informed Consent Document | Misha McCullough |  | The GRAF was completed without Pfizer approval, the ICD document was not considered Pfizer approved. Additionally, there was. |  |  | NA | Human Performance | Application Error |  | MODEL 0 - LEGACY | Oncology
QE-085502 | C4891023 | N | QE-085502 | 1010 | Amy Chien (C4891023-1010) | N | Minor | Closed | For Study C4891023, Site 1010 entered a subject in error in InForm. No other data was entered in the database other than subject ID. | 2023-12-05 | 2023-12-05 | 2023-12-06 17:55 | GCP_Minor_Dec-2023_C4891023: Data Entry Error_Chien, Amy_DNK |  | NO |  |  | No |  |  | 2023-12-06 |  | Data Collection and Management | Inadequate source data/documentation |  |  | No Process Assigned | Shireen Bethala-George |  | All functional lines were made aware of issue and followed up with Quality Lead. |  |  | NA | Human Performance | Learning Error |  | MODEL 0 - LEGACY | Oncology
QE-091044 | C4891023 | (Empty) | QE-091044 |  | PFIZER | N | Minor | Closed | Quality Event for late FSSF submission- for PI change from Dr. Ma to Dr. Clifton; for the C4891023, study 1006. | 2023-12-20 | 2024-01-08 | 2024-01-08 17:58 | GCP_Minor_Jan-2024_C4891023: Final Site Selection Form (FSSF)_Pfizer_USA |  | NO |  |  | No |  |  | 2024-01-08 |  | Quality Procedures | Failure to use adequate controls (e.g., Required Forms, templates) |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Misha McCullough |  | The current SRP, completed the FSSF outside of Siebel to rectify the error, and was filed in the PTMF. |  |  | NA | Human Performance | Omission Error |  | MODEL 0 - LEGACY | Oncology
QE-100648 | C4891023 | (Empty) | QE-100648 |  | ICON PLC, PFIZER | N | Minor | Closed | Some Firecrest users lost access as a result of a data fix. GPDIP team was deploying a data fix needing to reflect deleted records for SToD. While fixing this issue, some contact IDs were erroneously deleted. Without access, these users would not have access to training resulting in continuation of business processes. | 2024-02-16 | 2024-02-28 | 2024-02-28 22:48 | GCP_Minor_Feb-2024_Enterprise Level: Firecrest User Access_ICON; Pfizer_Global |  | NO |  |  | No |  |  | 2024-02-28 |  | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) |  |  | CP403 | Christine Hancock |  | Team identified the impacted records. Alerted the STOD and Firecrest teams. then team developed a plan to correct the issue. |  |  | NA | Equipment/System/Facility | System/Application |  | MODEL 0 - LEGACY | Oncology
QE-103298 | C4891023 | (Empty) | QE-103298 |  | PFIZER | N | Major | Closed | During site 1004's Pfizer C4891001 RQA audit, the Auditor noted there was no evidence that the investigator provided adequate investigational product (IP) instructions to the participants to protect the participants’ caregivers (other than the participants) from the hazardous IP (ARV-471). The C4891001 Global GSM noted the dosing diary and ICD do not contain language pertaining to the proper handling of the hazardous ARV-471 for the caretaker, as it is written in the current IP manual. | 2024-03-11 | 2024-03-11 | 2024-03-12 15:17 | GCP_Major_Mar-2024_Multiple C489 Studies: Investigational Product (IP) Handling_Pfizer_Global |  | YES |  | <p>Product Protocol Numbers:&nbsp;</p><p>C4891001</p><p>C4891002</p><p>C4891006</p><p>C4891023</p><p>C4891024</p><p>C4891026</p><p><br></p><p>Involved Party:</p><p>Pfizer Global</p><p><br></p><p>Protocol Titles:</p><p>C4891001: A phase 3, randomized, open-label, multicenter trial of ARV-471 (PF-07850327) vs fulvestrant in participants with estrogen receptor-positive, HER2-negative advanced breast cancer whose disease progressed after prior endocrine based treatment for advanced disease (VERITAC-2).</p><p><br></p><p>C4891002: A phase 3, randomized, open-label, multicenter study of ARV-471(PF-07850327) plus palbociclib versus letrozole plus palbociclib for the treatment of participants with estrogen receptor-positive, HER2-negative breast cancer who have not received any prior systemic anti-cancer treatment for advanced disease (VERITAC-3).</p><p><br></p><p>C4891006: TACTIVE-U: An interventional safety and efficacy Phase 1b/2, open-label umbrella study to investigate tolerability, pk, and antitumor activity of vepdegestrant (ARV-471/PF-07850327), an oral Proteolysis Targeting Chimera, in combination with other anticancer treatments in participants Aged 18 years and Over with ER+ advanced or Metastatic breast cancer, Sub-study A (ARV-471 in combination with Abemaciclib).</p><p><br></p><p>C4891023: TACTIVE-U: an interventional safety and efficacy phase 1B/2, open-label umbrella study to investigate tolerability, PK, and antitumor activity of vepdegestrant (ARV-471/PF-07850327), an oral proteolysis targeting chimera, in combination with other anticancer treatments in participants aged 18 years and over with ER+ advanced or metastatic breast cancer, sub-study B (ARV-471 in combination with ribociclib).</p><p><br></p><p>C4891024: TACTIVE-U: An interventional safety and efficacy phase 1B/2, open-label umbrella study to investigate tolerability, PK, and antitumor activity of vepdegestrant (ARV-471/PF-07850327), an oral proteolysis targeting chimera, in combination with other anticancer treatments in participants aged 18 and older with ER+ advanced or metastatic breast cancer, sub-study c (ARV-471 in combination with samuraciclib).</p><p><br></p><p>C4891026: An interventional safety and efficacy phase 1b/2, open-label study to investigate tolerability, PK, and antitumor activity of vepdegestrant (ARV-471/PF-07850327), an oral proteolysis targeting chimera, in combination with PF-07220060 in participants aged 18 years and older with ER+/HER2- advanced or metastatic breast cancer.</p><p><br></p><p>Description of the Issue:</p><p>During a routine Regulatory Quality Assurance (RQA) audit conducted on 01 Feb 2024 and 02 Feb 2024 at site 1004 in the C4891001 study (Audit Report# AIA-002725), the auditor noted there was no evidence that the investigator provided adequate investigational product (IP) instructions to the study participants to protect their caregivers on proper handling of hazardous IP ARV-471. The IP is considered hazardous per the IP manual, however all C489 studies (C4891001, C4891002, C4891006, C4891023, C4891024 C4891026) do not contain language pertaining to the proper handling of the hazardous ARV-471 for the caregivers.</p> | Yes |  | 2024-07-12 | 2026-02-10 |  | Medicinal Product | Inadequate handling, storage, availability |  | 2024-07-14 23:41 | IP13-Investigational Medicinal Product | Shelley Kilgore | FALSE | The C4891001 Global GSM followed-up with the GSMs from the other ARV-471 studies (C4891002, C4891006 and C4891023) and noted the dosing diaries and ICDs for those studies also do not contain language pertaining to the proper handling of the hazardous ARV-471 for the caretaker. The C4891001 CSTL is adding this topic to the next Clinical sub-team meeting on 18-Mar-24 to determine next steps for incorporating standard hazardous ARV-471 handling language into the C489 ICDs and dosing diaries. |  |  | Pfizer guidance documents are focused on the safety of the study participants. The Safety Core Data sheet section 8 for Occupational Exposure provide instructions to Health Care Professional that work in the drug preparation and for which the Level of Exposure (LOE) is potentially higher than the safe level. There is no mention of the Safety of the caregivers who may come in contact with Investigational Product (IP) ARV-471 in any Pfizer guidance document. | Method/Procedure | Procedure/Form/Plan | Inconsistency Between Documents (Document Standard Lacking/Incorrect Standard Content) | MODEL 0 - LEGACY | Oncology
QE-114062 | C4891023 | (Empty) | QE-114062 |  | SCOUT CLINICAL | N | Minor | Closed | Scout Clinical, the preferred provider for participant payments and travel support services, was informed 08May that their banking partner has adjusted the URL specified on the ScoutPass debit card and the accompanying cardholder agreement document. The images of the debit card and the cardholder agreement are submitted with the patient-facing documents for IRB/EC approval. The banking partner will begin using the updated card and agreement as early as today and it is possible participants will receive a card and agreement that include a different URL from what was IRB/EC approved. The URL listed on the cards and agreements previously will have a redirect functionality to the new URL for the next 12 months. | 2024-05-08 | 2024-05-08 | 2024-05-09 14:17 | GCP_Minor_May-2024_Multiple: Vendor Engagement: Participant Facing Materials_Scout Clinical_Global |  | NO |  |  | No |  |  | 2024-05-09 |  | Ethics Oversight | Lacks evidence of ethics oversight |  |  | CT17-Payment and Reimbursement to Study Participants | Caitlin Balascio |  | Working with vendor to obtain updated images that can be submitted for IRB/EC approval. |  |  | NA | Human Performance | Omission Error |  | MODEL 0 - LEGACY | Oncology
QE-120192 | C4891023 | (Empty) | QE-120192 |  | PFIZER | N | Major | Closed | Several site organizations across Pfizer study programs are following their own site standard training processes/SOPs. Site training processes are being assessed for equivalency to CT33-GSOP and marked as "Completed" in Firecrest when the following CT33-GSOP criteria may not be met: The PI must be trained by Pfizer process for protocol amendments after being trained by Pfizer process for initial PST (e.g., IM, SIV, Firecrest, online meeting). The PI will follow its organization's training process after the initial Pfizer PST training.The site is not providing a confirmation that current/approved training materials are reviewed in their entirety. The site-specific training record provides a confirmation that staff have read &amp; understood the study training material. | 2024-06-10 | 2024-06-10 | 2024-06-11 15:11 | GCP_Major_Jun-2024_Enterprise Level; Multiple Studies: CMCD: Trend: Study Training Process_Multiple Sites; Pfizer_Global, CAN |  | YES | 2025-01-21 | <p>Product Protocol Number:</p><p>C1071007</p><p>&nbsp;</p><p>Involved Party / Country:</p><p>Multiple Sites / Canada</p><p><span><br></span></p><p><span>Protocol Title(s):</span></p><p><span>C1071007: a Phase 3, open-label, randomized, 2-arm study of elranatamab monotherapy vs lenalidomide in participants with newly diagnosed multiple myeloma after undergoing ASCT.</span></p><p><span><br></span></p><p><span>Description of the Issue(s):</span></p><p><span>On 9-Jun-2024, a training documentation review was conducted by Site Care Partners for Study C1071007 where it was identified principal Investigator (PI) training documentation appeared to have inconsistencies with the expectations of Standard Operating Procedure (SOP), CT33-GSOP-RF03 Pfizer GCP Training Requirement - Investigators while adhering to the Study Training Plan (STP), Protocol #:C1071007, Version 4.0 (18-Mar-2024), Section 2; Specifically bullets 1 and 3.&nbsp;</span></p><p><span><br></span></p><p><span>Site training processes are being assessed for equivalency to CT33-GSOP-RF03 Pfizer GCP (Good Clinical Practice) Training Requirement - Investigators and marked as "Completed" in Firecrest when the following CT33-GSOP-RF03 Pfizer GCP Training Requirement - Investigators criteria may not be met:</span></p><p><span>&nbsp;</span></p><p><span>-&nbsp; &nbsp;&nbsp;The PI must be trained by Pfizer process for protocol amendments after being trained by Pfizer process for initial PST (e.g., IM, SIV, Firecrest, online meeting). The PI will follow its organization's training process after the initial Pfizer PST training.&nbsp;</span></p><p><span><br></span></p><p><span>-&nbsp; &nbsp;&nbsp;The site does not provide confirmation that current/approved training materials are reviewed in their entirety. The site-specific training record provides confirmation that staff have read &amp; understood the study training material.&nbsp;</span></p><p><span><br></span></p><p><span>There was no impact to training requirements or study data due to the inconsistencies; however, more training than required was being completed by site PI’s and was not reflected in Firecrest.&nbsp;</span></p><p><br></p><p><br></p> | No | CAPA Plan included error proofing that will prevent reoccurrence | 2024-07-31 | 2025-07-30 |  | Quality Procedures | Requirement/process not met |  | 2024-08-01 15:13 | CT33-Study Training | Chantal Leduc | FALSE | Informed study team C1071007 of discrepancy between CT33-GSOP requirement, site 1070 training process and completion record in Firecrest. |  |  | Inconsistency between CT33-GSOP-RF03, Section 2: Pre-Trial Assessment Guidance and the Study Training Plan led to confusion on the site’s need to complete more training than required. &nbsp; | Method/Procedure | Procedure/Form/Plan | Inconsistency Between Documents (Document Standard Lacking/Incorrect Standard Content) | MODEL 0 - LEGACY | Oncology
QE-121748 | C4891023 | N | QE-121748 | 1010 | Amy Chien (C4891023-1010) | N | Minor | Closed | Current SCP was unable to locate internal documentation that the site specific Investigational Product Accountability Log (IPAL) was reviewed against the Pfizer IPAL to ensure the required elements listed in the green text of the Pfizer IPAL were met and authorization provided to site to use site specific IPAL. Upon discussion with the site about IP accountability records available for review during a SIV for another study, the site indicated there is a 2nd IP verifier (which is a requirement of the Pfizer IPAL), is on another source and not in the site specific IPAL in Vestigo (site's electronic IP accountability system). Site pharmacist indicated the source for the 2nd verifier is not provided to the Site Monitor or Site Care Partner because it is in a separate binder and not uploaded to Vestigo. Site Pharmacist indicated Vestigo access is provided to the sponsor representatives. | 2024-06-18 | 2024-06-18 | 2024-06-20 14:03 | GCP_Minor_Jun-2024_C4891023: Monitoring Responsibilities: IPAL Review_PPD_USA |  | NO |  |  | No |  |  | 2024-06-20 |  | Quality Procedures, Site Management and Monitoring | Failure to detect/document, Requirement/process not met |  |  | IP13-Investigational Medicinal Product | Susan Espolong-Kanda |  | Current SCP escalated issue to Study Team after being unable to locate internal documentation that site specific IPAL was reviewed against the Pfizer IPAL and authorization given to site to use site specific IPAL. Study Team confirmed there was no documentation they were aware of regarding this issue and provided guidance to open a Quality Event. SCP also reached out to Site Monitor and prior SCP who conducted oversight visits and inquired which source was reviewed to confirm 2nd IP verifier and neither was able to provide specific source reviewed for 2nd IP verifier. |  |  | NA | Human Performance | Omission Error |  | MODEL 0 - LEGACY | Oncology
QE-121748 | C4891023 | (Empty) | QE-121748 |  | PFIZER, PPD, INC. | N | Minor | Closed | Current SCP was unable to locate internal documentation that the site specific Investigational Product Accountability Log (IPAL) was reviewed against the Pfizer IPAL to ensure the required elements listed in the green text of the Pfizer IPAL were met and authorization provided to site to use site specific IPAL. Upon discussion with the site about IP accountability records available for review during a SIV for another study, the site indicated there is a 2nd IP verifier (which is a requirement of the Pfizer IPAL), is on another source and not in the site specific IPAL in Vestigo (site's electronic IP accountability system). Site pharmacist indicated the source for the 2nd verifier is not provided to the Site Monitor or Site Care Partner because it is in a separate binder and not uploaded to Vestigo. Site Pharmacist indicated Vestigo access is provided to the sponsor representatives. | 2024-06-18 | 2024-06-18 | 2024-06-20 14:03 | GCP_Minor_Jun-2024_C4891023: Monitoring Responsibilities: IPAL Review_PPD_USA |  | NO |  |  | No |  |  | 2024-06-20 |  | Quality Procedures, Site Management and Monitoring | Failure to detect/document, Requirement/process not met |  |  | IP13-Investigational Medicinal Product | Susan Espolong-Kanda |  | Current SCP escalated issue to Study Team after being unable to locate internal documentation that site specific IPAL was reviewed against the Pfizer IPAL and authorization given to site to use site specific IPAL. Study Team confirmed there was no documentation they were aware of regarding this issue and provided guidance to open a Quality Event. SCP also reached out to Site Monitor and prior SCP who conducted oversight visits and inquired which source was reviewed to confirm 2nd IP verifier and neither was able to provide specific source reviewed for 2nd IP verifier. |  |  | NA | Human Performance | Omission Error |  | MODEL 0 - LEGACY | Oncology
QE-122798 | C4891023 | N | QE-122798 | 1003, 1010, 1013, 1037, 1093, 1425 | Amy Chien (C4891006-1010), Amy Chien (C4891023-1010), Amy Chien (C4891026-1010), Andrew Leavitt (C0371002-1093), Andrew Leavitt (C3731003-1003), Hope Rugo (A5481173-1010), Hope Rugo (C4391022-1425), Hope Rugo (C4551001-1037), Kieuhoa Vo (A5481092-1003), Sofia Verstraete (A3921210-1013) | N | Major | Closed | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | 2024-06-24 | 2024-06-24 | 2024-06-24 21:47 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA |  | YES |  | <p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">Product Protocol Number</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">C0371002</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">C3731003</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">C4551001</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">C4391022</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">C4891006</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">C4891023</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">C4891026</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">A5481173</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">A5481092</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">A3921210</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">&nbsp;</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">Involved Party / Site Number / Country</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Leavitt, Andrew / C0371002 Site Number 1093 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Leavitt, Andrew / C3731003 Site Number 1003 / Unites States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI:&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">Verstraete, Sofia&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">/ A3921210 Site Number 1013 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Vo, Kieuhoa&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">/ A5481092 Site Number 1003 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Rugo, Hope&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">/ C4551001 Site Number 1037 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Rugo, Hope&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">/ A5481173 Site Number 1010 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Rugo, Hope&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">/ 4391022 Site Number 1425 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Chien, Amy Jo&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">/ C4891006 Site Number 1010 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Chien, Amy Jo&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">/ C4891023 Site Number 1010 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Chien, Amy Jo&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">/ C4891026 Site Number 1010 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">Vendor: PPD / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">Vendor: Syneos Health / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">Vendor: ICON / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">Pfizer / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">&nbsp;</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">To document Investigational Product (IP) dispensing, Pfizer requires that Investigator sites utilize Pfizer’s Investigational Product Accountability Log (IPAL) or an equivalent form or system. The Pfizer IPAL requires the Investigator site to document verification of IP dispensing by a second individual. The Investigator’s IP dispensing process and associated documentation is discussed as part of the Pre-Trial Assessment (PTA) of the site, before site initiation. It is the responsibility of the individual conducting the PTA to confirm that the site will use the Pfizer IPAL or an equivalent form or system that meets the requirements included in the Pfizer IPAL.&nbsp;</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">&nbsp;</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">Ten ongoing studies have Investigator sites at the University of California in San Francisco (UCSF) which utilizes a central pharmacy for dispensing of IP. On 10 Jun 2024, during a Site Initiation Visit (SIV) for C4891026 at site 1010, the Pfizer Site Care Partner (SCP) noted that the pharmacy utilized the Vestigo system for IP dispensing in place of the Pfizer IPAL. When questioned about whether the Vestigo system could document a second verifier for IP dispensing the pharmacy informed the SCP that their system did not document a second verifier. The pharmacy stated it was their process to document the verification of IP dispensing by a second individual on a separate paper form which was filed in a binder within the pharmacy. When questioned further about their standard operating procedure (SOP), it was noted that the documentation of a second verifier was not included in the pharmacy’s SOP. The paper form filed in the pharmacy was not accessible to Site Monitors or SCPs as they are not granted access to the pharmacy, and therefore the Site Monitors and SCPs could not confirm that IP was verified by a second individual before being prepared and administered to study participants.</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">&nbsp;</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">The following issues were noted:</span></span></p><ol><li><span style="font-family: Arial, sans-serif;">The UCSF pharmacy process was not adequately documented to demonstrate compliance with Pfizer requirements for a second verifier for IP dispensing, however eleven PTAs were completed for the impacted ten studies between 2018 and 2023 and none of the PTA reports indicated that the pharmacy’s Vestigo system did not document a second verifier.</span></li><li><span style="font-family: Arial, sans-serif;">Site Monitors conducted Monitoring Visits at ongoing sites at UCSF but did not identify the lack of a second verifier for IP dispensing.</span></li></ol> | No | Other | 2024-08-13 | 2026-02-10 |  | Quality Procedures | Requirement/process not met |  | 2024-09-29 21:56 | INV02-Investigational Site Selection, Preparation, and Initiation, No Process Assigned | Susan Espolong-Kanda | FALSE | During C4891026 Site Initiation Visit, Site Care Partner (SCP) informed site of the requirement for sponsor representatives to be able to view 2nd IP verifier source. Site Care Partner requested access to this source be made available, but site pharmacy would not agree as this is not their current practice and sponsor representatives have not raised this on past studies. SCP reached out to Site Monitors and prior and current SCPs working on study to confirm if there was any other 2nd IP verifier source outside of pharmacy records. SCP opened a QE for sister study C4891023 (QE-121748) which was closed. SCP also submitted an inquiry to INV02-INV04 BPO, to inquire about alternative 2nd IP verifier documentation that would be acceptable for non-pharmacy staff to provide. SCP for C4891023/C4891026 also informed other SCPs with assigned studies with UCSF breast oncology group. Since this was found to be a broader issue for all studies at institution, a 2nd QE is being opened. Please note: entering date of occurrence as SIV for a sister study reporting SCP is currently assigned, but could be earlier for other studies. |  |  | Gap Analysis, The Site Monitors did not have adequate knowledge of the requirements or know how to verify that requirements were being met. | Gap Analysis, Human Performance | Learning Error, N/A | Inadequate Information for Determination, N/A | MODEL 0 - LEGACY | Oncology
QE-122798 | C4891023 | (Empty) | QE-122798 |  | ICON PLC, PFIZER, PPD, INC., SYNEOS HEALTH LLC | N | Major | Closed | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | 2024-06-24 | 2024-06-24 | 2024-06-24 21:47 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA |  | YES |  | <p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">Product Protocol Number</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">C0371002</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">C3731003</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">C4551001</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">C4391022</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">C4891006</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">C4891023</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">C4891026</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">A5481173</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">A5481092</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">A3921210</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">&nbsp;</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">Involved Party / Site Number / Country</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Leavitt, Andrew / C0371002 Site Number 1093 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Leavitt, Andrew / C3731003 Site Number 1003 / Unites States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI:&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">Verstraete, Sofia&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">/ A3921210 Site Number 1013 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Vo, Kieuhoa&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">/ A5481092 Site Number 1003 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Rugo, Hope&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">/ C4551001 Site Number 1037 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Rugo, Hope&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">/ A5481173 Site Number 1010 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Rugo, Hope&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">/ 4391022 Site Number 1425 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Chien, Amy Jo&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">/ C4891006 Site Number 1010 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Chien, Amy Jo&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">/ C4891023 Site Number 1010 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">PI: Chien, Amy Jo&nbsp;</span><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">/ C4891026 Site Number 1010 / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">Vendor: PPD / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">Vendor: Syneos Health / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">Vendor: ICON / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">Pfizer / United States</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">&nbsp;</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">To document Investigational Product (IP) dispensing, Pfizer requires that Investigator sites utilize Pfizer’s Investigational Product Accountability Log (IPAL) or an equivalent form or system. The Pfizer IPAL requires the Investigator site to document verification of IP dispensing by a second individual. The Investigator’s IP dispensing process and associated documentation is discussed as part of the Pre-Trial Assessment (PTA) of the site, before site initiation. It is the responsibility of the individual conducting the PTA to confirm that the site will use the Pfizer IPAL or an equivalent form or system that meets the requirements included in the Pfizer IPAL.&nbsp;</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">&nbsp;</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">Ten ongoing studies have Investigator sites at the University of California in San Francisco (UCSF) which utilizes a central pharmacy for dispensing of IP. On 10 Jun 2024, during a Site Initiation Visit (SIV) for C4891026 at site 1010, the Pfizer Site Care Partner (SCP) noted that the pharmacy utilized the Vestigo system for IP dispensing in place of the Pfizer IPAL. When questioned about whether the Vestigo system could document a second verifier for IP dispensing the pharmacy informed the SCP that their system did not document a second verifier. The pharmacy stated it was their process to document the verification of IP dispensing by a second individual on a separate paper form which was filed in a binder within the pharmacy. When questioned further about their standard operating procedure (SOP), it was noted that the documentation of a second verifier was not included in the pharmacy’s SOP. The paper form filed in the pharmacy was not accessible to Site Monitors or SCPs as they are not granted access to the pharmacy, and therefore the Site Monitors and SCPs could not confirm that IP was verified by a second individual before being prepared and administered to study participants.</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif; color: rgb(0, 0, 0);">&nbsp;</span></span></p><p><span style="font-size: 11pt;"><span style="font-family: Arial, sans-serif;">The following issues were noted:</span></span></p><ol><li><span style="font-family: Arial, sans-serif;">The UCSF pharmacy process was not adequately documented to demonstrate compliance with Pfizer requirements for a second verifier for IP dispensing, however eleven PTAs were completed for the impacted ten studies between 2018 and 2023 and none of the PTA reports indicated that the pharmacy’s Vestigo system did not document a second verifier.</span></li><li><span style="font-family: Arial, sans-serif;">Site Monitors conducted Monitoring Visits at ongoing sites at UCSF but did not identify the lack of a second verifier for IP dispensing.</span></li></ol> | No | Other | 2024-08-13 | 2026-02-10 |  | Quality Procedures | Requirement/process not met |  | 2024-09-29 21:56 | INV02-Investigational Site Selection, Preparation, and Initiation, No Process Assigned | Susan Espolong-Kanda | FALSE | During C4891026 Site Initiation Visit, Site Care Partner (SCP) informed site of the requirement for sponsor representatives to be able to view 2nd IP verifier source. Site Care Partner requested access to this source be made available, but site pharmacy would not agree as this is not their current practice and sponsor representatives have not raised this on past studies. SCP reached out to Site Monitors and prior and current SCPs working on study to confirm if there was any other 2nd IP verifier source outside of pharmacy records. SCP opened a QE for sister study C4891023 (QE-121748) which was closed. SCP also submitted an inquiry to INV02-INV04 BPO, to inquire about alternative 2nd IP verifier documentation that would be acceptable for non-pharmacy staff to provide. SCP for C4891023/C4891026 also informed other SCPs with assigned studies with UCSF breast oncology group. Since this was found to be a broader issue for all studies at institution, a 2nd QE is being opened. Please note: entering date of occurrence as SIV for a sister study reporting SCP is currently assigned, but could be earlier for other studies. |  |  | Gap Analysis, The Site Monitors did not have adequate knowledge of the requirements or know how to verify that requirements were being met. | Gap Analysis, Human Performance | Learning Error, N/A | Inadequate Information for Determination, N/A | MODEL 0 - LEGACY | Oncology
QE-125834 | C4891023 | (Empty) | QE-125834 |  | PFIZER | N | Minor | Closed | A CMCD was originally submitted and approved in the legacy quality management system: (PR ID 2226522). Due to an administrative oversight, although the request for extension was requested prior to the end date of 06-Jul-2024, the extension request was not processed in time, and nonconformance is continuing as a new CMCD exception is processed in eQMS. Accordingly this quality event documents the nonconformance between the period between 7-Jul-24 and the approval of this new exception request. | 2024-07-09 | 2024-07-09 | 2024-07-09 20:33 | GCP_Minor_Jul-2024_Multiple Studies: QMS04 CMCD Exception Extension Request_Pfizer_Global |  | NO |  |  | No |  |  | 2024-07-09 |  | Quality Procedures | Requirement/process not met |  |  | QMS04-Management of Procedural Documents | Helen Adair-Vos |  | Since we cannot extend the expired exception in the legacy system, a new exception request was submitted in eQMS on 09-Jul-24 |  |  | NA | Human Performance | Omission Error |  | MODEL 0 - LEGACY | Oncology
QE-138736 | C4891023 | N | QE-138736 | 1009 | Antonio Giordano (C4891006-1009), Antonio Giordano (C4891023-1009) | N | Minor | Closed | Site specific Informed Consent document for Amendment 3 was not Pfizer approved prior to IRB approval. | 2024-09-16 | 2024-09-18 | 2024-09-18 16:14 | GCP_Minor_Sep-2024_C4891023; C4891006: Informed Consent Process_Giordano, Antonio; Juric, Dejan; Pfizer_USA |  | NO |  |  | No |  |  | 2024-09-18 |  | Quality Procedures | Requirement/process not met |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Judith Pride |  | ICD sent to CIPT for review. Study Manager notified of potential issue. |  |  | NA | Human Performance | Learning Error |  | MODEL 0 - LEGACY | Oncology
QE-138736 | C4891023 | Y | QE-138736 | 1001 | Dejan Juric (C4891006-1001), Dejan Juric (C4891023-1001) | N | Minor | Closed | Site specific Informed Consent document for Amendment 3 was not Pfizer approved prior to IRB approval. | 2024-09-16 | 2024-09-18 | 2024-09-18 16:14 | GCP_Minor_Sep-2024_C4891023; C4891006: Informed Consent Process_Giordano, Antonio; Juric, Dejan; Pfizer_USA |  | NO |  |  | No |  |  | 2024-09-18 |  | Quality Procedures | Requirement/process not met |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Judith Pride |  | ICD sent to CIPT for review. Study Manager notified of potential issue. |  |  | NA | Human Performance | Learning Error |  | MODEL 0 - LEGACY | Oncology
QE-138736 | C4891023 | (Empty) | QE-138736 |  | PFIZER | N | Minor | Closed | Site specific Informed Consent document for Amendment 3 was not Pfizer approved prior to IRB approval. | 2024-09-16 | 2024-09-18 | 2024-09-18 16:14 | GCP_Minor_Sep-2024_C4891023; C4891006: Informed Consent Process_Giordano, Antonio; Juric, Dejan; Pfizer_USA |  | NO |  |  | No |  |  | 2024-09-18 |  | Quality Procedures | Requirement/process not met |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Judith Pride |  | ICD sent to CIPT for review. Study Manager notified of potential issue. |  |  | NA | Human Performance | Learning Error |  | MODEL 0 - LEGACY | Oncology
QE-150142 | C4891023 | (Empty) | QE-150142 |  | PPD, INC. | N | Minor | Closed | On Friday 08Nov2024, a freezer within the PPD EU biorepository lost power. Although the REES temperature monitoring system and accompanying alarm management processes are in place, the procedure for management of alarms was not followed resulting in samples falling outside of acceptable range. PPD has initiated a quality event (QE-047838) and upon completion of the investigation a report will be provided.Impacted studies include: .85pt;"PPD Study Code .85pt;"Protocol #.85pt;"PFIZ0136.85pt;"C4891006.85pt;"PFIZ0137.85pt;"C4891023.85pt;"PFIZ0134.85pt;"C4891001.85pt;"PFIZ0135.85pt;"C4891002.85pt;"PFIZ0132.85pt;"C4221023 | 2024-11-15 | 2024-11-15 | 2024-11-15 21:31 | GCP_Minor_Nov-2024_Multiple: Biospecimen Management_PPD, INC_Global |  | NO |  |  | No |  |  | 2024-11-15 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens | Kristen Smedley |  | Confirming with PPD what initial actions have been taken and if samples were transferred to another freezer and their inventory database updated to indicate if the samples thawed. |  |  | NA | Equipment/System/Facility | Equipment |  | MODEL 0 - LEGACY | Oncology
QE-152071 | C4891023 | (Empty) | QE-152071 |  | CLARINESS GMBH | N | Minor | Closed | I wanted to let you know about a potential cyber-security incident with the HCP form on the breast cancer portfolio website for Clariness . This website includes the following studies C4891001, C4891002, C4391024, C4391022, C4891006, C4891023, C4891024, C4391002.. On Sunday 24th November 2024, we started receiving email notifications that the form was being submitted, the submission rate was one form per second and the lasted approximately an hour. The form being completed was not by a genuine user/HCP and was likely to be a bot. We received approximately 2000 emails. | 2024-11-25 | 2024-11-26 | 2024-11-27 21:11 | GCP_Minor_Nov-2024_Multiple Studies: Cyber Security Incident_Clariness_USA_ DOWNGRADE |  | NO |  | <p>N/A</p> | No | Minor/Unrated Quality Event | 2024-12-19 | 2024-12-19 |  | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) |  |  | CP411 | Andrea Gentry | FALSE | escalated this to Clariness, and they have updated the CAPTCHA on the website to resolve these issues with automated bots. I have asked for further information regarding this incident including other measures in place to ensure the security on the website. This has also been reported to Protect Pfizer incident response team. | [6 empty] | MODEL 0 - LEGACY | Oncology
QE-170101 | C4891023 | N | QE-170101 | 1010 | Amy Chien (C4891023-1010) | N | Major | Approved - In CAPA | UCSF Medical Center in California, USA was audited on 11 to 12 Sep2024 for C4891023 study (site 1010) and the auditors were refused onsite access to the pharmacy and some relevant pharmacy records for the study. UCSF personnel stated that as per their SOPs monitors and auditors are not allowed access to the pharmacy. The expected CAPA action for this situation was for UCSF to at allow at least an above study onsite visit to the pharmacy C4891023, C4891026, and C489 1006 as all 3 of these studies have the same issue i.e. UCSF repeatedly denying sponsor monitor and auditors onsite access to the pharmacy. UCSF to date have not allowed onsite visit to their pharmacy hindering the sponsor’s efforts to comply sponsor oversight requirements. The current understanding is that the sponsor has never seen the pharmacy at this facility. UCSF keep providing pre-recorded video of the pharmacy. | 2025-03-11 | 2025-03-14 | 2025-03-17 17:55 | GCP_Major_Mar-2025_C489: Failed CAPA: Pharmacy Access_Chien, Amy; University California, San Francisco_USA |  | YES |  | <p><span>Product Protocol Numbers:&nbsp;</span></p><p><span>C4891006</span></p><p><span>C4891023</span></p><p><span>C4891026</span></p><p><span>&nbsp;</span></p><p><span>Involved Party / Country:</span></p><p><span>PI: Chien, Amy (Site Number: 1010) / United States</span></p><p><span>University California, San Francisco</span></p><p><span>&nbsp;</span></p><p><span>Protocol Titles:</span></p><p><span>C4891006: TACTIV-U: An interventional safety and efficacy Phase 1b/2, open-label umbrella study to investigate tolerability, pk, and antitumor activity of Vepdegestrant (ARV-471/PF-07850327), an oral Proteolysis Targeting Chimera, in combination with other anticancer treatments in participants Aged 18 years and Over with ER+ advanced or Metastatic breast cancer, Sub-study A (ARV-471 in combination with Abemaciclib).</span></p><p><span>&nbsp;</span></p><p><span>C4891023: TACTIVE-U: An interventional safety and efficacy phase 1B/2, open-label umbrella study to investigate tolerability, PK, and antitumor activity of Vepdegestrant (ARV-471/PF-07850327), an oral proteolysis targeting chimera, in combination with other anticancer treatments in participants aged 18 years and over with ER+ advanced or metastatic breast cancer, sub-study B (ARV471 in combination with Ribociclib.)</span></p><p><span>&nbsp;</span></p><p><span>C4891026: An interventional safety and efficacy phase 1B/2, open-label study to investigate tolerability, PK, and antitumor activity of Vepdegestrant (ARV471/PF07850327), an oral proteolysis targeting chimera, in combination with PF-07220060 in participants aged 18 years and older with ER+/HER2- advanced or metastatic breast cancer.</span></p><p><span>&nbsp;</span></p><p><span>Description of the Issue:</span></p><p><span><span style="color: rgb(48, 48, 48); background-color: rgb(255, 255, 255);">Site 1010 for the impacted studies has not allowed oversight access to the investigational product (IP) pharmacy. The site has provided a pre-recorded video for review during monitoring and oversight activities. Along with an attestation that the videos content is current. The site is also providing virtual confirmation of IP inventory via Zoom call and is demonstrating accountability of records via the Vestigo system and providing access for oversight and monitoring. These practices allow monitoring to be conducted per the requirements of INV04-GSOP <i>Investigational Site Management and Monitoring.</i> However, the site has refused access to the pharmacy for above study level oversight (i.e. audit and oversight visits) which hinders the ability to complete these oversight activities. This issue was noted during a routine onsite audit on 11 Sep 2024 to 12 Sep 2024. The resultant Corrective and Preventive Action (CAPA) (CAPA-141429) required that an onsite above study pharmacy visit be conducted. However, the site declined to provide physical access to the pharmacy or a live video tour of the pharmacy for oversight purposes.&nbsp;</span></span></p> | Yes |  | 2025-07-07 |  |  | Quality Oversight | Inadequate Principal Investigator quality oversight |  | 2025-07-08 14:17 | INV04-Investigational Site Management and Monitoring | Karen Clarke | FALSE | Study team was contacted to ascertain if UCSF granted the onsite visit to the pharmacy and they had not. |  |  | The site is committed to limiting traffic into the Investigational Product (IP) Pharmacy due to the number of studies ongoing at the site and the potential risk posed to immuno-compromised patients at the hospital. The site believes that virtual access, along with Board of Pharmacy inspections, meets the needs of sponsors for oversight of the IP Pharmacy. | Method/Procedure | Contracts/Agreements | Inconsistent with Pfizer Requirements (Document Standard Lacking/Incorrect Standard Content) | MODEL 0 - LEGACY | Oncology
QE-173319 | C4891023 | N | QE-173319 | 1006 | Andrew Davis (C4891024-1006), Cynthia Ma (C4891006-1006), Katherine Clifton (C4891023-1006) | N | Major | Approved - In CAPA | Site is refusing to now complete Sponsor specific trainings like Suspected Serious Breach and general Safety Standalone trainings in Firecrest per new Site Policy/SOPs that were provided to Pfizer. Alerted the PPD CRO study team who escalated to Pfizer clinical management. | 2025-03-26 | 2025-04-04 | 2025-04-07 15:26 | GCP_Major_Apr-2025_C4891006, C4891023, C4891024: Study Training_Multiple PIs (Washington University)_USA |  | YES |  | <p>Product Protocol Number(s):&nbsp;</p><p>C4891006</p><p>C4891023</p><p>C4891024</p><p><br></p><p>Involved Party / Country:</p><p>PI(s): Cynthia Ma / C4891006 (Site 1006) / United States&nbsp;</p><p>Katherine Clifton / C4891023(Site 1006) / United States</p><p>Andrew Davis/ C4891024 (Site 1006) / United States</p><p><br></p><p>C4891006 is an interventional safety and efficacy Phase 1b/2, open-label umbrella study to investigate tolerability, PK, and antitumor activity of Vepdegestrant (ARV-471/PF-07850327), an oral Proteolysis targeting Chimera, in combination with other anticancer treatments in participants aged 18 years and aver with ER+ advanced or metastatic breast cancer, Sub-study A (ARV-471 in combination with Abemaciclib).</p><p><br></p><p>C4891023 is an interventional safety and efficacy phase 1b/2, open-label umbrella study to investigate tolerability, PK, and antitumor activity of Vepdegestrant (ARV-471/PF-07850327), an oral Proteolysis targeting Chimera, in combination with other anticancer treatments in participants aged 18 years and over with er+ advanced or metastatic breast cancer, Sub-study B (arv-471 in combination with Ribociclib).</p><p><br></p><p>C4891024 is an interventional safety and efficacy phase 1b/2, open-label umbrella study to investigate tolerability, PK, and antitumor activity of Vepdegestrant (ARV-471/PF-07850327), an oral Proteolysis targeting Chimera, in combination with other anticancer treatments in participants aged 18 and older with er+ advanced or metastatic breast cancer, Sub-study C (arv-471 in combination with Samuraciclib).</p><p><br></p><ul><li>Site 1006 participated in the C4891024 and C4891006 studies since 15 Dec 20202 and 19 Jan 2023, respectively. On 21 Feb 2024 the site was initiated for the C4891023 study.</li><li>As part of the Site Initiation Visit (SIV) Training materials, Safety Reporting slides were included and served as Serious Adverse Event (SAE) Reporting Training for the C4891006, C4891023, and C4891024 studies, and a stand-alone SAE Reporting Training was required for new staff delegated to that activity post SIV.</li><li>Firecrest a Sponsor Learning Management System where training completion is tracked.</li></ul><p><br></p><p>On 04 Oct 2023, site 1006’s Training Policy changed to include that amendments to sponsor-provided or protocol-specific training would be assessed by Principal Investigators for whether completion of those trainings is required. On 28 Feb 2024, the institution’s Education Policy had been changed to include Serious Adverse Events as part of their Oncology Research Education and Training for all new clinical research staff members, and the institution's Senior Clinical Research Coordinator within Regulatory informed the PPD/Thermofisher Project Manager that site staff would not be completing the SAE Reporting stand-alone training; PPD/Thermofisher alerted Pfizer Management of the site’s Education Policy change.</p><p><br></p><p>On 18 Dec 2024, Suspected Serious Breach Training, which had not been part of the SIV training materials, became a required site training for completion in Firecrest. On 26 Mar 2025, the institutions’ Senior Clinical Research Coordinator within Regulatory informed the C4891024 Pfizer Site Care Partner that site staff will not complete the Suspected Serious Breach Training. For the C4891006 study, two active staff who were delegated to SAE reporting did not complete the SAE Reporting training and no C4891006, C4891023 and C4891024 study site staff completed the Suspected Serious Breach Training.</p> | Yes |  | 2025-05-23 |  |  | Quality Procedures | Requirement/process not met |  | 2025-05-23 18:35 | CT33-Study Training | Catherine Battle | FALSE | Reporting QE after follow up with the BPO team. |  |  | The institution’s regulatory office incorrectly determined that their training was equivalent to Sponsor training and superseded Pfizer’s requirements that were contracted. As their Education and Training policies had been changed to not require Sponsor-specific training per PrincipaI Investigator (PI) assessment, the PIs declined to have newly delegated staff complete the Suspected Serious Breach and stand-alone Serious Adverse Event (SAE) Reporting trainings. | Human Performance | Decision Error | Desired Results are/or are Perceived to be in Conflict with Other Priorities | MODEL 0 - LEGACY | Oncology
QE-173319 | C4891023 | (Empty) | QE-173319 |  |  | N | Major | Approved - In CAPA | Site is refusing to now complete Sponsor specific trainings like Suspected Serious Breach and general Safety Standalone trainings in Firecrest per new Site Policy/SOPs that were provided to Pfizer. Alerted the PPD CRO study team who escalated to Pfizer clinical management. | 2025-03-26 | 2025-04-04 | 2025-04-07 15:26 | GCP_Major_Apr-2025_C4891006, C4891023, C4891024: Study Training_Multiple PIs (Washington University)_USA |  | YES |  | <p>Product Protocol Number(s):&nbsp;</p><p>C4891006</p><p>C4891023</p><p>C4891024</p><p><br></p><p>Involved Party / Country:</p><p>PI(s): Cynthia Ma / C4891006 (Site 1006) / United States&nbsp;</p><p>Katherine Clifton / C4891023(Site 1006) / United States</p><p>Andrew Davis/ C4891024 (Site 1006) / United States</p><p><br></p><p>C4891006 is an interventional safety and efficacy Phase 1b/2, open-label umbrella study to investigate tolerability, PK, and antitumor activity of Vepdegestrant (ARV-471/PF-07850327), an oral Proteolysis targeting Chimera, in combination with other anticancer treatments in participants aged 18 years and aver with ER+ advanced or metastatic breast cancer, Sub-study A (ARV-471 in combination with Abemaciclib).</p><p><br></p><p>C4891023 is an interventional safety and efficacy phase 1b/2, open-label umbrella study to investigate tolerability, PK, and antitumor activity of Vepdegestrant (ARV-471/PF-07850327), an oral Proteolysis targeting Chimera, in combination with other anticancer treatments in participants aged 18 years and over with er+ advanced or metastatic breast cancer, Sub-study B (arv-471 in combination with Ribociclib).</p><p><br></p><p>C4891024 is an interventional safety and efficacy phase 1b/2, open-label umbrella study to investigate tolerability, PK, and antitumor activity of Vepdegestrant (ARV-471/PF-07850327), an oral Proteolysis targeting Chimera, in combination with other anticancer treatments in participants aged 18 and older with er+ advanced or metastatic breast cancer, Sub-study C (arv-471 in combination with Samuraciclib).</p><p><br></p><ul><li>Site 1006 participated in the C4891024 and C4891006 studies since 15 Dec 20202 and 19 Jan 2023, respectively. On 21 Feb 2024 the site was initiated for the C4891023 study.</li><li>As part of the Site Initiation Visit (SIV) Training materials, Safety Reporting slides were included and served as Serious Adverse Event (SAE) Reporting Training for the C4891006, C4891023, and C4891024 studies, and a stand-alone SAE Reporting Training was required for new staff delegated to that activity post SIV.</li><li>Firecrest a Sponsor Learning Management System where training completion is tracked.</li></ul><p><br></p><p>On 04 Oct 2023, site 1006’s Training Policy changed to include that amendments to sponsor-provided or protocol-specific training would be assessed by Principal Investigators for whether completion of those trainings is required. On 28 Feb 2024, the institution’s Education Policy had been changed to include Serious Adverse Events as part of their Oncology Research Education and Training for all new clinical research staff members, and the institution's Senior Clinical Research Coordinator within Regulatory informed the PPD/Thermofisher Project Manager that site staff would not be completing the SAE Reporting stand-alone training; PPD/Thermofisher alerted Pfizer Management of the site’s Education Policy change.</p><p><br></p><p>On 18 Dec 2024, Suspected Serious Breach Training, which had not been part of the SIV training materials, became a required site training for completion in Firecrest. On 26 Mar 2025, the institutions’ Senior Clinical Research Coordinator within Regulatory informed the C4891024 Pfizer Site Care Partner that site staff will not complete the Suspected Serious Breach Training. For the C4891006 study, two active staff who were delegated to SAE reporting did not complete the SAE Reporting training and no C4891006, C4891023 and C4891024 study site staff completed the Suspected Serious Breach Training.</p> | Yes |  | 2025-05-23 |  |  | Quality Procedures | Requirement/process not met |  | 2025-05-23 18:35 | CT33-Study Training | Catherine Battle | FALSE | Reporting QE after follow up with the BPO team. |  |  | The institution’s regulatory office incorrectly determined that their training was equivalent to Sponsor training and superseded Pfizer’s requirements that were contracted. As their Education and Training policies had been changed to not require Sponsor-specific training per PrincipaI Investigator (PI) assessment, the PIs declined to have newly delegated staff complete the Suspected Serious Breach and stand-alone Serious Adverse Event (SAE) Reporting trainings. | Human Performance | Decision Error | Desired Results are/or are Perceived to be in Conflict with Other Priorities | MODEL 0 - LEGACY | Oncology
QE-191992 | C4891023 | (Empty) | QE-191992 |  | PPD, INC. | N | Minor | Closed | Jocelyn Hwang was the primary Site Monitor assigned to studies C4891006, C4891023, C4891024 and C4891026. She planned to leave PPD company, and her departure date was 27Jun2025.The expected Handover calls were conducted as planned with the replacing Monitor, and issues discussed as per updates entered in the INV04-GSOP-SD-GL01 - Site Management/Monitor to Site management/Monitor Transition Document.Due to an oversight, the finalized Site Management/Monitor to Site management/Monitor Transition Document has not been provided to the incoming CRA by Jocelyn Hwang as well as the transition notification to sites and to Pfizer Study Team. | 2025-07-21 | 2025-07-23 | 2025-07-23 17:55 | GCP_Minor_Jul-2025_Multiple Studies: Monitor Transition Documentation_PPD_USA |  | NO |  |  | No |  |  | 2025-07-23 |  | CAPA Management | Inadequate issue evaluation, CAPA development and/or completion (eg., QE, Audit or Inspection) |  |  | INV04-Investigational Site Management and Monitoring | Elke Hartlieb |  | The very first action was the notification to sites about Site Monitor transition, and the clarification to Pfizer Study Manager that sites also have the aCRA (Remote Site Monitor) as primary contact in case of issues, so no risks or missed questions because of such lack of transition notification.With regards to the transition forms, a internal IT request has been made by PPD to recover the forms updated by departing Site Monitor. This is still on going, and once forms are obtained, it will be finalized and filed in pTMF.As of note, since the handover meetings happened between Incoming and Departing Study Monitor, the site management activities can continue despite the form has not been finalized. |  |  | NA | Human Performance | Omission Error |  | MODEL 0 - LEGACY | Oncology
QE-219824 | C4891023 | (Empty) | QE-219824 |  | ORACLE | N | Minor | Closed | Inform LNMT is a separate functionality within Inform EDC which is used to set-up Local Labs and configure the lab normal ranges which are associated to corresponding Studies and Sites. MedTech team has access to Inform LNMT to perform these functions.Inform is a product of Oracle. And Oracle identified that, if multiple users are working in the LNMT and making updates in it, it is causing the audit to capture the username of another user. Oracle notified Pfizer about this identified issue and the action they have taken on 3/Dec/2025.Please note, this issue only affected the username attribution in the LNMT audit trail; all other clinical trial audit data remains accurate. Additionally, users were never able to perform actions outside of their authorized permissions. | 2025-12-03 | 2025-12-19 | 2025-12-19 20:22 | GCP_Minor_Dec-2025_Multiple Studies: InForm LNMT User Audit Trail_Oracle_Global |  | NO |  |  | No |  |  | 2025-12-19 |  | Data Collection and Management | Data management error |  |  | DMB07-Study Data Set Design and Setup | Prathamesh Patil |  | Oracle has implemented preventative fixes to prevent incorrect user attribution in the LNMT audit going forward. Please note that Oracle is unable to retroactively correct past occurrences of this issue. |  |  | NA | Equipment/System/Facility | System/Application |  | MODEL 0 - LEGACY | Oncology
QE-222177 | C4891023 | (Empty) | QE-222177 |  | PFIZER | N | Minor | Closed | CT26 Termination plan completed for: C4891002, C4891023, C4891024 before LSLV. | 2026-01-07 | 2026-01-09 | 2026-01-09 20:52 | GCP_Minor_Jan-2026_C4891002, C4891023, C4891024: CMCD: Study Termination Plan_Pfizer_Global |  | NO |  |  | No |  |  | 2026-01-09 |  | Quality Procedures | Failure to use adequate controls (e.g., Required Forms, templates) |  |  | CT26-Study Interruption or Termination | Andrew Marshall |  | SM raised the audit finding to CSTL for the studies. Team agreed that a QE should be filed. |  |  | NA | Method/Procedure | Procedure/Form/Plan |  | MODEL 0 - LEGACY | Oncology
QE-222185 | C4891023 | (Empty) | QE-222185 |  | PFIZER | N | Minor | Closed | The CT26 termination plan was implemented into ongoing studies: C4891002, C4891023, C4891024 due to reasons other than for safety or efficacy. The operation plan was to halt further enrollment or opening: phase 3, or phase 2 for C4891002, and then C4891023, C4891024, respectively. The registry status was discussed at the core-team call and aligned on with Study Planner, External partner and Clinical Trial Disclosure Operations lead and. The status of the studies in CT.GOV was shifted to Active, but not recruiting. No exception was requested to BPO of CT27 to address discord between CT26 plan completion and study status. During CT26 Audit for C4891023, team learned of the FAQ which states an exception should be requested if the Plan is to developed and implemented before LSLV. | 2026-01-07 | 2026-01-09 | 2026-01-21 18:54 | GCP_Minor_Jan-2026_C4891002, C4891023, C4891024: CMCD: CT27 Registry and Study Termination Plan_Pfizer_Global |  | NO |  |  | No |  |  | 2026-01-09 |  | Quality Procedures | Failure to use adequate controls (e.g., Required Forms, templates) |  |  | CT28-Public Disclosure of Pfizer-Sponsored Studies | Andrew Marshall |  | The issue regarding not requesting an exception to the BPO of CT27 was raised to CSTLs, and CSTL for C4891023 agreed with SM to file a QE. No update to CT.GOV is required as that status was reviewed and is reflected appropriately. "Active, not-recruiting" |  |  | NA | Method/Procedure | Procedure/Form/Plan |  | MODEL 0 - LEGACY | Oncology
QE-229805 | C4891023 | (Empty) | QE-229805 |  | PFIZER | N | Major | In Investigation | This is an Applicable Clinical Trial (ACT) / Phase 2 study. Late for submission to clinicaltrials.gov Protocol Amendment 4 v. 28OCT2025 (IRB approval 08JAN2026) was due 08FEB2026. No protocol amendment activity was triggered in Prime disclosure system. A ticket with the vendor Xogene was submitted on 06FEB2026 #8645 and a logic correction to the system will be deployed in release 4.0. Manual creation of the protocol amendment activity will occur, and submission activities are in progress. | 2026-02-23 | 2026-02-23 | 2026-02-25 15:05 | MED_PV_Feb2026_C4891023_Delayed ClinicalTrials.gov Submission of Protocol Amendment 4 Due to Prime Disclosure System Logic Error_Global |  | NO | [11 empty] | No Process Assigned | Michelle Secchiaroli |  | Submitted ticket to Xogene (Prime vendor) on 06FEB2026 #8645 and logic will be updated in future Prime release 4.0. | [6 empty] | MODEL 0 - LEGACY | Oncology
QE-233605 | C4891023 | (Empty) | QE-233605 |  | ICON PLC, PFIZER | N | Minor | Closed | The Clinical Image Management (CIM) team, which is part of the Data Acquisition team in CDIS, receives and archives clinical image files from Pfizer-contracted vendors who received these image files from sites and read them during a clinical trial. For most studies, the vendors securely transfer these images to Pfizer during or at the end of the study. The receipt, QC, and archiving of these clinical image files is managed by the CIM team. During the setup of the end-of-study clinical image transfer process from ICON Medical Imaging &amp; Cardiac Safety Solutions for studies C4891006 and C4891023, the ICON PM sent an email with a question asking where in the s3-cim-automation-prd folder in Pfizer Aspera Shares website they should upload the image files because there were seeing a number of sub-folders. When the ICON Project Manager (PM) sent an email with a screenshot of what he was seeing, it included files from other vendors and folders from other studies. What was visible to the ICON PM is a view that should be visible to Pfizer colleagues but not to external vendors. | 2026-03-13 | 2026-03-13 | 2026-03-16 17:42 | GCP_Minor_Mar-2026_ C4891023, C4891006: System Access; Confidentiality_ICON; Pfizer_Global |  | NO |  |  | No |  |  | 2026-03-16 |  | IT Systems | Inadequate system access or account management |  |  | CP411 | Deborah Shepard |  | An email will be sent to the CIM team members today to identify the cause and quickly determine how to prevent any additional inappropriate folder access. I will also set up a meeting with the team on Monday morning. |  |  | NA | Human Performance | Application Error |  | MODEL 0 - LEGACY | Oncology