## Standard_Quality_Dashboard - SQ
Case ID | Case Status | Observation ID | Obs Status | Submission Date | Issue Audit Report (Actual) | Center Number | principal investigator | Country | Description | Study ID | Protocol ID | Title Short Description | Drug Program Code | Rating | Event Type | Case CAPA Approved Due Date | Case CAPA Approved On | CAPA Plan In Place Timely | Obs CAPA Approved Due Date | Obs CAPA Approved On | Obs Target Completion Date | Obs Actual Completion Date | Case CAPA Closure Timely | Case Target Completion Date | Case Actual Completion Date | Obs CAPA Closure Timely | Selected Business Process | Taxonomy Level 1 | Taxonomy Level 2 | Study Status | Business Category | Study Phase | Study Priority | Asset | Dev China | Dev Japan | Rapid Model | Business Category
AIA-005019 | Closed | QE-139112 | Closed | (Empty) | 2024-10-02 | 1010 | (Empty) | UNITED STATES | The Sponsor’s access to study source records at the investigator site to perform required oversight was not in accordance with the signed clinical trial agreement (CSA) impacting the sponsor’s ability to fulfill its obligation to perform required oversight of study conduct at the site. Additionally, this issue of the Investigator Site not granting sponsor representatives access to the pharmacy was not raised as an issue in a timely manner. [Clinical Study Agreement-Prism Research LLC dba Nucleus Network, 25Oct2022; ICH E6(R2) 4.9.7 and 5.1.2)] Sponsor representatives i.e., monitors/Clinical research associates (CRAs), Site Care Partner, and auditors were not granted access to the site’s pharmacy and IP dispensing verification records due to site policy of not granting access to the pharmacy. Additionally, virtual pre-trial assessment and Site Initiation visits (SIV) were conducted on the 14Jul2022 and 28Jul2023, respectively. Therefore, no Sponsor representatives were able to visualize the IP and IP storage facility at this investigator site since the study began there. The issue was raised as part of quality event QE-122798 when a newly assigned Site Care Partner noticed authorization for the site to use their investigational product accountability log (IPAL) was missing. The site used the electronic system Vestigo to manage IP accountability and house IP temperature monitoring records. | C4891023 | C4891023 | A Routine Onsite Investigator Site Audit of Study C4891023 Site 1010, Dr. Amy Jo Chien, San Francisco, CA, USA | (Empty) | Major | AUDIT | 2024-11-13 | (Empty) | N | (Empty) | (Empty) | 2024-12-20 | 2024-12-11 | N | 2024-12-20 | 2025-11-19 | Y | INV02 - Investigational Site Selection, Preparation, and Initiation | Site Management and Monitoring | Failure to escalate or resolve issue | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
AIA-005019 | Closed | QE-140651 | Closed | (Empty) | 2024-10-02 | 1010 | (Empty) | UNITED STATES | Organization of trial records in the electronic investigator site file (e-ISF), Complion was inadequate to facilitate efficient and timely traceability of trial conduct activities impacting the Sponsor’s ability to effect required oversight of study conduct at the site. [INV04-GSOP-RF17, 6.0 Requirements for Source Document Review and Source Data Verification, 15Mar2024] Complion e-ISF had two sections, one for housing the regulatory study documents and the other where scanned source documents (not included in the EMR) were kept. The e-ISF did not have a consistent organized file structure by study visit type to allow easy and efficient review of these source records by study visit type. The site batched source study records (including but not limited to ECG tracings, AE logs, Nursing Flow Sheet used to record PK sample draw times and ECG times) from various visit types and dates in a single dated portable document format (pdf) record containing three hundred or more pages then upload this pdf to Complion. Further organization and labeling of the type of source records in a batched pdf was not always available resulting in the user of Complion having to engage in a time-consuming task of scrolling endlessly through pages and pages of records to check if a particular record type (e.g., AE Log for participant 10102002 with some 20 AEs entered in the electronic data capture that was embedded in a batched pdf record) was included in the pdf batch record. Please note during the auditors interaction with site study staff, they became aware that the site staff had an internal electronic file share area where study records were organized by study visit type (screening etc.,) from which records were generated in pdf batched records and uploaded to Complion. The site study staff informed the auditors that only the site staff have access to this internal electronic file share area, the site monitor/clinical research associate was never granted access to this internal electronic file share area. Additionally, the Site’s Study Coordinator supervisor stated that this batched pdf approach was used because it took a lot of time (approximately 5 minutes) for a pdf record to be uploaded to Complion, a burden for site coordinators. | C4891023 | C4891023 | A Routine Onsite Investigator Site Audit of Study C4891023 Site 1010, Dr. Amy Jo Chien, San Francisco, CA, USA | (Empty) | Major | AUDIT | 2024-11-13 | (Empty) | N | (Empty) | (Empty) | 2024-12-20 | 2025-11-19 | N | 2024-12-20 | 2025-11-19 | N | INV04 - Investigational Site Management and Monitoring | Data Collection and Management | Inadequate source data/documentation | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
AIA-005019 | Closed | QE-140662 | Closed | (Empty) | 2024-10-02 | 1010 | (Empty) | UNITED STATES | The quality of essential trial records was deficient. [ICH E6 (R2) 4.9.0] a) For 3 of 3 participants (10102001, 10102002, 10102003) records reviewed, the quality of the signed Health Insurance Portability and Accountability Act consent documents was deficient. The e-sign electronic signatures affixed to form to denote the study participants initials in a specific section of the document obscured the text of HIPAA consent document. This was discussed with the site, and they acknowledged that remediation would require an Information Technology (IT) solution by the University of California San Francisco (UCSF) not the C4891023 Site 1010 study team. b) It could not be determined when the adverse event (AE) Log adverse event entries stop dates were added to the log nor when the causality assessment was performed for each entry on the log. The site utilized e-Sign electronic signature on the AE Logs where electronic signatures with several different dates were affixed to the bottom of the document. The AE Logs were cumulative with each AE occupying a separate line on the log with its respective start stop date, seriousness, and relatedness to each study medication. c) The site inconsistently completed the causality assessment field on the AE Log. For example, participant 10102003 AE Log (Day -7 10Apr2024; C1D1 17Apr2024) was completed using Y for related and N for not related instead of using the pre-printed relatedness number key at the bottom of the AE Log. | C4891023 | C4891023 | A Routine Onsite Investigator Site Audit of Study C4891023 Site 1010, Dr. Amy Jo Chien, San Francisco, CA, USA | (Empty) | Major | AUDIT | 2024-11-13 | (Empty) | N | (Empty) | (Empty) | 2024-12-20 | 2025-04-29 | N | 2024-12-20 | 2025-11-19 | N | INV04 - Investigational Site Management and Monitoring | Quality Oversight/Documentation | Inadequate quality documentation | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
AIA-005019 | Closed | QE-140667 | Approved - In CAPA | (Empty) | 2024-10-02 | 1010 | (Empty) | UNITED STATES | From the audit trail sample provided by the site for their Electronic Medical Record (EMR) Epic Hyperspace, it could not be determined if the e-Source Readiness Assessment responses for the EMR Audit Trail were accurate. [ICH E6(R2) 5.5.3 a.c] The audit trail record provided did not clearly demonstrate the exact data that was added and/or removed but only reference the titled section of the EMR accessed by the user. Additionally, it was unknown if and how the EMR’s audit trail functionality was protected from unauthorized deletion since an Information Technology (IT) subject matter expert (SME) for the site was not available during the audit to demonstrate the system or answer related questions. | C4891023 | C4891023 | A Routine Onsite Investigator Site Audit of Study C4891023 Site 1010, Dr. Amy Jo Chien, San Francisco, CA, USA | (Empty) | Major | AUDIT | 2024-11-13 | (Empty) | N | (Empty) | (Empty) | 2024-12-20 | 2025-03-26 | N | 2024-12-20 | 2025-11-19 | N | DMB03-GSOP - Data Management | IT Systems | Inadequate IT system (eg. planning, definitions, design, development, testing, validation, support) per regulatory requirements | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
AIA-005019 | Closed | QE-140673 | Closed | (Empty) | 2024-10-02 | 1010 | (Empty) | UNITED STATES | For 3 of 3 participants records reviewed, there were discrepancies between the source data and the corresponding electronic case report form(e-CRF). [ICH E6(R2) 4.9.2] The following examples (not all inclusive) were observed: Participant 10102001: Adverse event (AE) log entries had stop dates that were not recorded in the e-CRF &nbsp;Headache (start date 21Nov2023) stop date of 23Apr2024 was missing from the e-CRF. Constipation (start date 21Nov2023) stop date of 23 Apr2024 was missing from the e-CRF. Nausea (start date 22Nov2023) stop date of 23 Apr2024 was missing from the e-CRF. Fatigue (start date 06Dec2023) stop date of 23 Apr2024 was missing from the e-CRF. Hot flashes (Grade 2 with start date 17Jan2024) were missing stop date 24Apr2024 Neutrophil Count Decreased (Grade 3 with start date 06Dec2023) stop date 15Dec2023 was missing from e-CRF. AE entry of fatigue with start date 24Apr2024 was recorded on AE log but not the e-CRF. &nbsp;&nbsp; Participant 10102002: AEs causality relatedness entered in the e-CRF was missing from the AE Log for: Hot Flashes (Grade 1) with start date 25Jan2024 Neck ache (Grade 1) with start date 14Feb2024 Wrist ache (Grade 1) with start date 14Feb2024 Participant 10102003: Adverse events information recorded in the e-CRF but missing from the AE Log: - -Pruritic Rash Right exterior upper arm (Grade 1) with start date 16Jul2024 and ongoing -Neutrophil count decreased (Grade 3) start date 06Aug2024 stop date 12Aug2024 AE dyspnea (grade 1) recorded on the AE Log with start date 27Mar2024 and stop date 11Jun2024 had the stop date omitted from the e-CRF entry. | C4891023 | C4891023 | A Routine Onsite Investigator Site Audit of Study C4891023 Site 1010, Dr. Amy Jo Chien, San Francisco, CA, USA | (Empty) | Minor | AUDIT | 2024-11-13 | (Empty) | N | (Empty) | (Empty) | 2024-12-20 | 2024-12-16 | N | 2024-12-20 | 2025-11-19 | Y | DMB03-GSOP - Data Management | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-103298 | Closed | QE-103298 | Closed | 2024-03-11 | (Empty) | (Empty) | PFIZER | (Empty) | During site 1004's Pfizer C4891001 RQA audit, the Auditor noted there was no evidence that the investigator provided adequate investigational product (IP) instructions to the participants to protect the participants’ caregivers (other than the participants) from the hazardous IP (ARV-471). The C4891001 Global GSM noted the dosing diary and ICD do not contain language pertaining to the proper handling of the hazardous ARV-471 for the caretaker, as it is written in the current IP manual. | C4891023 | C4891023 | GCP_Major_Mar-2024_Multiple C489 Studies: Investigational Product (IP) Handling_Pfizer_Global | C489 | Major | SQE | 2024-07-08 | 2024-07-14 | N | 2024-07-08 | 2024-07-14 23:41 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | IP13 - Study Investigational Product Supplies | Medicinal Product | Inadequate handling, storage, availability | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-120192 | Closed | QE-120192 | Closed | 2024-06-10 | (Empty) | (Empty) | PFIZER | (Empty) | Several site organizations across Pfizer study programs are following their own site standard training processes/SOPs. Site training processes are being assessed for equivalency to CT33-GSOP and marked as "Completed" in Firecrest when the following CT33-GSOP criteria may not be met: The PI must be trained by Pfizer process for protocol amendments after being trained by Pfizer process for initial PST (e.g., IM, SIV, Firecrest, online meeting). The PI will follow its organization's training process after the initial Pfizer PST training.The site is not providing a confirmation that current/approved training materials are reviewed in their entirety. The site-specific training record provides a confirmation that staff have read &amp; understood the study training material. | C4891023 | C4891023 | GCP_Major_Jun-2024_Enterprise Level; Multiple Studies: CMCD: Trend: Study Training Process_Multiple Sites; Pfizer_Global, CAN | C489 | Major | SQE | 2024-07-26 | 2024-08-01 | N | 2024-07-26 | 2024-08-01 15:13 | 2025-01-21 | 2025-07-30 | N | 2025-01-21 | 2025-07-30 | N | CT33 - Study-Specific Training | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1003 | Andrew Leavitt (C3731003-1003) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1003 | Andrew Leavitt (C3731003-1003) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1003 | Kieuhoa Vo (A5481092-1003) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1003 | Kieuhoa Vo (A5481092-1003) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1010 | Amy Chien (C4891006-1010) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1010 | Amy Chien (C4891006-1010) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1010 | Amy Chien (C4891023-1010) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1010 | Amy Chien (C4891023-1010) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1010 | Amy Chien (C4891026-1010) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1010 | Amy Chien (C4891026-1010) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1010 | Hope Rugo (A5481173-1010) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1010 | Hope Rugo (A5481173-1010) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1013 | Sofia Verstraete (A3921210-1013) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1013 | Sofia Verstraete (A3921210-1013) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1037 | Hope Rugo (C4551001-1037) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1037 | Hope Rugo (C4551001-1037) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1093 | Andrew Leavitt (C0371002-1093) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1093 | Andrew Leavitt (C0371002-1093) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1425 | Hope Rugo (C4391022-1425) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | 1425 | Hope Rugo (C4391022-1425) | UNITED STATES | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | (Empty) | ICON PLC | (Empty) | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | (Empty) | ICON PLC | (Empty) | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | (Empty) | PFIZER | (Empty) | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | (Empty) | PFIZER | (Empty) | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | (Empty) | PPD, INC. | (Empty) | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | (Empty) | PPD, INC. | (Empty) | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | (Empty) | SYNEOS HEALTH LLC | (Empty) | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | INV02 - Investigational Site Selection, Preparation, and Initiation | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-122798 | Closed | QE-122798 | Closed | 2024-06-24 | (Empty) | (Empty) | SYNEOS HEALTH LLC | (Empty) | Past/Ongoing studies (C4891006, 1891023, C4551001, A5481173, 5481092) and studies in start-up (C4891026, C4391022) do not have prior internal documentation that the site specific IPAL was reviewed and authorization given to site to use site specific IPAL. In addition, the site does not provide access to all pharmacy source to sponsor representatives (eg: Site Monitor and Site Care Partner) specifically source to verify or QC 2nd IP verifier. Site uses an electronic IP accountability system called Vestigo. Vestigo captures the 1st IP Verifier. Vestigo review access is granted to sponsor representatives. The 2nd IP verifier is captured on a paper form that is filed in a physical binder in the pharmacy. This form is not scanned and uploaded into Vestigo. The pharmacy does not currently allow visitors so sponsor representatives are until to view the pharmacy binder. Site's current SOP does not include process regarding 2nd IP verifier. However, site pharmacist recently informed Site Care Partner that site pharmacy is in the process of updating SOP to reflect this. | C4891023 | C4891023 | GCP_Major_Jun-2024_Multiple Studies: CMCD: Process: IPAL Review, 2nd IP Verifier and Site SOP_UCSF; PPD; Syneos; ICON; Pfizer_USA | C489 | Major | SQE | 2024-08-08 | 2024-09-29 | N | 2024-08-08 | 2024-09-29 21:56 | (Empty) | 2026-02-11 | (Empty) | (Empty) | 2026-02-11 | (Empty) | NOT APPLICABLE | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-170101 | Approved - In CAPA | QE-170101 | Approved - In CAPA | 2025-03-14 | (Empty) | 1010 | Amy Chien (C4891023-1010) | UNITED STATES | UCSF Medical Center in California, USA was audited on 11 to 12 Sep2024 for C4891023 study (site 1010) and the auditors were refused onsite access to the pharmacy and some relevant pharmacy records for the study. UCSF personnel stated that as per their SOPs monitors and auditors are not allowed access to the pharmacy. The expected CAPA action for this situation was for UCSF to at allow at least an above study onsite visit to the pharmacy C4891023, C4891026, and C489 1006 as all 3 of these studies have the same issue i.e. UCSF repeatedly denying sponsor monitor and auditors onsite access to the pharmacy. UCSF to date have not allowed onsite visit to their pharmacy hindering the sponsor’s efforts to comply sponsor oversight requirements. The current understanding is that the sponsor has never seen the pharmacy at this facility. UCSF keep providing pre-recorded video of the pharmacy. | C4891023 | C4891023 | GCP_Major_Mar-2025_C489: Failed CAPA: Pharmacy Access_Chien, Amy; University California, San Francisco_USA | C489 | Major | SQE | 2025-05-01 | 2025-07-08 | N | 2025-05-01 | 2025-07-08 14:17 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | INV04 - Investigational Site Management and Monitoring | Quality Oversight | Inadequate Principal Investigator quality oversight | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-173319 | Approved - In CAPA | QE-173319 | Approved - In CAPA | 2025-04-04 | (Empty) | 1006 | Andrew Davis (C4891024-1006) | UNITED STATES | Site is refusing to now complete Sponsor specific trainings like Suspected Serious Breach and general Safety Standalone trainings in Firecrest per new Site Policy/SOPs that were provided to Pfizer. Alerted the PPD CRO study team who escalated to Pfizer clinical management. | C4891023 | C4891023 | GCP_Major_Apr-2025_C4891006, C4891023, C4891024: Study Training_Multiple PIs (Washington University)_USA | C489 | Major | SQE | 2025-05-22 | 2025-05-23 | N | 2025-05-22 | 2025-05-23 18:35 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT33 - Study-Specific Training | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-173319 | Approved - In CAPA | QE-173319 | Approved - In CAPA | 2025-04-04 | (Empty) | 1006 | Cynthia Ma (C4891006-1006) | UNITED STATES | Site is refusing to now complete Sponsor specific trainings like Suspected Serious Breach and general Safety Standalone trainings in Firecrest per new Site Policy/SOPs that were provided to Pfizer. Alerted the PPD CRO study team who escalated to Pfizer clinical management. | C4891023 | C4891023 | GCP_Major_Apr-2025_C4891006, C4891023, C4891024: Study Training_Multiple PIs (Washington University)_USA | C489 | Major | SQE | 2025-05-22 | 2025-05-23 | N | 2025-05-22 | 2025-05-23 18:35 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT33 - Study-Specific Training | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-173319 | Approved - In CAPA | QE-173319 | Approved - In CAPA | 2025-04-04 | (Empty) | 1006 | Katherine Clifton (C4891023-1006) | UNITED STATES | Site is refusing to now complete Sponsor specific trainings like Suspected Serious Breach and general Safety Standalone trainings in Firecrest per new Site Policy/SOPs that were provided to Pfizer. Alerted the PPD CRO study team who escalated to Pfizer clinical management. | C4891023 | C4891023 | GCP_Major_Apr-2025_C4891006, C4891023, C4891024: Study Training_Multiple PIs (Washington University)_USA | C489 | Major | SQE | 2025-05-22 | 2025-05-23 | N | 2025-05-22 | 2025-05-23 18:35 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT33 - Study-Specific Training | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-173319 | Approved - In CAPA | QE-173319 | Approved - In CAPA | 2025-04-04 | (Empty) | (Empty) | (Empty) | (Empty) | Site is refusing to now complete Sponsor specific trainings like Suspected Serious Breach and general Safety Standalone trainings in Firecrest per new Site Policy/SOPs that were provided to Pfizer. Alerted the PPD CRO study team who escalated to Pfizer clinical management. | C4891023 | C4891023 | GCP_Major_Apr-2025_C4891006, C4891023, C4891024: Study Training_Multiple PIs (Washington University)_USA | C489 | Major | SQE | 2025-05-22 | 2025-05-23 | N | 2025-05-22 | 2025-05-23 18:35 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | CT33 - Study-Specific Training | Quality Procedures | Requirement/process not met | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology
QE-229805 | In Investigation | QE-229805 | In Investigation | 2026-02-23 | (Empty) | (Empty) | PFIZER | (Empty) | This is an Applicable Clinical Trial (ACT) / Phase 2 study. Late for submission to clinicaltrials.gov Protocol Amendment 4 v. 28OCT2025 (IRB approval 08JAN2026) was due 08FEB2026. No protocol amendment activity was triggered in Prime disclosure system. A ticket with the vendor Xogene was submitted on 06FEB2026 #8645 and a logic correction to the system will be deployed in release 4.0. Manual creation of the protocol amendment activity will occur, and submission activities are in progress. | C4891023 | C4891023 | MED_PV_Feb2026_C4891023_Delayed ClinicalTrials.gov Submission of Protocol Amendment 4 Due to Prime Disclosure System Logic Error_Global | C489 | Major | SQE | 2026-04-11 | (Empty) | (Empty) | 2026-04-11 | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | (Empty) | ONGOING | Oncology | PHASE II | STREAMLINE | ARV-471 Combinations | (Empty) | (Empty) | MODEL 0 - LEGACY | Oncology