## Standard_Quality_Dashboard - Au
AMS Audit PR ID | AMS Observation PR ID | Target Completion Date | Actual Completion Date | TCD Due/Overdue Days | TCD Status | Observation Closed On | Observation Rating | Observation Phase | Investigator Full Name | Country | Unique Site Number | Type Of Entity | Issue Of Audit Report Actual | Issue Audit Closure Rpt Act | Observation Description | Response (Trackwise Only) | Actions Taken | CAPA Action Description | CAPA Action Created by | Responsibility | Responsible Contact | Audit Coordinator | Observation Status | Audit Status | Level 1 | Level 2 | Selected Business Process | Responsible Party Value | Rapid Model | Business Category | Site Care Partner | Cluster | Area ID | Area Name
AIA-005020 | QE-141568 | 2024-10-08 | 2024-10-08 |  | Completed On Time |  | Minor |  | Kan Yonemori, Kan Yonemori | JAPAN | C4891026_1056 | GCP Site Audit | 2024-10-16 |  | Essential documents in the Pfizer Trial Master File (PTMF) were missing/incomplete/inaccurate [Pfizer SOP CT01- GSOP 8.0, Trial Master Files, effective 03 Oct 2022] The following essential document was missing in the PTMF. 1) The revision history of Informed Consent Document (ICD) version 2.0 (15 Jan 2024) with the comments of Institutional Review Board (IRB) and the responses to the comments from Principal Investigator (PI). Note: It could not be confirmed from PTMF document the reason why the ICD version 1.0 was needed to revise to version 2.0 without above ICD revision history. There were comments to revise the ICD version 1.0 (13 Dec 2023) from IRB members via the electronic site file system (DDworks NX). The IRB comments and the responses to the comments were described in the revision history of ICD version 2.0 (15 Jan 2024), and this revision history of ICD version 2.0 (15 Jan 2024) and ICD version 2.0 (15 Jan 2024) was submitted to the site from Pfizer on 15 Jan 2024. However, the revision history of ICD version 2.0 (15 Jan 2024) was not filed in the PTMF nor attached to the Clinical trial application form (15 Jan 2024, IRB Submission Filing Package). The following essential document was inaccurate in the PTMF 2) &nbsp;Pregnant Partner Release of Information Form version 1.0 (11 Dec 2023) was not submitted to the site on 15 Jan 2024; however, it was attached to the Clinical trial application form (15 Jan 2024, IRB Submission Filing Package) in the PTMF. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | CRA deactivated below incorrect document which is stored in PTMF on 2-Oct-2024.- Clinical trial application form (15-Jan-2024, IRB Submission Filing Package) which is merged with ‘Pregnant Partner Release of Information Form version 1.0 (11-Dec-2023)’CRA submitted the updated below correct document to PTMF appropriately on 8-Oct-2024.- Clinical trial application form (15-Jan-2024, IRB Submission Filing Package) which is merged with ‘The revision history of Informed Consent Document (ICD) version 2.0 (15-Jan-2024)’ | CRA should deactivate the incorrect document and also store correct document to PTMF appropriately. | Kunimi Matsumi |  | - | Kunimi Matsumi | Closed | Closed | Document Management | Missing document | CT01 - Trial Master Files | PFIZER | MODEL 0 - LEGACY | Oncology |  | GSSO | 311 | APAC
AIA-005020 | QE-141580 | 2024-10-02 | 2024-10-02 |  | Completed On Time |  | Minor |  | Kan Yonemori, Kan Yonemori | JAPAN | C4891026_1056 | GCP Site Audit | 2024-10-16 |  | For 2 out of 2 participants reviewed, there were inconsistencies between source records and electronic Case Report Forms (eCRF). [Pfizer Protocol C4891026 (Amendment 2: 11 Apr 2024)] The following were noted:&nbsp; Participant 10564001 1) Dose frequency of CONCOMITANT MEDICATION [2] Rilmazafone Hydrochloride Hydrate was recorded “QD (once per day)” in Electronic Medical Record (EMR), but it was reported “QID (4 times per day)” in the eCRF. 2) PF-07220060 Treatment was QD on 25 Mar 2024 (Cycle1Day15) in Dosing Record, but it was reported “BID (2 times per day)” in the eCRF. &nbsp; 3) The reason the dose adjusted for PF-07220060 on 25 Mar 2024 (Cycle1Day15) was record “Adverse Event (AE)[3] Platelet count decreased ” in EMR, but the reason was not reported in the eCRF, Form TREATMENT - REPEATING - PF-07220060.&nbsp; 4) Dose Adjusted from planned for PF-07220060 Treatment was recorded “yes” in EMR on 25 Mar 2024 (Cycle1Day15) but it was reported “NO” in the eCRF 5) PK DOSING time of PF-07220060 in clinic on 18 Mar 2024 was recorded “10:30 am” in EMR but it was reported “8:54 am” in the eCRF.&nbsp; Participant 10564002 6) Dose description of CONCOMITANT MEDICATION [3] Molnupiravir was recorded “800mg” in Electronic Medical Record (EMR), but it was reported “200mg” in the eCRF. &nbsp; 7) Diameter of Target Lesion [1] Left breast at Screening was recorded “70.99” in the EMR (site used the rounding to the first decimal place, this means 71.0), &nbsp;but it was reported “70.9” in the eCRF. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | CRA requested the study coordinator to correct the data appropriately on 2-Oct-2024. Study coordinator corrected all the data and CRA confirmed them on 2-Oct-2024. | CRA should request the study coordinator to correct the data appropriately. | Kunimi Matsumi |  | - | Kunimi Matsumi | Closed | Closed | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | DMB07 - CRF and Database Design | PRINCIPAL INVESTIGATOR | MODEL 0 - LEGACY | Oncology |  | GSSO | 311 | APAC
AIA-005020 | QE-141580 | 2024-10-02 | 2024-10-02 |  | Completed On Time |  | Minor |  | Kan Yonemori, Kan Yonemori | JAPAN | C4891026_1056 | GCP Site Audit | 2024-10-16 |  | For 2 out of 2 participants reviewed, there were inconsistencies between source records and electronic Case Report Forms (eCRF). [Pfizer Protocol C4891026 (Amendment 2: 11 Apr 2024)] The following were noted:&nbsp; Participant 10564001 1) Dose frequency of CONCOMITANT MEDICATION [2] Rilmazafone Hydrochloride Hydrate was recorded “QD (once per day)” in Electronic Medical Record (EMR), but it was reported “QID (4 times per day)” in the eCRF. 2) PF-07220060 Treatment was QD on 25 Mar 2024 (Cycle1Day15) in Dosing Record, but it was reported “BID (2 times per day)” in the eCRF. &nbsp; 3) The reason the dose adjusted for PF-07220060 on 25 Mar 2024 (Cycle1Day15) was record “Adverse Event (AE)[3] Platelet count decreased ” in EMR, but the reason was not reported in the eCRF, Form TREATMENT - REPEATING - PF-07220060.&nbsp; 4) Dose Adjusted from planned for PF-07220060 Treatment was recorded “yes” in EMR on 25 Mar 2024 (Cycle1Day15) but it was reported “NO” in the eCRF 5) PK DOSING time of PF-07220060 in clinic on 18 Mar 2024 was recorded “10:30 am” in EMR but it was reported “8:54 am” in the eCRF.&nbsp; Participant 10564002 6) Dose description of CONCOMITANT MEDICATION [3] Molnupiravir was recorded “800mg” in Electronic Medical Record (EMR), but it was reported “200mg” in the eCRF. &nbsp; 7) Diameter of Target Lesion [1] Left breast at Screening was recorded “70.99” in the EMR (site used the rounding to the first decimal place, this means 71.0), &nbsp;but it was reported “70.9” in the eCRF. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | CRA requested the study coordinator to correct the data appropriately on 2-Oct-2024. Study coordinator corrected all the data and CRA confirmed them on 2-Oct-2024. | CRA should request the study coordinator to correct the data appropriately. | Kunimi Matsumi |  | - | Kunimi Matsumi | Closed | Closed | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | DMB07 - CRF and Database Design | SITE PERSONNEL | MODEL 0 - LEGACY | Oncology |  | GSSO | 311 | APAC
AIA-005020 | QE-141564 | 2024-10-01 | 2024-10-01 |  | Completed On Time |  | Minor |  | Kan Yonemori, Kan Yonemori | JAPAN | C4891026_1056 | GCP Site Audit | 2024-10-16 |  | Essential documents were missing in the Investigator Site File (ISF). [ICH E6 (R2) 4.9.4] The following essential documents were missing in ISF.&nbsp; &nbsp; &nbsp; &nbsp;1) Personal Data Consent Forms for Principal Investigator (PI) and 13 Sub-Investigators (SIs). &nbsp;&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | CRA sent all the missing PDCF to DDTS on 30-Sep-2024. PI confirmed them on 1-Oct-2024. | CRA should send all the missing PDCF to DDTS. And PI sohuld confirm it. | Kunimi Matsumi |  | - | Kunimi Matsumi | Closed | Closed | Document Management | Missing document | CT01 - Trial Master Files | PRINCIPAL INVESTIGATOR | MODEL 0 - LEGACY | Oncology |  | GSSO | 311 | APAC
AIA-007076 | QE-172688 | 2025-06-30 | 2025-06-05 |  | Completed On Time |  | Minor |  | Patnaik, Amita | UNITED STATES | C4891026_1062 | GCP Site Audit | 2025-04-07 |  | Six essential documents were not filed in the Investigator Site File (ISF) [ICH GCP E6 (R2) 4.9.4]. 1. The following documents could not be located in the ISF: a. The monitoring visit follow-up letters dated 16 Feb 2024 (post Site Initiation Visit), 19 Apr 2024, 01 Oct 2024 and 31 Jan 2025. b. Site Initiation Visit report for the visit conducted 16 Feb 2024. c. Site activation/green light letter dated 25 Nov 2024. Of note, The Subject Identification Code List had not been filed in the ISF, but the Quality Assurance representative indicated that this list would be generated from their electronic drug accountability system at site close-out. This list was used in lieu of the Pfizer provided log. A copy of the log was provided on 28 Mar 2024 during the audit for confirmation of completeness.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | As documented in the Monitoring Visit report, related to visit done at site on 30May and 05Jun, CRA added the following - as a result of audit finding (QE-176288) eISF was reviewed and confirmed that documents noted as missing in eISF were filed appropriately. MVR is being attached. | 1 a.b. Follow up letters for the Interim Monitoring Visits mentioned above were sent to site on 19Apr2024, 01Oct2024 and 31Jan2025 with instructions to file them in Investigator Site File. These letters were also provided again for filing on 13Mar2025.Follow up letter for the Site Initiation Visit was retrieved from pTMF and sent to site for filing on 12May2025. Site was asked to file these letters in ISF in a timely manner. Study Monitor reminded the Site Coordinators to always file the Follow up letters issued post SIV/IMVs as soon as this is sent.1c. Phase 2 Activation Email dated 25Nov2024 was sent to site for filing on 12May2025. Study Coordinators were reminded to file these letters in ISF as soon as they are shared by either Pfizer or PPD Study Team.The filing of documents will be reviewed and confirmed by Study Monitor at the next monitoring visit, planned on 30May2025. | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | Document Management | Missing document | CT01 - Trial Master Files | SITE PERSONNEL | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-007076 | QE-172690 | 2025-06-30 | 2025-06-05 |  | Completed On Time |  | Minor |  | Patnaik, Amita | UNITED STATES | C4891026_1062 | GCP Site Audit | 2025-04-07 |  | For 2 of 3 participants reviewed, there was a delay in the reporting of safety evaluations and safety evaluations were inconsistent with electronic Case Report Forms (eCRF) [Pfizer Protocol C4891026 (Amendment 2: 11 Apr 2024)]. 1. Participant 10624001: a. Regarding the adverse event (AE) of 'fracture', the AE occurred when the participant fell and was hospitalized on 20 Jul 2024. The AE was not reported in the source records or in the eCRF until 18 Mar 2025.&nbsp; b. The AE of pruritus (start date 25 Jun 2024 and ongoing) was not entered on the AE assessment source record or in the eCRF until 21 Mar 2025. &nbsp; &nbsp;&nbsp; 2. Participant 10624003: The AE source records were not consistent with the eCRF entries as follows: a. The end date for the AE of grade 1 gum infection was noted as 30 Sep 2024 on the AE log, but 25 Sep 2024 had been entered in the eCRF. This AE was subsequently increased to a grade 2 event on the AE log with a start date of 26 Sep 2024 and a stop date of 30 Sep 2024. The 26 Sep 2024 start date of the grade 2 AE was inconsistent with the 30 Sep 2024 end date of the grade 1 event noted on the AE log. b. The AE of grade 2 shingles had a start and stop date entered in the eCRF (05-24 Jan 2025) but these dates had not been noted on the AE assessment log. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | 1a. / 1b. / 2a. / 2b. As documented at Monitoring visit report, regarding Monitoring visit done on 30May2025 and 05Jun2025, Clinical Research Associate added the following: as a result of audit finding (QE-172690), where the AE source records were not consistent with the eCRF entries, CRA increased SDR/SDV sampling for subject 10624003, and reviewed AEs gum infection (varying grades) and grade 2 shingles. Site updated gum infection in EDC and also in the source. AE shingles has been updated into AE log. Sampling increase also made for 10624001, CRA confirmed AE pruritus (start date 25 Jun 2024 and ongoing) has been updated into AE log. An I/A has been opened to document SDR/SDV sampling increase as per process.In addition, CRA sampled for SDR the SAEs occurred with subject 10624001, since there are some queries that remain open in PSSA portal. Despite these queries have been addressed multiple times, either the response was not added to narrative section as expected, or PVG group wanted further clarification on status of PELVIC FRACTURE, since different responses were provided. CRA re-educated the main SC on how to address the PSSA queries to add the responses with details within narrative section, to avoid future re-queries. Refer to attached Monitoring Visit report. | 1a. The Serious Adverse Event FALL was submitted in PSSA on 22Jul2024. Per Completion requirements, when a fall results in an injury, both the injury and the fall should be recorded as Adverse Events (AEs). Multiple queries were issued in PSSA, for clarifications on status of pelvic fracture, if existed prior to the event and was not a result of the fall requiring hospitalization, or if it was indeed the outcome of fall. Site is pending to respond to a current OPEN PSSA query if pelvic fracture is to be considered as ADVERSE EVENT or MEDICAL HISTORY. Site was re-educated on specific guidelines for FALL, as per Completion Requirement section 7.48.4.2. Site was also asked to respond to the open PSSA query, and update EDC and safety database for correct status of PELVIC FRACTURE. As of note, Study Monitor has sent several messages to Study coordinator with instructions on SAE and AE reconciliation, including open PSSA queries or open discrepancies, refer to messages attached. Study Monitor will sample subject 10624001 for SDR/SDV at next Monitoring visit planned on 30May2025 and review updates expected to be made in the source and EDC as applicable. 1b. Per Study Monitoring Plan and low risk study assessment, SDV rate is 0%, Source Data Verification is not expected in EDC. As per site response on 12May2025, Pruritus AE was found during the audit preparation, request was sent to treating physician and once entered in Electronic Medical Record (EMR) –, the event was entered in EDC on 21Mar2025. Study Monitor will sample AE Pruritus for SDR/SDV at next Monitoring Visit planned on 30May2025.2a.b Per Study Monitoring Plan and SDR/SDV rates, subject 10624003 was not sampled for Source Document Review (SDR) nor Source Document Verification (SDV), except for Screening/eligibility, as documented in Site Issue 1-531FCDR in Siebel. As per site response on 12May2025, multiple gum infection AEs occurred with varying grades. Initial start date of grade 1 was on 15Jul2024 and progressed to grade 2 on 26Sep2024. Since EDC doesn't allow dates to overlap with varying grades, the grade 1 AE was ended on 25Sep2024 and the grade 2 AE was started on 26Sep2024. Data Manager should also review the AE assessment log for AE of grade 2 shingles, and make updates as needed. Study Monitor will sample AEs for SDR/SDV at next Monitoring Visit planned on 30May2025.Site staff were trained on Good Document Practices (GDPs) and ALCOA+ Principles by Study Monitor per message sent on 13May2025 to ensure the study coordinator and relevant staff are well-versed in proper documentation practices and the ALCOA+ principles. The site was reminded of the critical importance of maintaining consistency and accuracy between the electronic Case Report Form (eCRF) and the source AE/Medical History (MedHx) logs. The site was also reminded of training resources within the InForm system, along with the current eCRF completion requirements. | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | AE reporting to Sponsor | Incomplete AE reporting | AEM01 - Adverse Event Monitoring | PRINCIPAL INVESTIGATOR | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-007076 | QE-172681 | 2025-05-19 | 2025-05-19 |  | Completed On Time |  | Minor |  | Patnaik, Amita | UNITED STATES | C4891026_1062 | GCP Site Audit | 2025-04-07 |  | For 2 of 3 participants reviewed, electronic Case Report Form (eCRF) data was inconsistent with source documentation [ICH GCP E6 (R2) 4.9.1; 4.9.2]. 1. Participant 10624001: a. The medical records indicated that the participant had a pre-cancerous vulvar lesion, and additional medical records indicated the participant had vulvar cancer. Vulvectomy (1995) had been noted in the eCRF instead of the reason for the surgery. b. A Radiation Oncology note dated 15 Jul 2013 indicated that the participant had a history of basal cell carcinoma of the face; however, this condition had not been entered in the Medical History eCRF.&nbsp; 2. Participant 10624002: The source records indicated that: a. Abemaciclib treatment was given from 02 Dec 2021 to 16 Feb 2023; however, 02 Feb 2021 had been indicated as the start date in the eCRF. b. Capivasertib was taken from 17 Mar 2023 to 11 Mar 2024; however, and end date of 22 Mar 2024 was entered in the eCRF. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Corrections have been made and CAPA implementation completed, refer to attachment. | 1a. Study Monitor reviewed electronic Case Report Form (eCRF) for patient 10624001 and confirmed that the Medical History page had been updated on 27Mar2025, to include Precancerous Vulvar Lesion start / stop date 1995.On 13May2025, Study Monitor retrained the Data Manager on the eCRF Completion guidelines section 7.12.3, that states when a surgery or interventional procedure is recorded, the condition that led to the surgery/procedure must be recorded as a separate entry.1b. Study Monitor reviewed eCRF for patient 10624001 and confirmed that medical condition History of Basal Cell Carcinoma (face) had been entered into Medical History page on 27Mar2025.2 a.b. Study Monitor reviewed eCRF for patient 10624002 and confirmed the start of Abemaciclib was updated to 02Dec2021 on 27Mar2025. Capivasertib end date was updated to 11Mar2024 on 27Mar2025.Site staff were trained on Good Document Practices (GDPs) and ALCOA+ Principles by Study Monitor per message sent on 13May2025 to ensure the study coordinator and data manager are well-versed in proper documentation practices and the ALCOA+ principles. During the training, the site was reminded of the critical importance of maintaining consistency and accuracy between the electronic Case Report Form (eCRF) and the source Medical History (MedHx) logs. | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | DMB03-GSOP - Data Management | SITE PERSONNEL | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-007076 | QE-172687 | 2025-06-30 | 2025-06-27 |  | Completed On Time |  | Minor |  | Patnaik, Amita | UNITED STATES | C4891026_1062 | GCP Site Audit | 2025-04-07 |  | Two essential documents were not filed in the Pfizer Trial Master File (PTMF) [Pfizer SOP CT01‑GSOP 8.0, Trial Master Files (effective 03 Oct 2022)].&nbsp; The following documents were not present in the PTMF: a. The Form Food and Drug Administration (FDA) 1572, signed by the Principal Investigator on 14 Aug 2024 (version 2) and 25 Oct 2024 (version 3). | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | On 27Jun2025, site was able to update the facility name in SIP and Pfizer SAP has confirmed the FDA1572 signed in Oct2024 is now being processed and filed in pTMF. Refer to message attached from SAP. | a. Per Internalized study model, FDA 1572 updates during study should be processed/approved and filed by Pfizer Site Activation Partner (SAP). Study Monitor received confirmation from Site Activation Partner that FDA 1572 dated 14Aug2024 has been approved and submitted for filing in pTMF. FDA dated 25Oct2024 is not filed yet in pTMF as in order to process this document, site’s name has to be updated in SIP (Shared Investigator Platform). Pfizer SAP has reached out to site’s SIP delegate to update the name in SIP multiple times but site is experiencing technical difficulties with SIP and site is not being responsive to SAP’s emails. Recently, site has informed the study team that they are not wanting to use SIP. This has been escalated to Site Care Partner to discuss and address. SAP will process and file FDA 1572 dated 25Oct2024 as soon as SIP issue is resolved at the site.Per recent communication from SCP (Site Care Partner) dated 07May2025, site has an open ticket with support team – Cognizant to support them on resolution of SIP issues. | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | Document Management | Missing document | CT01 - Trial Master Files | VENDOR / CONTRACTOR | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-007076 | QE-172679 | 2025-05-19 | 2025-05-19 |  | Completed On Time |  | Minor |  | Patnaik, Amita | UNITED STATES | C4891026_1062 | GCP Site Audit | 2025-04-07 |  | Protocol non‑compliance was identified for 1 of 3 participants reviewed [Pfizer Protocol C4891026 (Amendment 2: 11 Apr 2024)]. Participant 10624003: The participant’s menopausal status was not assessed and documented appropriately prior to enrollment. &nbsp; The Cycle 1, Day 1 study drug treatment order form, dated 13 May 2024, indicated that a pregnancy test was not applicable as the participant was post-menopausal; however, 'pre-menopausal' was reported in the Screening Visit (08 May 2024) electronic case report form. The Principal Investigator noted on the 29 Apr 2024 History and Physical progress note that the participant's menopause status was unknown (Last menstrual period was in Jun 2017 and hormone levels had not been checked so the participant was unsure if she was perimenopausal or postmenopausal). A follicle stimulating hormone level of 5.3 was reported at the Screening Visit on 08 May 2024. A urine pregnancy test was noted as negative in the electronic medical records dated 15 May 2024, but it was unclear the menopausal status for this participant and the need for pregnancy testing and contraception use. a. A progress note dated 17 Jun 2024 by the Clinical Research Coordinator indicated that the participant was counselled at the Screening Visit (29 Apr 2024) on birth control and to continue abstinence from the time of informed consent signing to 30 days after last dose of study drugs. The progress note indicated that this discussion had not been noted in the eligibility checklist at the time as the participant was thought to be postmenopausal.&nbsp; b. A pregnancy test was not completed at the Cycle 5, Day 1 visit on 05 Sep 2024. A note on the study drug treatment order indicated 'NA per study schedule'. A pregnancy test had been completed at all other applicable visits, except Cycle 5, Day 1, and the results of testing were negative. c. Confirmation of the use of an effective contraceptive had not been noted at any study visits, except as indicated on the 17 Jun 2024 progress note.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | b. Protocol Deviation ID # 1-84ZDIKR has been added to Siebel CTMS. | a. According to the Monitoring Visit Report dated 28-29May2024, Source Document Review (SDR) has been increased and subject 10624003 has been sampled for SDR for screening only. This SDR sampling increase has been also documented in Issue/Action in Siebel CTMS (ID# 1-531FCDR). As documented in the Monitoring Visit report, the patient was noted to be Postmenopausal (PMP), but the Follicle Stimulating Hormone test done on Screening visit did not show adequate hormone levels to support Postmenopausal Status. In addition, site did not specify the birth control method to be utilized in the study. A protocol deviation was discussed with the Principal Investigator, and PI noted that this patient was a chemically induced postmenopausal. PI requested this to be discussed with the Pfizer Clinician and Study Monitor escalated it on 30May2024 (refer to message attached). The Pfizer Clinician confirmed that as the subject is chemically induced postmenopausal, the patient must be treated as a woman of childbearing potential (WOCBP). PI also confirmed that it is site's standard practice to discuss and note birth control method for all subjects in the study while in screening, but, because the patient was thought to be PMP initially this was not documented in the source document. PI agreed to provide an addendum to explain this oversight. The Protocol Deviation is now deleted in Siebel CTMS, and CRA reviewed the Note to File issued and added to the source document at the monitoring visit completed on 26Jun2024. CRA also retrained the Study Coordinator to ensure that all assessments for WOCBP will need to be done for this subject, according to the Schedule of Assessments per protocol (refer to message attached, email dated 10Jun2024). Protocol deviation language (currently deleted in Siebel CTMS) has been added below for further clarification.PD Description: Inclusion #1 Per protocol, the patient’s FSH level does not support Postmenopausal Status. However, site did not specify the birth control method to be utilized in the study.Action taken: 12Jun24 Post Visit Note: The PD was discussed with the PI and PI confirmed that it is site's standard practice to discuss and note birth control method for all subjects in the study while in screening, but, because the patient was thought to be PMP initially this was not documented in the source document. PI agreed to provide an addendum to explain this oversight. The PD is now deleted, and CRA will review the addendum source document at the next monitoring visit.CRA retrained SC to ensure that all assessments for WOCBP will need to be done for this subject.b. As per above, only the Screening Visit for subject 10624003 has been sampled for Source Document Review. Study Monitor asked the Study Coordinator to file this missed Pregnancy Test at Cycle 5, Day 1 as a protocol deviation. As per response from site on 12May2025, the missed procedure was determined by the PI to be a minor event. As such, they've been added to the study's Protocol Deviation Log, and no further action is required. This protocol deviation has been added to Siebel CTMS by Study Monitor. c. As per response from site on 12May2025, they confirm for the active subject 10624003, that contraception method will continue to be discussed and documented in the source per protocol.Site was re-educated on protocol section 5.3.1 on Contraception, 10.4.4 on contraception Methods as well as related procedures as per Schedule of Assessments, refer to message sent to site on 13May2025. | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | Protocol Deviations | Failure to follow protocol | CT40 - Protocol Deviations | PRINCIPAL INVESTIGATOR | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS
AIA-007076 | QE-172693 | 2025-06-30 | 2025-06-05 |  | Completed On Time |  | Minor |  | Patnaik, Amita | UNITED STATES | C4891026_1062 | GCP Site Audit | 2025-04-07 |  | The monitoring was found to be inadequate with respect to the execution and documentation of monitoring activities [Pfizer C4891026 Study Monitoring Plan (Version 2: 28 Feb 2024)]. 1. Monitoring did not identify the following issues reported in other sections of this audit report: a. Protocol compliance (QE-172679). b. Essential documents were filed in the Investigator site file (QE-172688). c. Delay in the reporting of safety evaluations and safety evaluations were inconsistent with electronic Case Report Forms (QE-172690). 2. Monitoring did not ensure that the Subject Identification (ID) Code List was maintained and met the Pfizer requirements. The Subject ID Code List had not been filed in the investigator site file, but the Quality Assurance (QA) representative indicated that this list was to be generated from their electronic drug accountability system, which the site used in lieu of the Pfizer provided log. A copy of the form was provided on 28 Mar 2024 during the audit for confirmation of completeness. The QA representative and the Clinical Research Coordinator indicated that this log had not been requested previously for review by the Monitor. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Please find attached the minutes from Team call held on 19May2025, with topics discussed with study team regarding findings a, b, c and 2. As documented in the Monitoring visit report regarding Monitoring visit completed on 30May2025 and 05Jun2025, CRA added the following for audit finding QE-172693: CRA noted that as per site's QA Director, ID code list not added to eISF until Study Closeout. The log in its interim is maintained by the IDS team using their Drug Accountability system. The QA director will capture the header of this log to ensure all required information is captured. This is being followed thru Issue/Action 1-85B36XQ in Siebel CTMS. Please refer to attached Monitoring Visit report. | a. During the Study Team call to be held on 19May2025, a training session on protocol requirements when subject is peri/premenopausal/WOCBP (woman/women of childbearing potential) will be conducted with the team: use of highly effective contraceptive measures, pregnancy tests and ensuring these requirements are followed while patient is active on study treatment, as well as updates in the source documentation. Missed procedures should be captured as Protocol Deviations by site and added into Siebel CTMS.b. During the Study Team call to be held on 19May2025, Study Monitors will be reminded to review Investigator Site File on a ongoing basis during the Monitoring Visits, and re-educate the site staff to file in ISF the Follow up Letters, Greenlight/activation/implementation messages being sent by either Pfizer or PPD team in timely manner. c. During the Study Team call to be held on 19May2025, the Study Monitors will be reminded when subject is sampled for Source Document Review, the Adverse Events assessment log and entries in EDC should be reviewed during the Monitoring Visits. Study Team has been re-educated on Completion Requirements in case of Fall as well as discrepancies to be addressed in PSSA, as applicable. 2. The use of Screening/Enrollment log was previously discussed and confirmed during the Site Initiation Visit (SIV) –that site specific log is to be used. Study Monitor noted that site specific log contains PHI, patient initials. Monitor requested this log to be updated and uploaded to VeevaVault (VV) ISF. This was again discussed with the study team during March 11, 2025 visit and Regulatory Team confirmed that screening and enrollment log is in VV ISF, refer to message attached. Study Monitor requested site-specific subject ID code list to be uploaded to VeevaVault ISF. As per site response on 13May2025, this list is not typically uploaded to Veeva until the study is prepared for archival. It contains PHI so the patient can be accurately matched to the subject number listed within the study files. PHI can be securely stored in VeevaVault, once Study Roster is filed after the study is closed. Study Monitor will review the subject ID code list at next monitoring visit on 30May2025 to ensure it contains the minimum information required.During the Study Team call to be held on 19May2025, the Study Monitors will be reminded the use of Screening / enrollment Log as well as Subject Identification Code List, in case site wants to use their own log, Study Monitor and / or Site Care partner to review it and approve the use in case the minimum requirements are met. | Sandra Banevicius |  | - | Sandra Banevicius | Closed | Closed | Site Management and Monitoring | Failure to follow study specific monitoring plan/ requirements | INV04 - Investigational Site Management and Monitoring | PFIZER | MODEL 0 - LEGACY | Oncology |  | GSSO | 84 | AMERICAS