## Standard_Quality_Dashboard - Au
AMS Audit PR ID | AMS Observation PR ID | Target Completion Date | Actual Completion Date | TCD Due/Overdue Days | TCD Status | Observation Closed On | Observation Rating | Observation Phase | Investigator Full Name | Country | Unique Site Number | Type Of Entity | Issue Of Audit Report Actual | Issue Audit Closure Rpt Act | Observation Description | Response (Trackwise Only) | Actions Taken | CAPA Action Description | CAPA Action Created by | Responsibility | Responsible Contact | Audit Coordinator | Observation Status | Audit Status | Level 1 | Level 2 | Selected Business Process | Responsible Party Value | Rapid Model | Business Category | Site Care Partner | Cluster | Area ID | Area Name
AIA-009586 | QE-233639 | [5 empty] | Minor |  | Essack Mitha, Essack Mitha | SOUTH AFRICA | C5091017_1095 | GCP Site Audit | 2026-03-17 |  | Computer system security was not adequately maintained for 1 site user [ICH E6 (R3) 2.12.10 (b)].&nbsp; One study coordinator (SC) who had a stop date of 20 Jan 2026 on the Signature Sheet and Delegations of Duties Log (SSDDL) had an active access to the Interactive Response Technology (IRT) system Impala. The Principal Investigator (PI) confirmed during the audit, that this SC was no longer assigned to the study; however, user access was not deactivated. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Liviu Arustei | Issued | Pending Finding Closure | IT Systems | Inadequate system access or account management | NOT APPLICABLE; NOT APPLICABLE | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Internal Medicine | Legodi, Lebogang | GSSO | 310 | EMEA
AIA-009586 | QE-233638 | [5 empty] | Minor |  | Essack Mitha, Essack Mitha | SOUTH AFRICA | C5091017_1095 | GCP Site Audit | 2026-03-17 |  | For 2 of 5 participants reviewed, electronic Case Report Forms (eCRFs) contained discrepancies with the source documentation and/or were not complete [Pfizer Protocol C5091017 (Amendment 1: 07 May 2025), C5091017 CRF Completion Requirements (Version 3.0: 19 May 2025)]. &nbsp; The following were noted:&nbsp; • For Participant 10951006 on the Visit Day 1 “Vital Signs” eCRF the systolic blood pressure on 11 Sep 2025 was reported as 163 mmHg; however, in the source worksheet it was recorded as 168 mmHg.&nbsp; • For Participant 10951011 on the Screening Visit “Microbiology Specimen – Sponsor Approved RAT” eCRF the test result on 25 Sep 2025 was reported as negative; however, in the source worksheet it was recorded as positive.&nbsp; • For Participant 10951011 on the Visit Day 5 “Vital Signs” eCRF the SPO2 pulse oximetry on 29 Sep 2025 was reported as 98%; however, in the source worksheet it was recorded as 95%.&nbsp; • For Participant 10951011 the “Date of Visit” and “Survival Follow Up” eCRFs on the Visit Week 20 were not completed; however, the visit occurred on 10 Feb 2026.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Liviu Arustei | Issued | Pending Finding Closure | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | CT03-GSOP - Case Report Forms | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Internal Medicine | Legodi, Lebogang | GSSO | 310 | EMEA
AIA-009586 | QE-233643 | [5 empty] | Minor |  | Essack Mitha, Essack Mitha | SOUTH AFRICA | C5091017_1095 | GCP Site Audit | 2026-03-17 |  | Seven essential documents were missing and/or inadequately completed in the Investigator Site File (ISF) [ICH GCP E6 (R3) 2.12.11].&nbsp; 1. The following documents were noted to be missing:&nbsp; &nbsp; • The Ethics Committee submission and approval letters for the Protocol Amendment 1. • The Ethics Committee submission letter for the Protocol Amendment 2.&nbsp; • The South African Health Products Regulatory Authority (SAHPRA) approval letter for the Protocol Amendment 1.&nbsp; &nbsp; 2. The following documents were inadequately completed:&nbsp; &nbsp; • The Subject Identification Code List included the participants who were screen failed; however, according to the instructions described within the “Principal Investigator / Site Responsibilities” section of the document, only participants who were enrolled in the study should be recorded, and the participants who were screen failures should not be entered.&nbsp; &nbsp; 3. The following documents were not adequately maintained in the electronic ISF system Florence:&nbsp; &nbsp; • The Signature Sheet and Delegation of Duties Log (SSDDL) version updated on 04 Feb 2026 was not filed in Florence.&nbsp; • The Site Initiation Visit (SIV) Follow Up letter dated 23 July 2025 was mistakenly assigned a different protocol number in the “Name” metadata section in Florence. &nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Liviu Arustei | Issued | Pending Finding Closure | Document Management | Missing document | CT01 - Trial Master Files | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Internal Medicine | Legodi, Lebogang | GSSO | 310 | EMEA
AIA-009586 | QE-233642 | [5 empty] | Minor |  | Essack Mitha, Essack Mitha | SOUTH AFRICA | C5091017_1095 | GCP Site Audit | 2026-03-17 |  | Site staff training was incomplete and/or not documented for 4 of 14 site staff members [Pfizer C5091017 Study Training Plan (Version 5: 22 Sep 2025), ICH E6 (R3) 2.1.1].&nbsp; The C5091017 Adjudication Overview Training was assigned to 4 delegated study coordinators on 15 May 2025, 17 Aug 2025 and 01 Feb 2026, according to the training system Firecrest report; however, at the time of the audit the completion status of the training was “Not Started”. According to the Study Training Plan, this training was required for Study Coordinators.&nbsp; Note: there were no cases submitted by the site to the adjudication committee at the time of the audit.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information |  |  |  |  | - | Liviu Arustei | Issued | Pending Finding Closure | Training & Qualifications | Training not completed or documented in a timely manner | CT33 - Study-Specific Training | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Internal Medicine | Legodi, Lebogang | GSSO | 310 | EMEA
AIA-008088 | QE-202156 | 2025-11-14 | 2025-10-23 |  | Completed On Time |  | Minor |  | Capote Jr, Eddy | UNITED STATES | C5091017_1006 | GCP Site Audit | 2025-09-26 |  | Three documents in the Pfizer Trial Master File (PTMF) were missing [Pfizer SOP CT01-GSOP Trial Master Files (Version 8.0: 03 Oct 2022)]. 1. &nbsp; &nbsp;There was only 1 Form FDA1572 (dated 03 Jul 2025) in the Pfizer Trial Master File (PTMF), the investigator site file (ISF) had two (2) 1572s, the original from 08 Dec 2024 and an updated one from 03 Jul 2025. 2. &nbsp; &nbsp;Two documents in the PTMF were corrupt and unable to be viewed. &nbsp; &nbsp; &nbsp; &nbsp; a) &nbsp; &nbsp;Interactive Response Technology (IRT) User Manual dated 28 Oct 2024. &nbsp; &nbsp; &nbsp; &nbsp; b)&nbsp; &nbsp; Initial Signature Sheet and Delegation of Duties Log.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | The SCP has uploaded the new 1572 and the initial Signature Sheet and Delegation of Duties log to Pfizer Trial Master File. The Interactive Response Technology User Manual was determined to be corrupt so that it is blocked to prevent potential unblinding. It is available in Impala with the appropriate access. See action items #1-9BJCSCG, 1-9BJC5C8, 1-9BJCSCC, 1-8CK1FQI. | 1. SCP uploaded the new 1572. 2. A. Interactive Response Technology (IRT) User Manual in pTMF is shown to be corrupt because it is blocked to prevent potential unblinding. It is available in Impala with site user access. B. SCP has uploaded the initial Site Signature and Delegation of Duties Log to the Pfizer trial master file. Responsible Roles: SCPTarget Completion Date: 14Nov25Action Owner: Georgina Perez | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | Document Management | Missing document | CT01 - Trial Master Files | PFIZER | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-008088 | QE-202151 | 2025-11-28 | 2025-10-30 |  | Completed On Time |  | Major |  | Capote Jr, Eddy | UNITED STATES | C5091017_1006 | GCP Site Audit | 2025-09-26 |  | For 1 out of 30 informed consent documents (ICDs) reviewed, the Principal Investigator (PI) did not ensure adequate documentation of the informed consent process as the ICD was not signed by investigator or delegated site staff &nbsp;[ICH E6 (R3) 2.8.7]. For Participant 10061022, the ICD (SPANISH IRB 26 Mar 25 Revised 08 Jul 25) signed by the participant on 19 Aug 2025, did not have the Printed Name, Signature and Date of the site representative delegated to obtained consent.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | The site has updated the ICF, made a late note entry, and provided the subject with a signed copy of the ICF. The monitor has confirmed all the above has been completed. See action item #19BJC59C. | .4px;"Site will update the informed consent with signatures and late entry note. Site to provide a signed copy to the subject. Site monitor will review ICD to ensure it was completed properly per ALCOA requirements. | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | Informed Consent | Inadequate consent process at the investigator site | CT05 - Informed Consent Documents | SITE PERSONNEL | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-008088 | QE-202151 | 2025-11-28 | 2025-10-30 |  | Completed On Time |  | Major |  | Capote Jr, Eddy | UNITED STATES | C5091017_1006 | GCP Site Audit | 2025-09-26 |  | For 1 out of 30 informed consent documents (ICDs) reviewed, the Principal Investigator (PI) did not ensure adequate documentation of the informed consent process as the ICD was not signed by investigator or delegated site staff &nbsp;[ICH E6 (R3) 2.8.7]. For Participant 10061022, the ICD (SPANISH IRB 26 Mar 25 Revised 08 Jul 25) signed by the participant on 19 Aug 2025, did not have the Printed Name, Signature and Date of the site representative delegated to obtained consent.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | The SCP reviewed the sites QC policy and confirmed it is adequate. The CRA confirmed the ICF was updated with a signature and a late entry was added. See action item #19BJC59C. | .4pt;"The sites QC policy was reviewed and determined to be adequate. The CRA has confirmed the ICF was updated and a late entry was created to document the error. CRA also confirmed that the subject was given a copy of the signed ICF. | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | Informed Consent | Inadequate consent process at the investigator site | CT05 - Informed Consent Documents | SITE PERSONNEL | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-008088 | QE-202151 | 2025-11-28 | 2025-10-30 |  | Completed On Time |  | Major |  | Capote Jr, Eddy | UNITED STATES | C5091017_1006 | GCP Site Audit | 2025-09-26 |  | For 1 out of 30 informed consent documents (ICDs) reviewed, the Principal Investigator (PI) did not ensure adequate documentation of the informed consent process as the ICD was not signed by investigator or delegated site staff &nbsp;[ICH E6 (R3) 2.8.7]. For Participant 10061022, the ICD (SPANISH IRB 26 Mar 25 Revised 08 Jul 25) signed by the participant on 19 Aug 2025, did not have the Printed Name, Signature and Date of the site representative delegated to obtained consent.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | The site has provided the updated source data template to the SCP for review. The SCP has reviewed and confirmed the source data meets the study requirements and is appropriately updated. See action item #1-9BJC5BK. | The SCP has confirmed the sites QC process for ICF's is adequate. | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | Informed Consent | Inadequate consent process at the investigator site | CT05 - Informed Consent Documents | SITE PERSONNEL | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-008088 | QE-202152 | 2026-03-04 | 2025-12-19 |  | Completed On Time |  | Minor |  | Capote Jr, Eddy | UNITED STATES | C5091017_1006 | GCP Site Audit | 2025-09-26 |  | For 3 of 7 participants’ records reviewed, discrepancies were noted between the electronic Case Report Forms (eCRFs) and the source documentation [C5091017 CRF Completion Requirements Version 3, 09 May 2025]; ICH GCP E6 (R3) Section 2.12.5]. 1. &nbsp;For Participant 10061003, the source worksheet for medical history (MedHx) had a third-degree atrioventricular block with a stop date of 22 Nov 2018; however, the electronic Case Report Form (eCRFs) had it as ongoing. 2. &nbsp;For Participant 10061004, the source worksheet had Day 14 (13 Feb 2025) Biomarker Samples with a collection time of 10:02; however, the eCRF had 10:06. 3. &nbsp;For Participant 10061029, the source worksheet had Day 1 (29 Jul 2025) Baseline Temperature as 97.7 degrees Fahrenheit; however, the eCRF had 97.8 degrees Fahrenheit. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | The site has updated all information per action items #1-9BJCSBF, 9BJCSB8, and 9BJCSB4. | 1. Site to update records to accurately reflect data. CRA to review and confirm data.2.Site to update records to accurately reflect data. CRA to review and confirm data.3. Site to update records to accurately reflect data. CRA to review and confirm data.Responsible Roles: CRC, CRATarget Completion Date: 28Nov25Action Owner: Georgina Perez | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | DMB07 - CRF and Database Design | SITE PERSONNEL | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-007684 | QE-177387 | 2025-06-23 | 2025-06-26 |  | Complete Late |  | Minor |  | Lilia Roque-Guerrero, Lilia Roque-Guerrero | UNITED STATES | C5091017_1008 | GCP Site Audit | 2025-05-09 |  | For 6 of 9 participant files reviewed discrepancies were noted between the electronic Case Report Forms (eCRFs) and source documentation [C509107 CRF Completion Guidelines version 2, dated 19 Mar 2025].&nbsp; 1. &nbsp;Participant 10081001&nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;For Concomitant Medication #1, Prednisone, the site staff did not delete data as required in the eCRF Completion Requirements section 3.17. The site staff deleted each value related to the Concomitant Medication, and all data was blank instead of having a strike-through. &nbsp; 2. &nbsp;Participant 10081006&nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;The photo of the medication in the participant's chart had the dosage as 10 milligrams (mg); however, it was listed as 5 mg in the eCRF.&nbsp; 3. &nbsp;Participant 10081007&nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;The Day 10 Visit (07 Feb 2025) vitals collection time was recorded in the site's source worksheet as 13:48; however, it was entered as 13:43 in the eCRF.&nbsp; 4. &nbsp;Participant 10081008&nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;The Day 10 Visit (07 Feb 2025) vitals collection time was recorded in the site's source worksheet as 13:58; however, it was entered as 13:53 in the eCRF. &nbsp; 5. &nbsp;Participant 10081010&nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;The source Concomitant Medication log listed Fluticasone Propionate with a start date of UN/UNK/1996; however, it was listed as 21 Feb 2025 in the eCRF.&nbsp; &nbsp; &nbsp; &nbsp;b. &nbsp;The Screening Visit (21 Feb 2025) source worksheet listed that the Follicle-Stimulating Hormone (FSH) test was completed; however, it was marked as "not done" in the eCRF.&nbsp; 6. &nbsp;Participant 10081011&nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;The Screening Visit (24 Feb 2025) source worksheet listed the participant's race as White; however, it was listed as Asian White in the eCRF.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | For all issues corrections were completed per Siebel Clinical Trial Management (CTMS) system Issue Action #'s, 1-7TI4IOX, 1-7TFSAB8, 1-7TGMLWZ, 1-7TGMME1, 1-7TGMME5, 1-7TGMME9, 1-7TGMMGB. | 1. Per electronic Case Report Form (eCRF) Completion Requirements , section 3.13- Reset Item Value, Clearing data for a particular question can be done if the data has not yet been submitted (if submitted the data can still be changed by clicking on the particular data point but it will appear in the audit trail).2. 2-6 The entries in the eCRF will be reviewed/updated to ensure data is accurate and consistent with source data. 3. For all findings, the site monitor will review and confirm all updates were made in the source document and eCRFs per ALCOACCEA requirements. Monitor will complete by 30July2025. | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | DMB07 - CRF and Database Design | SITE PERSONNEL | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-007684 | QE-177400 | 2025-06-23 | 2025-05-28 |  | Completed On Time |  | Minor |  | Lilia Roque-Guerrero, Lilia Roque-Guerrero | UNITED STATES | C5091017_1008 | GCP Site Audit | 2025-05-09 |  | For 1 of 9 participant files reviewed, an adverse event (AE) reported via the electronic Case Report Form (eCRF) from the investigator site to Pfizer was incomplete and/or inaccurate [Pfizer Protocol C5091017 (Original: 14 Oct 2024)].&nbsp; &nbsp; 1.&nbsp; Participant 10081004&nbsp; Adverse Event #1, Worsening Anemia, was listed as a grade 1 in the site's source AE log; however, it was listed as a grade 2 in the eCRF.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | SCP confirmed all adverse events were updated appropriately. all corrections were completed per Siebel Clinical Trial Management (CTMS) system Issue Action ID# 1-7TIXCA9. | The Principal Investigator (PI) will review the Adverse Event source document and ensure the electronic Case Report Form (eCRF) is consistent with the source. The site monitor will verify the source document and eCRF to ensure data is consistent. Site monitor to confirm by 30Jun2025. Responsible Roles: PI /Site MonitorThe site monitor will verify the source document and eCRF to ensure data is consistent. | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | AE reporting to Sponsor | Incomplete AE reporting | AEM01 - Adverse Event Monitoring | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-007684 | QE-177394 | 2025-06-23 | 2025-08-04 |  | Complete Late |  | Minor |  | Lilia Roque-Guerrero, Lilia Roque-Guerrero | UNITED STATES | C5091017_1008 | GCP Site Audit | 2025-05-09 |  | Eighteen essential documents were missing, incomplete or inaccurate in the electronic Investigator Site File (eISF) [ICH GCP E6 (R2) Section 4.9.4].&nbsp; &nbsp; 1. &nbsp;The following documents were missing from eISF&nbsp; Florence: &nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;Investigator Site Recruitment Plan version 1.&nbsp; &nbsp; &nbsp; &nbsp;b. &nbsp;Signant Health TrialMax- App Activation- English [dated 17 Oct 2024].&nbsp; &nbsp; &nbsp; &nbsp;c. &nbsp;Signant Health TrialMax- App Activation- Spanish [dated 21 Nov 2024]. &nbsp; &nbsp; &nbsp; &nbsp;d. &nbsp;Signant Health TrialMax - Site Facing Screen Report version 1 [dated 21 Oct 2024].&nbsp; &nbsp; &nbsp; &nbsp;e. &nbsp;Signant Health TrialMax &nbsp;Site Guidance for Participant eDiary Review version 1 [dated 04 Nov 2024].&nbsp; &nbsp; &nbsp; &nbsp;f. &nbsp;Signant Health TrialMax Site User Manual, version 2 [dated 17 Sep 2024].&nbsp; &nbsp; &nbsp; &nbsp;g. &nbsp;PPD Central Laboratory Manual, version 1 [dated 26 Nov 2024].&nbsp; &nbsp; &nbsp; &nbsp;h. &nbsp;Site Staff Manual for Verified Clinical Trials (VCT) version 1 [dated Oct 2024].&nbsp; &nbsp; &nbsp; &nbsp;i. &nbsp;VCT E-Training Module Instructions version 1 [dated 14 Oct 2024].&nbsp; &nbsp; &nbsp; &nbsp;j. &nbsp;VCT Site Staff Reference Guide version 1 [dated Oct 2024].&nbsp; &nbsp; &nbsp; &nbsp;k. &nbsp;VCT Scanner Installation Tutorial [dated Feb 2024].&nbsp; &nbsp; &nbsp; &nbsp;l. &nbsp;Site Staff Manual for Verified Clinical Trials (VCT) version 1 [dated Oct 2024].&nbsp; &nbsp; &nbsp; &nbsp;m. &nbsp;Case Report Form (CRF) Completion Guidelines version 2 [dated 19 Mar 2025].&nbsp; &nbsp; &nbsp; &nbsp;n. &nbsp;IMPALA User Guide version 1 [dated 25 Oct 2024].&nbsp; &nbsp; 2. &nbsp;The following documents did not follow the naming convention:&nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;Three versions of the Investigational Product Accountability Log (IPAL) were stored in Florence; however, the document name did not state a version number or a date for the document. &nbsp; &nbsp; &nbsp; &nbsp;b. &nbsp;Two versions of the Site Visit Log were stored in Florence; however, the document name did not state a version number or a date for the document. &nbsp; &nbsp; 3. &nbsp;The following documents were misfiled in Florence:&nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;The investigational review board approval letters were stored in the "Study Completion" folder.&nbsp; &nbsp; &nbsp; &nbsp;b. &nbsp;The CRF completion guidelines were stored in the "Blank CRF" folder; however, they should have been stored in the "EDC Guidance Document" folder. &nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | All action items have been completed. Please see AI# 1-7TI4IYV, 1-7TI4IYZ, 1-7TI4IZ3, 1-7TIXC77, 1-7TIXC7D, 1-7TIXC8L, 1-7TIXC8P, 1-7TIXC8P, 1-7TIXC9H, 1-7TIXC9L. | 1a-n) The Site Monitor will provide the site with the missing documents and confirm documents are filed in the ISF. 2a-b) The site will ensure a naming convention is used for version control of the Investigational Product Accountability Log (IPAL) and Site Visit log.3 a-b) The Investigational Review Board approval letters and Case Report Form (CRF) completion guidelines will be filed in the appropriate folders within the site’s electronic Investigator Site File (eISF).All items to be completed by 30Jul2025. | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | Document Management | Missing document | CT01 - Trial Master Files | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-007684 | QE-177411 | 2025-06-23 | 2025-06-25 |  | Complete Late |  | Minor |  | Lilia Roque-Guerrero, Lilia Roque-Guerrero | UNITED STATES | C5091017_1008 | GCP Site Audit | 2025-05-09 |  | For 9 of 9 participant files reviewed, there was a potential breach of privacy and data protection [ICH GCP E6 (R2) Section 2.11].&nbsp; 1. &nbsp;The site recorded and uploaded the names, phone numbers and /or email addresses&nbsp; of secondary contacts for the participants in both the paper and the electronic Investigator Site File; there was no documentation that these secondary contacts consented to their personal data being used.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Site personnel removed information from the eISF. | 1. The site personnel will remove the documents from the electronic Investigator Site File (eISF) containing personal identifiable information (PII) for secondary contacts for the participants.2. The Site Care Partner submitted a Quality Event (QE) per QMS 01 which was assessed as minor (QE-180683).3. The Site Monitor will confirm documents have been removed from eISF. Responsible Roles: Site Personnel/ Site Monitor/ Site Care PartnerThe SCP will confirm at the next on site visit. | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | Data Privacy | Data privacy/confidentiality | CT05 - Informed Consent Documents | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-007684 | QE-177401 | 2025-06-23 | 2025-06-23 |  | Completed On Time |  | Minor |  | Lilia Roque-Guerrero, Lilia Roque-Guerrero | UNITED STATES | C5091017_1008 | GCP Site Audit | 2025-05-09 |  | Twelve essential documents were missing from the Pfizer Trial Master File (PTMF) [CT01-GSOP 8.0 Trial Master Files 03-Oct-2022; ICH GCP E6 (R2) Section 4.9.4].&nbsp; &nbsp; 1. &nbsp;Spanish Translation of Assent [dated 11 Nov 2024] &nbsp; 2. &nbsp;Spanish Translation of Paternal Consent [dated 13 Nov 2024]&nbsp; 3. &nbsp;Spanish Translation of Optional Consent for Retained Sampled [dated 13 Nov 2024]&nbsp; 4. &nbsp;Optional Consent for Retained Sample [dated 13 Nov 2024] IRB approval on 10 Dec 2024&nbsp; 5. &nbsp;Paternal Consent [dated 26 Mar 2025]&nbsp; 6. &nbsp;Adult Main Consent [dated 26 Mar 2025]&nbsp; 7. &nbsp;IRB Notice of Translation [dated 16 Jan 2025] &nbsp; 8. &nbsp;IRB Notice of Translation for Appointment Card version 1 and additional documents [dated 17 Jan 2025]&nbsp; 9. &nbsp;IRB Notice of Translation Training Requirements and additional documents [dated 17 Jan 2025]&nbsp; 10. &nbsp;IRB Notice of Translation Instructions for use of pregnancy test [dated 17 Jan 2025]&nbsp; 11. &nbsp;IRB Notice of Translation [dated 19 Jan 2025]&nbsp; 12. &nbsp;IRB Notice of Translation [dated 04 Mar 2025]&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | All files have been sent to eTMF. | 1. 1-6 Site Care Partner has uploaded all documents in the Pfizer Trial Master File (PTMF). 2. 7-12 Site Activation Partner will ensure all documents are filed in the PTMF. All items will be completed by 30Jun2025. | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | Document Management | Missing document | CT01 - Trial Master Files | PFIZER | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-007684 | QE-177362 | 2025-08-29 | 2025-08-25 |  | Completed On Time |  | Major |  | Lilia Roque-Guerrero, Lilia Roque-Guerrero | UNITED STATES | C5091017_1008 | GCP Site Audit | 2025-05-09 |  | For 6 of 9 participant files reviewed, source documentation practices were not in accordance with ALCOACCEA (Attributable, Legible, Contemporaneous, Original, Accurate, Complete, Consistent, Enduring, and Available) [Pfizer Protocol C5091017 (Original: 14 Oct 2024); ICH E6 (R2) 2.10; 4.9.0].&nbsp; &nbsp; A. &nbsp;Source documentation was inaccurate:&nbsp; &nbsp; &nbsp; &nbsp;1. &nbsp;Participant 10081004&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; a. &nbsp;Baseline/Day 1 Visit (20 Jan 2025)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;i. &nbsp;The source worksheet listed that the participant was not a woman of childbearing potential (WOCBP); however, the participant is a WOCBP. &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;ii. &nbsp;On page 8 of the source worksheet, the Study Coordinator (SC) added a note which stated that he called the participant regarding the abnormal hematology laboratory result. The note stated that the abnormal value was clinically significant (cs); however, the investigator marked the results as not clinically significant (ncs) on laboratory report stored in the participant's chart.&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; b. &nbsp;Day 5 Visit (24 Jan 2025) source worksheet listed participant as a non-WOCBP; however, the participant was a WOCBP. &nbsp;&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; c. &nbsp;Day 34 Visit (21 Feb 2025) source worksheet listed participant as a non-WOCBP; however, the participant was a WOCBP. &nbsp;&nbsp; &nbsp; &nbsp; &nbsp; 2. &nbsp;Participant 10081008&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;Baseline/Day 1 Visit (30 Jan 2025) &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; i. &nbsp;Page 4 of the source worksheet for the Pre-Specified Significant Medical History Risk Factors, the site staff checked off that the participant was a "Cigarette Smoker"; however, on page 7 of the worksheet, the patient's smoking status was listed as not an active smoker and stopped smoking in 2021."&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;ii. &nbsp;Page 7 of the source worksheet asked "does the subject have previous history of use tobacco? Y / N". This was marked as "no"; however, it should have been marked as "yes" since the participant was a former smoker. &nbsp; &nbsp; B. &nbsp;Source documentation was incomplete:&nbsp; &nbsp; &nbsp; &nbsp; 1. &nbsp;Participant 10081004&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;Baseline/Day 1 Visit (20 Jan 2025), on page 4 of the source worksheet asked "was there any change to reproductive system?"; however, the worksheet did not ask if the participant was adhering to the agreed contraception method.&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;b. &nbsp;Day 5 Visit (24 Jan 2025) on page 4 of the source worksheet asked "was there any change to reproductive system?"; however, the worksheet did not ask if the participant was adhering to the agreed contraception method. &nbsp;&nbsp; &nbsp; &nbsp; &nbsp; 2. &nbsp;Participant 10081007's Baseline/Day 1 Visit (30 Jan 2025), the pharmacokinetic (PK) sample packing list with barcode labels was not labeled with the Participant Screen identification number.&nbsp; &nbsp; C. &nbsp;Source documentation was inconsistent:&nbsp; &nbsp; &nbsp; &nbsp; 1. &nbsp;Participant 10081006 &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;a. Screening Visit (24 Jan 2025) source worksheet for the Pre-Specified Significant Medical History Risk Factors, the site staff checked off that the participant was a "Cigarette Smoker"; however, on page 7 of the worksheet, the patient's smoking status listed the participant did not use tobacco product. &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;b. The source Concomitant Medication (ConMed) log, listed the dosage of &nbsp;Amlodipine as 5 milligrams (mg); however, the picture of the medication stored in the participant's chart showed the dosage was 10 mg. &nbsp; D. &nbsp;Source documentation was not contemporaneous:&nbsp; &nbsp; &nbsp; &nbsp;1. &nbsp;Participant 10081004's Day 1 Visit (20 Jan 2025), the SC added a note which stated that he called the participant regarding the abnormal hematology laboratory result, the hemoglobin level was 9.9 grams per deciliter (g/dL). The note was dated as 23 Jan 2025; however, the 9.9 g/dL test result was for the hematology sample collected on 24 Jan 2025. &nbsp; &nbsp; E. &nbsp;Source documentation was not attributable:&nbsp; &nbsp; &nbsp; &nbsp;1. &nbsp;Participant 10081004's Day 34 Visit (21 Feb 2025) Protein Biomarker were marked as collected, the date and time of collection was listed in the source worksheet; however, the initials of the person who collected the sample were missing. &nbsp; &nbsp; F. &nbsp;Source documentation was not available:&nbsp; &nbsp; &nbsp; 1. &nbsp;Participant 10081007's Screening Visit (30 Jan 2025) required the discussion to be documented as to whether the participant had any questions and if they were answered to their satisfaction documented on this worksheet; there was no documentation recorded.&nbsp; &nbsp; &nbsp; 2. &nbsp;Participant 10081009&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;The SC added a note on 07 Feb 25 which stated that the participant came to site since he lost his cellphone, and that the participant was given a study device to complete diary entries; however, there was no documentation of the device given to the participant.&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;b. &nbsp;Two data correction forms (DCF) (DCF# 141 and 161) were not stored in the participant's chart. &nbsp; &nbsp; &nbsp; 3. &nbsp;Participant 10081011's Screening Visit (24 Feb 2025) required the discussion whether participant had any questions and if they were answered to their satisfaction documented on this worksheet; there was no documentation recorded.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | The corrections for all items has been completed. Please see IA#'s, 1-7TFSA0M, 1-7TFSAB4, 1-7TFSAB8, 1-7TFSA60, 1-7TFSAMQ. | A1a (i), b, c- The site personnel will create a late entry in the source documents to confirm if participant is a women of child bearing potential (WOCBP). If confirmed a WOCBP, site monitor will confirm pregnancy test was performed per protocol. If not done per protocol, then protocol deviations will be reported, if applicable. A1a (ii) The Principal Investigator (PI) will review the abnormal lab result and provide a late entry to confirm if clinically significant or not. Once confirmed, the site personnel will communicate this to the participant and document this communication in the source. A2a (i &amp; ii) /C1a: The site personnel will contact participant 10081006, 10081008 to confirm smoking status and document the response in the source document as a late entry. All entries related to smoking status and previous use of tobacco will be reviewed and updated if applicable as a late entry to ensure there is consistency throughout the source document. If there are changes to the data that affect eligibility this will be communicated to the clinical team and protocol deviation will be reported, if applicable. B1a, b- Site personnel will contact participant to confirm they have adhered to contraception method throughout the study. A late entry will be added to capture this in the source document. B2. A late entry will be noted on the pharmacokinetic (PK) sample packing list with barcode labels, adding the Participant Screen identification number (10081007). If there is an open lab query related to this issue, the site will respond to the query. C1b. A late entry will be added to the source Concomitant Medication (ConMed) log, clarifying the correct dosage of Amlodipine. D1. The site personnel will add a late entry to explain why the note was dated 23 Jan 2025, prior to the actual test result date (24JAN2025). E1. A late entry including the initials of the person who collected the Protein Biomarker will be added to the source document. If this is not possible, a late entry noting who collected the sample will be entered in the source document. F1 &amp;F3 Site has a standard document that states the subject was given the opportunity to ask questions, the document was signed by the study coordinators and Principal Investigator (PI). The sites ICF form was reviewed for each subject by the monitor and all forms were found to be complete. This document is located in the participants’ screening folder titled ICF process. F2a. The site personnel will check which device was provided to the participant and add a late entry noting the device that was given to the participant at that time. F2b. The site personnel will file the data correction forms (DCF# 141 and 161) in the participant's chart. For issues noted in this Finding, the Site Monitor will review and verify the applicable data to ensure appropriate corrections were made per (Attributable, Legible, Contemporaneous, Original, Accurate, Complete, Consistent, Enduring, Available) (ALCOACCEA) requirements and data is consistent between source document. Responsible Roles: PI, Site Personnel/ Site Monitor Actions to be completed by 30Jun2025. | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Approved - In Effectiveness Check | Closed | Data Collection and Management | Inadequate source data/documentation | NOT APPLICABLE; NOT APPLICABLE | SITE PERSONNEL | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-007684 | QE-177362 | 2025-08-29 | 2025-08-25 |  | Completed On Time |  | Major |  | Lilia Roque-Guerrero, Lilia Roque-Guerrero | UNITED STATES | C5091017_1008 | GCP Site Audit | 2025-05-09 |  | For 6 of 9 participant files reviewed, source documentation practices were not in accordance with ALCOACCEA (Attributable, Legible, Contemporaneous, Original, Accurate, Complete, Consistent, Enduring, and Available) [Pfizer Protocol C5091017 (Original: 14 Oct 2024); ICH E6 (R2) 2.10; 4.9.0].&nbsp; &nbsp; A. &nbsp;Source documentation was inaccurate:&nbsp; &nbsp; &nbsp; &nbsp;1. &nbsp;Participant 10081004&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; a. &nbsp;Baseline/Day 1 Visit (20 Jan 2025)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;i. &nbsp;The source worksheet listed that the participant was not a woman of childbearing potential (WOCBP); however, the participant is a WOCBP. &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;ii. &nbsp;On page 8 of the source worksheet, the Study Coordinator (SC) added a note which stated that he called the participant regarding the abnormal hematology laboratory result. The note stated that the abnormal value was clinically significant (cs); however, the investigator marked the results as not clinically significant (ncs) on laboratory report stored in the participant's chart.&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; b. &nbsp;Day 5 Visit (24 Jan 2025) source worksheet listed participant as a non-WOCBP; however, the participant was a WOCBP. &nbsp;&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; c. &nbsp;Day 34 Visit (21 Feb 2025) source worksheet listed participant as a non-WOCBP; however, the participant was a WOCBP. &nbsp;&nbsp; &nbsp; &nbsp; &nbsp; 2. &nbsp;Participant 10081008&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;Baseline/Day 1 Visit (30 Jan 2025) &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; i. &nbsp;Page 4 of the source worksheet for the Pre-Specified Significant Medical History Risk Factors, the site staff checked off that the participant was a "Cigarette Smoker"; however, on page 7 of the worksheet, the patient's smoking status was listed as not an active smoker and stopped smoking in 2021."&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;ii. &nbsp;Page 7 of the source worksheet asked "does the subject have previous history of use tobacco? Y / N". This was marked as "no"; however, it should have been marked as "yes" since the participant was a former smoker. &nbsp; &nbsp; B. &nbsp;Source documentation was incomplete:&nbsp; &nbsp; &nbsp; &nbsp; 1. &nbsp;Participant 10081004&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;Baseline/Day 1 Visit (20 Jan 2025), on page 4 of the source worksheet asked "was there any change to reproductive system?"; however, the worksheet did not ask if the participant was adhering to the agreed contraception method.&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;b. &nbsp;Day 5 Visit (24 Jan 2025) on page 4 of the source worksheet asked "was there any change to reproductive system?"; however, the worksheet did not ask if the participant was adhering to the agreed contraception method. &nbsp;&nbsp; &nbsp; &nbsp; &nbsp; 2. &nbsp;Participant 10081007's Baseline/Day 1 Visit (30 Jan 2025), the pharmacokinetic (PK) sample packing list with barcode labels was not labeled with the Participant Screen identification number.&nbsp; &nbsp; C. &nbsp;Source documentation was inconsistent:&nbsp; &nbsp; &nbsp; &nbsp; 1. &nbsp;Participant 10081006 &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;a. Screening Visit (24 Jan 2025) source worksheet for the Pre-Specified Significant Medical History Risk Factors, the site staff checked off that the participant was a "Cigarette Smoker"; however, on page 7 of the worksheet, the patient's smoking status listed the participant did not use tobacco product. &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;b. The source Concomitant Medication (ConMed) log, listed the dosage of &nbsp;Amlodipine as 5 milligrams (mg); however, the picture of the medication stored in the participant's chart showed the dosage was 10 mg. &nbsp; D. &nbsp;Source documentation was not contemporaneous:&nbsp; &nbsp; &nbsp; &nbsp;1. &nbsp;Participant 10081004's Day 1 Visit (20 Jan 2025), the SC added a note which stated that he called the participant regarding the abnormal hematology laboratory result, the hemoglobin level was 9.9 grams per deciliter (g/dL). The note was dated as 23 Jan 2025; however, the 9.9 g/dL test result was for the hematology sample collected on 24 Jan 2025. &nbsp; &nbsp; E. &nbsp;Source documentation was not attributable:&nbsp; &nbsp; &nbsp; &nbsp;1. &nbsp;Participant 10081004's Day 34 Visit (21 Feb 2025) Protein Biomarker were marked as collected, the date and time of collection was listed in the source worksheet; however, the initials of the person who collected the sample were missing. &nbsp; &nbsp; F. &nbsp;Source documentation was not available:&nbsp; &nbsp; &nbsp; 1. &nbsp;Participant 10081007's Screening Visit (30 Jan 2025) required the discussion to be documented as to whether the participant had any questions and if they were answered to their satisfaction documented on this worksheet; there was no documentation recorded.&nbsp; &nbsp; &nbsp; 2. &nbsp;Participant 10081009&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;The SC added a note on 07 Feb 25 which stated that the participant came to site since he lost his cellphone, and that the participant was given a study device to complete diary entries; however, there was no documentation of the device given to the participant.&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;b. &nbsp;Two data correction forms (DCF) (DCF# 141 and 161) were not stored in the participant's chart. &nbsp; &nbsp; &nbsp; 3. &nbsp;Participant 10081011's Screening Visit (24 Feb 2025) required the discussion whether participant had any questions and if they were answered to their satisfaction documented on this worksheet; there was no documentation recorded.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | The site has updated their source document to align more clearly with protocol expectations. The site has completed ALCOA plus training with PI. | .4pt;"The current source document template will be reviewed by the site personnel to ensure it includes all fields needed to support data values required per protocol and electronic Case report Form (eCRF) completion requirements. Source document template will be updated if applicable. .4pt;"Site Care Partner will retrain site personnel on Good Clinical Practice (GCP), (ALCOACCEA) requirements. .4pt;" .4pt;"Responsible Roles: Site Personnel/ Site Care Partner | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Approved - In Effectiveness Check | Closed | Data Collection and Management | Inadequate source data/documentation | NOT APPLICABLE; NOT APPLICABLE | SITE PERSONNEL | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-007684 | QE-177362 | 2025-08-29 | 2025-08-25 |  | Completed On Time |  | Major |  | Lilia Roque-Guerrero, Lilia Roque-Guerrero | UNITED STATES | C5091017_1008 | GCP Site Audit | 2025-05-09 |  | For 6 of 9 participant files reviewed, source documentation practices were not in accordance with ALCOACCEA (Attributable, Legible, Contemporaneous, Original, Accurate, Complete, Consistent, Enduring, and Available) [Pfizer Protocol C5091017 (Original: 14 Oct 2024); ICH E6 (R2) 2.10; 4.9.0].&nbsp; &nbsp; A. &nbsp;Source documentation was inaccurate:&nbsp; &nbsp; &nbsp; &nbsp;1. &nbsp;Participant 10081004&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; a. &nbsp;Baseline/Day 1 Visit (20 Jan 2025)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;i. &nbsp;The source worksheet listed that the participant was not a woman of childbearing potential (WOCBP); however, the participant is a WOCBP. &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;ii. &nbsp;On page 8 of the source worksheet, the Study Coordinator (SC) added a note which stated that he called the participant regarding the abnormal hematology laboratory result. The note stated that the abnormal value was clinically significant (cs); however, the investigator marked the results as not clinically significant (ncs) on laboratory report stored in the participant's chart.&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; b. &nbsp;Day 5 Visit (24 Jan 2025) source worksheet listed participant as a non-WOCBP; however, the participant was a WOCBP. &nbsp;&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; c. &nbsp;Day 34 Visit (21 Feb 2025) source worksheet listed participant as a non-WOCBP; however, the participant was a WOCBP. &nbsp;&nbsp; &nbsp; &nbsp; &nbsp; 2. &nbsp;Participant 10081008&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;Baseline/Day 1 Visit (30 Jan 2025) &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; i. &nbsp;Page 4 of the source worksheet for the Pre-Specified Significant Medical History Risk Factors, the site staff checked off that the participant was a "Cigarette Smoker"; however, on page 7 of the worksheet, the patient's smoking status was listed as not an active smoker and stopped smoking in 2021."&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;ii. &nbsp;Page 7 of the source worksheet asked "does the subject have previous history of use tobacco? Y / N". This was marked as "no"; however, it should have been marked as "yes" since the participant was a former smoker. &nbsp; &nbsp; B. &nbsp;Source documentation was incomplete:&nbsp; &nbsp; &nbsp; &nbsp; 1. &nbsp;Participant 10081004&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;Baseline/Day 1 Visit (20 Jan 2025), on page 4 of the source worksheet asked "was there any change to reproductive system?"; however, the worksheet did not ask if the participant was adhering to the agreed contraception method.&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;b. &nbsp;Day 5 Visit (24 Jan 2025) on page 4 of the source worksheet asked "was there any change to reproductive system?"; however, the worksheet did not ask if the participant was adhering to the agreed contraception method. &nbsp;&nbsp; &nbsp; &nbsp; &nbsp; 2. &nbsp;Participant 10081007's Baseline/Day 1 Visit (30 Jan 2025), the pharmacokinetic (PK) sample packing list with barcode labels was not labeled with the Participant Screen identification number.&nbsp; &nbsp; C. &nbsp;Source documentation was inconsistent:&nbsp; &nbsp; &nbsp; &nbsp; 1. &nbsp;Participant 10081006 &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;a. Screening Visit (24 Jan 2025) source worksheet for the Pre-Specified Significant Medical History Risk Factors, the site staff checked off that the participant was a "Cigarette Smoker"; however, on page 7 of the worksheet, the patient's smoking status listed the participant did not use tobacco product. &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;b. The source Concomitant Medication (ConMed) log, listed the dosage of &nbsp;Amlodipine as 5 milligrams (mg); however, the picture of the medication stored in the participant's chart showed the dosage was 10 mg. &nbsp; D. &nbsp;Source documentation was not contemporaneous:&nbsp; &nbsp; &nbsp; &nbsp;1. &nbsp;Participant 10081004's Day 1 Visit (20 Jan 2025), the SC added a note which stated that he called the participant regarding the abnormal hematology laboratory result, the hemoglobin level was 9.9 grams per deciliter (g/dL). The note was dated as 23 Jan 2025; however, the 9.9 g/dL test result was for the hematology sample collected on 24 Jan 2025. &nbsp; &nbsp; E. &nbsp;Source documentation was not attributable:&nbsp; &nbsp; &nbsp; &nbsp;1. &nbsp;Participant 10081004's Day 34 Visit (21 Feb 2025) Protein Biomarker were marked as collected, the date and time of collection was listed in the source worksheet; however, the initials of the person who collected the sample were missing. &nbsp; &nbsp; F. &nbsp;Source documentation was not available:&nbsp; &nbsp; &nbsp; 1. &nbsp;Participant 10081007's Screening Visit (30 Jan 2025) required the discussion to be documented as to whether the participant had any questions and if they were answered to their satisfaction documented on this worksheet; there was no documentation recorded.&nbsp; &nbsp; &nbsp; 2. &nbsp;Participant 10081009&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;The SC added a note on 07 Feb 25 which stated that the participant came to site since he lost his cellphone, and that the participant was given a study device to complete diary entries; however, there was no documentation of the device given to the participant.&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp;b. &nbsp;Two data correction forms (DCF) (DCF# 141 and 161) were not stored in the participant's chart. &nbsp; &nbsp; &nbsp; 3. &nbsp;Participant 10081011's Screening Visit (24 Feb 2025) required the discussion whether participant had any questions and if they were answered to their satisfaction documented on this worksheet; there was no documentation recorded.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | The site has implemented a QC post visit as part of their process for patient review in order to better comply with ALCOACCEA. | .4pt;"The site confirmed they will create and implement a site process to include a quality check to verify data is consistent between the source document and meets ALCOACCEA requirements. .4pt;"Responsible Roles: Site Care Partner/ Site personnel | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Approved - In Effectiveness Check | Closed | Data Collection and Management | Inadequate source data/documentation | NOT APPLICABLE; NOT APPLICABLE | SITE PERSONNEL | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-007684 | QE-177488 | 2025-08-29 | 2025-10-22 |  | Complete Late |  | Major |  | Lilia Roque-Guerrero, Lilia Roque-Guerrero | UNITED STATES | C5091017_1008 | GCP Site Audit | 2025-05-09 |  | Monitoring activities were found to be inadequate with respect to the execution and documentation of monitoring [ICH GCP E6 [R3] 3.11.4.5.3 (v), 3.11.4.5.4 (b), (c); Study Monitoring Plan C5091017 (version 3: 20 Feb 2025)]. Monitoring activities failed to detect issues identified in this audit report: 1. There was inadequate source data collection and/or recording of the data with respect to Accurate, Legible, Contemporaneous, Original, Attributable, Complete, Consistent, Enduring, and Available (ALCOACCEA) criteria for Participants 10081007, 10081009, and 10081011 (see QE-177362). 2. There were discrepancies between source documentation and the electronic case report forms (eCRFs) for Participants 10081001, 10081007, and 10081011 (see QE-177387). 3. There were missing essential documents in the&nbsp; Pfizer Trial Master File (PTMF) (see QE-177401). 4. There were missing essential documents in the electronic&nbsp; Investigator Site File (eISF) (see QE-177442). 5. There was inadequate delegation of duties (see QE-177462). 6. There was a potential breach of privacy and data protection for Participants 10081001, 10081007, 10081009, and 10081011 (see QE-177411). 7. There was discrepant data between the 'Verification Report" earliest dosing date and the actual dosing date for Participants 10081001, 10081007, 10081009, and 10081011 (see QE-177442). | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | For all issues below, corrections were completed per Siebel Clinical Trial Management (CTMS) system Issue Action ID# 1-7TIXCBJ, 1-7TIXCDB, 1-7TIXC9L, 1-7TIXC8L, 1-7TIXC7D, 1-7TIXC77, 1-7TI4IZ3, 1-7TI4IYZ, 1-7TI4IYV, 1-7TIXCDF.1-7TIXCBJ, 1-7TIXCDB, 1-7TIXC9L, 1-7TIXC8L, 1-7TIXC7D, 1-7TIXC77, 1-7TI4IZ3, 1-7TI4IYZ, 1-7TI4IYV, 1-7TIXCDF | 1.The Site Monitor will review the applicable Source Document issues note in QE-177362 to ensure documents meet Accurate, Legible, Contemporaneous, Original, Attributable, Complete, Consistent, Enduring, and Available (ALCOACCEA) requirements. 2.This study utilizes Risk Based Monitoring per the C5091017 Study Monitoring plan. Two out of the three participants noted in Finding- QE-177387 were not part of the Source Document Verification Sample for Monitoring. For participant 10081001 who was part of the site monitor's SDV sample, the eCRF was updated appropriately per section 3.13. (Team to confirm)- 3.The Site Care Partner will confirm the missing documents are filed in the Pfizer Trial Master File. 4.The Site Monitor will ensure the essential documents noted in QE-177394 (although audit finding indicates QE-177442 in error) are filed appropriately in the electronic Investigator Site File.5.The SCP will review the Signature Sheet and Delegations of Duties Log (SSDDL) to ensure study required tasks are delegated appropriately and issues noted in QE-177642 are corrected on the SSDDL.6.The Site Monitor will confirm the documents containing personal identifiable information (PII) for secondary contacts for the participants have been removed from the electronic Investigator Site File (eISF). 7.On 25APR25, the Verified Clinical Trial (VCT) study build was updated to correct the issues noted in QE-177442. Team confirmed it was fully signed and filed in PTMF and SP/Teams. There are no actions required for site monitor. Responsible Roles: Site Care Partner/Site Monitor All items to be completed by 30Jul2025. | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | Site Management and Monitoring | Failure to detect/document | INV04 - Investigational Site Management and Monitoring | PFIZER | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-007684 | QE-177488 | 2025-08-29 | 2025-10-22 |  | Complete Late |  | Major |  | Lilia Roque-Guerrero, Lilia Roque-Guerrero | UNITED STATES | C5091017_1008 | GCP Site Audit | 2025-05-09 |  | Monitoring activities were found to be inadequate with respect to the execution and documentation of monitoring [ICH GCP E6 [R3] 3.11.4.5.3 (v), 3.11.4.5.4 (b), (c); Study Monitoring Plan C5091017 (version 3: 20 Feb 2025)]. Monitoring activities failed to detect issues identified in this audit report: 1. There was inadequate source data collection and/or recording of the data with respect to Accurate, Legible, Contemporaneous, Original, Attributable, Complete, Consistent, Enduring, and Available (ALCOACCEA) criteria for Participants 10081007, 10081009, and 10081011 (see QE-177362). 2. There were discrepancies between source documentation and the electronic case report forms (eCRFs) for Participants 10081001, 10081007, and 10081011 (see QE-177387). 3. There were missing essential documents in the&nbsp; Pfizer Trial Master File (PTMF) (see QE-177401). 4. There were missing essential documents in the electronic&nbsp; Investigator Site File (eISF) (see QE-177442). 5. There was inadequate delegation of duties (see QE-177462). 6. There was a potential breach of privacy and data protection for Participants 10081001, 10081007, 10081009, and 10081011 (see QE-177411). 7. There was discrepant data between the 'Verification Report" earliest dosing date and the actual dosing date for Participants 10081001, 10081007, 10081009, and 10081011 (see QE-177442). | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | All actions have been completed from 9May2025. See attached action item log. There is one additional documentation correction required for subject 1008-1004. This has been captured in action item #1-84LUWZD which remains outstanding. 10Nov25 The final action item noted above has been completed. Issue and action items have been updated and attached. | .4pt;"The Site Care Partner and Site Monitor will conduct Site Management and Monitoring Activities per INV04-GSOP-RF13 S to confirm all corrections have been made and mark the resolution in Siebel. .4pt;" .4pt;"The report reviewers country Study Operations Manager (cSOM) and SCP will review reports and associated logs. The cSOM and Site Care Partner will document their review per INV02-INV04- GSOP-RF14_Review of Site Activities. .4pt;" .4pt;"Responsible Roles: Site Care Partner/Site Monitor/cSOM | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | Site Management and Monitoring | Failure to detect/document | INV04 - Investigational Site Management and Monitoring | PFIZER | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-007684 | QE-177488 | 2025-08-29 | 2025-10-22 |  | Complete Late |  | Major |  | Lilia Roque-Guerrero, Lilia Roque-Guerrero | UNITED STATES | C5091017_1008 | GCP Site Audit | 2025-05-09 |  | Monitoring activities were found to be inadequate with respect to the execution and documentation of monitoring [ICH GCP E6 [R3] 3.11.4.5.3 (v), 3.11.4.5.4 (b), (c); Study Monitoring Plan C5091017 (version 3: 20 Feb 2025)]. Monitoring activities failed to detect issues identified in this audit report: 1. There was inadequate source data collection and/or recording of the data with respect to Accurate, Legible, Contemporaneous, Original, Attributable, Complete, Consistent, Enduring, and Available (ALCOACCEA) criteria for Participants 10081007, 10081009, and 10081011 (see QE-177362). 2. There were discrepancies between source documentation and the electronic case report forms (eCRFs) for Participants 10081001, 10081007, and 10081011 (see QE-177387). 3. There were missing essential documents in the&nbsp; Pfizer Trial Master File (PTMF) (see QE-177401). 4. There were missing essential documents in the electronic&nbsp; Investigator Site File (eISF) (see QE-177442). 5. There was inadequate delegation of duties (see QE-177462). 6. There was a potential breach of privacy and data protection for Participants 10081001, 10081007, 10081009, and 10081011 (see QE-177411). 7. There was discrepant data between the 'Verification Report" earliest dosing date and the actual dosing date for Participants 10081001, 10081007, 10081009, and 10081011 (see QE-177442). | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | See email attached for discussion regarding training. | .4pt;"The country Study Operations Manager (cSOM) will share some of the issues/actions noted in this Audit Finding with the Site Monitors/Site Care Partners during an upcoming country call. .4pt;"Responsible Roles: cSOM/Site Monitor/Site Care Patner | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | Site Management and Monitoring | Failure to detect/document | INV04 - Investigational Site Management and Monitoring | PFIZER | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-007684 | QE-177462 | 2025-06-23 | 2025-06-17 |  | Completed On Time |  | Minor |  | Lilia Roque-Guerrero, Lilia Roque-Guerrero | UNITED STATES | C5091017_1008 | GCP Site Audit | 2025-05-09 |  | The oversight of study personnel by the Principal Investigator (PI) was inadequate related to the delegation of duties. [Pfizer Protocol C5091017 (Original: 14 Oct 2024) and ICH E6 (R2) 4.2.6]. Specifically, according to the Signature Sheet and Delegations of Duties Log (SSDDL): 1. &nbsp;No one was delegated task 22 - Investigational Product (IP) Quality Control (QC) checker. &nbsp; 2. &nbsp;Only 1 person was delegated task 21 - Administer electronic Patient Reported Outcomes (ePRO).&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | SSDDL updated. For issues above all corrections were completed per Siebel Clinical Trial Management (CTMS) system Issue Action ID#1-7TIXCDF. | 1. The Site Care Partner will confirm the designated site personnel who are documenting dispensing of investigational product (IP) on the Investigational Product Accountability Log (IPAL) are listed on the Signature Sheet and Delegation of Duties Log (SSDDL ), delegated task (9b), Per INV02-INV04-GSOP-RF11, two designated site staff members document dispensing of investigational medicinal product.2. Site Personnel will add a late entry to the SSDDL to delegate additional site personnel for electronic Patient Reported Outcome (ePRO) task. Site Care Partner confirmed these site personnel completed the ePRO training. Responsible Roles: Site Care Partner/ Site Personnel Monitor will confirm at the next scheduled visit. | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | Quality Oversight | Inadequate Principal Investigator quality oversight | NOT APPLICABLE; NOT APPLICABLE | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-007684 | QE-177391 | 2025-10-15 | 2025-08-04 |  | Completed On Time |  | Minor |  | Lilia Roque-Guerrero, Lilia Roque-Guerrero | UNITED STATES | C5091017_1008 | GCP Site Audit | 2025-05-09 |  | For 2 of 9 participant files reviewed, study assessments and tests were not completed as required by the protocol [Pfizer Protocol C5091017 (Original: 14 Oct 2024)].&nbsp; 1. &nbsp;Participant 10081004&nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;The Day 5 Visit (24 Jan 2025), contraception check was not completed. Page 4 of the source worksheet had the participant listed as not a woman of childbearing potential (WOCBP); however, the participant was a WOCBP. &nbsp; &nbsp; &nbsp; &nbsp;b. &nbsp;Day 34 Visit (21 Feb 2025)&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; i. &nbsp;The Urine pregnancy test was not completed at this visit. &nbsp;&nbsp; &nbsp; &nbsp; &nbsp; &nbsp; &nbsp; ii. &nbsp;The Specified Protein was collected at this visit; however, it was not required to be collected at this visit. &nbsp; &nbsp; 2. &nbsp;Participant 10081008&nbsp; &nbsp; &nbsp; &nbsp;a. &nbsp;The Screening Visit (30 Jan 2025) source worksheet had the participant listed as a WOCBP, and the method of contraception listed the use of condom only; however, as per the protocol condoms were acceptable only if used with a hormonal contraception method. &nbsp; &nbsp; &nbsp; &nbsp;b. &nbsp;The Day 5 Visit (04 Feb 2025) contraception check was inadequate: the question listed on the worksheet asked, "was there any change to reproductive system?" &nbsp; &nbsp; &nbsp; &nbsp;c. &nbsp;The Day 10 Visit (04 Feb 2025), contraception check was inadequate: the question listed on the worksheet asked, "was there any change to reproductive system?" &nbsp; &nbsp; &nbsp; &nbsp;d. &nbsp;The Day 34 Visit (05 Mar 2025): urine pregnancy test was not completed at this visit. &nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | Subject 1008-1004 is of child bearing potential. Pregnancy test was confirmed at screening per action item #1-85OBW3D. Other actions completed as per IA #1-7TFSA5U and 1-7TGMMGF.Subject 1008-1008 confirmed to not be of child-bearing potential. | 1. 1a &amp; 2b/c- PDs will be reported if participants 10081004 &amp; 10081008 are women of child bearing potential (WOCBP), if not this will be clearly documented in the source as a late entry. 2. 1b &amp; 2 a/d- For Participants 10081004 &amp; 10081008, Protocol Deviations will be reported as required per their IRB and PDs will be entered into Siebel Protocol Deviation log. All items will be completed by 30Jun2025. | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | Protocol Deviations | Failure to follow protocol | CT40 - Protocol Deviations | SITE PERSONNEL | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-007684 | QE-177470 | 2025-06-23 | 2025-06-26 |  | Complete Late |  | Minor |  | Lilia Roque-Guerrero, Lilia Roque-Guerrero | UNITED STATES | C5091017_1008 | GCP Site Audit | 2025-05-09 |  | For 1 out of 9 participant files reviewed, data available in the electronic Case Report Form (eCRF) was not supported by source documentation [ICH GCP E6 [R2] 4.9.0]. 1. Participant 10081012's source Concomitant Medication log listed Lisinopril; however, a picture of the prescription bottle was not available in the participant's chart.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | For issues noted above all corrections were completed per Siebel Clinical Trial Management (CTMS) system Issue Action ID#1-7TFSAB8. | Site Monitor will confirm if a copy of the Lisinopril prescription is available to be filed in the source document. It is not required to have a copy of the prescription/ photo of the prescription bottle in the chart, per protocol. Global Study Manager confirmed a photo is not required for all medication, only corticosteroids. .4pt;"Responsible Roles: Site Personnel/Site Monitor .4pt;".4pt;" | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | Data Collection and Management | Inadequate source data/documentation | NOT APPLICABLE; NOT APPLICABLE | PRINCIPAL INVESTIGATOR | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-007684 | QE-177442 | 2025-06-23 | 2025-04-24 |  | Completed On Time |  | Minor |  | Lilia Roque-Guerrero, Lilia Roque-Guerrero | UNITED STATES | C5091017_1008 | GCP Site Audit | 2025-05-09 |  | The design/functionality of an Information Technology (IT) system f or 9 of 9 participant files reviewed provided inaccurate data [ICH E6 (R2) 5.5.3]. The Verified Clinical Trial (VCT) system provided the 'Verification Report' which reported that the 'Subject is eligible to continue to screening' and included the 'Earliest First Dosing Date'. This reported date was the day after the documented dosing date occurred, as per the source records. &nbsp; 1. Participant 10081001: VCT had 24 Dec 2024; dosing occurred 23 Dec 2024&nbsp; 2. Participant 10081004: VCT had 21 Jan 2025; dosing occurred 20 Jan 2025 3. Participant 10081006: VCT had 25 Jan 2025; dosing occurred 24 Jan 2025 4. Participant 10081007: VCT had 31 Jan 2025; dosing occurred 30 Jan 2025 5. Participant 10081008: VCT had 31 Jan 2025; dosing occurred 30 Jan 2025 6. Participant 10081009: VCT had 06 Feb 2025; dosing occurred 05 Feb 2025 7. Participant 10081010: VCT had 22 Feb 2025; dosing occurred 21 Feb 2025 8. Participant 10081011: VCT had 25 Feb 2025; dosing occurred 24 Feb 2025 9. Participant 10081012: VCT had 09 Apr 2025; dosing occurred 08 Apr 2025 | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | For issues above all corrections were completed per Siebel Clinical Trial Management (CTMS) system Issue Action ID# 1-7TIXC77. | “Verified Clinical Trials (VCT) has removed the screening window from the schedule of events and noted in the study build that the maximum screening window is '1 day.' This will correct the date on the verification reports and would still be receiving accurate enrollment data from all subjects from Impala/Inform, even for subjects that dose the day after.” On 25APR25, the updated VCT study build was fully signed and filed in PTMF and SP/Teams | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | IT Systems | Inadequate IT system (eg. planning, definitions, design, development, testing, validation, support) per regulatory requirements | NOT APPLICABLE; NOT APPLICABLE | PFIZER | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-008466 | QE-209233 | 2026-03-10 | 2025-12-11 |  | Completed On Time |  | Minor |  | Perez, Cesar | UNITED STATES | C5091017_1101 | GCP Site Audit | 2025-11-05 |  | For 2 of 8 participant files reviewed, the investigator site did not consistently adhere to the protocol [Pfizer Protocol C5091017 (Amendment 1: 07 May 2025); ICH E6 (R3) 2.5.2]. 1. &nbsp; &nbsp;For Participant 11011018, the site did not collect contact information for two secondary contacts as required by protocol which could have been used to determine if a participant was lost to follow-up and/or vital status check. 2. &nbsp; &nbsp;Participant 11011022 was a smoker since UNK/UNK/1978; however, it was not noted for Inclusion Criteria list of risk factors. &nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | .6667px; background-color: rgb(255, 255, 255);'All corrections were made. Please refer Siebel Clinical Trial Management System (CTMS) Issue Action ID: .6667px; background-color: rgb(255, 255, 255);'1-9VK6OF8,1-9VK6OF4 | 1 &amp; 2. The site personnel will ensure documentation is entered in the source as a late entry to explain the rationale for not following the protocol in these instances. The Clinical Research Associate (CRA) will ensure the Protocol Deviations (PDs)are entered on the PD log in the Clinical Trial Management System (CTMS) and that the site reports per their local requirements.The CRA will ensure site understands the protocol requirements for collecting contact information and Inclusion criteria list of risk factors, per the protocol. | Kelley Fennell |  | - | Kelley Fennell | Closed | Closed | Protocol Deviations | Failure to follow protocol | CT40 - Protocol Deviations | SITE PERSONNEL | MODEL 1 - INSOURCED | Internal Medicine | Fennell, Kelley | GSSO | 84 | AMERICAS
AIA-008466 | QE-210256 | 2026-03-10 | 2025-12-11 |  | Completed On Time |  | Minor |  | Perez, Cesar | UNITED STATES | C5091017_1101 | GCP Site Audit | 2025-11-05 |  | Two documents in the Pfizer Trial Master File (PTMF) were missing [Pfizer SOP CT01-GSOP Trial Master Files (Version 8.0: 03 Oct 2022)]. 1. &nbsp; &nbsp; There was a missing Approval Notice (Approval Date 09 Oct 2025- Letter date 13 Oct 2025) for Verified Clinical Trials (VCT) Research Subject Database Personal Information Authorization (Dated 05 Sep 2025). 2. &nbsp; &nbsp; The PTMF was missing electronic case report form (eCRF) Completion Requirements Versions 1.0 dated 02 Dec 2024 and 2.0 dated 19 Mar 2025. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | .6667px; background-color: rgb(255, 255, 255);'All corrections were made. Please refer Siebel Clinical Trial Management System (CTMS) Issue Action ID: | .25in;"The Clinical Research Associate (CRA) will ensure the Approval Notice (Approval Date 09 Oct 2025- Letter date 13 Oct 2025) for Verified Clinical Trials (VCT) Research Subject Database Personal Information Authorization (Dated 05 Sep 2025) is filed in the PTMF.The Global Study Manager (GSM) will ensure the electronic case report form (eCRF) Completion Requirements Versions 1.0 dated 02 Dec 2024 and 2.0 dated 19 Mar 2025 are filed in the PTMF..75in;" | Kelley Fennell |  | - | Kelley Fennell | Closed | Closed | Compliance Requirements - Applicable Approvals/Regulatory Required Essential Documents | Applicable regulatory approvals not obtained or inadequate use of regulatory required essential documents | CT01 - Trial Master Files | PFIZER | MODEL 1 - INSOURCED | Internal Medicine | Fennell, Kelley | GSSO | 84 | AMERICAS
AIA-008466 | QE-209217 | 2026-03-10 | 2026-01-12 |  | Completed On Time |  | Minor |  | Perez, Cesar | UNITED STATES | C5091017_1101 | GCP Site Audit | 2025-11-05 |  | Monitoring activities were inadequate with regards to issue detection and/or documentation [C5091017 Study Monitoring Plan (Version 5: dated 19 Sep 2025)]. Monitoring activities failed to identify issues noted for: 1. &nbsp;The investigator site did not consistently adhere to the protocol (see QE-209233). 2. &nbsp;The informed consent process was not accurately reflected in the source records (see QE-209236). 3. &nbsp;The Investigational Product accountability records were not completed as required (QE-209216). 4. There was inadequate source data collection and/or recording of the data with respect to Accurate, Legible, Contemporaneous, Original, Attributable, Complete, Consistent, Enduring, and Available (ALCOACCEA) criteria for Participant 11011005 (see QE-209214). 5. There were discrepancies between source documentation and the electronic case report forms for Participant 11011005 (see QE-QE-209234). 6. There were missing essential documents in the Pfizer Trial Master File (see QE-210256). 7. There were missing essential documents in the electronic Investigator Site File (see QE-210270). | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | All corrections were made. | .5in;"For issues 1, 2, 4, &amp;5: Based on the Risk-Based Monitoring model, Clinical Research Associates (CRAs) are provided with a sample of subjects to review. The participants identified in these findings were not included in the Source Document Review and Source Data Verification sample. .5in;"For Issues 1-7: The Clinical Research Associate will ensure all findings in this report are corrected per GCP (Good Clinical Practice)/ALCOACCEA (Attributable, Legible, Contemporaneous, Original, Accurate, Complete, Consistent, Enduring, Available) requirements. | Kelley Fennell |  | - | Kelley Fennell | Closed | Closed | Site Management and Monitoring | Failure to detect/document | INV04 - Investigational Site Management and Monitoring | VENDOR / CONTRACTOR | MODEL 1 - INSOURCED | Internal Medicine | Fennell, Kelley | GSSO | 84 | AMERICAS
AIA-008466 | QE-210270 | 2026-03-10 | 2026-01-12 |  | Completed On Time |  | Minor |  | Perez, Cesar | UNITED STATES | C5091017_1101 | GCP Site Audit | 2025-11-05 |  | Two essential documents were missing in the electronic Investigator Site File (e-ISF) [ICH GCP E6 (R3) 2.12.12]. The following documents were not available in the e-ISF: 1. &nbsp; &nbsp;Study Newsletter, Edition 7, dated 30 Sep 2025. 2. &nbsp; &nbsp;Electronic case report form (eCRF) completion Requirements Version 3.0 dated 19 May 2025. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | All corrections were made. | .5in;"1 &amp;2. The Clinical Research Associate will provide copies of these documents to the site for filing in their electronic Investigator Site File (eISF). The CRA will confirm documents are filed. | Kelley Fennell |  | - | Kelley Fennell | Closed | Closed | Compliance Requirements - Applicable Approvals/Regulatory Required Essential Documents | Applicable regulatory approvals not obtained or inadequate use of regulatory required essential documents | CT01 - Trial Master Files | SITE PERSONNEL | MODEL 1 - INSOURCED | Internal Medicine | Fennell, Kelley | GSSO | 84 | AMERICAS
AIA-008466 | QE-209234 | 2026-03-10 | 2025-12-18 |  | Completed On Time |  | Minor |  | Perez, Cesar | UNITED STATES | C5091017_1101 | GCP Site Audit | 2025-11-05 |  | For 5 of 8 participants’ records reviewed, discrepancies were noted between the electronic Case Report Forms (eCRFs) and the source documentation [C5091017 CRF Completion Requirements Version 3, 09 May 2025]; ICH GCP E6 (R3) 2.12.5]. 1. &nbsp; &nbsp; For Participant 11011002, the site's source documentation (Medical History) listed Type 2 Diabetes Mellitus with a start date of 11 Feb 2021; however, the electronic Case Report Form (eCRF) had the start date as 11 Feb 2012. 2. &nbsp; &nbsp; For participant 11011004, a late source entry dated 23 Sep 2025 documented as Iron, 200 milligrams administered orally since 05 Jul 2025 and ongoing, was not entered in the eCRF. 3. &nbsp; &nbsp; For Participant 11011004, the site’s source documentation (Concomitant and Prior Medications form) listed Atorvastatin with a start date of UNK/UNK/2025; however, the eCRF had the start date as UNK/Mar/2025. 4. &nbsp; &nbsp; For participant 11011005, the site’s source documentation (Medical History) listed Type 2 Diabetes Mellitus with a start date of UNK/UNK/2021; however, the eCRF had the start date as UNK/Sep/2021. 5. &nbsp; &nbsp; For participant 11011005, the site’s source documentation (Medical History) listed Hepatomegaly with a start date of UNK/UNK/2021; however, there was no corresponding entry in the eCRF. 6. &nbsp; &nbsp; For participant 11011018, the site’s source documentation (Pre-specified Significant Medical History Risk Factors) did not record cardiovascular disease; however, the eCRF had an entry for Cardiovascular with a start date of UNK/UNK/2022. 7. &nbsp; &nbsp; For participant 11011025, the site’s source documentation (Medical History) listed Chronic Obstructive Pulmonary with a start date of 14 Oct 2022; however, the eCRF had the start date as 04 Oct 2022. 8. &nbsp; &nbsp; For participant 11011025, the site’s source documentation (Medical History -Medication List) had Citalopram Hydrobromide with a start date of 27 Sep 2022; however, the site’s source documentation (Concomitant and Prior Medications) and the eCRF both had the start date as 27 Sep 2023. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | .6667px; background-color: rgb(255, 255, 255);'All corrections were made. Please refer Siebel Clinical Trial Management System (CTMS) Issue Action ID: .6667px; background-color: rgb(255, 255, 255);'1-9VK6OFZ, 1-9VK6OFH, 1-9VK6OG3, 1-9VK6OFD, 1-9VK6OFV | .5in;"1-8. Site Personnel to review and reconcile information recorded between source documentation and electronic Case Report Form to ensure alignment in subject data and discrepancies are corrected per ALCOACCEA (Attributable, Legible, Contemporaneous, Original, Accurate, Complete, Consistent, Enduring, Available) requirements..5in;"The Clinical Research Associate (CRA) to review and ensure data is updated as appropriate. | Kelley Fennell |  | - | Kelley Fennell | Closed | Closed | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry | DMB03-GSOP - Data Management | SITE PERSONNEL | MODEL 1 - INSOURCED | Internal Medicine | Fennell, Kelley | GSSO | 84 | AMERICAS
AIA-008466 | QE-209216 | 2026-03-10 | 2025-12-11 |  | Completed On Time |  | Minor |  | Perez, Cesar | UNITED STATES | C5091017_1101 | GCP Site Audit | 2025-11-05 |  | Investigational Product (IP) record keeping activities were inadequate as per the protocol and Investigational Product Manual [Pfizer Protocol C5091017 (Amendment 1: 07 May 2025) and Pfizer Protocol C5091017 Investigational Product Manual (version 1.0: 30 Oct 2024)]. 1. &nbsp; &nbsp; For 3 Drug Shipment and Proof of Receipts (1860182, 1870860 and 1882827), for the questions about whether or not the shipment was damaged or if the temperature monitoring device alarmed during shipment (on the 2nd page of the receipt acknowledgement) were left blank for 3 receipts. 2. &nbsp; &nbsp; For 2 Drug Shipment and Proof of Receipts (1860182 and 1870860), the 2nd page of the receipt acknowledgement was left blank for signature, printed name, title and date. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | .6667px; background-color: rgb(255, 255, 255);'All corrections were made. Please refer Siebel Clinical Trial Management System (CTMS) Issue Action ID: .6667px; background-color: rgb(255, 255, 255);'1-9VK6ODO, 1-9VK6OAS | .25in;"The delegate Site Personnel will view the temperature monitoring device print outs and confirm no damage for the 3 Drug Shipments (1860182, 1870860 and 1882827), and add a late entry to answer the questions that were initially left blank. The delegated site personnel will confirm if possible that the 2 Drug Shipments (1860182 and 1870860) were received and enter a late entry to acknowledge the receipt on the 2nd page. .5in;"The Clinical Research Associate (CRA) will review the source documents to confirm the corrections/ late entries were added perALCOACCEA (Attributable, Legible, Contemporaneous, Original, Accurate, Complete, Consistent, Enduring, and Available) requirements. | Kelley Fennell |  | - | Kelley Fennell | Closed | Closed | Medicinal Product | Inadequate accountability/record keeping | CT13-GSOP - Investigational Product | SITE PERSONNEL | MODEL 1 - INSOURCED | Internal Medicine | Fennell, Kelley | GSSO | 84 | AMERICAS
AIA-008466 | QE-209214 | 2026-03-10 | 2025-12-11 |  | Completed On Time |  | Minor |  | Perez, Cesar | UNITED STATES | C5091017_1101 | GCP Site Audit | 2025-11-05 |  | For 6 of 8 participant files reviewed, source documentation practices were not in accordance with ALCOACCEA (Attributable, Legible, Contemporaneous, Original, Accurate, Complete, Consistent, Enduring, and Available) [Pfizer Protocol C5091017 (Amendment 1: 07 May 2025); ICH E6 (R3) 2.12.2]. 1. &nbsp; &nbsp; The site’s documentation for the Partner Health and Safety section had the following question "Do you feel that your sexual relationships are based on mutual consent?” Participants 11011002, 11011005, 11011010, 11011018 and 11011025 all answered "NO"; however, after interviewing site personnel, it was determined that these checkboxes were incorrectly checked and should have been "YES".&nbsp; 2. &nbsp; &nbsp; For Participant 11011002, the site's source documentation section for Sexual History was checked “yes” for sexually active; however, the next section for which method of contraception was used was checked as “Sexual Abstinence”. 3. &nbsp; &nbsp; For Participant 11011004, the site’s source documentation (Concomitant and Prior Medications), had the start date month changed for #6 Famotidine from UNK/UNK/2025 to UNK/Mar/2025; however, there were no initials or date for this change.&nbsp; 4. &nbsp; &nbsp; For Participant 11011004, the Body Mass Index (BMI) was 28.0; however, the Inclusion/Exclusion Worksheet had "YES" checked for BMI ≥30 kg/m2. This checkbox error did not change subject eligibility. 5. &nbsp; &nbsp; For Participant 11011004, there was a Note to File dated 12 May 2025 referencing clotting of hematology samples that did not reference the participant number for whom the memo was applicable. 6. &nbsp; &nbsp; For Participant 11011010, the site’s source document (General Medical History) had the start date for cigarette smoking as UNK/UNK/2021; however, the site’s source documentation (Pre-specified Medical History Risk Factors) had the cigarette smoking start date as UNK/UNK/2001.&nbsp; 7. &nbsp; &nbsp; For Participant 11011018, the site’s screening source documentation (Vital Signs) had the BMI recorded as 28.3; however, the site's Inclusion/Exclusion Worksheet had "YES" checked for BMI ≥30 kg/m2. This checkbox error did not change subject eligibility. 8. &nbsp; &nbsp; For Participant 11011018, on the site’s screening source documentation (Day 1- Study Intervention Administration), the "Time of Administration" was not recorded. 9. &nbsp; &nbsp; For Participant 11011018, the printed copy of the Day 14 Covid-19 Symptoms Diary filed in participant's chart for 21 Aug 2025 through 25 Aug 2025 was stamped as "Certified To Be A True &amp; Exact Copy Of Original", however, it was not initialed and dated. | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | .6667px; background-color: rgb(255, 255, 255);'All corrections were made. Please refer Siebel Clinical Trial Management System (CTMS) Issue Action IDs: .6667px; background-color: rgb(255, 255, 255);'1-9VJOHPG, 1-9VK6OAM, 1-9VJOHR6, 1-9VJOHPB, 1-9VJOHR0 | .25in;"The site personnel will create a late entry in the source documents to explain checkboxes were incorrectly checked and should have been marked as "YES". The site personnel will create a late entry in the source documents to confirm/clarify Sexual History and Method of Contraception. If there is deviation from protocol this will be documented and entered into the Clinical Trial Management System (CTMS), if applicable.A late entry will be added to explain why date was updated..5in;"&amp;7 There will be a late entry added to source documents for participants 11011004 and 11011018 to explain discrepancy between the Body Mass Index (BMI)and Inclusion/Exclusion Worksheet.There will be a late entry to clarify the correct participant ID for the Note to File dated 12 May 2025 referencing clotting of hematology samples. The site personnel will contact participant 11011010 to clarify start date for cigarette smoking and add a late entry to correct incorrect date on applicable source document. 8. A late entry will be added to explain why the "Time of Administration" was not recorded at time of visit. 9. A late entry that is initialed and dated will be added to “re-confirm that the copy is "Certified To Be A True &amp; Exact Copy Of Original".The Clinical Research Associate (CRA) will review the source documents to confirm the corrections/ late entries were added perALCOACCEA (Attributable, Legible, Contemporaneous, Original, Accurate, Complete, Consistent, Enduring, andAvailable) requirements. | Kelley Fennell |  | - | Kelley Fennell | Closed | Closed | Data Collection and Management | Inadequate source data/documentation | NOT APPLICABLE; NOT APPLICABLE | SITE PERSONNEL | MODEL 1 - INSOURCED | Internal Medicine | Fennell, Kelley | GSSO | 84 | AMERICAS
AIA-008466 | QE-209236 | 2026-03-10 | 2025-12-11 |  | Completed On Time |  | Minor |  | Perez, Cesar | UNITED STATES | C5091017_1101 | GCP Site Audit | 2025-11-05 |  | For 2 of 26 participants' file reviewed, the informed consent process was not accurately reflected in the source records with respect to the participant's primary language and the signed informed consent forms or the informed consent process checklist [ICH E6 (R3) 2.8.1]. a. For Participant 11011015, on the "Informed Consent Process Form" the primary language of the participant was checked as Spanish; however, the next question "In what language was the informed consent form (ICF) signed?" was checked as English. The actual signed informed consent documents (main, optional, and Verified Clinical Trials) were in Spanish. b. For Participant 11011012, the "Informed Consent Process Form", signed on 31 Jul 2025, did not check the box to indicate who was the person providing consent: Subject, Study Partner, Caregiver, Parent(s), or Legally Authorized Representative (LAR). | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | .6667px; background-color: rgb(255, 255, 255);'All corrections were made. Please refer Siebel Clinical Trial Management System (CTMS) Issue Action ID: .6667px; background-color: rgb(255, 255, 255);'1-9VK6OLH, 1-9VK6OLL | .25in;"Site Personnel will correct the response to the question asking, what language was the informed consent form (ICF) signed, so it is consistent with the actual signed informed consent documents.Site Personnel will provide a late entry to mark box indicating the person providing consent..5in;"a &amp; b. The Clinical Research Associate (CRA) will review the "Informed Consent Process Forms” to ensure data is corrected per ALCOACCEA (Attributable, Legible, Contemporaneous, Original, Accurate, Complete, Consistent, Enduring, Available) requirements. | Kelley Fennell |  | - | Kelley Fennell | Closed | Closed | Informed Consent | Inadequate consent process at the investigator site | CT05 - Informed Consent Documents | SITE PERSONNEL | MODEL 1 - INSOURCED | Internal Medicine | Fennell, Kelley | GSSO | 84 | AMERICAS
AIA-008088 | QE-202153 | 2025-11-14 | 2025-10-30 |  | Completed On Time |  | Minor |  | Capote Jr, Eddy | UNITED STATES | C5091017_1006 | GCP Site Audit | 2025-09-26 |  | For 7 of 7 participant files reviewed, source documentation practices were not in accordance with ALCOACCEA (Attributable, Legible, Contemporaneous, Original, Accurate, Complete, Consistent, Enduring, and Available) [Pfizer Protocol C5091017 (Amendment 1: 07 May 2025); ICH E6 (R3) 2.12.2]. Site revised study worksheets were inaccurate with respect to page documentation references: &nbsp;&nbsp; 1. &nbsp;The site worksheet for Day 10 [Version 2 (17 Dec 22024)] for Participant completed diaries, on page 6 of 8, asked "Did the subject miss any diaries?". If yes, please comment in "Progress Note' on page 10"; however, the Progress Note section for the worksheet for this visit was on page 8 of 8. &nbsp; 2. &nbsp;The site worksheet for visit Day 14 [Version 1 (06 Dec 2024)] on page 4 of 6, asked "Did the subject miss any diaries?". If yes, please comment in "Progress Note' on page 10"; however, the Progress Note section for the worksheet for this visit was on page 6 of 6.&nbsp; 3. &nbsp;The site worksheet for visit Day 21 [Version 1 (06 Dec 2024)] on page 5 of 7, asked "Did the subject miss any diaries?". If yes, please comment in "Progress Note' on page 10"; however, the Progress Note section for the worksheet for this visit was on page 7 of 7.&nbsp; 4. &nbsp;The site worksheet for visit Day 34 [Version 2 (13 Jan 2025)] on page 4 of 9, asked "Did the subject miss any diaries?". If yes, please comment in "Progress Note' on page 10"; however, the Progress Note section for the worksheet for this visit was on page 9 of 9.&nbsp; | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | The site has updated their source template. The source template was reviewed by the SCP and determined to be adequate. See action item #1-9BJCSBK. | .4pt;"1-4. Site has provided updated source documentation. The updates were reviewed by the SCP for accuracy and confirmed to be adequate. .4pt;" Responsible Roles: Site personnel, SCP.4pt;"Target Completion Date: 15Nov25.4pt;" Action Owner: Georgina Perez-Lewis | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | Data Collection and Management | Inadequate source data/documentation | NOT APPLICABLE; NOT APPLICABLE | SITE PERSONNEL | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS
AIA-008088 | QE-203418 | 2025-11-14 | 2025-10-13 |  | Completed On Time |  | Minor |  | Capote Jr, Eddy | UNITED STATES | C5091017_1006 | GCP Site Audit | 2025-09-26 |  | Monitoring activities were inadequate with regards to issue detection and/or documentation [C5091017 Clinical Monitoring Plan (Version 3: dated 20 FEB 2025)]. Specifically: Monitoring failed to identify the missing site representative signature on the informed consent form (QE-202151). | Response is not in scope for Veeva records. Please check root cause and CAPA columns for additional information | The site has added a late entry into the subject's source and provided the patient with a signed copy. The CRA has completed a visit and confirmed the above has been completed. See action item #19BJCS9C. | The site has added a late entry regarding the signature. The monitor has reviewed the entry. Responsible Role: Site, CRATarget Completion Date: 14Nov25Action Owner: Georgina Perez-Lewis | Georgina Perez-Lewis |  | - | Georgina Perez-Lewis | Closed | Closed | Site Management and Monitoring | Failure to detect/document | INV04 - Investigational Site Management and Monitoring | PFIZER | MODEL 1 - INSOURCED | Internal Medicine | Perez-Lewis, Georgina | GSSO | 84 | AMERICAS