## Standard_Quality_Dashboard - QE
Observation ID | Study ID | Targeted | PR ID | Site(s) | principal Investigator | EX Comp? | QE Threshold | Status | Observation Description (as submitted) | Awareness Date | Submission Date | Assessment Date | Title/Short Description | Business CAPA Plan Endorsed On | CAPA Plan in Place | Last Action Due Date | Investigation Summary and Conclusion | Effectiveness Check Required | Effectiveness Check Rationale | Investigation Completion Date | Closed On | PDAL Decision | Level 1 | Level 2 | Quality CAPA Plan Endorsed On | Quality Reviewer Approved On | Business Process | Submitter | Confirmed Serious Breach | Remediation Actions Taken (when QE was submitted) | CAPA Action Details | CAPA Action Owner | Root Cause Description | Root Cause Level 1 | Root Cause Level 2 | Root Cause Level 3 | Rapid Model | Business Category
QE-142334 | C5091017 | N | QE-142334 | 1059 | Duane Anderson (C5241007-1059) | N | Minor | Closed | During a Pre-Trial Assessment visit conducted at the site for study C5091017 for site 1004; it was discovered that the site and potential PI had a recent FDA inspection which resulted into an FDA 483. The FDA 483 findings were in relations to a non-Pfizer trial. Upon the request of the findings from the site; the findings are as follow: Twelve occurrences, subjects who did not meet inclusion criteria -Body Mass Index from equal to or more than 18 up to equal to or less than 35, were randomized, and administered the investigational product. Subject diagnosed with Chronic Obstructive Pulmonary Disease during screening. Subject was enrolled and stratified into LRTD Risk Absent (Neither CHF nor COPD are at risk); and not to the protocol required LRTD Risk Present (Neither CHF nor COPD are at risk) cohort. Subsequently, subject was administered the investigational product. Expired clinical supplies in storage were not label/quarantined as required by the site's Laboratory Kit Inventory and Destruction Process instruction sheet, which states that the laboratory kits that have reached their expiration date will be marked with "Expired" by the Laboratory Technician and moved to a quarantine zone. More than 50 boxes with expiration date 30 Apr 2024.Additional supplies used for conducting clinical studies onsite: BD Vacutainer Blood Collection Set; two boxes expiration date 31 March 2024.On the "Investigator" tab, another study/site number was selected due to the C5091017-1004 was not an option to select. | 2024-10-04 | 2024-10-07 | 2024-10-08 14:13 | GCP_Minor_Oct-2024_C5091017: Investigator Availability Status_Anderson, Duane_USA_DOWNGRADE |  | NO |  | <p>N/A</p> | No | Minor/Unrated Quality Event | 2024-10-17 | 2024-10-17 |  | Training & Qualifications | Personnel inadequately trained to perform their assigned job function |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Adalberto Barba | FALSE | The site will not be recommended for trial selection for study C5091017 within the PTA report. |  |  | N/A | Personnel | Lack of or Inadequate Qualifications |  | MODEL 1 - INSOURCED | Internal Medicine
QE-156018 | C5091017 | (Empty) | QE-156018 |  | PFIZER | N | Minor | Closed | The Required Safety Text and Brief Required Safety Text document was approved without the QC step. | 2024-12-10 | 2024-12-18 | 2024-12-18 16:25 | GCP_Minor_Dec-2024_C5091017: CMCD: Informed Consent Document: Required Safety Text (RST/BRST)_Pfizer_Global |  | NO |  |  | No |  |  | 2024-12-18 |  | Quality Procedures | Requirement/process not met |  |  | CT05-Informed Consent Document | Simone Antonucci |  | QC on V2 RST BRST initiated on Dec 16th. A new version of the RST BRST has also being developed (V3) that will replace V2. V3 is currently being QC'd. Manager was also informed. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-159955 | C5091017 | (Empty) | QE-159955 |  | PFIZER | N | Minor | Closed | On study C5091017, site 1009 was activated with quarantined IP. | 2025-01-15 | 2025-01-15 | 2025-01-15 21:13 | GCP_Minor_Jan-2025_C5091017: Site Activation_Pfizer_USA |  | NO |  |  | No |  |  | 2025-01-15 |  | Quality Procedures | Requirement/process not met |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Jeffrey Barbour |  | GSM notified appropriate parties of enrollment hold needed at site until new IP is received. cSOM notified SCP of the need to hold enrollment at site. SCP confirmed site has been notified. New IP shipment created for site. |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-159957 | C5091017 | N | QE-159957 | 1009 | Chrisette Dharma (C5091017-1009) | N | Minor | Closed | For the C5091017 study, site 1009 did not follow guidance to submit temperature excursion notification to Clinical Supply Temperature Excursion report mailbox. | 2025-01-15 | 2025-01-15 | 2025-01-15 21:26 | GCP_Minor_Jan-2025_C5091017: IP Temperature Excursion_Dharma, Chrisette_USA |  | NO |  |  | No |  |  | 2025-01-15 |  | Medicinal Product | Inadequate handling, storage, availability |  |  | IP13-Investigational Medicinal Product | Jeffrey Barbour |  | SCP to retrain site on temperature excursion requirements/reporting. Enrollment pause initiated. New IP shipment created. |  |  | NA | Equipment/System/Facility | Equipment |  | MODEL 1 - INSOURCED | Internal Medicine
QE-161275 | C5091017 | (Empty) | QE-161275 |  | PFIZER | N | Minor | Closed | On study C5091017, site 1077 was activated without all necessary lab supplies on site. | 2025-01-20 | 2025-01-23 | 2025-05-08 14:50 | GCP_Minor_Jan-2025_C5091017: Site Activation_Pfizer_USA |  | NO |  |  | No |  |  | 2025-01-23 |  | Quality Procedures | Requirement/process not met |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Jeffrey Barbour |  | GSM notified cSOM that site was activated without all necessary lab supplies when vendor confirmed not all supplies were on site. cSOM notified SCP of enrollment hold needed at site until all supplies received. SCP confirmed site notification. Remaining lab supplies have been shipped to site. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-162576 | C5091017 | N | QE-162576 | 1006 | Eddy Capote Jr (C5091017-1006) | N | Minor | Closed | The participant ePRO provision device was locked so the participant could not enter the data. The participant contacted the Helpdesk but left the wrong phone # so the code was not received. The site submitted a DCF in the ePRO portal with the correct participant phone number. | 2025-01-30 | 2025-01-30 | 2025-01-31 15:14 | GCP_Minor_Jan-2025_C5091017: Communication Method: ePRO_Capote Jr., Eddy_USA |  | NO |  |  | No |  |  | 2025-01-31 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Eun Lee |  | A DCF was requested to be denied by the site to the site. |  |  | NA | Human Performance | Decision Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-164391 | C5091017 | (Empty) | QE-164391 |  | INNOVATIVE TRIALS LTD | N | Minor | Closed | On 06-Jan-25 the Content Delivery Hub Patient Recruitment Specialist (CDH PRS) received Central IRB approval for US English patient recruitment materials that was shared with Innovative Trials (translations, printing, and shipping vendor). On the same day the CDH PRS requested Innovative Trials to print and ship the materials to some specific sites and provided contact and Site SIV reports to use in that regard.On 20-Jan-25 Innovative Trials printed and shipped materials to all US sites.On 28-Jan-25 site 1157 (not included in CDH request) received the recruitment materials, despite not having local IRB approval yet. This was the only local site of the study.On 03-Feb-25 Innovative Trials provided a shipment report confirming that all US sites, including Site 1157, had received the patient recruitment materials.On 05-Feb-25 the CDH PRS reviewed the shipment report and realized that Site 1157 received the materials on 28-Jan-25. On the same day, the CDH PRS notified Innovative Trials of the issue and urgently contacted the Site Activation Partner (SAP) and Site Care Partner (SCP), requesting them to remind the site to refrain from using the materials until local IRB approval was obtained.06-Feb-25 the SCP confirmed that the site had been contacted and reminded of the requirement to wait for local IRB approval before using the materials for patient enrollment. | 2025-02-03 | 2025-02-12 | 2025-02-13 16:30 | GCP_Minor_Feb-2025_C5091017: Vendor Responsibilities: Recruitment Materials_Innovative Trials_USA |  | NO |  |  | No |  |  | 2025-02-13 |  | Quality Procedures | Requirement/process not met |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Valentina DalChiele |  | the CDH PRS notified Innovative Trials of the issue and urgently contacted the Site Activation Partner (SAP) and Site Care Partner (SCP), requesting them to remind the site to refrain from using the materials until local IRB approval was obtained. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-167146 | C5091017 | (Empty) | QE-167146 |  | PFIZER | N | Minor | Closed | 12 US sites were activated with one missing items in site activation checklist which is activated VCT scanner to scan a fingerprint to check multiple study enroller. However fingerprint scanning can be opted out and VCT verification can be done with personal information. Three subjects were screened at 2 sites and the VCT verification process was completed with personal information instead of fingerprint. | 2025-02-21 | 2025-02-26 | 2025-02-26 19:27 | GCP_Minor_Feb-2025_C5091017: Site Activation (VCT Scanner)_Pfizer_USA |  | NO |  |  | No |  |  | 2025-02-26 |  | Quality Procedures | Requirement/process not met |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Eun Lee |  | It was escalated to DCSO/SSU PM for their awareness and DCSO started to collect the root causes. It was discussed with asset DSM and CSTL as well. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-168973 | C5091017 | N | QE-168973 | 1008 | Lilia Roque Guerrero (C5091017-1008) | N | Minor | Closed | Study C5091017- site 1008. For the participants at site 1008, there are no medical records available to confirm eligibility of the participants. For subjects 1001, 1007 and 1008- one of the inclusion criteria that the participants met was based on their use of prednisone before entering the trial. However, when questioned if medical records/proof of prescription could be provided, the site couldn't obtain any medical records or prescription information. For participant 1001- the participant had discontinued from the study before the records could be requested. For participants 1007 and 1008- per the site, the records have been requested, but the site is unable to obtain any records. Also when the Site Care Partner/ Site Monitor looked at the source for smoking status (which can be part of inclusion criteria) for two participants, it looked like source had been changed from non-smoker to smoker. For two other participants, the source provided by the physician stated "smoker" and the CRC source stated "non-smoker". For the calculation of the BMI- the height recorded in the source did not match the drivers license for the three of the participants. | 2025-03-07 | 2025-03-07 | 2025-03-10 14:38 | GCP_Minor_Mar-2025_C5091017: Source Documentation_Roque Guerrero, Lilia_USA |  | NO |  |  | No |  |  | 2025-03-10 |  | Data Collection and Management | Inadequate source data/documentation |  |  | No Process Assigned | Brooke Hanscom |  | There was an initial meeting about this with the study team and site operations, and deadline has been reached of 07Mar for the records to be provided, which they havent been. 1. Decision Date: 21-Feb-252. Decision: The following actions will be taken in response to study team concerns on enrollment of patients with moderate immunocompromise at site 10081. SCP will request the prescription of prednisone, or any proof that the medication was taken by subject(s) for all subjects enrolled prior to 21FEB2025, with a deadline of 07MAR2025.2. If deadline for source document is missed, or documentation does not support eligibility, a call between Clinician and PI will be scheduled. The SCP will be invited to this call, if necessary. 3. QE will not be raised unless more observations (evidence) are collected that suggest the site does not or cannot collect adequate documentation of subject eligibility4. This issue doesn’t increase SDV/SDR rate or change monitoring activity type5. The Study Team is permitting the site to continue to continue to enroll, and will consider whether to request the same documentation for future patients6. The SCP will document this issue in the Siebel Issues &amp; Actions Log3. Decision makers: Simone Antonucci, Halley Rogers, Christopher Pitcherella, Sarah Combs Bevivino, Eun Lee, Georgina Perez-Lewis4. Team Members Notified Date: 21-Feb-255. Team Members Methods of Notification: meeting held on 21-Feb-256. Supporting document: attached7. Rationale: meeting was held with following attendance and agreed with the decisions and actions based on the observation from SCP on-site visit on 20-Feb-251. Simone Antonucci, Halley Rogers, Georgina Perez-Lewis, Brooke Katherine Hanscom, Christopher Pitcherella, Jose Alberto Fernandex, Alyssa Dantonio, Sarah Combs Bevivino |  |  | NA | Personnel | Inadequate Information for Determination |  | MODEL 1 - INSOURCED | Internal Medicine
QE-169651 | C5091017 | N | QE-169651 | 1008 | Lilia Roque Guerrero (C5091017-1008) | N | Minor | Closed | Site sent over PPI via email. | 2025-03-11 | 2025-03-12 | 2025-03-12 20:33 | GCP_Minor_Mar-2025_C5091017: Participant Confidentiality_Roque Guerrero, Lilia _USA |  | NO |  |  | No |  |  | 2025-03-12 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Georgina Perez-Lewis |  | The email was not opened. The site was re-trained and requested to upload subject information into Florence. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-172367 | C5091017 | N | QE-172367 | 1079 | Harvey Bowles (C5091017-1079) | N | Minor | Closed | Site 1079 did not report and submit the 31Jan2025 temperature excursion notification to Clinical Supply Temperature Excursion Support team mailbox for review. | 2025-03-26 | 2025-03-28 | 2025-03-28 19:04 | GCP_Minor_Mar-2025_C5091017: IP Temperature Excursion_Bowles, Harvey_USA |  | NO |  |  | No |  |  | 2025-03-28 |  | Medicinal Product | Inadequate handling, storage, availability |  |  | IP13-Investigational Medicinal Product | Carli Davis |  | -SCP provided the site staff with temperature excursion reporting form ( IP-GSOP-RF07) and requested site to report immediately to Pfizer temp excursion support team. -SCP instructed site staff to quarantine the impacted drug.-Site reported the temperature excursion to Pfizer on 27Mar2025.-SCP retrained PI, Sub-I and CRC on reporting temperature excursions criteria.-SCP documented the temperature excursion in the site management report. |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-173357 | C5091017 | (Empty) | QE-173357 |  | PFIZER | N | Minor | Closed | C5091017 Site # 1020 PI:- Dr. Juan ZapatasEvent:- The ISF was not transferred to the sites eISF - Realtime prior to activation. It should be noted that there are no subject screening and or enrollment since activation. | 2025-04-01 | 2025-04-03 | 2025-04-04 16:08 | GCP_Minor_Apr-2025_C5091017: Site Activation_Pfizer_USA |  | NO |  |  | No |  |  | 2025-04-04 |  | Quality Procedures | Requirement/process not met |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Dayon Fletcher |  | The SCP reached out to the SAP to create task with the CTA in My Trial Assistant for the ISF to be transferred to the site. On 03Apr2025 the ISF was sent to the SCP by the CTA. The SCP forwarded the eISF to the site. |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-174487 | C5091017 | N | QE-174487 | 1009 | Chrisette Dharma (C5091017-1009) | N | Minor | Closed | Study coordinator completed a patient visit with being fully train for some systems in the study. | 2025-04-09 | 2025-04-10 | 2025-04-11 15:39 | GCP_Minor_Apr-2025_C5091017: Study Training_Dharma, Chrisette_USA |  | NO |  |  | No |  |  | 2025-04-11 |  | Training & Qualifications | Training not completed or documented in a timely manner |  |  | CT33-Study Training | Arturo Alfaro |  | Notify site to have study coordinator to complete trainings. |  |  | NA | Personnel | Inadequate Information for Determination |  | MODEL 1 - INSOURCED | Internal Medicine
QE-176388 | C5091017 | N | QE-176388 | 1077 | John Beckes (C5091017-1077) | N | Minor | Closed | Data entry for site # 1077, protocol C5091017, patient 10771001 was delayed by 10 days. | 2025-04-21 | 2025-04-23 | 2025-04-23 22:58 | GCP_Minor_Apr-2025_C5091017: Data Entry Timeliness (DET)_Beckes, John_USA |  | NO |  |  | No |  |  | 2025-04-23 |  | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry |  |  | INV04-Investigational Site Management and Monitoring | Arturo Alfaro |  | SCP provided phone number for helpdesk to assist in addressing the issue. |  |  | NA | Equipment/System/Facility | System/Application |  | MODEL 1 - INSOURCED | Internal Medicine
QE-176495 | C5091017 | N | QE-176495 | 1102 | Luis Hernandez Rosado (C5091017-1102) | N | Minor | Closed | Study C5091017 Site 1102 missed their deadline for data entry on a screen failure by 3 weeks. | 2025-04-22 | 2025-04-24 | 2025-04-24 15:33 | GCP_Minor_Apr-2025_C5091017: Data Entry_Hernandez Rosado, Luis_USA |  | NO |  |  | No |  |  | 2025-04-24 |  | Data Collection and Management | Inadequate source data/documentation |  |  | INV04-Investigational Site Management and Monitoring | Kelley Fennell |  | SCP re-educated the site of the importance of timely data during a site management visit, and the responsible study coordinator assured me they would enter in the data. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-176570 | C5091017 | (Empty) | QE-176570 |  | PFIZER | N | Minor | Closed | C5091017 Site 1057 was activated in error. On 14Apr25, the SCP confirmed the site was ready to activate and provided the SAC to the SAP (who was acting as a backup for the original SAP). The SAP proceeded to send the SAL to the site. After the letter was sent, the SAP was made aware that the site's ongoing ICD updates which made the site ineligible for activation. The SAP attempted to recall the email however, the site still received and acknowledged activation. The SCP asked the site to hold enrollment until the ICD update was completed and the site agreed. Further, during a start up call on 15Apr25, the SUPMs noted that though the site had been activated, SART activation readiness was below expectations at 51%. This was confirmed during my review on 16Apr25. After continued discussion, it was determined on 23Apr25 that this should be documented as a quality event. | 2025-04-23 | 2025-04-24 | 2025-04-25 18:48 | GCP_Minor_Apr-2025_C5091017: CMCD: Site Activation_Pfizer_USA |  | NO |  |  | No |  |  | 2025-04-25 |  | Quality Procedures | Requirement/process not met |  |  | INV02-Investigational Site Selection, Preparation, and Initiation | Regan Hitt |  | Upon learning that the site was activated with an ICD version that had a GRAF completed as not approved by Pfizer, the SCP was request to contact the site to inform them of the issue and to hold enrollment. The site agreed. The ICD issue was escalated to Advarra with a request to expedite review for site activation. Advarra agreed and the ICD has since been approved and provided to the site. Upon reviewing SART against my personal study trackers, I confirmed that question in MyTrial Go were not completed correctly, despite available reports confirming otherwise. I reviewed this with the SCP on 16Apr25 to which the SCP noted that they completed the SAC in error but was unable to update the questions in MyTrial Go. The SCP attempted to complete the form manually but did not complete every quesiton. I requested they submit a support ticket to have this unlocked/opened to allow for these updates. However, during this review I also noted that the site had not activated their VCT Scanner. This is a requirement for site activation and SCPs have been reminded of their responsibility to ensure this is verified in report provided by VCT (as opposed to using site confirmation). The SCP acknowledged that he confirmed scanner activation with the site during the SIV but did not verify that against the report prior to sending the SAC. The SCP has since worked with the site to activate the scanner and activation has been confirmed by VCT. The site will be provided an updated SAC and SAL once available. |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-176721 | C5091017 | N | QE-176721 | 1144 | Justin Mansfield (C5091017-1144) | N | Minor | Closed | Missing baseline diaries data of subject 11441003. There is no affirmed Day 1 dosing and Questionnaires information from dose that was taken on site, althought the patient and the site were doing everything correctly | 2025-04-24 | 2025-04-25 | 2025-04-29 16:04 | GCP_Minor_Apr-2025_C5091017: eDiary Management_Mansfield, Justin; Signant Health_USA |  | NO |  |  | No |  |  | 2025-04-29 |  | Data Collection and Management | Inadequate source data/documentation |  |  | DMB08-Study Data Set Review Release and Archive | Anja Timmermann |  | Site was contacted to contact the patient and access what happened. The site confirmed they did set everything up on the day patient was enrolled (23Apr2025) and the Site helped the subject to get it going and watched them complete the questionnaires. The site even helped the subject to do the dosing diary part of it. When the subject got home the diary said it had been deactivated. Subject used a new code and got it started back up morning 24April2025. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-176721 | C5091017 | (Empty) | QE-176721 |  | SIGNANT HEALTH GLOBAL SOLUTIONS LIMITED | N | Minor | Closed | Missing baseline diaries data of subject 11441003. There is no affirmed Day 1 dosing and Questionnaires information from dose that was taken on site, althought the patient and the site were doing everything correctly | 2025-04-24 | 2025-04-25 | 2025-04-29 16:04 | GCP_Minor_Apr-2025_C5091017: eDiary Management_Mansfield, Justin; Signant Health_USA |  | NO |  |  | No |  |  | 2025-04-29 |  | Data Collection and Management | Inadequate source data/documentation |  |  | DMB08-Study Data Set Review Release and Archive | Anja Timmermann |  | Site was contacted to contact the patient and access what happened. The site confirmed they did set everything up on the day patient was enrolled (23Apr2025) and the Site helped the subject to get it going and watched them complete the questionnaires. The site even helped the subject to do the dosing diary part of it. When the subject got home the diary said it had been deactivated. Subject used a new code and got it started back up morning 24April2025. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-179237 | C5091017 | N | QE-179237 | 1077 | John Beckes (C5091017-1077) | N | Minor | Closed | S.C. was trained on the protocol by P.I. However, site lacks specific SOP to allow for this practce. | 2025-05-09 | 2025-05-12 | 2025-05-12 22:53 | GCP_Minor_May-2025_C5091017: Study Training_Beckes, John_USA |  | NO |  |  | No |  |  | 2025-05-12 |  | Training & Qualifications | Inadequate training material |  |  | CT33-Study Training | Arturo Alfaro |  | C.R.A. instructed S.C, to complete training in Firecrest immediately. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-180529 | C5091017 | N | QE-180529 | 1279 | Sachin Chatta (C5091017-1279) | N | Minor | Closed | C5091017 Site 1279 Dr. Chatta: On 17May2025, a concern was raised by the current coordinator at Site 1279 regarding Firecrest training certificates.The primary coordinator reported that Firecrest training certificates were issued under her name without her knowledge or participation. Also, she explained that she did not have access to the associated email address. Her claim suggests that the trainings were completed by someone else using her email address. The coordinator's claim suggests that the site generated email addresses may have functioned as generic or shared addresses, and trainings were completed under different site members.The training records should reflect trainings completed by the designated staff member and this issue raises concerns regarding documentation integrity, GCP compliance and staff qualification. | 2025-05-19 | 2025-05-19 | 2025-05-20 14:18 | GCP_Minor_May-2025_C5091017: System Access; Firecrest Training_Chatta, Sachin_USA |  | NO |  |  | No |  |  | 2025-05-20 |  | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) |  |  | CP403 | Mako Watanabe |  | Coordinator's claim was shared to SCP, DCSOs and cSOMs on the same day of awareness. Upon discussions with cSOM and DCSO, SCP decided to document this event as a QE. SCP will respond to the coordinator to confirm more detail. |  |  | NA | Personnel | Inadequate Information for Determination |  | MODEL 1 - INSOURCED | Internal Medicine
QE-180683 | C5091017 | N | QE-180683 | 1008 | Lilia Roque Guerrero (C5091017-1008) | N | Minor | Closed | Site uploaded patient emergency contact information into Florence RSA. | 2025-05-09 | 2025-05-20 | 2025-05-20 19:14 | GCP_Minor_May-2025_C5091017: Participant Confidentiality_Roque Guerrero, Lilia_USA |  | NO |  |  | No |  |  | 2025-05-20 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Georgina Perez-Lewis |  | Site requested to remove patient data from Florence RSA. 16May25 Site re-educated. 20May25 Discussed with PI and site director and re-educated. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-181132 | C5091017 | (Empty) | QE-181132 |  | PPD, INC. | N | Minor | Closed | Thermo Fisher/PPD Central Lab Services identified a quality issue that affects toxicity grade reporting (patient safety reporting) for 4 Pfizer studies: C2321014, C2321003, C5091017, C4221016. PPD has opened a quality event to document the investigation of this issue. To determine the impact of the issue, PPD re-evaluated all toxicity grades for active studies with toxicity criteria in place and categorized the impact as follows:1. Missing Toxicity Grades: An intermittent failure of the toxicity grade processor resulted in toxicity grades not being applied and therefore, were not reported on the daily site report (DSR).2. Toxicity Grades Which No Longer Apply: The system applied toxicity grades to results generated from out of stability samples resulting in toxicity grades that should not have been applied. Likewise, when baseline results were reported as out of stability and baseline comparison rules were applied to subsequent visits, the baseline comparison rule used out of stability baseline values for comparison resulting in toxicity grades that should not have been applied.3. Toxicity Grades Correctly Assigned in the Database, But Not Reported On a DSR: Toxicity grades were reported correctly on the initial DSR; however, when data amendments such as demographic changes or visit updates were made, new DSRs were not issued resulting in amended toxicity grades being present in the database but not reported on the DSR. On 08May2025 an IT change control was implemented as an emergency update to stop the intermittent failure of the toxicity grade processor. The next step is to implement an additional update to introduce a trigger ensuring any change in toxicity values prompts the test to be re-reported on a DSR. The update will also include a sweep to re-evaluate across all patient visits when there is recently changed data and re-issuance of a DSR as applicable.Patient safety impacts will need to be assessed by the study teams. | 2025-05-22 | 2025-05-22 | 2025-05-22 18:40 | GCP_Minor_May-2025_Multiple: Biospecimen Reporting (Toxicity Grade Processor)_PPD Inc_Global |  | NO |  |  | No |  |  | 2025-05-22 |  | Equipment, Facility and Sample/Specimens | Inadequate or incorrect test performance/analysis |  |  | CT29-Management of Clinical Study BioSpecimens | Karen Barrett |  | PPD re-evaluated all toxicity grades for active studies with toxicity criteria in place and categorized them as either missing, no longer apply, correctly assigned but not reported on the daily site report (DSR). PPD implemented an IT change control as an emergency update to stop the intermittent failure of the toxicity grade processor. |  |  | NA | Human Performance | Inconsistency Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-181149 | C5091017 | N | QE-181149 | 1010, 1027, 1031, 1040, 1054 | Lawrence Galitz (C4601012-1027), Lawrence Galitz (C5091017-1031), Lawrence Galitz (C5281001-1010), Wanda Boote (B7981080-1054), Wanda Boote (C4531002-1040) | N | Major | Approved - In CAPA | Fraudulent bank details received from 3rd party impersonating the CFO from site GCP Global Clinical Professionals, LLC. The email was not sent by the CFO and the account provided does not belong to the site . Banking details were updated and payments issued but these payments failed to reach the destination bank account as the account holder name and account details did not match. The fraudulent details were received for studies B7981090, C4601012, C4531002, C5281001 and C5091017 | 2025-05-20 | 2025-05-23 | 2025-05-23 17:55 | GCP_Major_May-2025_Multiple Studies: Potential Cyber/Hacking: Bank Details_Boote, Wanda; Galitz, Lawrence_USA |  | YES |  | <p>Product Protocol Numbers:&nbsp;</p><p>B7981080</p><p>C4531002</p><p>C4601012</p><p>C5091017</p><p>C5281001 (KAN-101-02)</p><p><br></p><p>Involved Party / Site Number (if applicable) / Country:</p><p>Principal Investigator (PI): Boote, Wanda / B7981080 Site 1054 / United States</p><p>PI: Boote, Wanda / C4531002 Site 1040 / United States</p><p>PI: Galitz, Lawrence / C4601012 Site 1027 / United States</p><p>PI: Galitz, Lawrence / C5091017 Site 1031 / United States</p><p>PI: Galitz, Lawrence / C5281001 Site 1010 / United States</p><p><br></p><p>Protocol Title(s):</p><p>B7981080 - A PHASE 3 RANDOMIZED, DOUBLE-BLIND, 52-WEEK PLACEBO-CONTROLLED MULTI-CENTER STUDY WITH A DOUBLE-BLIND 52-WEEK EXTENSION PERIOD WITH RANDOMIZED DOSE UP/DOSE DOWN TITRATION INVESTIGATING THE EFFICACY, SAFETY, AND TOLERABILITY OF RITLECITINIB IN ADULT PARTICIPANTS WITH NONSEGMENTAL VITILIGO</p><p><br></p><p>C4531002 - A PHASE 2, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED STUDY TO INVESTIGATE THE EFFICACY AND SAFETY OF PF-07275315 AND PF-07264660 IN ADULT PARTICIPANTS WITH MODERATE-SEVERE ATOPIC DERMATITIS</p><p><br></p><p>C4601012 - A PHASE 3, RANDOMIZED, PLACEBO-CONTROLLED, OBSERVER-BLINDED TRIAL TO EVALUATE THE SAFETY OF A 6-VALENT OspA-BASED LYME DISEASE VACCINE (VLA15) IN HEALTHY CHILDREN 5 THROUGH 17 YEARS OF AGE</p><p><br></p><p>C5091017 - AN INTERVENTIONAL EFFICACY AND SAFETY, PHASE 3, DOUBLE-BLIND, 2-ARM STUDY TO INVESTIGATE ORALLY ADMINISTERED IBUZATRELVIR COMPARED WITH PLACEBO IN NON-HOSPITALIZED SYMPTOMATIC ADULT AND ADOLESCENT PARTICIPANTS WITH COVID-19 WHO ARE AT HIGH RISK OF PROGRESSING TO SEVERE ILLNESS</p><p><br></p><p>C5281001 - A PHASE 1B OPEN-LABEL/ PHASE 2 DOUBLE-BLIND PLACEBO-CONTROLLED STUDY FOR PHARMACODYNAMIC ACTIVITY, PHARMACOKINETICS, SAFETY AND TOLERABILITY OF KAN-101 IN PATIENTS WITH CELIAC DISEASE</p><p><br></p><p>Description of Issue(s):</p><p>On 01 Apr 2025, the Pfizer Payments Team received a request to change banking information from a third party impersonating the Chief Financial Officer (CFO) of clinical site GCP Global Clinical Professionals, LLC, a site in the United States participating in the B7981090, C4531002, C4601012, C5281001 and C5091017 studies. On 03 Apr 2025, the Pfizer Payments Team updated the site’s banking details for the B7981090, C4531002, C4601012, and C5091017 studies using Payee Activation Forms (PAFs) for each study received from the impersonator which contained an electronic signature of the site’s Clinical Study Agreement signatory. In May 2025, Greenphire (the vendor contracted by Pfizer to make site payments) attempted to send six payments to the fraudulent account (three for B7981090 and one each for C4531002 and C4601012) totaling approximately $30,000. Wells Fargo, the bank processing the payments, did not complete the transactions as the account holder’s name and other details did not match those of the intended payee, GCP Global Clinical Professionals, LLC. On 19 May 2025, the Pfizer Payments Team received an e-mail from the site’s real CFO stating notices received from Greenphire showed payments being issued to an account that did not belong to the site.</p><p><br></p> | Yes |  | 2025-07-24 |  |  | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) |  | 2025-07-25 23:41 | CP411 | Corina McDermott | FALSE | Disabled banking on all studies for which the bank details had been updatedContacted the owner/CEO of the site to inform him of the issue Contacted Site Care Partner who visits the site to assist with verification of the identities of the Owner/CEO and CFO as the original instructions had appeared to have been issued by them |  |  | Gap analysis, The Pfizer process for sites to change site banking details lacked sufficient controls to verify the authenticity of requested changes.&nbsp; | Gap Analysis, Method/Procedure | N/A, Procedure/Form/Plan | Inadequate/Inaccurate/Confusing (Document Standard Lacking/Incorrect Standard Content), N/A | MODEL 1 - INSOURCED | Internal Medicine
QE-186405 | C5091017 | (Empty) | QE-186405 |  | PPD, INC. | N | Minor | Closed | On 19Jun2025 PPD labs notified Pfizer that they identified a critical quality event affecting custom report generation impacting Pfizer studies. There was a system disruption that occurred on 01Apr2025 and again from 25-29Apr2025. The disruption may have resulted in missing data from the associated reports (which could include safety data). Study teams can request a listing of the custom reports impacted by the event and can request these reports are regenerated. Summary for 01-02Apr outage:SOP-17330 Account Management version 3.0 updated the password requirements for service accounts used by applications and instrumentation. When the service password was reset for Preclarus Central Lab Database, the technician did not update the password on the mount used for the custom report engine causing the custom report engine to fail to write the SQL queries to the repository. WHY: because the tech didn’t know that the same password was used for the mount.The system didn’t fail immediately because the process was actively processing and writing files. When the queue had cleared and restarted, the system tried to re-authenticate and failed due to the incorrect password. After 3 attempts, the process was locked out causing the custom report engine to fail to generate custom reports between 01APR2025 at 1pm through 9am on 02APR2025.At 9am EDT the service password was updated on the mount and the custom reporting engine process was restored at 9am EDT. All custom reporting queues missed during the outage window were retriggered for evaluation.Accumulative reports were not impacted. Incremental reports were impacted since the retriggered report would have only reported updates from a defined window (last 24 hours).DM custom reports only report data that was updated within the defined previous window by looking at the mod date for the data type. This window is unique per custom report but typically 24-48 hrs.38in; text-align: left;"Summary for 25Apr-29Apr outage:The security team/ infrastructure team disabled a file sharing protocol (smb1 protocol software) causing the custom report process to fail to be able to communicate to the custom reporting mount.Outage window 25 APR 6pm à 29 APR 12:00pmThe smb1 protocol software is outdated and was disabled due to security concerns. Unfortunately, the infrastructure team making the change did not know how this software was used and did not consult our team before disabling it. | 2025-06-19 | 2025-07-07 | 2025-07-07 21:44 | GCP_Minor_Jul-2025_Multiple Studies: Custom Report Generation_PPD Laboratories_Global |  | NO |  |  | No |  |  | 2025-07-07 |  | IT Systems | Inadequate IT system (eg. planning, definitions, design, development, testing, validation, support) per regulatory requirements |  |  | No Process Assigned | Karen Barrett |  | Migrate all external reports to Preclarus Lab Data Portal Years ago, after a different incremental reporting failure, we implemented a feature in Preclarus Lab Data Portal to properly handle incremental reports.Instead of looking just at modification dates, it tracks what was already reported and what is newIf there was an outage, the report would report all new data from the entire outage (naturally recovering after an outage).•Always has an accumulative file available for review.Current Mercurial reporting process is at the end of life and needs to be retired.DM has not migrated to using this feature due to concerns about the gaps in functionality.Only able to create single study reports.Reporting trigger window is not hourly and has less reporting time windows.Will need to update Preclarus to allow files to be posted additional repositories.PPD will be working with DM through the migration process.PPD will evaluate additional gaps and work to mitigate risk through the migration process.PPD will need to consider how to handle internal reports after this migration is complete.Need to evaluate if internal reports are still required |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-187124 | C5091017 | (Empty) | QE-187124 |  | SCOUT CLINICAL | N | Minor | Closed | On June 24, 2025, Corporate Counsel in Global Privacy received a letter from the Quality Manager at the vendor Scout, stating the following : “Scout inadvertently disclosed Pfizer Company Confidential Information regarding details for proposed rates for patient visit and travel expenses for protocol C5091017 – without inclusion of any Personally Identifiable Information (PII) – within an email chain that included the email address for an individual employed by another client. This occurred when one of our team members inadvertently added the email address of another client in a reply to an email thread containing the information. Upon discovery, Scout immediately requested and then confirmed that the individual permanently deleted the emails that were received in error.Under the Scout and Pfizer Master Services Agreement (MSA) we are required to immediately report any discovery of unauthorized use or disclosure on non-PII confidential information. Upon discovery, Scout Quality and Executive Leadership were immediately notified and ensured that appropriate immediate actions were taken”. | 2025-06-24 | 2025-06-26 | 2025-06-27 14:21 | GCP_Minor_Jun-2025_C5091017: Sponsor Confidentiality_Scout Clinical_Global |  | NO |  |  | No |  |  | 2025-06-27 |  | Data Privacy | Data privacy/confidentiality |  |  | CP411 | Andrea Venegas |  | Upon discovery, Scout immediately requested and then confirmed that the individual permanently deleted the emails that were received in error. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-195626 | C5091017 | (Empty) | QE-195626 |  | PFIZER | N | Minor | Closed | SAHPRA (South African regulator) require site monitor names and CV etc as part of the submission package. Once notified though these names have not been getting updated to SAHPRA when they should have been.Ongoing protocol numbers where changes will be notified are:B7841007B7841008C1091009 C5851005 C2321003C2321014C3441021 C3441052 C3671032 C3671059 C4221016 C4391002 C4531029 C4551002 C4671026 C5091017 | 2025-08-07 | 2025-08-13 | 2025-08-14 16:31 | GCP_Minor_Aug-2025_Multiple Protocols: SAPHRA Submission Packages_Pfizer_ZAF |  | NO |  |  | No |  |  | 2025-08-14 |  | Quality Procedures | Requirement/process not met |  |  | INV04-Investigational Site Management and Monitoring | Valerie Jarvis-Evans |  | Reconciliation completed on active studies and cSOMs ask to prepare for submission of correct names. |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-197638 | C5091017 | N | QE-197638 | 1279, 1280 | Nam Le (C5091017-1280), Sachin Chatta (C5091017-1279) | N | Minor | Closed | Protocol: C5091017 Sites involved: 1279 and sister site 1280Site 1279: PI: Sachin Chatta, Sub-I Galeh MargossianSite 1280: PI: Nam Le, 07AUG2025- Site Care partner went on site 7301 Medical Center Drive, Suite #405, West Hills, CA 91307, Clinical Research of California. Study team and prior SCP had decided it was best to conduct study management visit in person due to concerns that had been raised in QE- 180529. Additional concerns have been observed during the 07AUG2025 visit. Investigational Product (GCP 4.1.2) (GCP 4.6.3) (GCP 4.6.4) When I asked the study manager to please show me the drug, she walked me to the front of the office near the reception cabinet where she unlocked a bike lock (it was about 6 feet long.) the unlocking process was unusually long because she was untangling the bike lock that was around the cabinet handles. Once the cabinet was opened, she struggled to find the IP. Inside the cabinet there were only lab kits visible. I noticed there were expired lab kits. After a few minutes I let her know I would wait in the conference room, I understood that it is harder to find something while someone is watching you. After approximately 5-10 minutes she let me know she had located the IP and took me to a separate room in the back of the office. This cabinet was kept locked with a padlock. I was able to account for all 10 bottles of IP. There were no thermometers in the cabinets for ambient drug. I noticed two refrigerators with thermometers but neither the refrigerators nor the thermometers appeared to be on. I could not confirm if they were plugged in but there was no indication that they were on or functioning. When I asked her if there were thermometers, she seemed confused as to why there would be thermometers measuring the temperature for the ambient drug. I asked if she had temperature logs available and she said those were written manually and that it would be easier to send them to me via email. It was confusing that she was offering logs when there were no visible thermometers. It should be noted that it was 95 degrees Fahrenheit the day of the visit and that the A/C was not working in the office. I cannot confirm that IP has been kept within recommended ranges.Since the visit she has provided a screenshot of a continuous temperature log, but it does not include daily minimums or maximums as specified in IP manual. I will attach Log that was provided by site. Inadequate number of qualified staff to conduct trial properly and safely. (GCP 4.2.2) (GCP 4.2.3) (GCP. 4.2.4)Upon visiting the site there was no evidence of computers, binders or phones. Emi Lecky, Study Manager, let me know staff were working from home that day since there were no patients. However, I did not see desk space for PI or Sub-I. The study manager said PI had an office downstairs. When speaking to PI he said he did not have any office near the clinic in West Hills. PI could not tell us what days he is in office. I asked him if a coordinator would be hired to replace Coordinator that had left, and he said that is something Emi would take care of. I let him know of the AC being broken, he said he was not aware of that. When discussing original QE issues with emails and when discussing PI availability and participation the study manager seemed noticeably nervous. This led me to review PI and Sub-I's medical license and practicing clinics. PI clinics are 60-90 miles away from clinical trial site. In the county of Los Angeles, it means his commute would be 2-3 hours (depending on traffic) to reach clinical trial site. Sub-I clinic is 95 miles away from Clinical trial site. Sub-I's commute would be 3-3.5 hours to complete. They are the only two people on the delegation log that can complete the physical exams and draw blood. Currently they only have three people listed on their delegation log. There are not enough personnel to properly complete tasks required by the study protocol. Emi, the study manager pronounces her name “AY-mee” and was one of the first corrections she made upon meeting her. PI mispronounced her name on the call and refers to her as “em-ee” and not “AY-mee” Although a minor detail, it is indicative that they are not in constant communication with each other. Study team has had issues with Delivering supplies to site. Fed ex has indicated that sites are closed or non-operational. There are multiple emails with this communication that I will attach. There are pictures of the FedEx notices that are left on the front door of site by FedEx. It is concerning that notices are stacking up on different days that site claims to be open and seeing patients. There are many gaps and inconsistencies when communicating with Study Manager, Emy Lecky. | 2025-08-07 | 2025-08-25 | 2025-08-26 16:51 | GCP_Minor_Aug-2025_C5091017: PI Oversight; Investigational Product Management_Chatta, Sachin, Nam, Le_USA |  | NO |  |  | No |  |  | 2025-08-26 |  | Medicinal Product, Quality Oversight | Inadequate handling, storage, availability, Inadequate Principal Investigator quality oversight |  |  | IP13-Investigational Medicinal Product, No Process Assigned | Isabel Gallegos |  | Issues were communicated to cSOM 07Aug2025 GSM was notified 14AUG2025 enrollment hold was placed 15Aug2025 for site 1279. We have requested an onsite visit with sister site 1280 and it will be potentially scheduled 16Sep2025. |  |  | NA | Personnel | Lack of or Inadequate Oversight |  | MODEL 1 - INSOURCED | Internal Medicine
QE-199345 | C5091017 | (Empty) | QE-199345 |  | CONTINUUM CLINICAL | N | Minor | Closed | We have a patient facing advertising campaign with our vendor Continuum. Launch date 28Jul25. Continuum incorrectly used C5091018 IRB approved US ES images on the C5091017 Patient media campaign. As a result, we paused the campaign 22Aug25. | 2025-08-22 | 2025-09-03 | 2025-09-04 16:01 | GCP_Minor_Sep-2025_C5091017: Participant Facing Materials_Continuum Clinical_USA |  | NO |  |  | No |  |  | 2025-09-04 |  | Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan) |  |  | INV03-Study Participant Recruitment and Retention Planning | Darcy Lerner |  | Campaign was paused immediately. Very clear SP folders for Patient Facing C5091017 ads and C509 HCP facing ads. Vendor has been notified with all the correct IRB approved images for C5091017. |  |  | NA | Human Performance | Inconsistency Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-199839 | C5091017 | N | QE-199839 | 1182 | Christoph Wyen (C5091017-1182) | N | Minor | Closed | HelpDesk received a call from SC at site 1182 C5091017, who confirmed she/he was logged into Impala with the PI’s access to confirm the availability of the Site Break Blind function. | 2025-08-28 | 2025-09-06 | 2025-09-08 15:26 | GCP_Minor_Sep-2025_C5091017: System Access Controls_Wyen, Christoph_DEU |  | NO |  |  | No |  |  | 2025-09-08 |  | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) |  |  | CP403 | Aneta Schnabel-Drewnicz |  | Account sharing is not allowed in Impala and HelpDesk had locked the PI’s account for this reason. For the account to be reactivated, the account holder and a Clinical Study Team member will need to arrange a conference call with the Impala helpdesk. SCP discussed this matter with cSOM who was back from leave on 05-Sep-2025 and decided to create an QE and document as an issue. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-200879 | C5091017 | (Empty) | QE-200879 |  | PFIZER | N | Minor | Closed | In following up with a question about a Pfizer rapid antigen test (RAT) result for C5091017 during a site monitoring visit for site 1101, the CRA assigned to this site, Anthony Jones, scanned the Pfizer RAT tracking log, some photos of the Pfizer RAT test results in question, but one of the files in the pdf in the email was a site source document that also included PHI. I deleted the email from my outlook server and instructed the CRA to also delete from his email and to delete the pdf file which he confirmed he did. I also emailed DSMM Sara Bevivino and suggested CRA retraining of best practices. | 2025-09-11 | 2025-09-11 | 2025-09-11 21:21 | GCP_Minor_Sep-2025_C5091017: Participant Confidentiality_Pfizer_USA |  | NO |  |  | No |  |  | 2025-09-11 |  | Data Privacy | Data privacy/confidentiality |  |  | CP404 | Alyssa Dantonio |  | Emailed CRA to inform of QE, and we both deleted emails from our servers. CRA also deleted pdf file. cSOM emailed DSMM to suggest retraining. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-201115 | C5091017 | (Empty) | QE-201115 |  | PFIZER | N | Critical | Approved - In CAPA | Initial Clinical Trial Application (iCTA) applications to the Regulatory Authority (RA) in Mexico (COFEPRIS) were initially completed in paper since 2018 by local Regulatory Strategist (RS) and electronically via DIGIPRIS (RA submission electronic platform) starting 14-May-2024. In July 2024, Clinical Trial Regulatory Strategy Execution Regional Submission Managers assumed responsibility for this. When the paper process was in effect, RNEC was updated manually by the local Regulatory Strategist. When the electronic process (via Digipris) went live in May 2024, the process was that once RA (Regulatory Authority) approval for the initial Clinical Trial Application (iCTA) was received, information included in the iCTA application in DIGIPRIS was migrated to RNEC automatically. Note: RNEC is an electronic database established by RA (COFEPRIS), it centralizes all authorized clinical trial protocols involving human subjects in Mexico. Information in RNEC can be accessed by public. Only the information included in the iCTA application form can be accessed by public; documents are not published for public access. Information in RNEC includes general information (Title, Number of Submission, Participant Countries, Disease, Sponsor) and research information (Full title, IMP name and dose, IMP administration dose and route, Study Phase, Key Inclusion criteria, Key Exclusion criteria, Primary Endpoints, Secondary Endpoints, Primary Objective, Blinded details, Random details, Population description, gender, ageThe CTRSE (Clinical Trial Regulatory Strategy Execution) SME (Subject Matter Expert) for Mexico checked RNEC for Study C5091017 and identified dose related information in RNEC that was publicly available. This dose information was considered Commercial Confidential Information (CCI) by Pfizer (based on redacted clinician reviewed protocol). Additionally there were PI names, names and email IDs of Pfizer internal colleagues in RNEC - SME is confirming if this is aligned with data privacy law in Mexico and any Pfizer internal data privacy requirements or if there is violation of Personal Protected Data (PPD) requirements. There are two versions of RNEC, old RNEC and RNEC 2.0. Old RNEC has information that was manually entered by Pfizer (Country Regulatory Strategists) based on paper submissions to the RA. And RNEC 2.0 was released in May 2024 and it automatically picks up information entered electronically in DIGIPRIS. In both cases unredacted documents were used to complete the application form (paper or electronic). Other protocols have not yet been reviewed to check if there is CCI and/or PPD, this action is in progress. Once a study is approved, the data in RNEC cannot be edited. SME is exploring how the CCI For Study C5091017 can be removed from RNEC. Date of occurrence: it was confirmed on 05 Sep 2025 that CCI is published in RNEC for study C5091017, however it is possible that CCI/PPD is also published for other studies. Review is ongoing. There are a total of 117 protocols registered in RNEC (86 from old RNEC and 31 from RNEC 2.0). Countries impacted: Only Mexico has been confirmed however other countries e.g. Peru and Chile have similar country registries and a review will need to be implemented to confirm impact to any other country. | 2025-09-11 | 2025-09-12 | 2025-09-17 18:02 | REG_Sep2025_Study C5091017 Regulatory Submissions_RNEC CT Public Electronic Database Includes Commercial Confidential Information (CCI) and PI Names_Mexico |  | YES |  | <p><b>Description:</b></p><p>• &nbsp; &nbsp;Clinical Trial Application (CTA) applications to the Regulatory Authority (RA) in Mexico (COFEPRIS) have been completed in paper form since 2018 by local Regulatory Strategist (RS) and moved to electronic submissions via DIGIPRIS (RA submission electronic platform) on 14-May-2024. In July 2024, Clinical Trial Regulatory Strategy Execution Regional Submission Managers assumed responsibility for this submission task.&nbsp;</p><p>• &nbsp; &nbsp;National Registry of Clinical Trials (RNEC) is an electronic database established by RA (COFEPRIS), centralizing all authorized clinical trial protocols involving human subjects in Mexico. When the paper process was in effect, RNEC was updated manually by the local Regulatory Strategist based on Final Approved Protocol (FAP). When the electronic process (via DIGIPRIS) went live in May 2024, the process was that once RA &nbsp;approved the Clinical Trial Application (CTA), information included in DIGIPRIS in fields marked “public” was migrated to RNEC (version 2.0) automatically upon approval by COFEPRIS. Fields marked ‘restricted’ were only meant to be accessible to specific departments in COFEPRIS, however, although dose information was in a restricted field in DIGIPRIS, it was made available publicly in RNEC 2.0.&nbsp;</p><p>• &nbsp; &nbsp;Information in RNEC can be accessed by the public. &nbsp;Once a CTA was approved, the data in RNEC 2.0 can not be edited.&nbsp;</p><p>• &nbsp; &nbsp;Information in RNEC included general information (Title, Number of Submission, Participant Countries, Disease, Sponsor) and research information (Full title, IMP name and dose, IMP administration dose and route, Study Phase, Key Inclusion criteria, Key Exclusion criteria, Primary Endpoints, Secondary Endpoints, Primary Objective, Blinded details, Random details, Population description, gender, age and, for amendments, the summary of changes is required.</p><p>• &nbsp; &nbsp;Only summary information could be accessed by the public; complete documents were not made public.&nbsp;</p><p>• &nbsp; &nbsp;The CTRSE (Clinical Trial Regulatory Strategy Execution) SME (Subject Matter Expert) for Mexico checked RNEC for Study C5091017 and identified dose related information in RNEC that was publicly available. This dose information was considered Commercial Confidential Information (CCI) by Pfizer (based on redacted clinician reviewed protocol).&nbsp;</p><p>• &nbsp; &nbsp;There were a total of 117 protocols registered in RNEC (86 from old RNEC and 31 from RNEC 2.0). It was confirmed on 05-Sep-2025 that CCI was published in RNEC for study C5091017 (this prompted the reporting of the QE). It was later confirmed through the investigation that out of the 117 studies in the clinical trials public registry in Mexico (RNEC), Commercial Confidential Information (CCI) was published for the following 9 studies: C1071005, C4671026, B7981041, C4951002 (BHV3000-311), C5241007, C5091017, C0251013, B7921005, C3601002.&nbsp;</p><p>• &nbsp; &nbsp;Unredacted Final Approved Protocols (FAPs) i.e. FAPs that were not marked by Clinicians for CCI were used to complete RNEC (paper CTA process) or to complete information in fields marked public in DIGIPRIS (electronic process). &nbsp;</p><p>• &nbsp; &nbsp;This QE impacts Mexico, however other countries e.g. Peru and Chile have similar country registries, and a review will be implemented to confirm impact to any other country. Additionally, there were PI names, names and email IDs of Pfizer internal colleagues and Ethics Committe (EC) &nbsp;details in RNEC. SME confirmed with Global Corporate Counsel and local legal that this was aligned with data privacy law in Mexico and Pfizer internal data privacy requirements and there was no violation of Personal Protected Data (PPD) requirements.</p><p><br><b>Investigation Details</b></p><p><b>The following stakeholders were interviewed as part of the investigation:</b></p><p>• &nbsp; &nbsp;Head CTRSE (Clinical Trial Regulatory Strategic Execution) Americas and Global Programme Lead,</p><p>• &nbsp; &nbsp;CTA SMs ( Clinical Trial Application Submission Managers) for Mexico,</p><p>• &nbsp; &nbsp;CTA SM SME (Subject Matter Expert) for Mexico,</p><p>• &nbsp; &nbsp;Clinical Trial Transparency &amp; Disclosure Lead and team,</p><p>• &nbsp; &nbsp;CTRSE EUCTR (European Union Clinical Trial Register) Advocacy Lead &amp; Strategic Execution,</p><p>• &nbsp; &nbsp;CTRSE Training and Compliance Lead,</p><p>• &nbsp; &nbsp;I&amp;I (Immunology and Inflammation) and IM (Internal Medicine) Clinical Development,</p><p>• &nbsp; &nbsp;Study Clinicians&nbsp;</p><p>• &nbsp; &nbsp;Intellectual Patent (IP) Attorneys</p><p>• &nbsp; &nbsp;Global Corporate Counsel,</p><p>• &nbsp; &nbsp;Local Legal Manager (Mexico)</p><p><br></p><p><b>Documents reviewed as part of the investigation included:</b></p><p>• &nbsp; &nbsp;Old RNEC and RNEC 2.0,</p><p>• &nbsp; &nbsp;Final approved protocols and redacted final approved protocols for the studies published in Old RNEC and RNEC 2.0,</p><p>• &nbsp; &nbsp;CT28-GSOP (PUBLIC DISCLOSURE OF PFIZER SPONSORED STUDIES) v9.0 (Eff. &nbsp;02-Oct-2023),&nbsp;</p><p>• &nbsp; &nbsp;INV02-INV04-WI-GL02 (Managing Investigational Site Documents) v7.0 (Eff. 02-Dec-2024),</p><p>• &nbsp; &nbsp;INV02-INV04-WI-GL02-RF06 (Personal Data Privacy Consent Form – Non-US Sites Except EU, EEA, UK and Switzerland) v6.0 (Eff. 17-Apr-2023),</p><p>• &nbsp; &nbsp;REG03-GSOP (Clinical Trial Applications) v8.0 (Eff. 02-Jun-2025),</p><p>• &nbsp; &nbsp;REG03-GSOP-RF03d CLINICAL TRIAL APPLICATION RESPONSIBILITIES – INSOURCED SUBMISSION MODELv6.0 mentioned</p><p><br></p><p><b>Background Information:&nbsp;</b></p><p><b>CTA (Clinical Trial Application) process in Mexico</b></p><p>Historically, all Clinical Trial Applications (CTAs) to the Regulatory Authority (RA) in Mexico (COFEPRIS) were completed via a paper application process by the local Regulatory Strategist (RS). &nbsp;Starting on 14-May-2024, CTA applications began to be submitted electronically via DIGIPRIS (electronic RA submission platform). Electronic submissions were initially being performed by the Country Regulatory Strategist (CRS) but were transitioned to Clinical Trial Application Submission Managers (CTA SMs) for Mexico in July-2024. &nbsp;Note: the paper CTA process is still in effect for any CTAs initially submitted in that format, but starting 14-May-2024 all new CTAs were submitted via DIGIPRIS.</p><p><br></p><p><b>RNEC Public Registry in Mexico</b></p><p>In 2018, COFEPRIS launched RNEC, an electronic database which centralized all authorized clinical trial protocols involving human subjects in Mexico. All information in RNEC was accessible to the public. &nbsp;Information in RNEC consists of the following that was obtained from the Final Approved Protocol (FAP) or Protocol Amendment to be submitted as part of the iCTA.:</p><p>• &nbsp; &nbsp;General information (title, submission number, participant countries, disease, sponsor)</p><p>• &nbsp; &nbsp;Research information (full title, IMP (Investigational Medicinal Product)</p><p>• &nbsp; &nbsp;Name and dose,</p><p>• &nbsp; &nbsp;IMP administration dose and route,</p><p>• &nbsp; &nbsp;Study phase,</p><p>• &nbsp; &nbsp;Key inclusion and exclusion criteria,</p><p>• &nbsp; &nbsp;Primary and secondary endpoints,</p><p>• &nbsp; &nbsp;Primary objective,</p><p>• &nbsp; &nbsp;Blinded and randomisation details,</p><p>• &nbsp; &nbsp;Population description, gender and age.</p><p><br></p><p><b>Process for entering study information in RNEC:</b></p><p><b>Old RNEC (Pre 14-May-2024 – Paper CTA – Manual RNEC update).</b></p><p><br></p><p>Prior to the introduction of DIGIPRIS on 14-May-2024, RNEC was manually updated by the CRS. &nbsp;</p><p>When a CTA was approved by COFEPRIS, they issued a paper CTA approval letter and provided login details for the RNEC (v1.0) system to the CRS. Login details were unique to a specific study. The CRS then logged into RNEC (v1.0) and transcribed the information using the FAP or Protocol Amendment to be submitted. Information in RNEC (v1.0) went live as soon as the online transcription was saved and completed. &nbsp;</p><p><br></p><p>In case of CTA amendments, on receipt of approval for the amended FAP, the CRS accessed RNEC (v1.0) and updated the information if needed.&nbsp;</p><p><br></p><p><b>RNEC 2.0 (Post 14-May-2024 – Electronic CTA / DIGIPRIS – Automatic RNEC 2.0 update).</b></p><p>With the implementation of DIGIPRIS, RNEC 2.0 which was linked to DIGIPRIS was launched by COFEPRIS. &nbsp;All new initial CTAs were submitted via DIGIPRIS from 14-May-2024 onwards. The CRS (prior to July 2024) or CTA SM (from July 2024) entered CTA information into DIGIPRIS using the FAP as a reference and this information was automatically migrated into RNEC 2.0 once COFEPRIS approved the CTA. &nbsp;DIGIPRIS had the following categories of fields i.e. “Public”, “Internal Use” and “Restricted”. &nbsp;Any information added into “Public” fields were made public via RNEC v2.0 as soon as the CTA was approved. Fields marked as internal use were only accessible to RA in Mexico (COFEPRIS) and fields marked ‘restricted’ were only intended be accessible to specific departments in the Mexico RA.</p><p>Documents submitted to COFEPRIS were not made available publicly via RNEC, but only the summary information was made available for the public to access. &nbsp;In case of CTA amendments, any information that was amended in fields marked “Public” in DIGIPRIS was automatically made public in RNEC v2.0 once the amended CTA was approved.</p><p><br></p><p>The previous RNEC system (referred to as RNEC (v1.0)” in this document) was still in use, but only as a repository for closed and ongoing CTAs that were submitted prior to 14-May-2024. &nbsp;</p><p><br></p><p><b>Issue Background<br></b></p><p>Since information in RNEC is accessible to public, it must be free from CCI (Commercial Confidential Information) and only documents redacted for CCI such as redacted FAP should have been used to complete information in RNEC (v1.0) or in ‘Public’ fields in DIGIPRIS that were linked to RNEC v2.0. If unredacted information is entered this could result in CCI being made available publicly, which is not in compliance with Corporate Policy (CP) 401 ‘Safeguarding Sensitive Information’. Alternatively, as per CT28-GSOP (PUBLIC DISCLOSURE OF PFIZER SPONSORED STUDIES) v9.0, Studies registered on databases other than ClinicalTrials.gov and other than EudraCT (European Union Drug Regulating Authorities Clinical Trials) Database i.e., local country registries (the category to which RNEC belongs) were out of scope, should be consistent with the information in ClinicalTrials.gov and/or EudraCT.&nbsp;</p><p><br></p><p>On 05-Sep-2025, the CTA SM SME for Mexico checked RNEC v2.0 for Study C5091017 against the redacted FAP and identified that dose information, which was considered CCI by Pfizer (based on redacted clinician reviewed protocol) was publicly available. This dose information was in a restricted field in DIGIPRIS and therefore should not have been made available publicly in RNEC 2.0. This prompted the reporting of this SQE.</p><p><br></p><p>Subsequently, all studies publicly accessible via RNEC v1.0 and RNEC v2.0 were reviewed by the CTA SMs in Mexico (see Attachment 1) and below is a summary of the issues noted:&nbsp;</p><p><b>RNEC v1.0: All 85 entries were reviewed and CCI was identified for the following protocols as specified below:<br></b></p><p>• &nbsp; &nbsp;B7921005: Section 4.2 (point 23).</p><p>• &nbsp; &nbsp;C0251013: Section 6.1. Study Intervention(s) Administered.</p><p>• &nbsp; &nbsp;C1071005: Information about mortality relative to Arm C, included in sections 1,1 Synopsys and 2.1 Study Rationale in PA8 redacted protocol.</p><p>• &nbsp; &nbsp;C3601002: Section 4.1.4.</p><p>• &nbsp; &nbsp;C4671026: Information regarding dose for interventions, in overall study also dose and information regarding discordance between Tasso M20 PK sample and paired venous plasma samples.</p><p><br></p><p><b>RNEC v2.0: All 34 studies were reviewed and CCI was identified as specified below.<br></b></p><p>• &nbsp; &nbsp;B7981041: one secondary endpoint.</p><p>• &nbsp; &nbsp;C5091017: Dose and dose frequency.</p><p>• &nbsp; &nbsp;C1071005: information about mortality relative to Arm C included in sections 1.1 Synopsys and 2.1 Study Rationale.</p><p>• &nbsp; &nbsp;C4671026: Information regarding dose for interventions, in overall study also dose and information regarding discordance between Tasso M20 PK sample and paired venous plasma samples.</p><p>• &nbsp; &nbsp;C4951002 (BHV3000-311): Inclusion criteria c, i and g.</p><p>• &nbsp; &nbsp;C0251013: unit dose strength &amp; dosage level, arm description.</p><p>• &nbsp; &nbsp;C5241007: information in one exclusion criteria, dosage in study interventions.</p><p>• &nbsp; &nbsp;B7981041: one Secondary Endpoint.</p><p><br></p><p>Out of the above, CCI was in a Restricted Field: Dose for interventions (e.g. frequency, strength, level, arm description) for the following Studies: C5091017, C0251013, C4671026, C5241007.</p><p>In total, Nine (09) studies were found to have CCI information available for public view, spread between thirteen (13) entries in RNEC v1.0 and RNEC v2.0. &nbsp;Two (2) were transcribed into RNEC v1.0 directly by CRS under the previous RNEC v1.0 process. Seven (7) studies were transcribed into RNEC 2.0 through entries into DIGIPRIS under the RNEC v2.0 process either by CRS (prior to July 2024) or CTA SM (from July 2024). It was noted that for Four (4) studies that had CCI available for public viewing, the information was entered into “Restricted” fields in DIGIRPIS under the RNEC v2.0 process; meaning that COFEPRIS should have restricted this information from public viewing.</p><p><br></p><p><b>Note on Personal Protected Data:</b></p><p>At the time of reporting the QE, it was noted that RNEC v2.0 for Study C5091017 mentioned PI names, names and email IDs of Pfizer internal colleagues. It was not known if this was breach of Personal Protected Data (PPD) based on data privacy law in Mexico or Pfizer internal data privacy policies. Subsequently a review of RNEC (v1.0 and v2.0) was completed and the below was noted:&nbsp;</p><p>• &nbsp; &nbsp;RNEC v1.0 had the following personal information: PI (Principal Investigator) name and site address.&nbsp;</p><p>• &nbsp; &nbsp;RNECv 2.0 had the following personal information: PI (Principal Investigator) details such as name, affiliation to site and email, Ethics Committee (EC) names, contact details and Pfizer internal colleagues name and email address i.e. CTA SM entering the information or other colleague relevant to the study i.e. from Global Study and Site Operations (GSSO)</p><p><br></p><p>For global studies, information on professional affiliations related to PIs and ECs was obtained from clinical trial sites for study purposes and consent was obtained from PIs in accordance with INV02-INV04-WI-GL02 (Managing Investigational Site Documents) v7.0, utilizing form INV02-INV04-WI-GL02-RF06 (Personal Data Privacy Consent Form - Non-US Sites Except EU, EEA, UK and Switzerland) v6.0 not applicable in Mexico.</p><p>For local studies (Bioequivalence and bioavailability studies), contracts provided by local legal had the appropriate data privacy clauses included.</p><p>Based on the above, local Legal Manager (Mexico) and Global Corporate Counsel confirmed that there was no PPD breach with respect to PIs and ECs since the consent used was applicable in US not Mexico and also confirmed that publication of Pfizer internal colleagues professional business details only also complied with data privacy requirements. In view of this, no further investigation was required and this issue was considered closed.&nbsp;</p><p><br></p><p><b>Investigation:</b></p><p>The 5-WHYs Root Cause Analysis methodology was used to investigate the SQE. &nbsp;The Root Cause Analysis identified the following problem statement(s), root cause(s), Corrective and Preventive Action(s) (CAPA) and Effectiveness Check plan.&nbsp;</p><p><br></p><p>The following problem statements were identifie | Yes |  | 2026-03-17 |  |  | Data Privacy | Data privacy/confidentiality |  | 2026-03-18 11:54 | REG03-Clinical Trial Applications | Andrea Francis | FALSE | Mexico SME is exploring how the CCI For Study C5091017 can be removed from RNEC. SME is also confirming if the names, email addresses and other personal information of internal Pfizr colleagues and Investigators is aligned with data privacy law in Mexico and any Pfizer internal data privacy requirements or if there is violation of PPD requirementsReview is ongoing to check if other studies are impacted – both for Pfizer managed submissions and CRO (Clinical Research Organization) managed submissions. This will depend on what is publicly available and whether it is still considered CCI and PPD at this point. This may also depend on factors such as whether the study is still ongoing or if results are published for public access. Other countries e.g. Peru and Chile have similar country registries and a review is being planned to confirm impact to any other country. |  |  | CRS and CTA SMs were aware of Corporate Policy 401 (Safeguarding Sensitive Information) however did not make the linkage to the RNEC activity; the team believed that as the Mexico Regulatory Authority (RA) required certain information to be made public, they were simply complying with regulations by using the FAP (Final Approved Protocol)/Protocol Amendment as a reference. They did not consider internal document classification (Confidential) as they were not aware this could go wrong., Neither CRS nor CTA SMs were using redacted copies of FAP to enter information in RNEC v1.0 or in Public fields (RNEC v2.0) as there was no clear end to end process instructing them to do so., REG03-GSOP-RF03d CLINICAL TRIAL APPLICATION RESPONSIBILITIES – INSOURCED SUBMISSION MODELv6.0 mentioned the following: “for public registries i.e. where required by local regulations, upload the clinical study information to the country registry in coordination with CRS where applicable”, however did not specify use of redacted FAP. Note: REG03-GSOP CTA governs CTA applications whereas CT28-GSOP covers the registration of CTA information (i.e., into RA owned databases) which were two distinct activities unless the local registry was linked to the application form (which was the case for RNEC 2.0). &nbsp;, The CRS and CTA SMs were trained on CT28-GSOP (PUBLIC DISCLOSURE OF PFIZER SPONSORED STUDIES) v9.0, which mentioned that studies registered on ClinicalTrials.gov and EudraCT should not contain trade secret / Commercially Confidential Information (CCI), however, CT28-GSOP mentioned the following in the out-of-scope section: &nbsp;Out of Scope- Studies registered on databases other than ClinicalTrials.gov and EudraCT (ie, local country registries). However, study teams are responsible to ensure that study registration and results data are consistent with the information required on ClinicalTrials.gov and/or EudraCT. As RNEC was a local country registry and out of scope of CT28-GSOP as mentioned above, CRS and CTA SMs did not realize the CT28-GSOP and guidance on local country registries applied to them.&nbsp; | Human Performance, Method/Procedure | Inconsistency Error, Procedure/Form/Plan | Document Doesn't Exist/Lack of Access or Availability (Signals to Use Standard or Use of Standard), Inadequate/Inaccurate/Confusing (Document Standard Lacking/Incorrect Standard Content), Inconsistent With or a Different Interpretation of Regulatory Requirements (Document Standard Lacking/Incorrect Standard... | MODEL 1 - INSOURCED | Internal Medicine
QE-202162 | C5091017 | (Empty) | QE-202162 |  | PAREXEL INTERNATIONAL | N | Minor | Closed | The cooler bags for protocols C5091017 and C5091018 were purchased and distributed incorrectly.Protocol C5091017 was initiated in October 2024. The Parexel Supply &amp; Logistics Manager (SLPM) agreed with the Pfizer study team that the cooler bag should be used for refrigerated temperatures. The cooler bags were for transport of patient samples enrolled in the study. However, when Pfizer Global Study Manager sent the instructions to Parexel SLPM for the purchase process, the SLPM made a mistake in the reference when providing the instructions for internal Parexel logistics team for ordering the cooler bags. So, the Parexel study logistics team placed the order for the supplier for +15°C to +25°C cooler bags, instead of +2°C to +8°C, which is what is required by the study.When protocol C5091018 was initiated in February 2024, Pfizer study team informed that they needed the same items as for protocol C5091017. However, at the time they did not realize that the reference of the cooler bags were incorrect and approved the item as it had already been set up for protocol C5091017.The Pfizer local study team in Taiwan brought this to the attention of Parexel logistics team on 8 September 2025. Upon investigation of the issue, Pfizer Global Study Manager and SLPM performed a meeting on 11 September 2025, where this issue has been confirmed. | 2025-09-11 | 2025-09-18 | 2025-09-19 12:14 | GCP_Minor_Sep-2025_C5091017; C50910018: Clinical Logistics Services_Parexel International_TWN |  | NO |  |  | No |  |  | 2025-09-19 |  | Protocol Deviations | Failure to follow protocol |  |  | CT29-Management of Clinical Study BioSpecimens | Julia Mello |  | - Parexel logistics team has obtained stability information of the gel packs. The supplier provided the information/instructions for use for ambient temperature use. There is no stability information for using the gel packs in frozen or refrigerated conditions. This information has been provided by Parexel SLPM to Pfizer Global Study Manager on 15 September 2025.- Parexel logistics team is currently working to order the correct gel packs and protection plates for refrigerated conditions. The same cooler bags can be used.- Parexel logistics team has raised the Quality Event PR #434027 in Parexel TrackWise system for investigating this issue and defining the required CAPA actions. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-202420 | C5091017 | N | QE-202420 | 1101 | Cesar Perez (C5091017-1101) | N | Minor | Closed | Issue On 10 April 2025, Subject 11011002 was consented using an unapproved version of the RRS ICD (dated 13 Nov 2024, revised 26 Nov 2024). The site’s IRB had previously approved the correct version (dated 13 Nov 2024, revised 08 Jan 2025) on 09 January 2025. The error was later corrected when the subject was re-consented on 24 April 2025 using the IRB-approved RRS ICD version.Details The site reported that the RRS ICD (13 Nov 2024, revised 26 Nov 2024) was provided by the Pfizer study team via secure email and subsequently printed by site staff. Concurrently, the IRB provided the IRB-approved RRS ICD (13 Nov 2024, revised 08 Jan 2025). Both documents were available at the site, and staff mistakenly used the unapproved version when consenting Subject 11011002. Once the error was identified, the subject was informed and appropriately re-consented at the next study visit. | 2025-09-17 | 2025-09-19 | 2025-09-22 14:55 | GCP_Minor_Sep-2025_C5091017: Informed Consent Process_Perez, Cesar_USA |  | NO |  |  | No |  |  | 2025-09-22 |  | Informed Consent | Inadequate consent process at the investigator site |  |  | CT05-Informed Consent Document | Anthony Jones |  | Corrective and Preventive Actions A Quality Event (QE) has been submitted, and a corresponding Protocol Deviation (PD) has been logged in the site PD log.The site has been counseled on best practices for the informed consent process, and remote retraining will be conducted to reinforce compliance.The site successfully re-consented Subject 11011002 on 24 April 2025 with the correct IRB-approved version (revised 08 Jan 2025).The site will report the QE to their IRB and provide updates to the assigned CRA (A. Jones) regarding any required follow-up actions.The CRA will await QE team determination on event classification and next steps, and will ensure updates are shared with the study team and line management. |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-207681 | C5091017 | N | QE-207681 | 1064 | Augusto Focil (C5091017-1064) | N | Minor | Closed | The Principal Investigator (PI) randomized and dispensed investigational product to nine (9) participants prior to confirming eligibility. Review of the site’s electronic source system (CRIO) indicates that eligibility documentation was signed after the visit was completed for each of these participants, site was not able to provide paper source showing eligibility was confirmed before randomization. This suggests that eligibility review was not conducted prior to randomization and dispensing, which is a deviation from protocol and Good Clinical Practice (GCP) standards. | 2025-10-16 | 2025-10-17 | 2025-10-19 20:15 | GCP_Minor_Oct-2025_C5091017: Eligibility Criteria Review and Documentation_Focil, Augusto_USA |  | NO |  |  | No |  |  | 2025-10-19 |  | Quality Oversight | Inadequate Principal Investigator quality oversight |  |  | CT40-Management of Protocol Deviations | Yesenia Arriaga Mata |  | On 03Oct25 site monitor made site care partner aware that data was not entered into electronic source system in real time. Site monitor discussed issue with site staff on 03Oct25, and site staff confirmed that progress notes were available for data not entered in real time including PI eligibility. Site monitor requested progress notes be uploaded prior to next on-site monitoring visit 16Oct25. On 16Oct25 site monitor reviewed paper source on-site and was able to confirm that eligibility was not captured on paper source and only in electronic source system (CRIO). Site staff confirmed that site staff reviews inclusion and exclusion with subject and cross references medical history and pertinent records which is then verified by the principal investigator. Site was not able to provide documentation showing principal investigator determine eligibility prior to dispensation of investigational product. Site monitor made Site Care Partner and Country Study Operations Manager aware of issue and was instructed to submit a QE on 16Oct25. Site was made aware of issue and asked to provide a note to file clarifying the late entry of principal investigator signature on electronic source system for patient eligibility. Site was asked to include the principal's investigator's detailed process moving forward on 16Oct25. Site monitor entered an issue and action item in Siebel for follow-up (1-9FPTPIF). Site uploaded note to file in eISF on 16Oct25, but site monitor unable to download. Site monitor has requested document by email. Note to file includes clarification on late entry for inclusion and exclusion in eISF. |  |  | NA | Personnel | Lack of or Inadequate Oversight |  | MODEL 1 - INSOURCED | Internal Medicine
QE-207685 | C5091017 | N | QE-207685 | 1064 | Augusto Focil (C5091017-1064) | N | Minor | Closed | Study Activities Conducted by Undelegated and Untrained Site Staff: On 15-Aug-2025 and 19-Aug-2025, site staff Yamileet Castellon performed lab specimen management and nasal swab collection activities prior to being formally delegated to these tasks by the Principal Investigator on 20-Aug-2025. Additionally, a remote member, Juan Moncayo, of the site's centralized trial management team, who is neither delegated nor trained on study procedures, collected medical history, prior/concomitant medications, and inclusion/exclusion criteria via Microsoft Teams. | 2025-10-16 | 2025-10-17 | 2025-10-19 19:47 | GCP_Minor_Oct-2025_C5091017: CMCD: Delegation of Duties and Study Training_Focil, Augusto_USA |  | NO |  |  | No |  |  | 2025-10-19 |  | Quality Oversight, Training & Qualifications | Inadequate Principal Investigator quality oversight, Training not completed or documented in a timely manner |  |  | CT33-Study Training, INV02-Investigational Site Selection, Preparation, and Initiation | Yesenia Arriaga Mata |  | Site monitor made site aware of pending Firecrest training for Yamileet Castellon on 03Sept25. Fircrest training was completed on 12Sept25. On O2Oct25, site made site monitor aware that they needed assistance getting access for Juan Moncayo. Monitor instructed team to add site staff to Shared Investigational Portal which would trigger Firecrest training according to assigned role on SIP. On 03Oct25, site was made aware of issue and site provide an internal training log on 07Oct25 when asked to clarify. Site was retrained by email on 08Oct25 and monitor requested site's SOP. Site provided SOP on 13Oct25 and note to file on 15Oct25 which details that some staff not delegated and trained may support trained and delegated site staff. Site monitor made site care partner and country site operations manager aware of findings and was instructed to submit QE on 16Oct25. Site monitor made site aware of finding on 16Oct25 and requested a note to file clarifying issue with corrective action plan. Furthermore, site confirmed Juan Moncayo has not received Firecrest Training since being added on SIP. Site monitor asked site to please review Juan's assigned role on SIP, if incorrect role was assigned this might explain why Juan has not received Firecrest Training. Site monitor added Issue and Action item in Siebel for follow-up (1-99M5GYR, 1-9BSZK69, 1-9NY6O30, 1-8CBM8LO, 1-8CBQ4LY). |  |  | NA | Personnel | Lack of or Inadequate Oversight |  | MODEL 1 - INSOURCED | Internal Medicine
QE-207698 | C5091017 | N | QE-207698 | 1064 | Augusto Focil (C5091017-1064) | N | Minor | Closed | During routine monitoring, it was observed that the site is documenting study-related data in two locations: a single progress note and the electronic source system (CRIO). The progress note includes vital signs, physical exam findings, and a list of assessments/procedures with corresponding dates, times, and coordinator initials. However, not all data is being captured in real time within CRIO. Additionally, it was noted that data entry into CRIO is being performed by a remote centralized team and other site staff rather than the original site staff who conducted the assessments. This practice raises concerns regarding the contemporaneous documentation of source data and the integrity of the data entry process. Furthermore, corrections and date entries within CRIO do not consistently follow GCP guidelines for proper documentation practices. Corrections are not being appropriately struck through, initialed, and dated, and recorded dates on lab reports and other paper source are not consistent. It was also observed that CRIO contains more information than what is documented in the paper source, and this data is being entered after the participant visit, rather than in real time. | 2025-10-16 | 2025-10-17 | 2025-10-19 20:29 | GCP_Minor_Oct-2025_C5091017: Source Documentation_Focil, Augusto_USA |  | NO |  |  | No |  |  | 2025-10-19 |  | Data Collection and Management | Inadequate source data/documentation |  |  | No Process Assigned | Yesenia Arriaga Mata |  | Site was made aware and informed of the concern and reminded of the importance of real-time data entry by the individual performing the assessments on 03Oct25. Site was retrained by email on 10Oct25. Site was advised to ensure that all source data is documented contemporaneously and by the original data collector, in alignment with protocol and GCP requirements. Site provided SOP on 13Oct25. Site monitor entered issue and action in Siebel for follow-up (1-9FPTPIF, 1-9O06MAK)Site monitor made site care partner and country site operations manager aware and was instructed to report quality event on 16Oct25. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-209508 | C5091017 | N | QE-209508 | 1168 | Erik Buntinx (C5091017-1168) | N | Minor | Closed | Patients 11681001, 11681002, 11681003, 11681004 signed a local site owned ICD informing the patient about the patient reimbursement procedure. Anima Research has an own ICD about Scout patient reimbursement informing their study participants about the patient reimbursement. This ICD was not submitted neither approved. The approved "L2_3a_ICD Scout_C5091017_BE_NL_V2_28Apr2025_Public" for patient reimbursement was not presented to the patients. However, the patient data identification information was already shared with Scout Vendor. | 2025-10-07 | 2025-10-28 | 2025-10-28 16:19 | GCP_Minor_Oct-2025_C5091017: Informed Consent Process_Buntinx, Erik_BEL |  | NO |  |  | No |  |  | 2025-10-28 |  | Informed Consent | Inadequate consent process at the investigator site |  |  | CT05-Informed Consent Document | Christella Ukunda |  | The CRA informed the Study Coordinator (SC) and SC will instruct the investigator to inform the patient about the Scout ICD at the next scheduled visit. The investigator will also be asked to document a certified clarifying comment on the Scout ICD form explaining why the patient signed late. This is to ensure that the investigator provides a certified comment confirming that the patient was appropriately informed.At the time the issue was identified during monitoring dd07 Oct 2025, no patient reimbursements had been processed. |  |  | NA | Human Performance | Omission Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-210252 | C5091017 | (Empty) | QE-210252 |  | PFIZER | N | Minor | Closed | A discrepancy has been identified in study C5091017 between the Central Monitoring Plan (CMP) and the actual implementation and outputs of the CluePoints analysis. Specifically, from the time that QTL and sister KRI were applicable ( 28-Jul-2025 ) and for two consecutive Central Monitoring analyses ( 28-Jul-2025 and 4-Sept-2025) due to human oversight, the implementation of sister KRI was not executed.This constitutes a deviation from the planned risk-based monitoring approach described in the official documentation.The issue was identified during a thorough review of CMP and CluePoints setup. It has been discussed with the Data Surveillance leadership team, and a Quality Event is being filed to document this unplanned deviation and initiate appropriate corrective and preventive actions. | 2025-10-30 | 2025-10-31 | 2025-10-31 16:22 | GCP_Minor_Oct-2025_C5091017: CMCD: Central Monitoring Plan (CMP) and Cluepoints_Pfizer_Global |  | NO |  |  | No |  |  | 2025-10-31 |  | Data Collection and Management | Data management error |  |  | DMB07-Study Data Set Design and Setup | Konstantinos Vylliotis |  | Sister KRI has been implemented in CluePoints during the latest Central Monitoring analysis 13-Oct-2025. Deviation and update has been recorded in Central Monitoring analysis tracking log. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-211387 | C5091017 | (Empty) | QE-211387 |  | ICON PLC | N | Critical | Approved - In CAPA | It appears that a Site Activation Partner has manipulated a site document (IPAF) to answer a query from a Essential Document Reviewer (EDR) in an IIP.The initial IPAF provided was signed on template V3 while V4 was already in force.To answer the query, the SAP has sent an altered V4 (used the V3 added 2 white frames to hide the left and right side of the footer and a screenshot of the footer of V4 in the middle).The cEDR noticed it, and reported this to the SAP TL managing his country on 20Oct. This SAP TL then shared it to me as the SAP who did the alteration is based in one of the country I managed. | 2025-10-31 | 2025-11-06 | 2025-11-06 18:47 | GCP_Critical_Nov-2025_C5091018, C5091017, C5751003: Potential Allegation: IPAF Document_ICON_BEL, NL |  | YES |  | <p>It was alleged on 06 Nov 2025 that a Site Activation Partner (SAP), hired as an ICON Functional Service Provider (FSP) may have manipulated site documents in response to a query from the Essential Document Reviewer (EDR) during review of submitted Investigator Initiation Package (IIP) documents. &nbsp;Documents from three sites across two protocols (C5091018 and C5091017) were included in this allegation.&nbsp;</p><p>&nbsp;</p><p>A Due Diligence investigation was conducted.&nbsp;</p><p>&nbsp;</p><p>Upon identification and reporting of the allegation, the SAP was removed from work on Pfizer studies by ICON. &nbsp;The investigation team reviewed documents from five sites on three protocols in which the SAP had submitted documents for IIP approval.&nbsp; As part of the investigation, potentially impacted sites were requested to provide copies of the documents in question to compare to the versions submitted by the SAP. &nbsp; While this was ongoing, no enrolment was permitted at potentially impacted sites. &nbsp;In addition, a review of the SAP’s Pfizer email account and Pfizer One Drive was conducted by the Issue Lead (IL) to identify any potential additional altered documents.</p><p>&nbsp;</p><p>The investigation confirmed inconsistencies between the document versions maintained by two sites and those submitted by the SAP in the IIP submission. The text of the documents, including signature line was extracted and inserted onto the updated Pfizer template version, thereby substantiating the allegation that the SAP had manipulated the IIP documents. &nbsp;</p><p>&nbsp;</p><p>As this QE was a Due Diligence investigation, no assessment for repeat occurrence is required.&nbsp;</p> | No | Quality Event only required due diligence investigation | 2025-12-19 |  |  | Potential allegation of Falsification or misconduct | Potential allegation of Scientific fraud, falsification or misconduct |  | 2025-12-19 16:30 | INV02-Investigational Site Selection, Preparation, and Initiation | Delphine Chapsal | FALSE | I set up a meeting the next morning, with the SAP FSP manager to share what we found, so she could discuss with the SAP.The FSP manager had a 1:1 planned the same day, and discussed with the SAP, who had no explanation to provide.I took the decision to end our collaboration with this FSP with immediate effect once we had been informed of the outcome of the discussion between the SAP and FSP Manager.I have consulted with one of our PSL to assess the need to all the IIPs the SAP had submitted since she joined (5IIPs) to ensure this was the only time documents were altered.After further review, it appears that 2 other IPAFs have been altered after PI signature (to add the PA version on one, and to probably correct the V in the same way one the second document).After going back to the PSL with these details, it was mentioned that we may need to raise a QE. |  |  | Due Diligence | Due Diligence | N/A | N/A | MODEL 1 - INSOURCED | Internal Medicine
QE-215263 | C5091017 | (Empty) | QE-215263 |  | PFIZER | N | Minor | Closed | Study site received German Retained Research Sample ICD/ RRS (optional), dated 17 Mai 2025 that was different than the approved by the EC. By the EC approved version had crossed out the word 'Ort' (place) on page 9. Study site received version with not crossed out word on page 9. The cross-out word should have been deleted by translation agency, but the translater oversaw the removal. This minor issue was not identified by the EC too.The difference is minimal and does not change the content. | 2025-11-24 | 2025-11-26 | 2025-11-26 19:53 | GCP_Minor_Nov-2025_C5091017: Retained Research Sample ICD: Translation_Pfizer_DEU |  | NO |  |  | No |  |  | 2025-11-26 |  | Informed Consent | Inadequate consent document content |  |  | CT05-Informed Consent Document | Aneta Schnabel-Drewnicz |  | A verification must be conducted in all study sites that received the document (in paper and electronic version). Based on the verification results, corrective action in form of written information, must be implemented. |  |  | NA | Human Performance | Inconsistency Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-215581 | C5091017 | N | QE-215581 | 1247 | Angelika Sieber (C5091017-1247) | N | Minor | Closed | The study site was originally initiated with Main ICD V19May2025 and Optional ICD Retained Research Samples v19May2025. On 17 Oct2025, Optional ICD Retained Research Samples v19May2025 was replaced by Optional ICD Retained Research Samples v19Sep2025, which became the active. The site received formal communication via email on 17Okt2025 instructing staff to review the updated document, complete and record training, and implement Optional ICD Retained Research Samples v19May2025 immediately. Changes were administrative and no content changed. During a review at onsite Monitoring Visit, on 20Nov2025, CRA identified that participant 12471003 (screening failure) and participant 12471004 (screening failure), on his/her screening visit was incorrectly provided with the Optional ICD Retained Research Samples v19May2025, instead of the required optional ICD Retained Research Samples v19Sep2025. CRA could not communicate the Quality event by herself because of lacking access to the system. Thus, information was communicated via Email to SCP and cSOM on 25Nov2025. | 2025-11-25 | 2025-11-28 | 2025-12-01 17:31 | GCP_Minor_Nov-2025_C5091017: Informed Consent Process_Sieber, Angelika_DEU |  | NO |  |  | No |  |  | 2025-12-01 |  | Informed Consent | Inadequate consent process at the investigator site |  |  | CT05-Informed Consent Document | Aneta Schnabel-Drewnicz |  | Site staff were promptly instructed to discontinue use of ICD RSS19May2025 and trained on 25Nov2025 to implement of ICD RSS 19Sep2025. Training was documented on training log.The issue was documented during the monitoring visit in the monitoring visit report.Both participants are screening failure no further follow-up is required. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-218356 | C5091017 | N | QE-218356 | 1133 | Mario Jimenez (C5091017-1133) | N | Minor | Closed | Study C5091017 Site 1133 has had consistent ALCOA issues related to their source documents, as well as delayed source uploads within the eSource platform for monitor review. | 2025-12-11 | 2025-12-12 | 2025-12-15 16:27 | GCP_Minor_Dec-2025_C5091017: eSource: Source Documentation_Jimenez, Mario A_USA |  | NO |  |  | No |  |  | 2025-12-15 |  | Data Collection and Management | Inadequate source data/documentation |  |  | DMB08-Study Data Set Review Release and Archive | Aimee Brigmond |  | 26Nov2025 the site informed the CRA and study team that they had received a form 483 from their audit. 03Dec2025 the study team requested the CRAs feedback on the findings and correlations between audit findings and CRA findings. The CRA provided feedback on 03Dec2025. 05Dec2025 the CSOM requested the CRA schedule an on-site visit. On 05Dec2025 the Director of Site Management confirmed that further guidance on what should be reviewed would be provided in the coming days. 11Dec2025 the Director of Site Management requested the documentation of the Quality Event to document the issues found in the previous monitoring visits. |  |  | NA | Human Performance | Decision Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-218744 | C5091017 | (Empty) | QE-218744 |  | PFIZER | N | Minor | Closed | RedCap Cloud access for Site Data Entry personnel (user ppetkova1) to site C5091017-1085 was granted to incorrect instance (Study Central instance) in addition to their access of the Execution instance. Site Data Entry roles should not have access to Study Central instance. Access was corrected, but in the meantime the user entered data for a subject in the Study Central instance (report is available). | 2025-12-11 | 2025-12-15 | 2025-12-15 19:35 | GCP_Minor_Dec-2025_C5091017: Incorrect Instance Access Granted – RedCap Cloud (Site Data Entry Role)_Pfizer_BGR |  | NO |  |  | No | Minor/Unrated Quality Event |  | 2025-12-15 |  | Data Collection and Management | Incomplete or inaccurate data transcription and/or entry |  |  | CP406 | Elena D Angelo |  | Access to SC instance was revoked, analyst who granted the access was remediated, account provisioning team reminded of the correct procedure. |  |  | None.&nbsp; | Equipment/System/Facility | System/Application |  | MODEL 1 - INSOURCED | Internal Medicine
QE-219824 | C5091017 | (Empty) | QE-219824 |  | ORACLE | N | Minor | Closed | Inform LNMT is a separate functionality within Inform EDC which is used to set-up Local Labs and configure the lab normal ranges which are associated to corresponding Studies and Sites. MedTech team has access to Inform LNMT to perform these functions.Inform is a product of Oracle. And Oracle identified that, if multiple users are working in the LNMT and making updates in it, it is causing the audit to capture the username of another user. Oracle notified Pfizer about this identified issue and the action they have taken on 3/Dec/2025.Please note, this issue only affected the username attribution in the LNMT audit trail; all other clinical trial audit data remains accurate. Additionally, users were never able to perform actions outside of their authorized permissions. | 2025-12-03 | 2025-12-19 | 2025-12-19 20:22 | GCP_Minor_Dec-2025_Multiple Studies: InForm LNMT User Audit Trail_Oracle_Global |  | NO |  |  | No |  |  | 2025-12-19 |  | Data Collection and Management | Data management error |  |  | DMB07-Study Data Set Design and Setup | Prathamesh Patil |  | Oracle has implemented preventative fixes to prevent incorrect user attribution in the LNMT audit going forward. Please note that Oracle is unable to retroactively correct past occurrences of this issue. |  |  | NA | Equipment/System/Facility | System/Application |  | MODEL 1 - INSOURCED | Internal Medicine
QE-222180 | C5091017 | (Empty) | QE-222180 |  | NPHASE INC (REDCAP CLOUD), PFIZER | N | Major | In Investigation | We are raising this event to please request that the minor assessment for QE-219754 be reconsidered. To again summarize the what occured, a legitimate query was raised in the C4601019 study by our medical monitor. However in RCC this query changed to a different user name and role (LabTech). That different user is a real person at Pfizer, but they never requested access to C4601019 and they are not on our Site User Report. This user does not have access to the C4601019 study in RCC, as confirmed by the RCC Admin team's review of the study's audit logs. Further, the Lab Tech role does NOT have access to issue a query in RCC. As a result, the RCC system does not clearly link back to user who issued the query, which we believe violates FDA guidance per CFR 21 Part 11, likely with guidance from EMA and other regulators similarly breached. When this QE was initally submitted, there were 3 such known issues across 2 RCC studies. There are now 9 known issues across 6 RCC studies. | 2025-12-16 | 2026-01-09 | 2026-01-12 20:17 | GCP_Major_Jan-2026_System/Enterprise Level_System Access Controls Redcap Cloud (RCC): Broader Issue_Pfizer; NPHASE INC (REDCAP CLOUD)_Global |  | NO | [7 empty] | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) |  |  | CP403 | Katherine Paternel |  | Raised as a critical finding for RCC white glove as of 17 Dec2025 - CAS00002285. Raised the topic to Pfizer and RCC SMEs for immediate action. | [6 empty] | MODEL 1 - INSOURCED | Internal Medicine
QE-224035 | C5091017 | (Empty) | QE-224035 |  | PAREXEL INTERNATIONAL | N | Minor | Closed | .5pt; background-image: initial; background-position: initial; background-size: initial; background-repeat: initial; background-attachment: initial; background-origin: initial; background-clip: initial;'CRA employment was terminated based on concerns related to quality of work and overall performance. .0pt"CRA was advised of termination on 16JAN26, last day of employment planned for 23JAN26. CRA departed with one day notice, instead of 7 day notice previously agreed upon. CRA did not complete monitoring visit report for two visits and did not address open PDs or issues prior to her exit. | 2026-01-20 | 2026-01-21 | 2026-01-21 16:55 | GCP_Minor_Jan-2026_C4591076, C5091017: CMCD: Monitoring Responsibilities: Employment_Parexel_USA |  | NO |  |  | No |  |  | 2026-01-21 |  | Site Management and Monitoring | Failure to detect/document |  |  | INV04-Investigational Site Management and Monitoring | Shawn Szalay |  | CRA was removed from Pfizer partnership with Parexel. |  |  | NA | Personnel | Lack of or Inadequate Oversight |  | MODEL 1 - INSOURCED | Internal Medicine
QE-224040 | C5091017 | N | QE-224040 | 1087 | Elena Gyuzeleva (C5091017-1087) | N | Major | In Investigation | The bioanalytical lab reported that blinded pharmacokinetic results from multiple participants in C5091017 at study site #1087 in Bulgaria are significantly above the limit of quantification for Ibuzatrelvir. These results were observed in the Day 5 PK samples. There have been no adverse events reported for any of the participants at this site, and there are no immediate safety concerns. No participants at this site are currently on active study treatment. The assays were repeated, which confirmed that the results initially observed. While the team continues to investigate, a decision was made to report a quality event and to temporarily pause enrollment at site 1087. | 2026-01-16 | 2026-01-21 | 2026-01-21 20:32 | GCP_Critical_Jan-2026_C5091017; B7981040: Unblinding: Pharmakenetics (PK) Data_Pfizer; York Bioanyalytical Solutions; Gyuzeleva; Stoyanova_BUL Upgrade |  | NO | [7 empty] | Data Collection and Management, Equipment, Facility and Sample/Specimens, Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan), Inadequate sample/specimen collection and management, Incorrect assignment/randomization and/or maintenance of the study blind |  |  | CT29-Management of Clinical Study BioSpecimens, DMB06-Randomization Schedule Data Blinding and Break Blind, QMS06-Risk Management for Clinical Development | Halley Rogers |  | Immediate actions taken included:1. Notification of the GCL and study clinician by the bioanalytical team lead - 16Jan20262. Review all AEs reported at site 1087 - 16Jan20263. Review PK sample collection times and dosing times to look for anomalies - 16 Jan 20264. Repeat of PK assays to confirm results - 16Jan2026-20Jan20265. Discuss issue in a blinded manner at study team meeting to get alignment on the issue and next steps - 21Jan20266. Decision to pause enrollment temporarily at site 1087 - 21Jan20267. Decision to report a QE while the issue is under investigation - 21Jan2026Planned Actions:1. Consider testing PK samples for placebo participants2. Look at other samples from the site for abnormalities (ie viral load)3. Continue to investigate potential causes4. Consider whether an additional unblinded CSM or other role is needed | [6 empty] | MODEL 1 - INSOURCED | Internal Medicine
QE-224040 | C5091017 | Y | QE-224040 | 1178 | Boyka Stoyanova (B7981040-1178) | N | Major | In Investigation | The bioanalytical lab reported that blinded pharmacokinetic results from multiple participants in C5091017 at study site #1087 in Bulgaria are significantly above the limit of quantification for Ibuzatrelvir. These results were observed in the Day 5 PK samples. There have been no adverse events reported for any of the participants at this site, and there are no immediate safety concerns. No participants at this site are currently on active study treatment. The assays were repeated, which confirmed that the results initially observed. While the team continues to investigate, a decision was made to report a quality event and to temporarily pause enrollment at site 1087. | 2026-01-16 | 2026-01-21 | 2026-01-21 20:32 | GCP_Critical_Jan-2026_C5091017; B7981040: Unblinding: Pharmakenetics (PK) Data_Pfizer; York Bioanyalytical Solutions; Gyuzeleva; Stoyanova_BUL Upgrade |  | NO | [7 empty] | Data Collection and Management, Equipment, Facility and Sample/Specimens, Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan), Inadequate sample/specimen collection and management, Incorrect assignment/randomization and/or maintenance of the study blind |  |  | CT29-Management of Clinical Study BioSpecimens, DMB06-Randomization Schedule Data Blinding and Break Blind, QMS06-Risk Management for Clinical Development | Halley Rogers |  | Immediate actions taken included:1. Notification of the GCL and study clinician by the bioanalytical team lead - 16Jan20262. Review all AEs reported at site 1087 - 16Jan20263. Review PK sample collection times and dosing times to look for anomalies - 16 Jan 20264. Repeat of PK assays to confirm results - 16Jan2026-20Jan20265. Discuss issue in a blinded manner at study team meeting to get alignment on the issue and next steps - 21Jan20266. Decision to pause enrollment temporarily at site 1087 - 21Jan20267. Decision to report a QE while the issue is under investigation - 21Jan2026Planned Actions:1. Consider testing PK samples for placebo participants2. Look at other samples from the site for abnormalities (ie viral load)3. Continue to investigate potential causes4. Consider whether an additional unblinded CSM or other role is needed | [6 empty] | MODEL 1 - INSOURCED | Internal Medicine
QE-224040 | C5091017 | (Empty) | QE-224040 |  | PFIZER, YORK BIOANALYTICAL SOLUTIONS LTD | N | Major | In Investigation | The bioanalytical lab reported that blinded pharmacokinetic results from multiple participants in C5091017 at study site #1087 in Bulgaria are significantly above the limit of quantification for Ibuzatrelvir. These results were observed in the Day 5 PK samples. There have been no adverse events reported for any of the participants at this site, and there are no immediate safety concerns. No participants at this site are currently on active study treatment. The assays were repeated, which confirmed that the results initially observed. While the team continues to investigate, a decision was made to report a quality event and to temporarily pause enrollment at site 1087. | 2026-01-16 | 2026-01-21 | 2026-01-21 20:32 | GCP_Critical_Jan-2026_C5091017; B7981040: Unblinding: Pharmakenetics (PK) Data_Pfizer; York Bioanyalytical Solutions; Gyuzeleva; Stoyanova_BUL Upgrade |  | NO | [7 empty] | Data Collection and Management, Equipment, Facility and Sample/Specimens, Quality Procedures | Failure to a follow sponsor/third party/site controlled procedure (e.g., SOP or statistical analysis plan), Inadequate sample/specimen collection and management, Incorrect assignment/randomization and/or maintenance of the study blind |  |  | CT29-Management of Clinical Study BioSpecimens, DMB06-Randomization Schedule Data Blinding and Break Blind, QMS06-Risk Management for Clinical Development | Halley Rogers |  | Immediate actions taken included:1. Notification of the GCL and study clinician by the bioanalytical team lead - 16Jan20262. Review all AEs reported at site 1087 - 16Jan20263. Review PK sample collection times and dosing times to look for anomalies - 16 Jan 20264. Repeat of PK assays to confirm results - 16Jan2026-20Jan20265. Discuss issue in a blinded manner at study team meeting to get alignment on the issue and next steps - 21Jan20266. Decision to pause enrollment temporarily at site 1087 - 21Jan20267. Decision to report a QE while the issue is under investigation - 21Jan2026Planned Actions:1. Consider testing PK samples for placebo participants2. Look at other samples from the site for abnormalities (ie viral load)3. Continue to investigate potential causes4. Consider whether an additional unblinded CSM or other role is needed | [6 empty] | MODEL 1 - INSOURCED | Internal Medicine
QE-226766 | C5091017 | N | QE-226766 | 1134 | John Hill (C5091017-1134) | N | Minor | Closed | Site staff at site 1134 PI for the C5091017 study re-consented subject 11341011 on 13Jan26 to protocol amendment 2 (PA2) prior to completing all minimum required training for PA2. All minimum required PA2 training has been completed by the site on 29Jan26. | 2026-02-05 | 2026-02-05 | 2026-02-05 21:30 | GCP_Minor_Feb-2026_C5091017: Study Training_Hill, John_USA |  | NO |  |  | No |  |  | 2026-02-05 |  | Training & Qualifications | Training not completed or documented in a timely manner |  |  | CT33-Study Training | Carolyn Stricklin |  | cSOM and SCP has been notified. CRA to re-train site staff and PI. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-227309 | C5091017 | (Empty) | QE-227309 |  | PFIZER | N | Minor | Closed | Site ICDs related to the Protocol amendment 2 dated 05Nov2025 were customized with errors and submit them to Committes for sites: 1065, 1264, 1178 and 1069 due to the some errors in the Country Eng/Spa ICDs were identified later for instance Country Spa ICD version does not have track of changes, Header of the Country Eng/Spa ICD versions did not report correct protocol amendment date and Country Main Eng/Spa ICD did not have track of changes to delete signatures space for iliterate participants (All potential participants should know read and write). | 2026-02-05 | 2026-02-09 | 2026-02-10 22:33 | GCP_Minor_Feb-2026_C5091017: Informed Consent Document_Pfizer_MEX |  | NO |  |  | No |  |  | 2026-02-10 |  | Informed Consent | Inadequate consent document content |  |  | CT05-Informed Consent Document | Luis Omar Trujillo |  | Site ICDs are being corrected according to the updated Country Eng/Spa Main ICD and Parental ICD. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-228482 | C5091017 | N | QE-228482 | 1101 | Cesar Perez (C5091017-1101) | N | Minor | Closed | Issue:On January 27, 2026 (Day 1), subject 11011028 was enrolled in the study under the incorrect age group (50-64 years) and with two (2) risk factors. However, the subject only presented with one (1) risk factor, rendering them ineligible for the study cohort as defined by inclusion criterion #2 of the protocol.Details:Subject 11011028 was erroneously enrolled in the study in the 50-64 age group, with an incorrect categorization of risk factors. The subject was documented as having two (2) risk factors; however, upon review, it was determined that the subject only had one (1) risk factor. The reported risk factors were smoking and stage 2 Chronic Kidney Disease (CKD). According to the protocol, stage 2 CKD is classified as "mild" and does not meet the criteria for "mild to moderate" stage 3a CKD, which is required for eligibility. As such, the subject does not fulfill inclusion criterion #2, specifically the requirement for appropriate CKD stage.Despite this discrepancy, the Lead Clinician has confirmed that the subject will be allowed to continue in the study per their authority. | 2026-02-11 | 2026-02-16 | 2026-02-16 17:56 | GCP_Minor_Feb-2026_C5091017: Protocol Deviation: Inclusion/Exclusion Criteria_Perez, Cesar_USA |  | NO |  |  | No |  |  | 2026-02-16 |  | Protocol Deviations | Failure to comply with protocol inclusion/exclusion criteria |  |  | CT40-Management of Protocol Deviations | Anthony Jones |  | Query and issue of subject eligibility was escalated to lead clinician and study team for evaluation. Lead clinician confirmed that the subject was not eligible for study per the cohort noted per subject age (50-64 with two (2) risk factors). Despite the erroneous enrollment, the lead clinician allows the subject to continue as enrolled per their authority. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-228700 | C5091017 | (Empty) | QE-228700 |  | PFIZER | N | Minor | Closed | One of our study sites received a suspicious phone call from someone claiming to be from Prescient Health Group and asking questions about the C5091017 study, including recruitment and study progress, even implying other sites had already shared information. The team confirmed this contact was not authorized, and the incident was escalated internally under CP411 for appropriate handling. | 2026-02-11 | 2026-02-17 | 2026-02-17 17:13 | GCP_Minor_Feb-2026_C5091017: Sponsor and Site Confidentiality_Pfizer_USA |  | NO |  |  | No |  |  | 2026-02-17 |  | Data Privacy | Data privacy/confidentiality |  |  | CP411 | Eun Lee |  | The alert email was sent to all US sites to inform the incident. |  |  | NA | Personnel | Inadequate Information for Determination |  | MODEL 1 - INSOURCED | Internal Medicine
QE-228938 | C5091017 | Y | QE-228938 | 1056 | Veselin Kalfov (C5091017-1056) | N | Minor | Closed | For site 1056 it was noticed following Clue point signal review that NP swabs and serology tests were not performed for patients 10561001 - 10561005 at week 12 and for patient 10561006 D14 as per the requirements of the study Protocol. Issue and PDs for respective visits were created. This QE is now created based on lead GSM request. | 2026-02-02 | 2026-02-18 | 2026-02-18 17:32 | GCP_Minor_Feb-2026_C5091017: Protocol Deviation: Biospecimen Collection_Kalfov, Veselin_BGR |  | NO |  |  | No |  |  | 2026-02-18 |  | Equipment, Facility and Sample/Specimens | Inadequate sample/specimen collection and management |  |  | CT29-Management of Clinical Study BioSpecimens | Ivaylo Ivanov |  | CRA emailed and discussed the issue by phone several times. Site was re-trained and it was agreed that they will follow strictly procedures outlined in the Protocol schedule of activities. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-229483 | C5091017 | N | QE-229483 | 1247 | Angelika Sieber (C5091017-1247) | N | Minor | Closed | During the Managment Visit conducted on 18 Dez 2025, the Principal Investigator (PI) informed the SCP that she was unable to locate the calibration certificate for the thermometer used to monitor the temperature of the freezer designated for blood sample storage. She stated that the certificate was most likely archived. Between 29 July 2025 (SIV) and 25 September 2025 (thermometer replaced), the thermometer continued to be used; however, the calibration certificate could not be located. Upon realizing that the certificate was unavailable, the PI immediately purchased a new thermometer, which is supplied with a valid calibration certificate, and replaced the previous device in September 2025. A thorough search of the archive was subsequently conducted, but the calibration certificate for the previous thermometer could not be found. The first patient was screened on 16 September 2025.While the Team meeting it was decided that this event should be documented as QE. | 2026-02-19 | 2026-02-23 | 2026-02-23 15:57 | GCP_Minor_Feb-2026_C5091017: Biospecimen Storage: Thermometer Calibration Certificate_Sieber, Angelika_DEU |  | NO |  |  | No |  |  | 2026-02-23 |  | Equipment, Facility and Sample/Specimens | Inadequate facility design |  |  | No Process Assigned | Aneta Schnabel-Drewnicz |  | • The PI performed a comprehensive search of the archive to locate the missing calibration certificate. • After confirming that the certificate could not be found, the PI purchased a new thermometer with a valid calibration certificate and replaced the previous device in September 2025. • The SCP was informed on 18 December 2025, and an Issue was formally opened.PI confirmed that the certificate was not found in Feb2026. SCP closed Issue and opened Quality event. |  |  | NA | Equipment/System/Facility | Equipment |  | MODEL 1 - INSOURCED | Internal Medicine
QE-229798 | C5091017 | (Empty) | QE-229798 |  | ADVARRA INC | N | Minor | Closed | During implementation of protocol amendment 2 (C5091017), ICDs were updated to reflect protocol changes and US tax language updates. Advarra approved our country-level language and was tasked with pushing these from the US country-level template to US site-level consents. Following site-level approvals we identified issues with IRB-approved consents at 23, or approximately one-third of sites. These issues were overwhelmingly related to a failure to update tax language or ensure that updates were made to the incorrect type of consents (adult vs. pediatric). | 2026-01-13 | 2026-02-23 | 2026-02-23 22:35 | GCP_Minor_Feb-2026_C5091017: Informed Consent Document_Advarra_USA |  | NO |  |  | No |  |  | 2026-02-23 |  | Informed Consent | Inadequate consent process by sponsor |  |  | CT05-Informed Consent Document | Regan Hitt |  | The issue was raised with (and in some cases by) CIPT and the SCPs to ensure we were actively highlighting instances of these issues. The GRAFs were completed as "Pfizer Not Approved" and returned to Advarra for correction. I contacted Advarra PoC Benjamin Quast on 13Jan26 to make him aware of these issues and request a comment on the root cause of this failing. Benjamin confirmed that a protocol note was added and a message was sent to their CFD (unsure of acronym meaning) team to make sure these were incorporated but did not elaborate further. Due to the volume of issues identified, we requested a meeting with Benjamin to discuss things in greater detail. We did not receive a response and the meeting did not occur. In an effort to determine if we can proceed with ICDs missing this language, I contacted CD legal who encouraged me to reach out to the CT17 BPO team to discuss further. We had a meeting on 23Feb26 where we determined a QE for this issue was necessary. During this we also confirmed that all ICDs should accurately reflect the country-level updates and that we should engage further with the Pfizer Vendor Lead to ensure this issue is not repeated. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-230104 | C5091017 | N | QE-230104 | 1171 | Ronald Pucillo (C5091017-1171) | N | Minor | Closed | The site did not utilize the VCT Authorization form during subject screening as required per protocol for the following subjects: 11711001, 11711002, 11711003, 11711004, 11711005, 11711006, 11711007, 11711008. The VCT Authorization form was not filed in the ISF at the time of the monitoring visit on 24Feb2026. Upon identification, the CRA re-educated site staff on VCT authorization for all subjects during screening. CRA provided site with the VCT authorization form to be filed in ISF. | 2026-02-24 | 2026-02-24 | 2026-02-25 18:05 | GCP_Minor_Feb-2026_C5091017: VCT Authorization Form_Pucillo, Ronald_USA |  | NO |  |  | No |  |  | 2026-02-25 |  | Informed Consent | Inadequate consent process at the investigator site |  |  | CT05-Informed Consent Document | Temitope Oladimeji |  | CRA re-educated site and provided VCT Authorization form to be filed in ISF and to be used at every subject's screening visit moving forward. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-230104 | C5091017 | (Empty) | QE-230104 |  | PFIZER | N | Minor | Closed | The site did not utilize the VCT Authorization form during subject screening as required per protocol for the following subjects: 11711001, 11711002, 11711003, 11711004, 11711005, 11711006, 11711007, 11711008. The VCT Authorization form was not filed in the ISF at the time of the monitoring visit on 24Feb2026. Upon identification, the CRA re-educated site staff on VCT authorization for all subjects during screening. CRA provided site with the VCT authorization form to be filed in ISF. | 2026-02-24 | 2026-02-24 | 2026-02-25 18:05 | GCP_Minor_Feb-2026_C5091017: VCT Authorization Form_Pucillo, Ronald_USA |  | NO |  |  | No |  |  | 2026-02-25 |  | Informed Consent | Inadequate consent process at the investigator site |  |  | CT05-Informed Consent Document | Temitope Oladimeji |  | CRA re-educated site and provided VCT Authorization form to be filed in ISF and to be used at every subject's screening visit moving forward. |  |  | NA | Human Performance | Learning Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-230579 | C5091017 | N | QE-230579 | 1171 | Ronald Pucillo (C5091017-1171) | N | Minor | Closed | While reviewing ICDs at site 1107, monitor discovered that subject 11711004 signed the ICD for a different site (site 1002). | 2026-02-24 | 2026-02-26 | 2026-02-27 17:47 | GCP_Minor_Feb-2026_C5091017: Informed Consent Process_Pucillo, Ronald_USA |  | NO |  |  | No |  |  | 2026-02-27 |  | Informed Consent | Inadequate consent process at the investigator site |  |  | CT05-Informed Consent Document | Temitope Oladimeji |  | CRA brought discrepancy to site's attention. CRA re-trained site and notified PI and cSOMs of discrepancy. NTF documenting CAPA has been filed in site's ISF and PTMF. |  |  | NA | Human Performance | Inconsistency Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-231175 | C5091017 | N | QE-231175 | 1171 | Ronald Pucillo (C5091017-1171) | N | Minor | Closed | Based on QE-230579: While reviewing ICDs, monitor discovered that participant 11711004 signed the ICD for a different site (site 1002). Update 03MAR2026: The site is unable to bring the subject back in for re-consent due to subject being a screen fail. | 2026-02-24 | 2026-03-03 | 2026-03-03 19:06 | GCP_Minor_Mar-2026_C5091017: Informed Consent Process_Pucillo, Ronald_USA |  | NO |  |  | No |  |  | 2026-03-03 |  | Informed Consent | Inadequate consent process at the investigator site |  |  | CT05-Informed Consent Document | Temitope Oladimeji |  | CRA brought discrepancy to site's attention. CRA re-trained site and notified PI and cSOMs of discrepancy. NTF documenting CAPA has been filed in site's ISF and PTMF. |  |  | NA | Human Performance | Application Error |  | MODEL 1 - INSOURCED | Internal Medicine
QE-232816 | C5091017 | (Empty) | QE-232816 |  | PFIZER | N | Minor | Closed | On 09/18/2025 Site Coordinator Victoria Brumby (vbrumby) was mistakenly granted access in the RedCap Cloud EDC system to an incorrect study: C5091017-1170. The access she had requested was for study C4771002-1170. As a result of this, she entered data and enrolled a patient on 03/03/2026 under the incorrect study/site. After that, Victoria realized the study she had access to appeared to be the wrong study and notified her Study Team. On 03/04/2026 the Study Team emailed HCL, the Account Provisioning Team, reporting that Victoria had been granted access to the wrong study and site. On 03/06/2026 the issue was corrected: the incorrect Study access (C5091017 1170) was removed, and proper access to C4771002 1170 was granted. | 2026-03-10 | 2026-03-10 | 2026-03-11 15:18 | GCP_Minor_Mar-2026_C5091017, C4771002: System Access Controls: REDCap Cloud (RCC)_Pfizer_Global |  | NO |  |  | No |  |  | 2026-03-11 |  | IT Systems | Inadequate system access or account management |  |  | CP403 | Elena D Angelo |  | User`s access to the wrong study was removedUser`s access was assigned to the correct study |  |  | NA | Personnel | Inadequate Information for Determination |  | MODEL 1 - INSOURCED | Internal Medicine
QE-234317 | C5091017 | N | QE-234317 | 1025 | Alton Walters (C5091017-1025) | N | Major | In Investigation | Cyber attack at Elite Clinical Network / Las Vegas Clinical Trials. Head of Business Continuity, Theresa Riddle, was informed of event. She asked me to see if Pfizer conducted any clinical trials at this site. One site identified. No additional details available. Requested Theresa Riddle to identify how she learned of the cyber attack. | 2026-03-17 | 2026-03-18 | 2026-03-18 19:02 | GCP_Major_Mar-2026_C5091017: Cyber Security Incident_Walters, Alton-Elite Clinical Network / Las Vegas Clinical Trials_USA |  | NO | [7 empty] | IT Systems | IT system security threat/compromise (inappropriate use/access, intrusion detection, mgmt/unintended release of non-subj info) |  |  | CP411 | Alexander Polman |  | Unknown | [6 empty] | MODEL 1 - INSOURCED | Internal Medicine